## Slide 1: Nodal Program Update to Cops 06-08-2010
Jim Galvin

## Slide 2: Program Status
Please refer to ERCOT presentations for readiness metrics and participation metrics
Presentations to COPS going forward will focus on Market Trial items around
  DAM
  RTM and LFC
  CRR
  Settlements/COMS/Credit

## Slide 3: CRR
No new issues reported
ERCOT will this week:
  Post July Auction Notice
  Post the CRR Ownership File
  Allow NOIEs to begin submitting their nominations for 2011 and 2012

## Slide 4: DAM
Phase 5 has ramped up to running 5x per week DAM with associated settlement
DAM is including credit simulation
  Credit reports on available credit are available prior to DAM
  Update exposure reports provide changes based on market simulation activity
  Participants can increase their credit limits at their discretion
Participation remains good, prices are modest ranging from $20 to $50

## Slide 5: DAM
Issues-
  RUC Commitments are still high, ERCOT says they are not operationally approved but communicating the commitments for experience for participants
  Focus on data issues pertaining to breaker statuses, line ratings and load distribution factors in resolving the high RUC commitments
  Various one off issues around COP updates are being addressed with participants also contributing to high commitment of RUC units
  Credit exposure calculations

## Slide 6: DAM
Upcoming Weeks
  No guardrails- ERCOT requests bids and offers to be reasonable
  DAM failure simulation (6/8/10)
  SASM twice within the same operating interval (Hour) and increase in load forecast between DAM and DRUC/HRUC (6/10/10)

## Slide 7: RTM/LFC
New Issues center around 4 certified reports and changes to them:
  NP8-143 QSE Ancillary Service Capacity Monitor
  NP6-552-Group 1 and Group 2 Load Resources for RRS
  NP8-501 Monthly Resource Energy Deployment Performance Report
  NP8-143-Ancillary Services Capacity Monitor

## Slide 8: RTM/LFC
LFC Test May 20, 2010:
  System on full Nodal control from 11:55 am to 12:25 pm
  Nodal prices trended approximately $10 higher than Zonal prices with the exception of the Houston Zone
  Houston Zone experienced congestion Houston Hub price cleared $40 less than Houston Load Zone price
  ERCOT has provided more analysis on the prices during LFC test, presentation is available at the following link: http://www.ercot.com/calendar/2010/06/20100604-MT

## Slide 9: RTM/LFC
Real Time prices are seeing some volatility both negative and positive
  May 27 example in RTM/LFC presentation from Friday call
Prices still reflect information submitted for market trial purposes that may be insufficient for declaring them “reasonable”
8-hour LFC test workshop on June 8 with 8-hour test to be conducted June 16-18

## Slide 10: Settlements/Coms/Credit
Statements, Invoices and Extracts continue to be delivered under protocol timelines for Market Trial activity
ERCOT provides a total dollar breakdown by charge type of settlement activity on the weekly call
Most charge types are being calculated in Market Trials, examples of those not are BLT, Emergency Energy, DC Tie Export etc
Settlements for BPD and RT Energy Imbalance appear high, but keep in mind that is based on actual Zonal output/demand compared to Nodal simulation

## Slide 11: Settlement/COMS/Credit
Very few questions are coming through Market Trials program team regarding settlements
Data made available in the COMS extracts appear to be complete with determinants available for all calculations
There are differences in extract data, it is important for market participants to review and utilize extract information to get accustomed to Nodal data points
Deeper dives in SEWG planned to look at data samples

## Slide 12: Questions?