## Slide 1: 2011 Project Prioritization
Troy Anderson
ERCOT Program Management Office
June 2010

## Slide 2: 2011 Project Prioritization - Schedule
April 2010
  CARTs develop draft 2011 project lists
    Request and incorporate input from the market
    5 year project forecast referenced and updated
May 2010
  Initial review at market subcommittee meetings
    MO - COPS (May 11)
    RO - RMS (May 12)
    SO - ROS, WMS (May 13 / May 19)
June 2010
  Approval/endorsement by market subcommittees
    MO - COPS (June 8)
    RO - RMS (June 9)
    SO - ROS, WMS (June 10 / June 16)
    CO, IO, MO, RO, SO – PRS (June 17)
July 2010
  Approval/endorsement by TAC (July 1)
  Available for F&A and Board review (July 20)

## Slide 3: 2011 Project Prioritization – Reminder
Nodal System Stabilization will be the primary focus in 2011
  Code freeze will likely extend into Q2 2011
  Parking deck items will be assessed for impact and prioritized prior to the start of release planning
  First major release planned for 2012
  2011 funding based on estimated resource requirements for:
    Stabilization
    Planning for 2012 major release

## Slide 4: 2011 Project Prioritization – Primary Components
There are 3 primary components to ERCOT’s 2011 project funding request:
1 – Nodal Stabilization and Release Planning $30M*
2 – Data Center Hardware Purchase and Installation $47M
3 – Other critical projects that have limited resource
impacts on items 1 and 2 $ TBD
* ROS and WMS are asked to weigh in on the proposed funding

## Slide 5: 2011 Project Prioritization – Funding Estimate
Basis of $30M Funding Estimate
Using data from recent development and testing activities from the Nodal project, ERCOT has projected the staffing needs for Nodal stabilization. This activity will involve 75-100 staff members (both ERCOT and vendor) and will initially focus on stabilization. As time allows, their attention will shift to release planning.
Important Note: It is assumed that some portion of this estimate will be O&M. The remainder will be capital. The breakdown will be determined prior to ERCOT’s final budget filing.

## Slide 6: 2011 Project Prioritization
Suggested Motion
Motion to endorse ERCOT’s proposal to fund 2011 Nodal stabilization and release planning in the amount of $30M.

## Slide 7: 2011 Project Prioritization
Appendix – Nodal Parking Deck
  Items for consideration in release planning

## Slide 8: Nodal Parking Deck - Approved by Board of Directors
Source Document | Title | Priority | Current Status
NPRR131 | Ancillary Service Trades with ERCOT | High | BoD Approved 1/19/2010
NPRR181 | FIP Definition Revision | High | BoD Approved 1/19/2010
NPRR153 | Generation Resource Fixed Quantity Block Offer | Medium | BoD Approved 1/19/2010
NPRR164 | Resubmitting Ancillary Service offers in SASM | Medium | BoD Approved 1/19/2010
SCR755 | ERCOT.com Website Enhancements | Medium | BoD Approved 2/16/2010

## Slide 9: Nodal Parking Deck – Pending Approval
Source Document | Title | Suggested Priority | Current Status
NPRR146 | ICCP Telemetry Information Submittals | High | Pending at Board TAC approved 6/3/2010
NPRR207 | Unit Deselection | High | Tabled at TAC PRS approved 2/19/2009
NPRR210 | Wind Forecasting Change to P50, Synchronization with PRR841 (gray-boxed portion) | High | Pending at Board TAC approved 6/3/2010
NPRR222 | Half-Hour Start Unit RUC Clawback | High | Pending at Board TAC approved 6/3/2010
NOGRR034 | Rescind Telemetry Performance Calculation Exclusions | TBD | Pending at ROS OWG approved 5/19/2010
SCR756 | Enhancements to the MarkeTrack Application | Critical | Pending at Board TAC approved 6/3/2010

## Slide 10: Nodal Parking Deck – Possible Additions
Title | Current Status
NPRR218 – Resolution of Alignment A71 – Add Protocol Description of the Power Balance Penalty Factor Used in SCED | Possible gray-box of language
NPRR219 – Alignment – TSPs Must Submit Outages for Resource Owned Equipment… | Possible gray-box of language
Wind Cost Allocation | High level impact assessment of two options is near completion
Deferred NOGRR025 Reports | Draft NPRR in progress to gray-box reports planned for delivery after Nodal go-live
NMMS API | Pending consideration as part of post-go-live release
CRR API | Pending consideration as part of post-go-live release
MMS Multiple Network Models | Pending consideration as part of post-go-live release
Add PSS Status to RARF | Currently below the cutline on the Market Operations (MO) PPL – automation of manual process as a result of NPRR156
Automated Default Uplift Invoice | Automation of manual process as a result of NPRR221