| NPRR Number | 146 | NPRR Title | ICCP Telemetry Information Submittals |  |
| --- | --- | --- | --- | --- |
| Timeline | Normal | Action |  | Approved |
| Date of Decision |  | June 15, 2010 |  |  |
| Nodal Protocol Section Requiring Revision |  | 3.10.1, Time Line for Network Operations Model Change Requests |  |  |
| Effective Date |  | Upon the Nodal Protocol Transition Plan’s Texas Nodal Market Implementation Date as prescribed by zonal Protocol Section 21.12, Process for Transition to Nodal Market Protocol Sections, for all language except grey boxes in paragraphs (3) and (6) of Section 3.10.1, which will be Upon System Implementation - Post Texas Nodal Market Implementation Date. |  |  |
| Priority and Rank Assigned |  | Priority High (applicable only to grey boxes in paragraphs (3) and (6) of Section 3.10.1) |  |  |
| Revision Description |  | This Nodal Protocol Revision Request (NPRR) requires that changes to an existing Network Operations Model Change Request (NOMCR) that modify only Inter-Control Center Communications Protocol (ICCP) data object names be submitted prior to the completion of the testing for the Network Operations Model. |  |  |
| Overall Market Benefit |  | This NPRR will improve the quality of information ERCOT receives on ICCP data object names and will reduce burden on Transmission Service Providers (TSPs) and Qualified Scheduling Entities (QSEs) to provide needed information in a timely and correct manner. |  |  |
| Overall Market Impact |  | This NPRR will prevent TSPs and ERCOT from modeling ICCP data object names that may not ever exist and then removing them at a later date. |  |  |
| Consumer Impact |  | None. |  |  |
| Credit Impacts |  | ERCOT Credit Staff and the Credit Work Group (Credit WG) have reviewed NPRR146 and do not believe that it requires changes to credit monitoring activity or the calculation of liability. |  |  |
| Procedural History |  | - On 7/31/08, NPRR146 was posted. - On 8/8/08, ERCOT comments were posted. - On 8/21/08, PRS considered NPRR146. - On 9/2/08, Transition Plan Task Force (TPTF) comments were posted. - On 9/10/08, a second set of TPTF comments were posted. - On 9/24/08, PRS again considered NPRR146. - On 10/22/08, a second set of ERCOT comments were posted. - On 10/23/08, PRS again considered NPRR146. - On 11/13/08, a third set of ERCOT comments were posted. - On 11/20/08, PRS again considered NPRR146. - On 12/17/08, a third set of TPTF comments were posted. - On 12/18/08, PRS again considered NPRR146. - On 1/22/09, AEP comments were posted. - On 1/22/09, Oncor comments were posted. - On 1/22/09, PRS again considered NPRR146. - On 2/18/09, a fourth set of ERCOT comments were posted. - On 2/19/09, PRS again considered NPRR146. - On 3/5/09, TAC considered NPRR146. - On 1/6/10, TAC again considered NPRR146. - On 2/4/10, TAC again considered NPRR146. - On 4/6/10, a fifth set of ERCOT comments were posted. - On 4/8/10, TAC again considered NPRR146. - On 5/3/10, Network Data Support Working Group (NDSWG) comments were posted. - On 5/6/10, TAC again considered NPRR146. - On 5/18/10, ROS comments were posted. - On 5/28/10, a sixth set of ERCOT comments were posted. - On 6/3/10, TAC again considered NPRR146. - On 6/4/10, a CEO Revision Request Review and an Impact Analysis were posted. - On 6/15/10, the ERCOT Board considered NPRR146. |  |  |
| PRS Decision |  | On 8/21/08, PRS unanimously voted to refer NPRR146 to TPTF. All Market Segments were present for the vote. On 9/24/08, PRS unanimously voted to recommend approval of NPRR146 as amended by TPTF comments dated September 2, 2008. All Market Segments were present for the vote. On 10/23/08, PRS unanimously voted to table NPRR146 pending the development of an Impact Analysis. All Market Segments were present for the vote. On 11/20/08, PRS unanimously voted to refer NPRR146 to TPTF. All Market Segments were present for the vote. On 12/18/08, PRS unanimously voted to recommend approval of NPRR146 as amended by the 12/17/08 TPTF comments. The Independent Generator Market Segment was not present for the vote. On 1/22/09, PRS unanimously voted to table NPRR146. All Market Segments were present for the vote. On 2/19/09, PRS unanimously voted to forward the PRS Recommendation Report to TAC and note to TAC that NPRR146 has been approved post-Nodal Go-Live as stated in the 2/18/09 ERCOT comments and therefore would be slated to be in a future release. All Market Segments were present for the vote. |  |  |
| Summary of PRS Discussion |  | On 8/21/08, PRS noted that TPTF had not reviewed NPRR146. On 9/24/08, PRS noted that TPTF proposed revisions to NPRR146. On 10/23/08, there was no discussion. On 11/20/08, it was noted that ERCOT submitted comments that were posted on 11/13/08, and it was requested that NPRR146 be referred to TPTF to consider these comments. On 12/18/08, ERCOT Staff explained that the changes proposed by the 12/17/08 TPTF comments added clarity to the Protocol language but did not change the functionality of the process. On 1/22/09, it was noted that ERCOT believes that NPRR146 is not Needed for Go-Live. On 2/19/09, ERCOT Staff explained that ERCOT has determined that NPRR146 is not needed for Nodal Go-Live, as further explained in the 2/18/09 ERCOT comments, and that pursuant to the procedure put in place pursuant to PRR799, ERCOT CEO Approval of NPRRs and SCRs Prior to Posting on MIS, an appeal of this decision must be filed within ten Business Days after 2/18/09. The PRS chair stated that since this was the first NPRR subject to the PRR799 procedure, it would be forwarded to TAC to receive additional input. |  |  |
| TAC Decision |  | On 3/5/09, TAC unanimously voted to table NPRR146 pending a recommendation from PRS on the “parking deck” procedure for post-Nodal Go-Live NPRRs and to reevaluate the projected system impacts of NPRR146. All Market Segments were present for the vote. On 1/6/10, TAC unanimously voted to table NPRR146 for one month. All Market Segments were present for the vote. On 2/4/10, TAC unanimously voted to table NPRR146 indefinitely. All Market Segments were present for the vote. On 4/8/10, TAC unanimously voted to table NPRR146 for one month. All Market Segments were present for the vote. On 5/6/10, TAC unanimously voted to table NPRR146. All Market Segments were present for the vote. On 6/3/10, TAC voted to recommend approval of NPRR146 as amended by the 5/28/10 ERCOT comments and as revised by TAC and to assign a priority of High to the proposed grey boxed language. There was one opposing vote from the Municipal Market Segment and one abstention from the Independent Generator Market Segment. All Market Segments were present for the vote. |  |  |
| Summary of TAC Discussion |  | On 3/5/09, it was noted that it has been determined that NPRR146 is not needed for Nodal Go-Live, and that a “parking deck” procedure for dealing with such NPRRs is still under development. It was requested that while NPRR146 is tabled, ERCOT and interested Market Participants consider whether the projected system impacts are due to a subset of data points only, and if so, whether the essentiality status might be reevaluated as to the remaining data points. On 1/6/10, ERCOT Staff explained that the ERCOT CEO is reevaluating the original determination that NPRR146 was not necessary prior to the Texas Nodal Market Implementation Date, and that the final determination may depend on the resolution of ongoing discussions regarding the frequency of Network Operations Model loading. On 2/4/10, it was again noted that NPRR146 is connected to the issue of how often ERCOT will load the Network Operations Model, which is still under discussion by other stakeholder bodies. On 4/8/10, it was requested that ROS consider the 4/6/10 ERCOT comments. On 5/6/10, it was suggested that TAC table NPRR146 to allow ROS to review the 5/3/10 NDSWG comments. On 6/3/10, ERCOT Staff explained that the ERCOT CEO has not formally reviewed the 5/18/10 ROS comments but that after preliminary evaluation, the ERCOT CEO believes that NPRR146, if amended by the 5/18/10 ROS comments, would not be necessary prior to the Texas Nodal Market Implementation Date. It was suggested that the revisions proposed in the 5/18/10 ROS comments be grey-boxed for future implementation. |  |  |
| Board Decision |  | On 6/15/10, the ERCOT Board approved NPRR146 as recommended by TAC in the 6/3/10 TAC Report. |  |  |

Quantitative Impacts and Benefits

| Assumptions | 1 |  |  |
| --- | --- | --- | --- |
|  | 2 |  |  |
|  | 3 |  |  |
|  | 4 |  |  |
| Market Cost |  | Impact Area | Monetary Impact |
|  | 1 | None. | No additional implementation cost. |
|  | 2 |  | No additional staffing cost. Possible contractor reduction. |
|  | 3 |  |  |
|  | 4 |  |  |
| Market Benefit |  | Impact Area | Monetary Impact |
|  | 1 | Improve the quality of information ERCOT receives on ICCP data object names. |  |
|  | 2 | Reduce burden on TSPs and QSEs to provide needed information in a timely and correct manner. |  |
|  | 3 | Reduced congestion cost. | Potential to reduce congestion cost with more accurate telemetry data. |
|  | 4 |  |  |
| Additional Qualitative Information | 1 | Fewer model changes for ERCOT models. Testing will be reduced due to fewer changes. |  |
|  | 2 |  |  |
|  | 3 |  |  |
|  | 4 |  |  |
| Other Comments | 1 | ERCOT systems require less changes and better modeling of telemetry information. |  |
|  | 2 | Fewer work-arounds and better telemetry information. |  |
|  | 3 |  |  |
|  | 4 |  |  |

| Comments Received |  |
| --- | --- |
| Comment Author | Comment Summary |
| ERCOT 080808 | Expressed opposition to proposed revisions; stated that ERCOT system designs and business processes would require significant changes that would overshadow any perceived benefit proposed. |
| TPTF 090208 | Proposed revisions to change the proposed seven-day timeline for submitting ICCP telemetry to 15 days; proposed revisions to the NPRR cover page language. |
| TPTF 091008 | Indicated that on 9/8/08, TPTF declared NPRR146 to be "Needed for Go-Live." |
| ERCOT 102208 | Indicated that the development of an Impact Analysis for NPRR146 will be deferred until the 11/20/08 PRS meeting. |
| ERCOT 111308 | Explained how ICCP data submittals will be treated and what modifications to NMMS will need to be made. |
| TPTF 121708 | Inserted table from the 11/13/08 ERCOT comments that explains how ICCP data submittals will be treated into paragraph (6) of Section 3.10.1. |
| AEP 012209 | Contended for this change to go into effect before Nodal Go-Live. |
| Oncor 012209 | Proposed language that would require ICCP/Telemetry points to be submitted and follow the 15 day submission requirement. |
| ERCOT 021809 | Stated that ERCOT believes that NPRR146 is not needed for Nodal Go-Live. |
| ERCOT 040610 | Proposed revisions to reflect discussions regarding the frequency of ERCOT’s loading of the Network Operations Model database and the decision to target weekly loading. |
| NDSWG 050310 | Proposed revisions to allow ICCP naming changes up to two weeks prior to each weekly database load. |
| ROS 051810 | Endorsed NPRR146 as amended by the 5/3/10 NDSWG comments |
| ERCOT 052810 | Stated that the revisions proposed in the 4/6/10 ERCOT comments reflect the extent that ERCOT is staffed and the procedures it can accommodate prior to the Texas Nodal Market Implementation Date. |

| Original Sponsor |  |
| --- | --- |
| Name | Jim Jacoby |
| Company | American Electric Power |
| Market Segment | Investor Owned Utility (IOU) |

Comments

The Nodal Protocol language has been updated due to administrative revisions made during the implementation of NPRR133, Addition of PSSE Format, on September 1, 2008 and NPRR202, Clarification of Network Operations Model and State Estimator Postings, on February 1, 2010.  Revisions are reflected in redline with “NPRR133” or “NPRR202,” respectively, as the author.

Proposed Protocol Language Revision

3.10.1	Time Line for Network Operations Model Change Requests

(1)	ERCOT shall perform periodic updates to the Network Operations Model.  Market Participants may provide Network Operations Model updates to ERCOT to implement planned transmission and Resource construction one year before the required submittal date below.  TSPs and Resource Entities must timely submit Network Operations Model changes pursuant to the schedule in this Section to be included in the updates.

(2)	For a facility addition, revision, or deletion to be included in any Network Operations Model update, all technical modeling information must be submitted to ERCOT pursuant to the ERCOT NOMCR process.

(3)	TSPs and Resource Entities shall submit Network Operations Model updates at least three months prior to the physical equipment change.  ERCOT shall update the Network Operations Model according to the following table:

| Deadline to Submit Information to ERCOT Note 1 | Model Complete and Available for Test Note 2 | Updated Network Operations Model Testing Complete Note 3 | Update Network Operations Model Production Environment | Target Physical Equipment In-Service Date Note 4 |
| --- | --- | --- | --- | --- |
| Jan 1 | Feb 15 | March 15 | April 1 | Month of April |
| Feb 1 | March 15 | April 15 | May 1 | Month of May |
| March 1 | April 15 | May 15 | June 1 | Months of June–August SUMMER MODEL |
| June 1 | July 15 | August 15 | September 1 | Month of September |
| July 1 | August 15 | September 15 | October 1 | Month of October |
| August 1 | September 15 | October 15 | November 1 | Month of November |
| September 1 | October 15 | November 15 | December 1 | Month of December |
| October 1 | November 15 | December 15 | January 1 | Month of January (the next year) |
| November 1 | December 15 | January 15 | February 1 | Month of February (the next year) |
| December 1 | January 15 | February 15 | March 1 | Month of March (the next year) |

Notes:

1.	Transmission and Resource data submissions complete per NOMCR process for inclusion in next update period.

2.	Network Operations Model data changes and preliminary fidelity test complete by using the Network Operations Model test facility described in paragraph (3) of Section 3.10.4, ERCOT Responsibilities.  A test version of the Redacted Network Operations Model will be posted to the MIS Secure Area for Market Participants and Network Operations Model to the MIS Certified Area for TSPs as described in paragraph (8) of Section 3.10.4, for market review and further testing by Market Participants.

3.	Testing of the Redacted Network Operations Model by Market Participants and Network Operations Model by TSPs is complete and ERCOT begins the Energy Management System (EMS) testing prior to placing the new model into the production environment.

4.	Updates include changes starting at this date and ending within the same month.

[NPRR146: Replace paragraph (3) above with the following upon system implementation:] (3) TSPs and Resource Entities shall submit Network Operations Model updates at least three months prior to the physical equipment change. ERCOT shall update the Network Operations Model according to the following table: Deadline to Submit Information to ERCOT Note 1; Model Complete and Available for Test Note 2; Updated Network Operations Model Testing Complete Note 3 Paragraph (6); Update Network Operations Model Production Environment; Target Physical Equipment included in Production Model Note 4. Jan 1; Feb 15; March 15; April 1; Month of April. Feb 1; March 15; April 15; May 1; Month of May. March 1; April 15; May 15; June 1; Months of June–August SUMMER MODEL. June 1; July 15; August 15; September 1; Month of September. July 1; August 15; September 15; October 1; Month of October. August 1; September 15; October 15; November 1; Month of November. September 1; October 15; November 15; December 1; Month of December. October 1; November 15; December 15; January 1; Month of January (the next year). November 1; December 15; January 15; February 1; Month of February (the next year). December 1; January 15; February 15; March 1; Month of March (the next year). Notes: 1. Transmission and Resource data submissions complete per NOMCR process for inclusion in next update period. 2. Network Operations Model data changes and preliminary fidelity test complete by using the Network Operations Model test facility described in paragraph (3) of Section 3.10.4, ERCOT Responsibilities. A test version of the Redacted Network Operations Model will be posted to the MIS Secure Area for Market Participants and Network Operations Model to the MIS Certified Area for TSPs as described in paragraph (8) of Section 3.10.4, for market review and further testing by Market Participants. 3. Testing of the Redacted Network Operations Model by Market Participants and Network Operations Model by TSPs is complete and ERCOT begins the Energy Management System (EMS) testing prior to placing the new model into the production environment. 4. Updates include changes starting at this date and ending within the same month.

(4) 	ERCOT shall only approve energization requests when the Transmission Element is satisfactorily modeled in the Network Operations Model.

(5)	In order to allow for construction schedules, TSPs may use pseudo-breakers and switches to designate future facilities configurations such that the Network Operations Model may be correctly implemented as construction of new facilities is accomplished.

(6)	Changes to an existing NOMCR that modify only Inter-Control Center Communications Protocol (ICCP) data object names shall be provided prior to the completion of the testing for the Network Operations Model in which the Transmission Elements represented by the ICCP data object names were first modeled (reference table in paragraph (3) above).  NOMCR modifications containing only ICCP data object names shall not be subject to Independent Market Monitor (IMM) and Public Utility Commission of Texas (PUCT) reporting (reference paragraph (5) of Section 3.10.4, ERCOT Responsibilities), according to the following:

| NOMCR that contains ICCP Data and is submitted … | ERCOT shall … | Subject to IMM & PUC Reporting |
| --- | --- | --- |
| Beyond 90 days of the energization date | Allow modification of an existing NOMCR with only ICCP data | No |
| Prior to the completion of the market testing | Allow modification of an existing NOMCR with only ICCP data | No |
| After the completion of market testing | Require a new NOMCR to be submitted containing the ICCP data | Yes |

[NPRR146: Replace paragraph (6) above with the following upon system implementation:] (6) Changes to an existing NOMCR that modify only Inter-Control Center Communications Protocol (ICCP) data object names shall be provided 15 days prior to the Network Operations Model load date. NOMCR modifications containing only ICCP data object names shall not be subject to interim update reporting to the Independent Market Monitor (IMM) and Public Utility Commission of Texas (PUCT) (reference paragraph (5) of Section 3.10.4, ERCOT Responsibilities), according to the following: NOMCR that contains ICCP Data and is submitted …; ERCOT shall …; Subject to IMM & PUC Reporting. Beyond 90 days of the energization date; Allow modification of only ICCP data for an existing NOMCR; No. Between 90 and 15 days prior to the scheduled database load.; Allow modification of only ICCP data for an existing NOMCR; No. Less than 15 days before scheduled database load.; Require a new NOMCR to be submitted containing the ICCP data; Yes.