## Goals for 2010
DSWG Goals for 2010 Update
# | DSWG Goal | Deliverable | Target Date | Primary Owner | Team Members | Status
1 | SCED Load Participation | Report to DSWG on feasibility and scope | End of 2nd Quarter | Alice Jackson | Tim C., Jay Z., Eric G., Mark S | Not Started
2 | RUC Load Participation (Project #37897 Workshop) | Report to DSWG on feasibility and scope | End of 2nd Quarter | Alice Jackson | Floyd, Eric G, Tim C., Jay Z., Mark S | Not Started
3 | Real Time LMPZ Pricing Latenency | LMPZ Prices posted via ICCP (NPRR169) | End of 4th Quarter | Mark Smith | All | In Progress
4 | DADS Update and Impacts in ERCOT | Presentation at DSWG | End of 4th Quarter | Paul Wattles | All | Not Started
5 | Review of performance evaluation of Load Resources under Nodal (companion to PRR 714) | Develop draft NPRR and Review of Zonal | End of 1st Quarter | Mary Anne Brelinsky | Scott W., John T. Steve K, Paul W.
6 | EILS Improvements | EILS Subgroup Report to the DSWG | End of 4th Quarter | Steve Isser | All | Not Started
7 | 4CP and Price Responsive Load Analysis | Report and Presentation to the DSWG | End of 4th Quarter | Paul Wattles | Steve Isser | Not Started
8 | Update of California and New England A/S Participation by Residential Loads | Presentation at DSWG | End of 3rd Quarter | Jay Z | Steve I, Paul W Steve K
9 | Greater participation of small and midsize loads in ERCOT markets. | Review FERC rules covering participation by advanced meter aggs, including ancillaries. | End of 3rd Quarter | Steve Isser | Paul W., Carl R., Steve K., Robert H., Steve I. | Not Started
10 | Update of Nodal Load Participation documents | Update Load Participation Document to include split deployment and other nodal changes. | End of 2nd Quarter | Tim Carter | Steve, Mary Anne, Nelson | Not Started

## Goals for 2009
DSWG Goals for 2009 Update
# | DSWG Goal | Deliverable | Target Date | Primary Owner | Team Members | Status
1 | SCED and RUC - Load Participation | Report to DSWG on feasibility and scope; potential NPRR draft | 2010 | Scott Wardle | Floyd, Eric G, Tim C., Jay Z., Eric G. | 2010
2 | NERC Demand Response Registration | Keep DSWG apprised of NERC working group activities; possible participation | End of 4th Quarter | Eric Goff | Nelson, Paul W., Mary Anne
3 | Review of Dynamics Working Group Study on LaaR Participation | Summary Report and Presentation to DSWG, Possibly Comments to ROS | End of 1st Quarter | Steve Krein | Scott W, Rick K, Roger Y
4 | Clarify and/or modify LaaR performance standards | Draft or amend a PRR if there is consensus | End of 3rd Quarter | Tim Carter | Mary Anne
5 | Performance evaluation of Load Resources under Nodal Protocols (companion to PRR 714) | Develop draft NPRR | End of 1st Quarter | Mary Anne Brelinsky | Scott W., John T. Steve K | 2010
6 | EILS Improvements including 2 additional baselines | Work with ERCOT staff and EILS subgroup; draft PRR/NPRR | End of 3rd Quarter | Brett Perlman | Paul W., Carl R., Roger Y., Alberto M., Nelson
7 | 4CP and Price Responsive Load Analysis | Report and Presentation to the DSWG | 2010 | Paul Wattles | Mark S. | 2010
8 | Minimum MW offer for Ancillary Services | Draft NPRR if there is consensus | End of 4th Quarter | Mary Anne Brelinsky | Malcolm S, Brett P, John T
9 | Greater participation of small and midsize loads in ERCOT markets. | Review FERC rules covering participation by advanced meter aggs, including ancillaries. | End of 4th Quarter | Steve Isser | Paul W., Carl R., Steve K., Robert H., Steve I.
10 | XML Notice for LaaR and EILS Events | Operating Guide Change to support VDI notice after XML | End of 4th Quarter | Tim Carter | Steve, Mary Anne, Nelson

## Goals for 2008
DSWG Goals for 2008 Update
# | DSWG Goal | Deliverable | Target Date | Primary Owner | Team Members | Status
1 | Conduct Nodal Training Workshop for End Use Consumers | Workshops Completed and Presentations Posted on Website | End of 2nd Quarter | Paul Wattles | Jay Z, Mary Anne B, Floyd, Scott W
2 | Notice of Nodal LMP & Load Zone Prices | Document to post on DSWG web site | End of 1st Quarter | Jay Zarnikau | Mary Anne, Floyd T, Nelson N
3 | RUC Capacity Short Charge—How do you insulate price responsive loads from these charges | Overview at DSWG Meeting in August | End of 2nd Quarter | Mark Smith | Nelson N, Scott W, John T, Tim B
4 | Review of Dynamics Working Group Study on LaaR Participation | Summary Report and Presentation to DSWG, Possibly Comments to ROS | End of 4th Quarter | Steve Krein | Scott W, Rick K, Malcolm S, Roger Y | In Progress
5 | Revisit Demand Response and Energy Aggregation and create Roadmap related to AMI settlements | Review Infrastructure requirements to support DLC and Mass Market Programs | End of 4th Quarter | Steve Isser | Jay Zarnikau and Eric Goff
6 | LR Participation in Nodal and Potential Issues of Negative Bidding | NPRR to address Issue | End of 3rd Quarter | Mary Anne Brelinsky | Malcolm S, Scott W.
7 | Develop Guidelines for Alternative to IDR Metering for EILS | Protocol revision | End of 3rd Quarter | Paul Wattles | John T
8 | 4CP and Price Responsive Load Analysis | Report and Presentation to the DSWG | End of 4th Quarter | Paul Wattles | Malcolm S, Mark S. | In Progress
9 | Nodal Implementation of LR and How Procurement and Proration will work with Unit Specific Procurement | Presentation to DSWG | End of 2nd Quarter | Steve Krein | Paul W
10 | Wind Study Ancillary Service Product | Outline potential 15 minute AS Product | End of 4th Quarter | Tim Carter | Mary Anne, Floyd T, Nelson N

## Goals for 2007
DSWG Goals for 2007 Update
# | DSWG Goal | Deliverable | Target Date | Primary Owner | Additional Team Members | Status
1 | Nodal Training for Load Participation | ERCOT sponsored training class | End of 4th Quarter | Paul Wattles | Mark Patterson, Mary Anne B, Floyd T, Scott W | In Progress, initial meeting held
2 | Notice of Nodal LMP & Load Zone Prices | Document to post on DSWG web site | End of 4th Quarter | Mary Anne Brelinsky | Jay Z, Floyd T, Nelson N | In Progress
3 | RUC Capacity Short Charge—How do you insulate price responsive loads from these charges | Overview at DSWG Meeting in December | End of 4th Quarter | Nelson Nease |  | In Progress
4 | Priority Pricing—Long term BUL Commitment | Conceptual Design Complete Special Task Force Formed | End of 3rd Quarter | Jay Zarnikau | Shmuel Oren
5 | Develop Improvements to LaaR Performance | PRR supported by WMS and submitted to PRS (PRR714) | End of 2nd Quarter | Mary Anne Brelinsky
6 | Revisit DLC and Energy Aggregation | Review Infrastructure requirements to support DLC and Mass Market Programs | End of 4th Quarter | Steve Isser | Jay Zarnikau | Joint meeting to be scheduled with PWG
7 | Load participation in RPRS and BES | Training and PRR Sponsorship if necessary | No Longer Priority | Mary Anne Brelinsky | Mark P
8 | CLR for Dummies | Documents for posting on DSWG web site | End of 3rd Quarter | Scott Wardle | Mark P
9 | Survey of LSEs on Load Response | Report and Presentation to the DSWG | End of 2nd Quarter | Paul Wattles | DSWG
10 | Finalize the Load for Dummies in the Nodal Market | Document to post on DSWG web site | End of 2nd Quarter | Floyd Trefny | Mary Anne B, Jay Z, Mark P

## Goals for 2006
DSWG Goals for 2006 Update
Item # | DSWG Goal | Deliverable | Target Date | Primary Owner | Team Members | Status
1 | Identify a permanent solution for negative LaaR bidding | List of solution alternatives identified, comparative analysis completed, and PRR's introduced | End of 2nd Quarter | Mary Anne Brelinsky | Special Task Force
2 | Develop a description of demand side opportunities for the Nodal Market Design | HTML document that has been peer reviewed and posted to the ERCOT website | End of 4th Quarter | All | Jay Zarnikau
3 | Develop a Price Responsive Load Participation Program for all customer segments | Program concept & preliminary analysis completed. Present to WMS for feedback on next steps | End of 4rd Quarter | Malcolm Smith | Jay Zarnikau, Dan Austin, George Arnold
4 | Review comments from an Ad Hoc Group on Proposed Rules for Resource Adequacy and Automated Metering | Comments to Proposed Rules filed with the PUCT | End of 1st Quarter | Jay Zarnikau | Malcolm Smith
5 | Compare demand response resource programs being run in other ISO markets | Report Completed and Posted to ERCOT Website | End of 3rd Quarter | Steve Isser | Steve Krein
6 | Identify by market segment: a. customer ability to respond to prices b. barriers to participation c. proposed solutions to remove those barriers | Assessment and basis for ERCOT's reporting requirements under the PUCT Demand Response Project #32853 | End of 4th Quarter | Steve Krein | All
7 | Identify demand side program opportunities to solve a once in ten year loss of load type event | Present analysis and recommendations to WMS | End of 1st Quarter | Steve Krein | All
8 | Update description of demand side opportunities on ERCOT website and include status of Replacement Reserve | HTML document that has been peer reviewed and posted to the ERCOT website | End of 2nd Quarter | Mary Anne Brelinsky | Steve Krein