## Slide 1: Outage Scheduler Transition Plan
Kenneth Ragsdale
NATF
June 23, 2010

## Slide 2: Agenda
Market Readiness Protocols
Outage Scheduler Transition Timeline
ERCOT Readiness for OS
Market Readiness for OS
Outage Scheduler Implementation Timeline
Notes: 2

## Slide 3
Market Readiness Protocols
Section 21 Zonal Protocols – Process for Protocols Revision
21.12.3 Notice to Market Participants of Effective Date for Nodal Protocol Provisions and Retirement of Zonal Protocol Provision
No part of the nodal market design may start operation until all the Market Readiness Criteria for that part of the nodal market design have been met. Certification that all Market Readiness Criteria have been met must be made at least by each of the following: the Technical Advisory Committee (TAC), ERCOT and the ERCOT Board. Upon such certification, ERCOT shall issue two Notices alerting Market Participants to the effective date of Nodal Protocol sections and the retirement of Zonal Protocol sections, as applicable. ERCOT shall issue the first Notice no less than thirty (30) days prior to the effective date or retirement date, as applicable, and the second Notice no less than ten (10) days prior to the effective date or retirement date, as applicable. The Notice shall include:

## Slide 4
Outage Scheduler Transition Timeline – Approach A
Clean Outage Scheduler, No Zonal Outage Import
  Delete all outages Monday, 8/2.
  From beginning of August to end of September, QSEs and TSPs enter outages effective during September for the 168 hour test.
  Outages starting and ending in October and/or November are optional to maintain.
  All outages effective December and beyond need to be entered into the Nodal Outage Scheduler.
  First production pull of Outages on10/2 for CRR Auction Model.

## Slide 5
Outage Scheduler Transition Timeline – Approach B
Outage Scheduler with Zonal Outage Import
  Delete all Outages and run Zonal to Nodal Transfer Tool Monday, 8/14.
    Available for review and submissions Monday afternoon, 8/14.
    List of Outages not transferred can be provided upon request.
    Due to sensitive nature of Resource Outages, they will not be transferred by the Transfer tool.
  TSPs are requested to enter remaining outages not imported by the start of the 168 hour test.
  TSPs should also begin entering outages effective December and beyond to support Go-Live.
  Outages starting and ending in October and/or November are optional to maintain .
  TSPs required to certify Outages in the Nodal Outage Scheduler by 9/17 for all Outages December and beyond.
  First production pull of OS data 10/2 for first CRR Auction.
TSPs are responsible to ensure that the outages in the Nodal Outage Scheduler are correct

## Slide 6
ERCOT OS Readiness – Nodal Metric EMO3
Nodal Metric EMO3, criteria #1 – “A test of the Outage Management Process is completed”
  Integration between Outage Scheduler and Outage Evaluation has been tested successfully throughout Market Trials.
  Outage Coordinators able to approve outages in Outage Evaluation and send data back to the Outage Scheduler.

## Slide 7
Nodal Metric EMO3, criteria #2 – “An approved Outage Minimization Plan is implemented”
  Guideline requests TSPs to limit the submission of outages starting after November 21, 2010 and ending before January 4, 2010
  ERCOT recommends removing criteria #2 because Outage Coordinators have sufficient authority to approve/reject outages without a Outage Minimization Guideline.
ERCOT OS Readiness – Nodal Metric EMO3

## Slide 8
ERCOT OS Readiness – Software Defects
Currently only two Sev2 defects in process for Outage Scheduler (Sev2 means that ERCOT does not have a manual workaround).
  Defect 16525 – Load Resources are not appearing in the OS Database.
    Fix scheduled to migrate to N-Prod in late June.
  Defect 15052 – Future equipment, yet to be energized, is not being loaded in the OS Database.
    Limits ERCOT ability to studies outage with forward looking models.
    Software fix in process, target migration to N-Prod in early July.

## Slide 9
ERCOT Readiness Criteria – Manager/Director Sign-Off
ERCOT will present a manager/director sign-off for Outage Scheduler at the TAC Meeting in August and ERCOT Board of Directors meeting in September.

## Slide 10
MP Readiness Criteria – Outage Scheduler Qualification
In Market Trials, to quality for Outage Scheduler, QSEs and TSPs had to submit transactions for the following scenarios
QSEs – 78/79 QSERs completed qualification
  99% completed (based on generation share)
  1 Load Resource remaining
TSPs – 20/23 TSPs completed qualification
  99.8% completed (based on ownership share)
  Remaining 3 due to operatorship issues that must be confirmed by the TSP and changed by ERCOT in NMMS
  9 new TSPs in 30 day grace period (.3% ownership share)

## Slide 11
MP Readiness Criteria – Training
ERCOT has developed a user guide along with a web-based user interface training module to introduce the user interface and provide ongoing reference material for end users of the application.
Instructor led sessions are targeted at personnel from TSPs, QSEs and Resource Entities and are intended to:
  Review ERCOT market rules related to outage coordination
  Describe roles and responsibilities for ERCOT and market participants
  Introduce the use and design of the Outage Scheduler
  Demonstrate the basic functions of the Outage Scheduler
  Describe the interfaces between the outage scheduler and other Nodal Market applications.
TSPs and QSEs are encouraged to send personnel that will either submit or maintain outage information on the Outage Scheduler as well as those that may need to generate reports on outages.
Sign up using LMS - https://www.ercottraining.com/lms/default.asp
The location and schedules of the course are shown below:
Date | Time | City | Address
22-Jun-10 | 09:00 to 15:00 | Austin, TX | ERCOT Austin
 |  |  | 7620 Metro Center Dr.
 |  |  | Austin, TX 78744
28-Jun-10 | 09:00 to 15:00 | Dallas, TX | Oncor Energy Plaza
 |  |  | 1601 Bryan St.
 |  |  | Dallas, TX 75201
15-Jul-10 | 09:00 to 15:00 | Houston, TX | CenterPoint Energy
 |  |  | Energy Control and Data Center
 |  |  | 16303 Tomball Parkway
 |  |  | Houston, TX 77065

## Slide 12
Outage Scheduler Protocol Timeline
ERCOT proposes that Section 3.1 “Outage Coordination” of the Nodal Protocols will become binding on November 1st, 2010.
  Allows 30 days necessary for Outage Coordination to review and approve outages that will be effective post Go-Live.
Based on the November 1st, 2010 binding date:
  Two Market Notices to be sent notifying the Market of the 11/1 effective date of Section 3.1
    30 days out
    10 day out
  BOD Approval in September
  TAC Approval in July or August
  NATF Review in June and/or July