## Slide 1
NATF Readiness Update
Brandon McElfresh
June 23, 2010

## Slide 2: Reminder – Nodal Registration Cutoff – QSEs and CRRAHs
Scope
  What is the cutoff date for QSEs and CRRAHs to begin registration for Nodal Go-Live from the 168 hour test to Nodal Go-Live (based on ERCOT resource availability)?
Registration must begin by these dates to be qualified for Nodal Go-Live
  August 13th, 2010
    QSEs with Resources with a new WAN connection *
    CRRAHs (to be qualified for the 10/13 PCRR nomination and for the 11/11 December 2010 CRR Auction) * ~
  October 1st, 2010
    QSE with Resources using a Nodal qualified service provider *
    QSEs without Resources *
    Sub-QSEs using a Nodal qualified parent QSE *
Mechanics
    Qualification will follow the Nodal production qualification process and all testing will be done in the MOTE environment
    MPs that want to begin registration past these
    deadlines will be examined on a case-by-case basis
    Nodal Metric MP22 will measure progress of
    new entrants
  * QSE Application or CRRAH Application must be submitted, which includes Credit Application
  ~ Doesn’t include NOIE Allocation Eligibility Form, which must be submitted by 6/30 for CRRAHs eligible for PCRRs
QSERs (new wan),
CRRAHs
QSERs (existing wan),
Sub-QSERs,
QSEs w/o Resources

## Slide 3: Missing Telemetry – Exclusion Points
Scope
  ERCOT has ~600 remaining telemetry points with no ICCP data.
  These are the difficult points that typically require coordination between multiple MPs (ownership, operatorship, lack of an RTU, does not exist)
Current Statistics
  QSEs with Resources
    357 total points
  TSPs
    253 total points
Going Forward
  ERCOT will continue to publish dashboards and reach out to QSEs and TSPs
  ERCOT requesting that NATF representatives communicate this effort to its ICCP contacts in order to resolve these points
Class | kV | Total
QSE | 13 | 90
 | 69 | 113
 | 138 | 131
 | 345 | 23
TSP | 13 | 31
 | 69 | 76
 | 138 | 118
 | 345 | 8
Grand Total |  | 590

## Slide 4: MP21 WGR MET Telemetry – Follow-up
Scope
  This metric will measure WGRs ability to submit required MET based on Nodal Protocols 3.13 Renewable Production Potential Forecasts and 4.2.2 Wind-Powered Generation Resource Production Potential
  ERCOT will move forward with the MP21 metric to ensure this is area is addressed prior to the completion of the 168 hour test
Base Line
  ERCOT will use the status of MET data performance of WGRs as of July 1st, 2010 data to initiate scoring starting mid-July through the end of the 168 hour test
Going Forward
  Resource Entities with WGRs will be notified by ERCOT 5 business days prior to posting scores
  Dashboard with July 1, 2010 data will be posted July 2nd
  Account Managers will begin reaching out the REs with WGRs July 5th
  Metric will begin July 14th

## Slide 5: Next 60-days of Classes/Workshops
Course | Start Date | Location
Load Serving Entity 201 | June 23 | Austin Energy Town Lake Center (Austin)
NOIE QSE Operations | June 23 | Sam Rayburn Plant (Victoria)
Credit Management Workshop | June 24 | ERCOT Met Center (Austin)
ERCOT 101 for Wind Generation | June 28 | ERCOT Met Center (Austin)
Outage Scheduler | June 28 | Energy Plaza (Dallas)
Transmission 101 | June 29 | Energy Plaza (Dallas)
Congestion Revenue Rights | June 29 | Calpine (Houston)
Ancillary Services Workshop | June 30 | ERCOT Met Center (Austin)
Market Settlements 301 | July 6 | ERCOT Met Center (Austin)
ERCOT 101 for Wind Generation | July 12 | Norris Conference Center (Houston)
Generation 201 | July 13 | Norris Conference Center (Houston)
Transmission 101 | July 13 | CenterPoint Energy (Houston)
Enrollment at: http://nodal.ercot.com/training/courses/index.html

## Slide 6: Next 60-days of Classes/Workshops - continued
Course | Start Date | Location
Outage Scheduler | July 15 | CenterPoint Energy (Houston)
Load Serving Entity 201 | July 20 | Optim Energy (Dallas)
Congestion Revenue Rights | July 21 | Optim Energy (Dallas)
ERCOT Nodal 101 | July 26 | First Choice (Dallas)
Generation 101 | July 27 | Calpine (Houston)
Transmission 101 | August 3 | ERCOT Met Center (Austin)
Basic Training Program | August 10 | Calpine (Houston)
ERCOT Nodal 101 | August 10 | ERCOT Met Center (Austin)
Market Settlements 301 | August 17 | City of Garland Fire Administration Building (Dallas)
Enrollment at: http://nodal.ercot.com/training/courses/index.html

## Slide 7: RED/AMBER Metrics Summary
ERCOT Metrics
Market Participant Metrics
Metric Name | Current Score | Applies to | Weight | Green % | Yellow % | Red % | Not Scored % | Primary Criteria | Notes
Market Participant Metrics |  |  |  |  |  |  |  |  | 
MP15(B) CRR Connectivity Qualification | Red | CRRAHs | Even weighting | 94.2% | 0.0% | 0.0% | 5.8% | Successful submission CRR transactions | 66/74 CRRAHs qualified. Greater than 5% RED.
CRR3 Operation of CRR Auctions and Allocations | Red | CRRAHs | Even weighting | 83.3% | 0% | 17.7% | 0.0% | Participation in at least one of the last two auctions or allocations. | 56/66 CRRAHs with adequate participation in June or July auction or allocation
MP16 DAM Participation | Amber | QSEs | Even Weighting | 78.6% | 6.6% | 12.6% | 1.1% | Participation in 50% of the Day-Ahead Market runs | 143/182 QSEs w/o Resources
Metric Name | Current Score | Applies to | Weight | Green % | Yellow % | Red % | Not Scored % | Primary Criteria | Notes
ERCOT Metrics |  |  |  |  |  |  |  |  | 
EMO9(A) State Estimator Convergence | Amber | ERCOT | N/A | N/A | 95.44 | N/A | N/A | State Estimator converges 97% of runs during a monthly test period. | 95.44% Convergence for State Estimator for the month of May.
EMO9(B) RTCA Modeling Differences | Red | ERCOT | N/A | N/A | N/A | 84.33% | N/A | 95% of load tap setting values matched between Zonal/Nodal | 84.33% Match for transformer tap settings. 1430 transformers in Nodal.

## Slide 8
BACKUP SLIDES

## Slide 9: Active Nodal Metrics
ACTIVE NODAL METRICS |  |  |  |  |  |  |  | 
Metric # | Metrics Name | Category | ERCOT | QSERs | QSEs | TSPs | CRRAHs | REs
MO4 | Verify SCED Execution Quality | RT | Green | N/A | N/A | N/A | N/A | N/A
MO5 | Generate LMPs for 6 months | RT | Green | N/A | N/A | N/A | N/A | N/A
CRR3 (ERCOT) | Operation of CRR Auctions and Allocations | CRR | Green | N/A | N/A | N/A | N/A | N/A
MO9 | Generate Day-Ahead LMPs | DAM | Green | N/A | N/A | N/A | N/A | N/A
MO10 | DRUC Execution | DAM | Green | N/A | N/A | N/A | N/A | N/A
CO8 | Verify CRR Auction Invoices | COMS | Green | N/A | N/A | N/A | N/A | N/A
EMO9(A) | State Estimator Convergence | NM | Amber | N/A | N/A | N/A | N/A | N/A
EMO9(B) | RTCA Modeling Differences | NM | Red | N/A | N/A | N/A | N/A | N/A
EMO10 | Anomalous/Auto-Disabled Telemeted Points | NM | Green | N/A | N/A | N/A | N/A | N/A
E1 | ERCOT Internal Training | READ | Green | N/A | N/A | N/A | N/A | N/A
E9 | Develop Nodal Procedures | READ | Green | N/A | N/A | N/A | N/A | N/A
MP3 | Market Submissions Connectivity Qualification | CONN | Green | Green | Green | N/A | N/A | N/A
MP15B | CRR Connectivity Qualification | CONN | Red | N/A | N/A | N/A | Red | N/A
MP20 | Outage Scheduler Connectivity Qualification | CONN | Green | Green | N/A | Green | N/A | N/A
EMO6 | Individual LFC Testing | RT | N/A | Green | N/A | N/A | N/A | N/A
MP15A | Real-Time Market Daily Participation | RT | N/A | Green | N/A | N/A | N/A | N/A
EMO6 | Individual LFC Testing | RT | N/A | Green | N/A | N/A | N/A | N/A
CRR3 | Operation of CRR Auctions and Allocations | CRR | N/A | N/A | N/A | N/A | Red | N/A
MP16 | DAM Participation | DAM | N/A | Green | Amber | N/A | N/A | N/A
MP20 | Outage Scheduler Connectivity Qualification | OS | N/A | Green | N/A | Green | N/A | N/A
N2 | Telemetry/ICCP System Failover | NM | N/A | Green | N/A | N/A | N/A | N/A
MP6(SE) | Telemetry Compliance 3.10.7.5 | NM | N/A | Green | N/A | N/A | N/A | N/A
MP6(SCED) | Telemetry Compliance 3.10.7.5 | NM | N/A | Green | N/A | N/A | N/A | N/A
MP6 (TSP) | Telemetry Compliance 3.10.7.5 | NM | N/A | N/A | N/A | Green | N/A | N/A
MP14B | Participation in NOMCR Trials | NM | N/A | N/A | N/A | Green | N/A | N/A
MP14C | Network Model Validation | NM | N/A | N/A | N/A | Green | N/A | N/A
MP11 | Resource Registration | RES | N/A | N/A | N/A | N/A | N/A | Green

## Slide 10: New Metrics
2010
New
Metrics
October
September
August
July
MP21 WGR ICCP Met Telemetry
CO2 Verify Disputes
C10 Credit Calculations
EMO2 Verify Voltage Support
EMO9(C) Validate Zonal and Nodal Security Analysis (CSCs)
MO8 Verify DAM Execution Quality
N1 ERCOT Telemetry Alarm Processing
E7 Validate ISM Access for IMM
E10 Validate ISM, CDR, and Lodestar Report Access for Internal Use
MP22 New Entrant Readiness
EMO9(D) Validate Zonal and Nodal Security Analysis (all security violations
E5 Nodal SAS 70 Readiness
C1 – C10 Contingency Plan Procedures
R2 Develop Texas Nodal Market Launch Plan
R3 168-Hour System Stability Test and Trial Real Time Settlement

## Slide 11: Metrics Roadmap
PURPLE
ORANGE
Timing and Design Confirmed
Timing subject to change, design in progress
MP15A
MP16
MP20
MP3
MP6
MP11
MP14C
E9
E1
N2
EMO9(B)
CRR3
EMO6
MO4
MO5
CO1
CO2
CO3
CO4
CO5
CO6
CO7
CO8
CO9
C10
E7
E11
E12
C1-C10
EMO13
MO7
CRR4
E5
IMM1
R0
R2
R3
MP15B
MP3
N1
E3
E10
R1
MP22
EMO9(D)
MO9
MO8
MO3
MO10
EMO10
EMO9(C)
EMO7
EMO9(A)
New Metric
MP23
EMO2
EMO8

## Slide 12: CRR Metrics
Metric Name | Current Score | Applies to | Weight | Green % | Yellow % | Red % | Not Scored % | Primary Criteria | Notes
Market Participant Metrics |  |  |  |  |  |  |  |  | 
MP15(B) CRR Connectivity Qualification | Red | CRRAHs | Even weighting | 90.7% | 0.0% | 9.3% | 0.0% | Successful submission CRR transactions | 68/75 CRRAHs qualified. Greater than 5% RED.
CRR3 Operation of CRR Auctions and Allocations | Red | CRRAHs | Even weighting | 85.3% | 0% | 14.7% | 0.0% | Participation in at least one of the last two auctions or allocations. | 58/68 CRRAHs with adequate participation in June or July auction or allocation
ERCOT Metrics |  |  |  |  |  |  |  |  | 
CRR3 Operation of CRR Auctions and Allocations | 6/21/2010 | ERCOT | N/A | N/A | N/A | N/A | N/A | Auction results distributed to participants per schedule in CRR Handbook | 6/21 2010 June Monthly Auction results posted to market.
 | TBD | ERCOT | N/A | 100% | 0% | 0% | 0% | Allocated Revenue Rights in statistical sample = 100% accurate | Source – Sink prices = CRR Clearing prices for obligations for BOY auction. ERCOT working on similar validation process for options.
CO8 Verify CRR Auction Invoices | 6/22/2010 | ERCOT | N/A | 100% | 0% | 0% | 0% | CRR Auction Result for MP(n) – CRR Auction Invoices for MP(n) = 0$ | July CRR auction invoices to be released on 6/22
 | 6/22/2010 | ERCOT | N/A | 100% | 0% | 0% | 0% | System Generated CRR Auction Invoices not posted = 0 | July CRR auction invoices to be released on 6/22

## Slide 13: Real-Time Metrics
Metric Name | Current Score | Applies to | Weight | Green % | Yellow % | Red % | Not Scored % | Primary Criteria | Notes
Market Participant Metrics |  |  |  |  |  |  |  |  | 
MP3 Market Submissions Connectivity Qualification | Green | QSERs | Generation Ratio Share | 99.0% | 1.0% | 0.0% | 0.0% | Successful submission of RT and DAM transactions | 79/81 QSERS qualified
 | Green | QSEs | Even weighting | 98.9% | 1.1% | 0.0% | 0.0% |  | 178/182 QSEs qualified.
EMO6 Individual LFC Testing | Green | QSERs | Generation Ratio Share | 96.9% | 0% | 0% | 3.1% | 80% of system-wide generation has completed individual QSE tests for LFC | 70/73 QSERs completed their individual LFC test or provided attestation
MP15-A Real-time Market Participation | Green | QSERs | Generation Ratio Share | 100.0% | 0.0% | 0.0% | 0.0% | Weekly average of daily SCED submissions | 79/79 QSERs above 95% weekly average for SCED submissions.
ERCOT Metrics |  |  |  |  |  |  |  |  | 
MO3 Verify SASM | Green | ERCOT | N/A | 100% | N/A | N/A | N/A | Multiple SASMs are successfully executed during Market Trials and the 168 hour test. | SASMs successfully run on 4/28, 4/30, 5/4, 5/6, 5/7, 5/12, 5/14, 6/9, and 6/10. No issues reported.
MO4 Verify SCED Execution Quality | Green | ERCOT | N/A | 100% | 0% | 0% | 0% | All successful SCED executions passed the post-execution price validations. | 6/1 - 6/14 period - 4,035 Price Validation runs with no rule violations
MO5 Generate 6 Months of LMPs | Green | ERCOT | N/A | 98.1%. | 0% | 1.9% | 0% | 95% of SCED executions completed with LMPs posted on MIS. | 6/1 - 6/14 period, 3,971 out of 4,031 SCED runs with LMPs posted.
CO5 Verify RTM Settlement Statements/CO6 Verify RTM Settlement Invoices | Green | ERCOT | N/A | 100% | 0% | 0% | 0% | System Generated RT Statement Dollars- Independently Generated RT Calculation Dollars =$0 | 6660 RTM Statements; 1609 RTM Invoices All validated $$ = system generated (with some rounding differences)
 | Green | ERCOT | N/A | 100% | 0% | 0% | 0% | System Generated RT Statements/Invoices not posted = 0 | 6660 RTM Statements; 1609 RTM Invoices All posted on time

## Slide 14: Day-Ahead Market Metrics
Metric Name | Current Score | Applies to | Weight | Green % | Yellow % | Red % | Not Scored % | Primary Criteria | Notes
Market Participant Metrics |  |  |  |  |  |  |  |  | 
MP16 DAM Participation | Green | QSERs | Generation Ratio Share | 99.0% | 1.0% | 0.0% | 0.0% | Participation in 50% of the Day-Ahead Market runs | 78/79 QSEs with Resources
 | Amber | QSEs | Even Weighting | 78.6% | 6.6% | 12.6% | 1.1% |  | 143/182 QSEs w/o Resources
CO10 Credit Calculations | 6/30/2010 | QSERs, QSEs | Gen Ratio Share, Even Weighting | N/A | N/A | N/A | N/A | <= 25% of MPs credit limits inconsistent with protocols | To be determined
ERCOT Metrics |  |  |  |  |  |  |  |  | 
MO8 Verify DAM Execution Quality | Report in Progress | ERCOT | N/A | N/A | N/A | N/A | Red | DAM executions pass the post-execution price validations | Report in progress
MO9 Generate DAM LMPs | Green | ERCOT | N/A | N/A | N/A | N/A | N/A | 95 percent DAM execution as evidenced by DAM LMP postings | 6/1 – 6/14 – 7/7 DAM runs execute(doesn’t measure quality)
MO10 DRUC Execution | Green | ERCOT | N/A | N/A | N/A | N/A | N/A | 95 percent DRUC execution | 6/1 – 6/14 - 7 out of 7 DRUC runs executed (doesn’t measure quality)
CO3 Verify DAM Settlement Statements/CO7 Verify DAM Invoices | Green | ERCOT | N/A | 100% | 0% | 0% | 0% | System Generated RT Statement Dollars- Independently Generated RT Calculation Dollars =$0 | 4715 DAM Statements and Invoices All validated $$ = system generated (with some rounding differences)
 | Green | ERCOT | N/A | 100% | 0% | 0% | 0% | System Generated RT Statements/Invoices not posted = 0 | 4715 DAM Statements and Invoices All posted on time
CO10 Credit Calculations | 6/30/2010 | ERCOT | N/A | N/A | N/A | N/A | N/A | ERCOT performs credit calcs for a stat. sample of MPs | To be determined
MP16 – Metric is based on a 2 week rolling average (6/7 – 6/18 – 9 runs).
MP16 – 97% Load participating.

## Slide 15: Network Modeling Metrics
Metric Name | Current Score | Applies to | Weight | Green % | Yellow % | Red % | Not Scored % | Primary Criteria | Notes
Market Participant Metrics |  |  |  |  |  |  |  |  | 
MP14-C TSP Model Validation | Green | TSPs | Ownership Ratio Share | 99.9% | .1% | 0.0% | 0.0% | Network Model data validated by TSP | 24/28 TSPs have submitted model validation e-mail to ERCOT.
MP6 Telemetry Compliance with Nodal Protocols 3.10.7.5 | Green | QSERs | Generation Ratio Share | 100% | 0.0% | 0.0% | 0.0% | Expected State Estimator telemetry submitted. | 78/78 complete. 3502 total SE points provided
 | Green | QSERs | Generation Ratio Share | 100% | 0.0% | 0.0% | 0.0% | Expected SCED telemetry submitted. | 78/78 complete. 7629 SCED points provided
 | Green | TSPs | Ownership Ratio Share | 99.3% | 0.0% | 0.0% | .7% | Expected TSP telemetry per ICCP Handbook submitted | 14/17 TSPs above 98% threshold for GREEN. 143 points outstanding
N2 Telemetry ICCP System Failover | Green/White only | QSERs | Generation Ratio Share | 18.3% | 0% | 0% | 81.7% | ICCP Failover test completed successfully prior to the 8-hour LFC test. | 22/78 QSERs completed ICCP telemetry failover test.
MP18 Mapping of Resources and Loads in Private Use Networks | 6/30/2010 | QSERs | Generation Ratio Share | N/A | N/A | N/A | N/A | # of QSE(n) PUN Points Provided / # of QSE(n) PUN Points Expected | 306 points across 7 QSEs with Resources. 15 points still assigned to TSP.
MP21 WGRs ICCP Meteorological Telemetry | 6/30/2010 | REs (only WGRs) | Registered MW Capacity Ratio Share | N/A | N/A | N/A | N/A | WGRs must meet reasonability tests for MET ICCP | To be determined
MP23 Telemetry Quality (MP to ICCP server) | 6/30/2010 | TSPs | Ownership Ratio Share | N/A | N/A | N/A | N/A | # of TSP(n) Suspect/Bad points provided / # of TSP(n) points total | 1077 Suspect/Bad points (98.3% good quality).
 | 6/30/2010 | QSERs | Generation Ratio Share | N/A | N/A | N/A | N/A | # of QSER(n) Suspect/Bad points provides / # of QSER(n) points total | 277 Suspect/Bad points (98% good quality)
Network Model Metrics
MP6 does not include 405 QSE CB and DSC points from TSP outreach. ERCOT is determining whether these rollback into the QSER MP6 measurement.

## Slide 16: Network Model Metrics
Network Modeling Metrics
Metric Name | Current Score | Applies to | Weight | Green % | Yellow % | Red % | Not Scored % | Primary Criteria | Notes
ERCOT Metrics |  |  |  |  |  |  |  |  | 
EMO9(A) State Estimator Standards Performance | Amber | ERCOT | N/A | N/A | N/A | N/A | N/A | State Estimator converges 97% during monthly test period | 95.44% Convergence for State Estimator for the month of May.
EMO9(B) RTCA Modeling Differences | Green | ERCOT | N/A | 96.8% | N/A | N/A | N/A | 95% of impedance values matched between Zonal/Nodal | 97.9% match for impedances for lines and transformers. 6718 lines and transformers in Nodal.
 | Green | ERCOT | N/A | 96.8% | N/A | N/A | N/A | 95% of dynamic line ratings matched between Zonal/Nodal | 97.5% match for ratings for lines. 5288 lines in Nodal.
 | Red | ERCOT | N/A | N/A | N/A | 84.33 | N/A | 95% of load tap setting values matched between Zonal/Nodal | 84.3% Match for transformer tap settings. 1430 xfrms in Nodal.
EMO10 Anomalous / Auto-Disabled Telemetered Points | Green | ERCOT | N/A | 1.91% | N/A | N/A | N/A | The % of Anomalous and Auto-Disabled Measurements < 2% of Total Measurements | April Nodal 2.58% May Nodal 1.92% June Nodal 1.91%
EMO9(C) RTCA CSC Comparison | 7/14/2010 | ERCOT | N/A | N/A | N/A | N/A | N/A | CSC Pre-contingency SE Flows within 5% (Hourly snapshot) | Measurement establishes baseline flows on Commercial lines to indicate the significance of Psuedo modeling and multi-section lines on the SE flows.
EMO9(D) Validate Zonal and Nodal Security Analysis Results | 9/8/2010 | ERCOT | N/A | N/A | N/A | N/A | N/A | 90% of active constraints in Zonal RTCA are also detected in Nodal RTCA | To be determined

## Slide 17: Other Readiness Metrics
Metric Name | Current Score | Applies to | Weight | Green % | Yellow % | Red % | Not Scored % | Primary Criteria | Notes
Market Participant Metrics |  |  |  |  |  |  |  |  | 
MP20 Outage Scheduler Connectivity Qualification | Green | QSERs | Generation Ratio Share | 98.9% | 0.0% | 0.0% | 1.1% | Successful submission of OS transactions | 78/79 QSERS qualified.
 | Green | TSPs | Ownership Ratio Share | 99.7% | 0% | 0% | .3% |  | 20/23 TSPs qualified.
MP11 Resource Registration | Green | REs | Registered MW Capacity Ratio Share | 99.6% | 0.0% | .4% | 0.0% | Decision Making Authority form submitted, and GENMAP validated | 154/157 Resources completed.
CO2 Verify Dispute Process | 7/14/2010 | QSERs, QSEs | Generation Ratio Share, Even Weighting | N/A | N/A | N/A | N/A | >=1 dispute submit per MP. # of unprocessed disputes by 168 = 0 | To be determined
ERCOT Metrics |  |  |  |  |  |  |  |  | 
E1 ERCOT Staff Completes Training | Green | ERCOT | N/A | 100% | N/A | N/A | N/A | Training plans must be adhered to for highly impacted departments | 15 out of 15 highly impacted departments are up to date with their training plans.
E9 Develop Nodal Procedures | Green | ERCOT | N/A | 100% | N/A | N/A | N/A | Procedures developed 1 month prior an exercised in the appropriate Market Trials Phase | All MT4 and MT5 are developed and the MT4 procedures exercised as scheduled in MT4.
EMO3 Verify Outage Evaluation System Functionality | 6/23/2010 | ERCOT | N/A | N/A | N/A | N/A | N/A | A test of the Outage Management Process is completed | Will be reviewed as part of Outage Scheduler Go-Live at 6/23 NATF

## Slide 18: Participant Readiness Touch Points
2010
Meetings
Training
Outreach
Market trials
September
August
July
NATF 7/8
MRS #5 168 Hour Test (Tentative)
Dispute & Reports Metrics
Standby site visits
Weekly Trials calls
48 hr system-wide LFC test
Verifiable costs loaded into N-Prod
Nodal 101
Transmission 101
Generation 101, 201
Basic Training Program
NOIE QSE Operations
Settlements 301
Weekly Trials calls
Prepare for 168 hr test
NATF 8/19
Nodal 101
Transmission 101
Generation 101, 201
Basic Training Program
NOIE QSE Operations
Settlements 301
Standby site visits
Weekly Trials calls
Execute 168 hr test
NATF 9/14
Nodal 101
Transmission 101
Generation 101, 201
NOIE QSE Operations
Settlements 301
MMS & MIS GUI (Online only)
Standby site visits
October
Preparation for Nodal Go-Live
NATF 10/5
TBD
TBD