## Slide 1: Nodal Go-Live Update Review of Network Modeling Go-Live Items
Kenneth Ragsdale
NATF
June 23, 2010

## Slide 2: Readiness Methodology
ERCOT will measure readiness by the following categories:
  System Readiness – an evaluation of a particular system needed to support identified market activities
  Process Readiness – an evaluation of the Processes and Procedures necessary to support identified market activities
  People Readiness – an evaluation of ERCOT and Market Participant capabilities to support identified market activities
ERCOT will review the readiness criteria with NATF prior to requesting a vote from TAC

## Slide 3
Nodal Program Cutover
Cutover Timeline Key Dates (Aug – Oct) |  | 
Network Operations Modeling | 08/01 09/01 10/02 10/13 10/15 | Begin transition plan for Network Modeling timelines Deadline to submit Model changes for Month of December Network Model built for PCRR Allocation Network Model built for CRR Auction Model complete and available for Market Participant testing
Outage Scheduling | 08/14 10/02 10/13 | Begin transition plan for Outages occurring in December December Outages pulled for initial CRR Network Model December Outages pulled for CRR Network Model
Credit Management | 10/21 | Initial Credit Limit for CRR Auction posted
Congestion Revenue Rights | 10/18 10/20 | Last day to Register for CRR Monthly Auction PCRR Nominations close for December Allocation Allocation results published / Network Model Posted
  The table below outlines key dates and activities requiring Market Participant support

## Slide 4
Network Operations Modeling – Go Live
System Readiness | Planned Completion | Status
SEM Go-Live | 8/31/09 | Complete
TSP Model Validation (Metric MP14C) | 4/30/10 | Complete
Model Change Request Tools Support Market Updates | Ongoing | Green
Regular Model Loads into Market Trials Systems | Ongoing | Green
8 Hour LFC Test Executed w/ Network Model from NMMS | 6/17/10 | Complete
Process Readiness |  | 
Network Operations Change Request Timeline Transition Plan established | 6/03/10 | Complete
Network Modeling Procedures Ready | 8/01/10 | Ongoing
Market Rules – Protocol Transition Plan for September | 7/23/10 | In Progress

## Slide 5
Network Operations Modeling – Go Live
People Readiness | Planned Completion | Status
ERCOT Staff Support of Market Trials | Ongoing | Green
ERCOT Staff Trained on System and Processes | 6/22/10 | Green
Market Participant Training Delivered | 7/29/09 | Green
Readiness Review and Approval |  | 
NATF Review | 6/23/10 | In Progress
ERCOT Management Approval | 6/26/10 | In Progress
TAC Approval | 7/01/10 | 
BOD Approval | 7/20/10 | 
30 Day Market Notice | 7/30/10 | 
10 Day Market Notice | 8/20/10 |