## Slide 1: Network Operations Model Go-Live Decision
Kenneth Ragsdale
TAC
July 1, 2010

## Slide 2: Readiness Methodology
ERCOT will measure readiness by the following categories:
  System Readiness – an evaluation of a particular system needed to support identified market activities
  Process Readiness – an evaluation of the Processes and Procedures necessary to support identified market activities
  People Readiness – an evaluation of ERCOT and Market Participant capabilities to support identified market activities
ERCOT reviewed the readiness criteria at the 6/23/10 NATF and is requesting a vote from the 7/1/10 TAC on the Market Readiness Criteria per Section 21.12.3, Notice to Market Participants of Effective Date for Nodal Protocol Provisions and Retirement of Zonal Protocol Provision.

## Slide 3: Protocol 21.12.3
21.12.3 Notice to Market Participants of Effective Date for Nodal Protocol Provisions and Retirement of Zonal Protocol Provision
No part of the nodal market design may start operation until all the Market Readiness Criteria for that part of the nodal market design have been met. Certification that all Market Readiness Criteria have been met must be made at least by each of the following: the Technical Advisory Committee (TAC), ERCOT and the ERCOT Board. Upon such certification, ERCOT shall issue two Notices alerting Market Participants to the effective date of Nodal Protocol sections and the retirement of Zonal Protocol sections, as applicable. ERCOT shall issue the first Notice no less than thirty (30) days prior to the effective date or retirement date, as applicable, and the second Notice no less than ten (10) days prior to the effective date or retirement date, as applicable. The Notice shall include:
  (1) The Nodal Protocol Sections to become effective; and
  (2) The Zonal Protocol Sections to be retired, if any.

## Slide 4
Nodal Program Cutover
Cutover Timeline Key Dates (Aug – Oct) |  | 
Network Operations Modeling | 08/01 09/01 10/02 10/13 10/15 | Begin transition plan for Network Modeling timelines Deadline to submit Model changes for Month of December Network Model built for PCRR Allocation Network Model built for CRR Auction Model complete and available for Market Participant testing
Outage Scheduling | 08/14 10/02 10/13 | Begin transition plan for Outages occurring in December December Outages pulled for initial CRR Network Model December Outages pulled for CRR Network Model
Credit Management | 10/21 | Initial Credit Limit for CRR Auction posted
Congestion Revenue Rights | 8/13 10/18 10/20 | Last day to Register for CRR Monthly Auction PCRR Nominations close for December Allocation Allocation results published / Network Model Posted
  The table below outlines key dates and activities requiring Market Participant support

## Slide 5
Network Operations Modeling – Go Live
System Readiness | Planned Completion | Status
SEM Go-Live | 8/31/09 | Complete
TSP Model Validation (Metric MP14C) | 4/30/10 | Complete
Model Change Request Tools Support Market Updates | Ongoing | Green
Regular Model Loads into Market Trials Systems | Ongoing | Green
8 Hour LFC Test Executed w/ Network Model from NMMS | 6/17/10 | Complete
Process Readiness |  | 
Network Operations Change Request Timeline Transition Plan established | 6/03/10 | Complete
Network Modeling Procedures Ready | 8/01/10 | Ongoing
Market Rules – Protocol Transition Plan for September | 7/23/10 | In Progress

## Slide 6
Network Operations Modeling – Go Live
People Readiness | Planned Completion | Status
ERCOT Staff Support of Market Trials | Ongoing | Green
ERCOT Staff Trained on System and Processes | 6/22/10 | Green
Market Participant Training Delivered | 7/29/09 | Green
Readiness Review and Approval |  | 
NATF Review | 6/23/10 | Reviewed
ERCOT Management Approval | 6/26/10 | In Progress
TAC Approval | 7/01/10 | 
BOD Approval | 7/20/10 | 
30 Day Market Notice | 7/30/10 | 
10 Day Market Notice | 8/20/10 | 

## Slide 7: 6/23/10 NATF Issues Discussed
Placeholder slide – update forthcoming
NATF Risks/Concerns Identified
Mitigation Plan/Recommendations

## Slide 8: For TAC Consideration
Possible motion for TAC consideration:
TAC certifies that all Network Operations Model Go-Live Market Readiness Criteria have been met or are on schedule to be delivered according to the go-live sequence. TAC recommends that the Board also certify that all Market Readiness Criteria have been met for the Network Operations Model Go-Live on September 1, 2010. TAC requests ERCOT Staff promptly notify NATF if any outstanding issues prevent proper maintenance and operation of the Network Operations Model.