| TSP Combined Issues List 7/7/2010 |
| --- |
| Number | Priority | Issue Description | Impact to Transmission Operations | Potential Resolution | Comments |
| NMMS Business Process Issues |
| 1 | 2 | What is the definition of an Interim Update? The protocols give ERCOT 15 days to review the NOMCR for completeness. Responding to ERCOT’s request during this review period does not cause the NOMCR to convert to an Interim Update. Design of the Interim Update approval process and how interim updates have not yet been vetted in the NDSWG. | The submittal of interims updates are allowed by the protocols. However the protocols don't clearly defined what type of changes to the ERCOT network model can be made as an interim updates | The Protocols need to clearly state that all types of changes to the network model will be accept as an interim update with the understanding that these change will be implemented with the full review of the IMM. |  |
| 2 | 2 | Processes for operational status changes need to be addressed before go-live. | There are many types of operational changes that are performed in the real-time that need to be reflected into the NMMS application. Most of these changes are not controlled by the ERCOT protocols. Examples are operational changes to switching status (what lines are being operated normally open), what voltage is being regulated to by generators, autotransformers or capacitors, what are the operating taps on an autotransformer. | Operational changes that occur in the real-time, as such should not be treated as an interim update. The ERCOT protocols should be updated to reflect this and allow these changes so that the NMMS network model provides the must accurate information possible about the transmission system. | There is perception that there are not protocol changes being driven because of metric issues. |
| 3 | High 2 | System Performance issues with NMMS needs to be resolved. | The performance of the NMMS application has been substantially degraded since the last major update of the application. It takes more then 10 minutes to validate changes to the model. There are times when you might be disconnected from the server due to this delay. When you restart the IMM session there is a possibility that the model change will need to be re-entered into NMMS. This could be the lost of hours of work. Do to timing issues when submitting these changes what might have been a standard time NOMCR submission might become an Interim update. | The performance of the NMMS application needs to be improved so that the system does not disconnect the users. This leads to loss of submitted data. A long validation time, sometimes in excess of 30 minutes, leads to user frustration and loss of continuity when submitting changes. ERCOT has indicated that they have Siemens working on this issue | This could have further impact to the market if changes cannot be submitted in a timely manner and the energization date must be delayed for one month. This has been an issue since May 1. ERCOT/ Siemens need to get this resolved. We are scheduled to begin following nodal protocol timelines August 1, and we can not have this issue unresolved by then. |
| 4 | 2 | What is the process for placing NOMCRs into service under Nodal protocols? | In the Zonal process ERCOT has a document call 'Transmission and Generation Energize Approval' This process has not been defined for the Nodal process. | ERCOT needs to update this process document to follow Nodal requirements. | Need prior to the 168 Hour Test. |
| Documentation Needs |
| 5 | 2 | Network Operations Modeling Expectations needs to have a clear description of how the Network Model and the Outage Scheduler systems are to work together on issues such as 1) how new equipment is to be energized and loaded into the outage scheduler (i.e. an operating procedure would be good); 2) how retiring equipment is to be decommissioned in the Network Model and Outage Scheduler (i.e. an operating procedure would be good here too) | Clear procedures will allow consistency and reduce unnecessary errors | Develop procedures and operating guides for consistency among TSPs and less errors, few interim upgrades. | Network Operations Modeling Expectations needs to have a clear description of how the Network Model and the Outage Scheduler systems are to work together on issues such as 1) how new equipment is to be energized and loaded into the outage scheduler (i.e. an operating procedure would be good); 2) how retiring equipment is to be decommissioned in the Network Model and Outage Scheduler (i.e. an operating procedure would be good here too) |
| 6 | 2 | What is the process for using Outage Scheduler for energizing new or relocated facilities? | ERCOT needs to provide MPs the process that should be used to notify ERCOT when placing new or relocated facilities into service. The protocols require that the ERCOT Outage Scheduler be used for this activity. The MPs have not been provided any training to accomplish this task | ERCOT needs to provide MPs the process that should be used to notify ERCOT when placing new or relocated facilities into service. The protocols require that the ERCOT Outage Scheduler be used for this activity. The MPs have not been provided any training to accomplish this task | It appears the software does not match the Protocols concerning relocation of existing lines. TSPs may not be able to use the Outage Scheduler to relocate an existing line to a new breaker on another buss. This may be due to the line will have the same name (under business practice) and if the breaker and line timing are off a day or two, there is no mechanism to take the line in Outage Scheduler to match the still energized old breaker. TSPs have no feedback from ERCOT on ICCP relinking verses Outage Scheduler to |
| 7 | 2 | Outage Scheduler is being use for much more than it was intended (Energization of new construction, retirement of old equipment, construction modifications …). The Documentation for the Outage Scheduler and schedule has not been shared with TSPs. AEP is unsure of the go-live plan and schedule as of 6/15/10 | This results in NMMS & Outage Scheduler needing to be highly coordinated. In the event there are minor discrepancies between these systems. Upgrades and network changes could be delayed and not reflect what is actually happening on the grid. | No proposed solution. Need to discuss with ERCOT. |  |
| 8 | 3 | What is the ERCOT business for managing and approving SPSs? | When will ERCOT have the 'Procedure for Approval and Distribution of RAP MP and SPS ' documentation updated to reference Nodal Protocols? | Update the document to reference Nodal Protocols and process. |  |
| 9 | 2 | What does a November 1st Binding date mean for Outage Scheduler? | ERCOT when presenting the transition plan for the outage scheduler showed a binding date to the Nodal Protocols for the Outage Scheduler of November 1st. What does this mean? Outages in the Zonal Outage Scheduler are treated using the Zonal Protocols and the Nodal Outage Scheduler uses the Nodal Protocols? Or is there some combination? | Provide a business process that clarifies this transitional period. |  |
| Modeling Issues |
| 10 | 3 | The role and amount of information expected from the TSP is more than expected and outside many of the protocols. | More resources and effort by the TSP resulting in higher costs than anticipated There are 3 potential impacts: 1. Date of energization for used and useful and the TSP can get paid for an energized asset on new facilities. 2. Customer Impact if a shift due to change in energization due to interim updates as well as the impact on revenue collection. 3. There are concerns that some one could come back and sue a TSP for an interim update which caused a market participant to lose money. The interim update has no impact on reliability; it is strictly for use by ERCOT. | Clarification of the TSP roles and a process for eliminating redundant information. Amnesty for providing interim updates. Would ERCOT consider allowing TSPs some number of interim updates and allow TSPs to prioritize and allow the interim updates to be implemented? | Interim Updates can impact reliability and that statement was removed. However, there are many changes that do not impact topology and really shouldn't be classified as an interim update. Interim updates can have impact on reliability and that statement probably needs to be removed. However, there are many, many changes that do not affect topology and really shouldn't be classified as interim updates. Also, all interim updates are at ERCOT discretion and there aren’t any rules on what will or will not be allowed. A great potential exists to have stranded assets for several weeks if ERCOT will not allow an interim update. ERCOT processes as described in their white paper are all built around the assumption that interim updates will practically never happen and I'm not sure that is a good assumption to build all of their processes around. |
| 11 | 2 | All CNP line names have an extra character (“1”) appended to the end of the line names. We understand this is necessary for some asset owners in ERCOT. This extra numerical character is a source of confusion to CenterPoint Energy users and systems and should be removed. Our users and our systems expect the same equipment names (including lines) in ERCOT’s NMMS system. For example, Line NEWTGF04 incorrectly appears as NEWTGF041 in the Nodal outage scheduler. Would you eliminate the extra characters appended to CenterPoint energy line name? We have crossed checked in NMMS and verified these extra character are not part of our line identifiers. (Applies to both Human Interface and web services interface) |  |  | Need by 168 Hour Test. |
| 12 | 3 | ERCOT's current Modeling Expectations (non-binding document) puts modeling and outage scheduling burden on TSPs. | ERCOT is introducing confusion between equipment "energization" and "Model ready" dates. It also increases model submittal timelines for TSPs. Additionally, this may force potential use of pseudo equipment and expected maintenance burden. |  |  |
| 13 | 2 | ERCOT introduced NOMCRs (associated with TSP owned equipment) should remain ERCOT responsibility from a compliance perspective. |  |  |  |
| 14 | 2 | Monthly Database Load: Requirement to have information for NMMS locked in on the 15th of the Month rather than a rolling schedule. | ERCOT needs to provide a process where there is a two week lock down prior to each weekly database load. A potential exists that it may be up to six weeks to energize a piece of equipment if a NOMCR problem is discovered at the last minute. ERCOT needs to have some reasonable mechanisms to accommodate interim updates. | Reasonable interim update policy. Rolling two week lock down requirement prior to each database load. Access by TSPs to a forward looking test environment to verify NOMCR and telemetry prior to energization. | NDSWG has asked several times about access to an ERCOT test environment to validate models prior to them being put into production. In our own shops, we will typically load a new model on a development system to verify changes and telemetry prior to putting it into production. We would like a similar capability with ERCOT. If ERCOT is going to push the modeling responsibilities onto the TSPs and then lock down any ability to make last minute changes through interim updates, then the TSPs need better tools to evaluate NOMCR being put into production prior to production dates. |
| 15 | 2 | The information submitted into NMMS may be duplicative causing inaccurate models. | Incorrect information will affect LMP prices. | Templates to describe the exact information needed by ERCOT on NOMCRs would facilitate better transition of information need by ERCOT and more accurate modeling information transfer. |  |
| 16 | 2 | There has always been an issue in managing the Network model and outages. Does this problem still exist with Nodal tools? | When submitting model changes into the Zonal Network Model the model change could break approved outages. What has ERCOT done with the Nodal implementations to prevent this from happening? | Explain why this problem existed in the Zonal systems and ERCOT's response on how the system prevents this from occurring or at least how this problem was minimized. |  |
| 17 | 3 | Where are the published EMS cases for MP review? | In Nodal Protocol section 3.10(8) there is a statement 'ERCOT shall notify each NOMCR requestor when the requested change is processed and implemented in accordance with Section 3.10.1, Time Line for Network Operations Model Change Requests, and ERCOT shall also provide the submitting TSP a link to a Network Operations Model containing the change for verifying the implementation of the NOMCR and associated one-line displays.' When will ERCOT starting providing the TOs with a link to these Network Operations Models for verification of the implementation of the NIOMCR. Also Nodal Protocols 3.10.4 sections; (7) A TSP, with ERCOT’s assistance, shall validate its portion of the Network Operations Model according to the timeline provided in Section 3.10.1. ERCOT shall provide TSPs access, consistent with applicable policies regarding release of CEII, to an environment of the ERCOT EMS where the Network Operations Model and the results of the Real-Time SE are available for review and analysis within five minutes of the Real-Time solution. This environment is provided as a tool to TSPs to perform power flow studies, contingency analyses and validation of SE results. (8) ERCOT shall make available to TSPs, consistent with applicable policies regarding release of CEII, the Network Operations Model used to manage the reliability of the transmission system as well as proposed Network Operations Models to be implemented at a future date. ERCOT shall make the Redacted Network Operations Model available to non-TSP Market Participants, consistent with applicable policies regarding release of CEII as well as proposed Redacted Network Operations Models to be implemented at a future date. ERCOT shall provide model information through the use of the EPRI and NERC-sponsored CIM and web-based XML communications. | ERCOT should implement the required notification so that the TO can verify the implementation of the NOMCR in the operational model. | No last minute fouls ups. How to accomplish this? |
| Reports |
| 18 | 2 | When will the State Estimator and Telemetry performance metrics and reports be available? | When will the Telemetry and SE Metrics and Performance reports be available via the Secure MIS? The MPs need this information so they can monitor their performance. | ERCOT needs to start publishing these reports so that MPs can see how they are performing. | Due to the lack of availability of reports, ERCOT has been making many ad-hoc requests for review of telemetry and SE data. |
| 19 | 3 | State Estimator Solution is not getting better. Concern that the State Estimator is very inaccurate. What is the issue from ERCOT's perspective? | If the State Estimator is not matching the zonal trend we will have many problems with LMP prices, as well as operational issues with network and reliability concerns. Decisions on what the model tells ERCOT could result in bad decisions based on invalid information. So ERCOT directives could be contradiction physical condition of the network. | Publish the State Estimator and Telemetry metrics. | ERCOT has been working on the state Estimator and Telemetry metrics reports for months and the TSPs still have not seen them. We do not know if these metrics are being met and what problems exist. We do not want these metrics reports light up on the wall of shame prior to the TSPs being able to see them and have a chance to correct any issues. |
| 20 | 3 | There needs to be an exclusion to the Outage Scheduler metrics as related to outages used to manage NOMCR energization. | The ERCOT Nodal Protocols requires the use of the ERCOT Outage Schedule to place New or Relocated Facilities into service. The metrics for this usage of the Outage Scheduler needs to be treated separately from the usage of the Outage Scheduler for operational outages. | Update the reporting metrics. |  |
| Issues Being Tracked by Other Stakeholder Groups in Addition to TSPs |
| 21 | 3 | To verify outages have been entered correctly for all segments of a line, each tap station has to be entered in the search criteria. |  |  | Might be the grouping issue. |
| 22 | 3 | There is not a “Historical Tracking” of outages. The previous version had {View Update Log}. |  |  |  |
| 23 | 3 | Selecting “Time” when entering outages is a click and drag, not a drop down box that worked quite well on the previous version |  |  |  |
| 24 | 3 | Custom Filter – “Requesting Company” defaults to TCNPE, the “Operating Company” should, also. If someone needs to change that option, so be it. |  |  |  |
| 25 | 2 | Line segments are not selectable from both terminating substations, moreover, the search pattern is not obvious to users (IE., segment NEWTGF04 between NEW and TGF substations is only available from the (NEW) substation, and missing from the TGF substation). This issue applies to both Human Interface and web services interface. |  |  | There is an outage scheduler list of issues that is owned by market trails. This issue is on that list. |
| Planning Model Issues |
| 26 | 4 | SSWG has identified items that need to be incorporated into the Annual Planning Model build process |  | Will require changes to IMM and/or Topology Processor. SSWG has plans to write a new System Change Request and submit this year. | See tab labeled 'All open issues 5-26-10' for all the details |
| 27 | 4 | Annual Planning Model process Go-Live occurs before IMM changes and-or Topology Processor changes are implemented (see issue #1) |  | 1. Can move forward with new process while making large number of changes until IMM/TP is updated. Or 2. Delay Annual Planning Model Go-Live until changes are implemented, tested, and working. |  |
| 28 | 4 | What if SCR 759 is not implemented? (SCR 759 is the acLineSegment Name Length Increase in IMM) Topology Processor is still not performing radial line reduction and multi-section line grouping correctly as originally proposed by Siemens Topology Processor will not be able to create planning models that are currently being used for planning models and studies | Multi-section line creation will not work properly in building Annual Planning Models | Siemens is supposed to be aware and working on the solution |  |
| 29 | 4 | The actual process for building the Annual Planning Models is still an unknown. It depends on how the IMM/TP is enhanced in the future. | Common assumption is that every quarter new TP download will be planning case starting point, but using new TP download every quarter to start building the cases as of right now would cause an enormous amount of SSWG work. | Will test creating 2010 summer case and 2012 summer case later this year to determine just how difficult this is going to be. |  |
| 30 | 2 | Inconsistencies in RARF data versus current planning models. | In new nodal process, RARF data is input into IMM and that data will come out of the TP whether it's correct or not. | NPRR246 is a start that provides a method of getting comments to ERCOT who will ask resources to resubmit the RARF. | Some of this data is very important for TSP planning studies and future project justification. |
| 31 | 4 | Problem with SVCs additions. (Nominal KV error). |  |  |  |
| 32 | 4 | FACTS devices modeled as generators and not as desired | The only option may be to change in MOD environment. This should not be a high number. |  | As per 02/03/2010 SSWG Bi-Weekly Conference call all members agreed to modeled the SVCs as generators. It may be more correct/accurate for the Operation Model to represent Statcoms as generators and SVCs as SVCs. This represents the MVaR output on the fill of the Voltage correctly. |
| 33 | 4 | Assigning cap banks to the right CNG | Some cap banks which are tapped off of lines inside of a substation are modeled connected to their own bus in PSSE. Collapsing these into the correct CNG in the IMM is sometimes difficult. MOD cannot move these from one bus to another in the Control Profile; therefore, the cap bank must be connected to the correct bus in the topology processor output or corrected through a PRJ file in MOD for the Control Profile to be able to adjust the cap bank. |  | Can impact CRR cases |
| 34 | 4 | Assigning loads to the right CNG | Some loads inside a substation may have a hard time being collapsed into the correct CNG. MOD cannot move these from one bus to another in the Load Profile, therefore, the load must be connected to the correct bus in the topology processor output or corrected through a PRJ file in MOD for the Load Profile to be able assign load to the correct bus. |  | Can Impact CRR cases |
| 35 | 4 | Zero impedance lines created by TP have default 9999 MVA ratings |  |  |  |
| 36 | 4 | Load ownership assignments, including zero impedance branches created by TP | The Owner Number/Name data for the load is incorrectly propagated by the TP. |  |  |
| 37 | 4 | Generator Pmax and Pmin | IMM contains limits for generators from RARF data. The RARF data used currently is HR_LMT for Maximum Operating MW and LR_LMT for Minimum Operating MW. These come across TP as Pmax and Pmin |  | HR_LMT and LR_LMT in most cases are clearly unreasonable values to use for planning cases. Pmax and Pmin can be set by the generator profile in MOD, so SSWG does have that option for creating the planning cases. However, SSWG would recommend the ERCOT Network Modeling group use something more reasonable to populate in IMM. |
| 38 | 4 | Cap banks on distribution voltage instead of modeled on transmission level bus | Is this a problem if distribution caps are reflected in station power factors? |  |  |
| 39 | 4 | Distributed generation modeled instead of negative load | Modeling distributed gens should not be a problem |  |  |
| 40 | 4 | Specific models added for contingency analysis, dynamics analysis, or short circuit analysis | Can some of this be done in-house after case creation - short circuit? Are the mutual-coupling concerns for sequence data due to use of old program that may be updated? This is only used in SPWG cases. (WDW Note: I am not talking about adding sequence data to the cases. I am pointing out some buses are created for planning study purposes without being associated with any particular node.) |  | As far as short circuit cases are concerned, SPWG will not be using SSWG cases as their base cases as far as we know. SPWG will still be building the cases from scratch using PSSE. |
| 41 | 4 | Autotransformer differences Op model vs. Planning model |  |  |  |
| 42 | 4 | Phase Shift of autos for short circuit studies | Topology processor does not include phase shift data (30 deg) placed for short circuit calculations |  |  |
| Grey Box |
| 43 | 2 | Based on NPRR219, additional and unknown PUN modeling and outage scheduling is a large burden on the TSPs. | Potential support PUN (behind the fence) model in the TSPs' EMS systems to ensure reliable monitoring of statuses. | Future grey boxed enhancement in Outage Scheduling allowing REs to enter their own outages. Also, the metrics need to be changed for outage scheduling. |  |
| 44 | 3 | NPRR146 implementation plan and schedule for implementing grey box changes | Allows for shorter lead time when submitting ICCP information for telemetry objects. | The NPRR was approved with grey boxed language. Need a plan for how these change we be un-grey boxed and implemented after go-live. |  |
| 45 | 3 | NOGRR034 Rescind Telemetry Performance Calculation Exclusions | Compromise was to grey box future development of a Planned RTU outage tracking method to remove associated points for Telemetry standard performance metrics. |  |  |
| 46 |  | Grey Box items and additional upgrades need some kind of guarantee that they will be completed in a timely manner. | TSPs have increased manpower and our workload due to the fact that several protocols and business processes were designed to be done by ERCOT. However the systems do not have the capability envisioned in the original design. The results is instead of ERCOT performing these functions, 17 different TSPs are performing these functions at a much higher cost to TSPs than anticipated. |  |  |
| Parking Lot |
| 467 |  | Parking lot items and additional upgrades need some kind of guarantee that they will be completed in a timely manner. | TSPs have increased manpower and our workload due to the fact that several protocols and business processes were designed to be done by ERCOT. However the systems do not have the capability envisioned in the original design. The results is instead of ERCOT performing these functions, 17 different TSPs are performing these functions at a much higher cost to TSPs than anticipated. | Set funding aside for parking lot items. |  |

# PRIORITY KEY

1 = Show stopper; Needs resolution before Go-live can be accomplished.

# 2 = High priority issue that should be resolved by Go-live

3 = Needed but can be implement post Go-live

4 = Needed by Planning Go-Live (approximately March 2011)