SSWG REPORT TO ROS

July 2010

- SSWG has met three times since the June ROS meeting, June 15-17, June 23 and July 7.

Nodal items

- SSWG is still correcting Connectivity Node Groups.  As of July 2, 198 Connectivity Node Groups need to be given appropriate PSSE bus numbers.

- SSWG will begin Phase 2 of Information Model Management (IMM) corrections/updates in July.  This will include correcting PSSE Area and Zone #s, PSSE Load, Branch,  Generator IDs, and mileage.  ERCOT agreed to allow spreadsheet changes and create batch NOMCRs for SSWG members.  Due date for changes is July 30.

- Topology Processor enhancements did not work as expected.  ERCOT working with Siemens to rectify.  Some changes have yet to be made in IMM because of the delay.

- SSWG seeks approval of SCR759.

- SSWG and ERCOT are working on a NPRR related to data needs for wind generator RARF submittals.

- SSWG is targeting August for a test of the new case building process to create a 2010 Summer Peak case and November to create a 2012 Summer Peak case as first proposed in the Planning Go-Live Procedure document.  This test should help identify what issues and deficiencies exist with the new process prior to the current plan of using the process to create cases in 2011.

Other items

- 11 Data Set A base cases should be posted July 12.

- At the request of the PLWG, SSWG sent the PLWG Chair comments identifying those items that should be considered binding and included in the future Planning Guides, while removing parts of the manual that are more informational or educational in nature.

- Calendar with all SSWG activities included (Nodal Planning Model related):

  - June – July	TPIT update work - only 345 kV updates required to 10DSB

  - July 9	TSP Pass 9 comments due to ERCOT by EOB

  - July 9	TSP TPIT update Pass 1 changes to ERCOT

  - July 12	ERCOT posts final 11DSA cases

  - July 16	TPIT update posted

  - July 	TSPs Complete changes based on TP enhancements

  - July	MOD/PMCR training

  - July 30	TSPs send Phase II spreadsheet changes to ERCOT

  - July 30	TSP 11DSB Pass 0 and NOIE dispatch due to ERCOT

  - Aug 6	ERCOT sends Pass 1 to SSWG

  - Aug 13	TSPs send Pass1 changes to ERCOT

  - Aug 20	ERCOT sends Pass 2 to SSWG

  - Aug 27	TSPs send Pass 2 changes to ERCOT

  - Aug	Compare TP output to SSWG 2010 summer peak case

  - Sept 1	TPIT spreadsheet updates due to ERCOT

  - Sept 3	ERCOT sends Pass 3 to SSWG

  - Sept 10	TSPs send Pass 3 changes to ERCOT

  - Sept 21-23	SSWG meeting to finalize DSB cases

  - Sept – Oct	TPIT update work – 11 win & 11 DSA only

  - Nov	Create 2012 summer peak case using TP and MOD

  - Dec – Feb 	Review, update, and modify TP/MOD process for case creation

  - Dec 1	TPIT spreadsheet updates due to ERCOT

  - Dec 1	Nodal Go-Live

  - Dec – Jan 2011	TPIT update work

  - Mar 1 2011 	ALDR due to ERCOT

  - Mar-April 2011	Assuming Nov test meets SSWG approval, begin work to create 12DSA using Nodal method

Wes Woitt

2010 SSWG Chair