## Slide 1: NODAL PROGRAM UPDATE TO COPS 07-13-2010
Jim Galvin

## Slide 2: PROGRAM STATUS
Please refer to ERCOT presentations for readiness metrics and participation metrics
Presentations to COPS going forward will focus on Market Trial items around
  DAM
  RTM and LFC
  CRR
  Settlements/COMS/Credit

## Slide 3: CRR
No new issues reported
  All known defects to CRR application have been fixed
Future Activities:
  July 12 (yesterday) August Auction window opens
  July 15 Auction bid window closes

## Slide 4: DAM
Phase 5 has ramped up to running 5x per week DAM with associated settlement
DAM is including credit simulation
  Credit reports on available credit are available prior to DAM
  ERCOT reduced some market participant credit limits for entities that had not updated credit information (more in Settlements/Credit update
ERCOT will provide more information on July 8 DAM where South Load Zone prices for a few hours cleared at $250

## Slide 5: DAM
RUC Issues
  RUC commitments are on the decline, an indication that information being submitted and results from ERCOT systems appear to be more realistic
  DRUC for July 7-9 saw approximately 5 RUC commitments per day
  HRUC for July 7 was 34 RUC commitments reducing to 15 on July 8
  ERCOT is running a WRUC requiring valid COP data 7-days out for a good solution

## Slide 6: DAM
Upcoming Weeks
  No guardrails- ERCOT requests bids and offers to be reasonable and COPs to reflect Zonal
  DRUC with each DAM, HRUC as needed
  SASM will be run as needed
  No specific Operational Scenarios
To better support LFC testing:
  On LFC test days ERCOT will provide a focused input day where MPs will submit trades, bids, offers and COPs that more representative of the post go-live market
  Non LFC days ERCOT will continue to run DAM 5x per week

## Slide 7: RTM/LFC
Real Time metrics on State Estimator convergence remains strong
Offer cap price ($2250) intervals at 34 down from 100+ for the previous week
Eight hour LFC test review is included in the Real Time/LFC summary from Friday’s meeting presentation with the following highlights:
  System Frequency was managed and maintained
  Emergency Base Points tested
  Responsive Reserve deployment tested successfully
  GREDP calculations tracked and provided to MPs
  SPPs questionable due to shift factors not being migrated from MMS to EMS systems

## Slide 8: RTM/LFC
Upcoming Changes will focus concentration on additional LFC tests
  Additional LFC testing will be scheduled
    5-hour test week of June 19
    24-hour test week of August 2
    August will include and additional 1-2 tests, September 1-3 tests
  As updated in the DAM section, LFC tests will include a “focused input day” to have MPs include trades, bids, offers and COPs that are more indicative of Nodal operations

## Slide 9: SETTLEMENTS/COMS/CREDIT
Statements, Invoices and Extracts continue to be delivered under protocol timelines for Market Trial activity
ERCOT provides a total dollar breakdown by charge type of settlement activity on the weekly call
All Settlement algorithms will be tested by August, please consult the latest presentation on Settlements/Credit for an update
LFC test for June 17 contained real time prices that were suspect due to lack of shift factors imported from MMS to EMS

## Slide 10: LFC TEST TOTALS
http://nodal.ercot.com <number>

## Slide 11: SETTLEMENT/COMS/CREDIT
Credit
  Reports are still being generated and posted for MPs
  July 7 (reflected on July 8 AM reports) ERCOT reduced credit limits to 30% above TPE for entities that have not given instructions in the past week
    This created the need to send collateral calls and 90% warnings sent to MPs
    This activity may have limited DAM activity in the July 8 DAM for Operating Day July 9
  ERCOT continues to mitigate historical RTM price to DAM clearing price difference to $20
  Overall, exposures still remain high due to limited history in market trials and RTM market trial prices

## Slide 12: QUESTIONS?