|  |  |  |  | System Planning Division |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report to Reliability and Operations Subcommittee for June 2010 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
| Item |  |  |  |  |  |  |  |  |
| 1. | - ERCOT is currently tracking 220 active generation interconnection requests totaling over 72,000 MW. This includes over 44,000 MW of wind generation. |  |  |  |  |  |  |  |
| 2. | - Regional Planning is currently reviewing proposed transmission improvements with a total of $661.8 Million - Transmission Projects approved in 2010 total $55.4 Million - All projects (in engineering, routing, licensing and construction) total approximately $9.6 Billion - Transmission Projects energized in 2010 total about $435 million |  |  |  |  |  |  |  |
| 3. | - The Voltage Ride Through Study, required by the Board as a part of OGRR 208, was completed and presented to RPG and ROS |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	New Generation Beginning Commercial Operations	1

1.2	New Generation Interconnection Agreements	1

1.3	Summary of Active Generation Interconnection Requests	1

1.4      Publicly Disclosed Generation Interconnection Projects	4

1.5	Generation Projects Undergoing Full Interconnection Studies	6

1.6	Wind Generation	8

2.	Regional Planning Group Project Reviews	10

3.	Other Notable Activities	11

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## New Generation Registering for Commercial Operations

## Papalote Creek Phase 2 (08INR0012b) in San Patricio County for 200 MW of wind capacity.

## The total installed wind capacity has increased to  9,317 MW, of which 7,958 MW (85%) is located within the Western Congestion Management Zone.

## New Generation Interconnection Agreements  - none

## Summary of Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |  |  |  |  |
| --- | --- | --- | --- | --- |
| Currently tracking 220 active generation interconnection or change requests |  |  |  |  |
| As of June 30, 2010 | North | South | West | Total |
| Security Screening Study | 3 | 5 | 11 | 19 |
| SSS Completed | 11 | 12 | 16 | 39 |
| Full Interconnect Study | 21 | 16 | 88 | 125 |
| FIS Completed | 3 | 14 | 2 | 19 |
| Interconnect Agreement Completed | 8 | 5 | 5 | 18 |
| Capacity under Interconnection Agreements | 5,192 | 2,575 | 626 | 8,393 |
| Capacity for Grid, MW | 20,663 | 17,778 | 34,103 | 72,544 |
| Wind Capacity, MW | 5,191 | 7,496 | 31,618 | 44,305 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Projects w/ Interconnect Agreement/Public Letter (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- |
| Gas-CC | - | - | 3,972 | 13,417 |
| Gas-CT | - | - | 0 | 547 |
| Total Gas | 4,770 | 5,222 | 3,972 | 13,964 |
| Nuclear | 0 | 0 | 5,900 | 5,900 |
| Coal | 15 | 1,756 | 3,213 | 4,984 |
| Wind | 11,457 | 27,110 | 5,738 | 44,305 |
| Solar | 459 | 639 | 0 | 1,098 |
| Biomass | 58 | 50 | 145 | 253 |
| Other | 0 | 740 | 1,300 | 2,040 |
| Grand Total | 16,759 | 35,517 | 20,268 | 72,544 |

## Publicly Disclosed Generation Interconnection Projects

The table below summarizes the publicly disclosed generation projects for the ERCOT region.

(Status: IA=Interconnect Agreement, PL=Public Letter, XX= cancelled)

| Generation Interconnections as of June 30, 2010 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR | SiteName | Status | County | Region | COD | Fuel Type |  | MW For Grid | Change from Last Report |
| 05INR0015c | Gulf Wind 3 | PL | Kenedy | South | Sep-10 |  | Wind | 400 |  |
| 09INR0082 | Cedro Hill Wind | IA | Webb | South | Sep-10 |  | Wind | 150 |  |
| 05INR0015b | Gulf Wind 2 | PL | Kenedy | South | Oct-10 |  | Wind | 400 |  |
| 08INR0033 | Lufkin | IA | Angelina | North | Dec-10 |  | Biomass | 45 |  |
| 12INR0003 | Throckmorton Wind Farm | PL | Throckmorton | West | Dec-10 |  | Wind | 400 |  |
| 08INR0065 | Buffalo Gap 4 and 5 | PL | Nolan | West | Mar-11 |  | Wind | 465 |  |
| 09INR0029 | CFB Power Plant Units 11&12 | IA | Calhoun | South | Mar-11 |  | Coal | 263 |  |
| 10INR0010 | Jack County 2 | IA | Jack | North | Jun-11 |  | Gas-CC | 620 |  |
| 08INR0011 | Senate Wind Project | IA | Jack | North | Nov-11 |  | Wind | 150 |  |
| 08INR0038 | M Bar Wind | PL | Andrews | West | Dec-11 |  | Wind | 194 |  |
| 09INR0034 | Gatesville Wind Farm | PL | Coryell | North | Dec-11 |  | Wind | 200 |  |
| 08INR0025 | Pistol Hill Energy Center | PL | Ector | West | Dec-11 |  | Wind | 300 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Feb-12 |  | Coal | 925 |  |
| 09INR0007 | Nacogdoches Project | IA | Nacogdoches | North | Apr-12 |  | Biomass | 100 |  |
| 07INR0004 | Pampa Energy Center | PL | Gray | West | May-12 |  | Coal | 165 |  |
| 09INR0024 | B&B Panhandle Wind | PL | Carson | West | Jun-12 |  | Wind | 1,001 |  |
| 09INR0037 | Scurry County Wind III | PL | Scurry | West | Jun-12 |  | Wind | 350 |  |
| 12INR0004 | Fort Concho Wind Farm | PL | Tom Green | West | Jul-12 |  | Wind | 400 |  |
| 06INR0012b | Sherbino Mesa Wind Farm 2 | IA | Pecos | West | Jul-12 |  | Wind | 150 |  |
| 09INR0036 | McAdoo Energy Center II | PL | Dickens | West | Dec-12 |  | Wind | 500 |  |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Dec-12 |  | Wind | 120 |  |
| 06INR0022c | Penascal Wind Farm 3 | IA | Kenedy | South | Dec-12 |  | Wind | 202 |  |
| 06INR0026 | Wild Horse Mountain | IA | Howard | West | Dec-12 |  | Wind | 120 |  |
| 06INR0006 | Cobisa-Greenville | IA | Hunt | North | May-13 |  | Gas-CC | 1,792 |  |
| 10INR0020a | Panda Temple Power | IA | Bell | North | May-13 |  | Gas-CC | 780 |  |
| 04INR0011c | Cottonwood Wind | IA | Shackelford | West | Jun-14 |  | Wind | 100 |  |
| 04INR0011b | Cedar Elm | IA | Shackelford | West | Jun-14 |  | Wind | 136 |  |
| 14INR0005 | White Stallion Energy Center | PL | Matagorda | South | Jul-14 |  | Coal | 1,200 |  |
| 12INR0016 | Las Brisas Energy Center | IA | Nueces | South | Sep-14 |  | Other | 1,300 |  |
| 14INR0002 | Coleto Creek Unit 2 | IA | Goliad | South | Nov-14 |  | Coal | 660 | Date-Capacity |
| 10INR0020b | Panda Temple Power | IA | Bell | North | Dec-14 |  | Gas-CC | 780 |  |
| 15INR0002 | Comanche Peak 3 and 4 | PL | Somervel | North | Jan-15 |  | Nuclear | 3,200 |  |
| 15INR0008 | STP 3 and 4 | PL | Matagorda | South | Jan-15 |  | Nuclear | 2,700 |  |
|  |  |  |  |  |  |  | Total | 20,268 |  |

County Location of Installed Generation and Interconnection Requests (all fuels)

## Generation Projects Undergoing Full Interconnection Studies (not otherwise public)

| INR | County | Capacity | COD | Fuel |  | INR | County | Capacity | COD | Fuel |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 09INR0054 | Stonewall | 148.5 | TBD | Wind |  | 10INR0048 | Hardeman | 1000 | TBD | Wind |
| 10INR0016 | Childress | 150 | TBD | Wind |  | 09INR0070 | Reagan | 42 | TBD | Wind |
| 09INR0069 | Reagan | 36 | TBD | Wind |  | 10INR0054 | Palo Pinto | 36 | TBD | Wind |
| 10INR0079 | Nolan | 60 | TBD | Wind |  | 10INR0069 | Rusk | 13 | TBD | Coal |
| 10INR0029 | Hood | 810 | TBD | Gas |  | 09INR0081 | Rusk | 18 | TBD | Coal |
| 10INR0013 | Upton | 400 | TBD | Wind |  | 10INR0052a | Knox | 21 | TBD | Wind |
| 10INR0057 | Taylor | 200 | TBD | Wind |  | 10INR0015 | Mitchell | 350 | Oct-10 | Wind |
| 10INR0041 | Floyd | 135 | Oct-10 | Wind |  | 09INR0074 | Motley | 70 | Oct-10 | Wind |
| 10INR0081a | Clay | 30.4 | Oct-10 | Wind |  | 10INR0089 | Harris | 40 | Oct-10 | Other |
| 11INR0029 | Throckmorton | 200 | Nov-10 | Wind |  | 07INR0013 | Coke | 200 | Dec-10 | Wind |
| 07INR0015 | Foard | 180 | Dec-10 | Wind |  | 07INR0035 | Tom Green | 270 | Dec-10 | Wind |
| 10INR0008 | Pecos | 500 | Dec-10 | Wind |  | 08INR0062 | Archer | 249 | Dec-10 | Wind |
| 08INR0061 | Hardeman | 200 | Dec-10 | Wind |  | 10INR0019 | Deaf Smith | 609 | Dec-10 | Wind |
| 10INR0032 | Navarro | 775 | Dec-10 | Gas |  | 10INR0033 | Armstrong | 399 | Dec-10 | Wind |
| 10INR0042 | Mason | 170 | Dec-10 | Wind |  | 09INR0076 | Jackson | 300 | Dec-10 | Wind |
| 10INR0051 | Brazoria | 200 | Dec-10 | Wind |  | 10INR0056 | Borden | 249 | Dec-10 | Wind |
| 10INR0077 | Callahan | 101 | Dec-10 | Wind |  | 10INR0080 | Presidio | 144 | Dec-10 | Solar |
| 10INR0082 | Travis | 30 | Dec-10 | Solar |  | 11INR0050 | Crosby | 149 | Mar-11 | Wind |
| 11INR0081 | Live Oak | 72 | Mar-11 | Wind |  | 11INR0071 | Harris | 7 | Apr-11 | Gas |
| 11INR0086 | Travis | 60 | Apr-11 | Solar |  | 10INR0009 | Castro | 300 | May-11 | Wind |
| 11INR0037 | Smith | 50 | May-11 | Biomass |  | 11INR0061 | Presidio | 90 | May-11 | Solar |
| 11INR0060 | Tom Green | 90 | May-11 | Solar |  | 11INR0058 | Pecos | 135 | May-11 | Solar |
| 11INR0062 | Nueces | 149 | May-11 | Wind |  | 11INR0087 | Wise | 90 | May-11 | Gas |
| 08INR0020 | Eastland | 200 | Jun-11 | Wind |  | 09INR0050 | Fannin | 1200 | Jun-11 | Gas |
| 10INR0023 | Haskell | 386 | Jun-11 | Wind |  | 11INR0019 | Upton | 200 | Jun-11 | Wind |
| 11INR0054 | San Patricio | 161 | Jun-11 | Wind |  | 11INR0057 | Cameron | 165 | Jun-11 | Wind |
| 11INR0065 | Nueces | 240 | Jun-11 | Wind |  | 11INR0006 | Lamar | 579 | Jul-11 | Gas |
| 11INR0040 | Freestone | 640 | Aug-11 | Gas |  | 11INR0008a | Roberts | 1000 | Sep-11 | Wind |
| 11INR0047 | Deaf Smith | 600 | Sep-11 | Wind |  | 07INR0014a | Wilbarger | 140 | Oct-11 | Wind |
| 07INR0014b | Wilbarger | 70 | Oct-11 | Wind |  | 10INR0062a | Pecos | 80 | Oct-11 | Wind |
| 10INR0081b | Clay | 19.2 | Oct-11 | Wind |  | 11INR0005 | Upton | 500 | Dec-11 | Wind |
| 11INR0013 | Mills | 150 | Dec-11 | Wind |  | 11INR0025 | Crockett | 400 | Dec-11 | Wind |
| 11INR0043 | Coke | 300 | Dec-11 | Wind |  | 11INR0067 | Cameron | 78 | Dec-11 | Wind |
| 11INR0070 | Reeves | 50 | Dec-11 | Solar |  | 12INR0034 | Borden | 342 | Dec-11 | Wind |
| 12INR0021 | Edwards | 165 | Jan-12 | Wind |  | 12INR0033 | Motley | 150 | Jan-12 | Wind |
| 10INR0085 | Ector | 40 | Jan-12 | Solar |  | 10INR0018 | Madison | 550 | Mar-12 | Gas |
| 12INR0042 | Deaf Smith | 400 | Mar-12 | Wind |  | 09INR0031 | Ector | 275 | May-12 | Gas |
| 12INR0007 | Lamar | 296 | May-12 | Gas |  | 08INR0031 | Childress | 100 | Jun-12 | Wind |
| 12INR0006 | Limestone | 875 | Jun-12 | Coal |  | 08INR0041 | Coke | 200 | Oct-12 | Wind |
| 12INR0026 | Randall | 400 | Oct-12 | Wind |  | 08INR0044 | Concho | 200 | Nov-12 | Wind |
| 12INR0035 | Nueces | 249 | Nov-12 | Wind |  | 08INR0042 | Coke | 200 | Dec-12 | Wind |
| 09INR0025 | Concho | 180 | Dec-12 | Wind |  | 08INR0054 | Comanche | 401 | Dec-12 | Wind |
| 08INR0056 | Nolan | 149 | Dec-12 | Wind |  | 12INR0005 | Floyd | 1100 | Dec-12 | Wind |
| 12INR0029 | Swisher | 500 | Dec-12 | Wind |  | 10INR0024 | Briscoe | 2940 | Jan-13 | Wind |
| 12INR0027 | Gray | 200 | Jan-13 | Wind |  | 09INR0058 | Howard | 250 | Mar-13 | Wind |
| 12INR0018 | Gray | 500 | Apr-13 | Wind |  | 10INR0062b | Pecos | 220 | May-13 | Wind |
| 09INR0051 | Borden | 249 | Jun-13 | Wind |  | 13INR0004 | Deaf Smith | 500 | Oct-13 | Wind |
| 13INR0005 | Carson | 600 | Oct-13 | Wind |  | 08INR0023 | Floyd | 100 | Dec-13 | Wind |
| 08INR0022 | Floyd | 100 | Dec-13 | Wind |  | 12INR0002a | Briscoe | 200 | Dec-13 | Wind |
| 09INR0077 | Reagan | 500 | Dec-13 | Wind |  | 13INR0007 | Pecos | 200 | Dec-13 | Wind |
| 09INR0073 | Scurry | 200 | Dec-13 | Wind |  | 13INR0010 | Parmer | 1200 | Dec-13 | Wind |
| 08INR0019c | Gray | 250 | Jan-14 | Wind |  | 08INR0019b | Gray | 250 | Jan-14 | Wind |
| 08INR0019a | Gray | 250 | Jan-14 | Wind |  | 13INR0006 | Gray | 750 | Jan-14 | Wind |
| 14INR0003 | Nolan | 850 | Jun-14 | Coal |  | 12INR0002b | Briscoe | 200 | Dec-14 | Wind |
| 14INR0001 | Pecos | 500 | Dec-14 | Wind |  | 12INR0002c | Briscoe | 350 | Dec-15 | Wind |
| 16INR0002 | Brazoria | 700 | Jun-17 | Other |  |  |  |  |  |  |

## Wind Generation

Wind Capacity Installed by Year

County Location of Installed Capacity and Interconnection Requests (Wind only)

# Regional Planning Group Project Reviews

# Oncor submitted a project to relieve congestion related to new wind units in the Lamesa area.  The project will upgrade the Lamesa to Bluff Creek 138 kV line, rebuild the Bluff Creek to China Grove 138 kV line, rebuild the Lamesa to Ackerly Vealmoor 69 kV line to 138/69 kV double circuit, rebuild the Lamesa 138 kV switching station, build a new 138 kV Ackerly Vealmoor station, add second circuits to all rebuilt lines and include station upgrades at China Grove and Big Spring.  The cost of this project is $ 80.8 M.  This project will be reviewed to ensure that the improvements fit into the likely CREZ transmission solution for the area.  This project is in ERCOT Independent Review.

# Sharyland Utilities submitted a project to construct and operate the ERCOT Southeast Loop facilities consisting of a 345 kV double circuit from Lufkin to Canal 345 kV substation on the northeast side of Houston.  This project will cost $359 M with an estimated completion date of summer 2013.  This project is in ERCOT Independent Review.

# Centerpoint Energy has submitted a project to construct a new 345 kV double circuit line to allow greater power imports into the Houston area.  The project involves expanding the Fayetteville and Zenith substations and constructing a new 345 kV double circuit from Fayetteville to Zenith.  The proposal also includes looping the Fayette Power Project to Salem 345 kV circuit into Fayetteville and upgrading the Fayette Power Project to Fayetteville 345 kV double circuit lines.  The project is estimated to be complete by September 2014 at a cost of $222 M.  This project is in ERCOT Independent Review.

# Austin Energy has submitted a project to construct a new 345 kV bus with a 345/ 138 kV autotransformer at the Dunlap station.  The project also involves rerouting several nearby transmission lines.  The revised estimated cost of the project is $18.5 M.  The comment period and study mode phase have been completed and an RPG acceptance letter has been sent to Austin Energy.

  - American Electric Power Service Corporation (AEPSC) submitted a project to rebuild the Matador to Paducah 69 kV line at an estimated cost of $34.0 M.  The comment period and study mode phase have been completed and an RPG acceptance letter has been sent to AEPSC.

# Congestion Costs

Dollars shown in graphs are settlement quality.

OOMC – last 13 months in million$

OOM Down – last 13 months in million$

Local Balancing Energy Down – last 13 months in million$

OOM Up – last 13 months in million$

Local Balancing Energy Up – last 13 months in million$

Replacement Reserve – last 13 months in thousand$

Binding Constraints & Capacity Shortages– May, 2010

| Contingency | Binding Element | Estimated Costs | Transmission Project | Clearance |
| --- | --- | --- | --- | --- |
| Greens Bayou - Gable & Hardy - Crockett 138kV | Garrott - Midtown 138kV | $ 3,556,448 | Garrott - Midtown - Polk Ckt. 90 11TPIT0072 | Outage on Oasis - PH Robinson 345kV circuit |
|  | DFW Reactive | $ 2,065,562 | Renner SVCs [10TPIT0056; 11TPIT0095] |  |
| Bellaire Autotransformer | Bellaire Autotransformer | $ 1,967,361 |  | Outage on 345/138kV Bellaire AT1 |
| PH Robinson Autotransformer #2 | PH Robinson Autotransformer #1 | $ 1,303,705 |  | Outage on PH Robinson 345kV “F” bus including the 345/138kV autotransformer AT4_H |
| Graham SES - Parker Switch 345kV | Flat Creek - Leon Switch 138kV | $ 1,112,532 |  | Outage on Jacksboro Switching to Bowman Switch 345KV |
| Graham SES - Parker Switch 345kV | Barton Switch - Oran 138kV | $ 596,130 |  | Outage on Jacksboro Switching to Bowman Switch 345KV |
|  | RPRS | $ 220,824 |  |  |
| Fisher Road Switch - Oklaunion - Bowman 345kV | Abilene Mulberry - Long Creek 345kV | $ 184,804 |  |  |
| Planned Outages – multiple |  | $ 155,481 |  |  |
| Coleto Creek - Victoria #2 138kV | Coleto Creek - Victoria #1 138kV | $ 153,126 |  |  |

Inter-zonal Congestion

# Other Notable Activities

- Work on the 2010 Five-Year Transmission Plan is underway.  The initial set of projects needed to reliably serve load in 2015 has been identified and comments have been received.  The analysis is currently focused on finding reliability projects for the years 2011-2014.  Work on the economic analysis portion of the study has just begun.

- Nodal Network Model Management System Topology Processor work continues with bi-weekly meetings/calls with SSWG and weekly ERCOT topology processor output.  ERCOT has removed the final 99xxxx series buses and begun producing the spreadsheet that will be used for Phase II updates.  ERCOT will host on-site training for TSPs for Model on Demand.

- The results for the Voltage Ride-Through (VRT) study, performed for ERCOT by PB World to meet the requirements of OGRR 208, were presented and discussed at the June 11 RPG meeting.  The VRT results were also be presented to ROS at a special meeting on June 25.  The public report on the study can be found at: http://www.ercot.com/content/meetings/ros/keydocs/2010/0625/03._ERCOT_VRT_Study_-_Phase_III_-_Final.pdf

- The CREZ Reactive Study, being performed by ABB and led jointly by ERCOT and the CREZ TSPs, to optimize the reactive support equipment required to implement the CREZ plan is ongoing.  This study will define the size, type and location of the equipment as well as study any associated subsynchronous issues.

- Work on the Long-Term System Assessment/DOE Study has begun.  A separate subgroup of RPG has been established to focus on this study and is meeting monthly.  The current focus is on background information that will be used for developing the scenarios to be studied.  The next meeting is July 23rd.