## Nodal Protocol Effective Dates
Nodal Protocol Section | Nodal Protocol Title | Texas Nodal Market Implementation Date* | Notes
1 | Overview | 2010-12-01
2 | Definitions and Acronyms | 2010-09-01
3 | Management Activities for the ERCOT System | See Below
3.1 | Outage Coordination | 2010-11-01
3.2 | Analysis of Resource Adequacy | 2010-12-01
3.3 | Management of Changes to ERCOT Transmission Grid | 2010-11-01
3.4 (except 3.4.5) | Load Zones | 2010-11-30
3.4.5 | Additional Load Buses | 2010-09-01
3.5 | Hubs | See Below
3.5.1(1)-(3) | Process for Defining Hubs | 2010-09-01
3.5.1(4)-(5) | Process for Defining Hubs | 2010-11-30
3.5.1(6) | Process for Defining Hubs | 2010-09-01
3.5.2.1(1) | North 345 kv Hub (North 345) | 2010-09-01
3.5.2.1(2)-(4) | North 345 kv Hub (North 345) | 2010-11-30
3.5.2.2(1) | South 345 kV Hub (South 345) | 2010-09-01
3.5.2.2(2)-(4) | South 345 kV Hub (South 345) | 2010-11-30
3.5.2.3(1) | Houston 345 kV Hub (Houston 345) | 2010-09-01
3.5.2.3(2)-(4) | Houston 345 kV Hub (Houston 345) | 2010-11-30
3.5.2.4(1) | West 345 kV Hub (West 345) | 2010-09-01
3.5.2.4(2)-(4) | West 345 kV Hub (West 345) | 2010-11-30
3.5.2.5 | ERCOT Hub Average 345 kV Hub (ERCOT 345) | 2010-11-30
3.5.2.6 | ERCOT Bus Average 345 kV Hub (ERCOT 345 Bus) | 2010-11-30
3.5.3.1 | Posting of Hub Buses and Electrical Buses included in Hubs | 2010-09-01
3.5.3.2 | Calculation of Hub Prices | 2010-11-30
3.6 | Load Participation | 2010-12-01
3.7 | Resource Parameters | See Below
3.7(1) | Resource Parameters | 2010-09-01
3.7(2)-(6) | Resource Parameters | 2010-11-24
3.7.1.1 | Generation Resource Parameters | 2010-09-01
3.7.1.2 | Load Resource Parameters | 2010-09-01
3.7.1.3 | Changes in Resource Parameters with Operational Impacts | 2010-11-24
3.7.2 | Resource Parameter Validation | 2010-09-01
3.8 | Special Considerations for Split Generation Meters | 2010-09-01
3.9 | Current Operating Plan (COP) | 2010-11-23
3.1 | Network Operations Modeling and Telemetry | See Below
3.10 (1)-(4) | Network Operations Modeling and Telemetry | 2010-09-01
3.10 (5) | Network Operations Modeling and Telemetry | 2010-12-01
3.10 (6)-(8) | Network Operations Modeling and Telemetry | 2010-09-01
3.10 (9) | Network Operations Modeling and Telemetry | 2010-12-01
3.10 (10)-(11) | Network Operations Modeling and Telemetry | 2010-09-01
3.10.1 | Time Line for Network Operations Model Change Requests | 2010-09-01
3.10.2 | Annual Planning Model | 2010-12-01
3.10.3 | CRR Network Model | 2010-09-01
3.10.4(1)-(2) | ERCOT Responsibilities | 2010-12-01
3.10.4(3)-(8) | ERCOT Responsibilities | 2010-09-01
3.10.5(1) | TSP Responsibilities | 2010-09-01
3.10.5(2) | TSP Responsibilities | 2010-12-01
3.10.5(3)-(4) | TSP Responsibilities | 2010-09-01
3.10.6 | Resource Entity Responsibilities | 2010-09-01
3.10.7 (except 3.10.7.3(3)) | ERCOT System Modeling Requirements | 2010-09-01
3.10.7.3(3) | Modeling of Private Use Networks | 2010-12-01
3.10.7.4(2)** | Definition of Special Protection Systems and Remedial Action Plans | 9/1/2010** | **Following sentence not yet effective 9/1/10: "Execution of an SPS or RAP must be included or assumed in the calculation of LMPs as well as the Network Operations Model." This sentence to be effective 12/1/10.
3.10.7.4(2)** | Definition of Special Protection Systems and Remedial Action Plans | 12/1/2010** | **See above for effective date of beginning of item. Last sentence becomes effective 12/1/10: "Execution of an SPS or RAP must be included or assumed in the calculation of LMPs as well as the Network Operations Model."
3.10.8(1) | Dynamic Ratings | 2010-09-01
3.10.8(2)-(4) | Dynamic Ratings | 2010-12-01
3.10.8.1 | Dynamic Ratings Delivered via ICCP | 2010-12-01
3.10.8.2 | Dynamic Ratings Delivered via Static Table and Telemetered Temperature | 2010-12-01
3.10.8.3 | Dynamic Rating Network Operations Model Change Requests | 2010-09-01
3.10.8.4 | ERCOT Responsibilities Related to Dynamic Ratings | 2010-12-01
3.10.8.5 | Transmission Service Provider Responsibilities Related to Dynamic Ratings | 2010-12-01
3.10.9 | State Estimator Performance Standard | 2010-09-01
3.11 | Transmission Planning | 2010-12-01
3.12 | Load Forecasting | See Below
3.12(a) | Load Forecasting | 2010-11-24
3.12(b) | Load Forecasting | 2010-12-01
3.12.1 | Seven-Day Load Forecast | 2010-11-24
3.12.2 | 36-Month Load Forecast | 2010-12-01
3.13 | Renewable Production Potential Forecasts | 2010-11-30
3.14 (except as noted below) | Contracts for Reliability Resources and EILS Loads | 2010-12-01
3.14.1.7-3.14.1.8 | RMR or MRA Contract Termination; RMR and/or MRA Contract Extension | 2010-11-01
3.14.3 | Emergency Interruptible Load Service (EILS) | 2011-02-01 | Coincide with EILS Contract period
3.15 | Voltage Support | 2010-12-01
3.16 | Standards for Determining Ancillary Service Quantities | 2010-12-01
3.17 | Ancillary Service Capacity Products | 2010-12-01
3.18 | Resource Limits in Providing Ancillary Service | 2010-12-01
3.19 | Constraint Competitive Tests | 2010-12-01
4 | Day-Ahead Market Operations | See Below
4.1 | Introduction | 2010-11-30
4.2 (except 4.2.2) | ERCOT Activities in the Day-Ahead | 2010-11-30
4.2.2 | Wind-Powered Generation Resource Production Potential | 2010-11-29
4.3 | QSE Activities and Responsibilities in the Day-Ahead | 2010-11-30
4.4 (except as noted below) | Inputs into DAM and Other Trades | 2010-11-24 | Due to submission 7 days in advance
4.4.4 (3) | DC Tie Schedules | 2010-11-30
4.4.7.4 (3) | Ancillary Service Supply Responsibility | 2010-11-30
4.4.8 | RMR Offers | 2010-11-30
4.4.9.2.4 | Verifiable Startup Offer and Minimum-Energy Offer Caps | 2010-11-30
4.4.9.4 | Mitigated Offer Cap and Mitigated Offer Floor | 2010-11-20 | Early to comply with (d) The previous 12 months’ capacity factor must be updated by ERCOT by the 20th day of each month using the most recent data for use in the next month.
4.4.10 | Credit Requirement for DAM Bids and Offers | 2010-12-01 | Credit limits will be sent on 11/29
4.4.11 | System-Wide Offer Caps | 2010-11-30
4.5 | DAM Execution and Results | 2010-11-30
4.6 (except 4.6.1) | DAM Settlement | 2010-12-01 | Reflects Operating Day being settled.
4.6.1 | Day-Ahead Settlement Point Prices | 2010-11-30 | DAM for 12/1 will be executed on 11/30
5 | Transmission Security Analysis and RUC | See Below
5.1 | Introduction | 2010-11-30
5.2 | Reliability Unit Commitment Timeline Summary | 2010-11-30
5.3 | ERCOT Security Sequence Responsibilities | 2010-11-30
5.4 | QSE Security Sequence Responsibilities | 2010-11-24 | Due to submissions 7 days in advance
5.5 | Security Sequence, Including RUC | 2010-11-30
5.6 | RUC Cost Eligibility | 2010-12-01
5.7 | Settlement for RUC Process | 2010-12-01
6 (except 6.3.1; 6.6.11) | Adjustment Period and Real-Time Operations | 2010-12-01
6.3.1 | Activities for the Adjustment Period | 2010-11-30 | 6.3.1 - 11/30 for day-ahead activities
6.6.11 | Emergency Interruptible Load Service (EILS) Capacity | 2011-02-01 | EILS Contract Period; Includes both 6.6.11.1 and 6.6.11.2
7 | Congestion Revenue Rights | See Below
7.1 | Function of Congestion Revenue Rights | 2010-10-20 | Cutover plan -ERCOT to allocate PCRRs to NOIEs for Dec 2010 Auction
7.2 | Characteristics of Congestion Revenue Rights | 2010-10-20 | Cutover plan -ERCOT to allocate PCRRs to NOIEs for Dec 2010 Auction
7.3 | Types of Congestion Revenue Rights to Be Auctioned | 2010-10-20 | Cutover plan -ERCOT to allocate PCRRs to NOIEs for Dec 2010 Auction
7.4 | Allocation of Preassigned Congestion Revenue Rights | 2010-10-20
7.5 | CRR Auctions | See Below
7.5.1 | Nature and Timing | 2010-11-11 | Cutover plan - Run Dec 2010 CRR Auction
7.5.2 | CRR Auction Offers and Bids | 2010-11-04 | Cutover plan - Start Bid Offer submission window for Dec 2010 CRR auction
7.5.3 | ERCOT Responsibilities | 2010-10-24 | Cutover plan - ERCOT to post the Dec 2010 Monthly Auction Notice
7.5.4 | CRR Account Holder Responsibilities | 2010-10-24 | Credit submission window opens (simultaneous with Auction Notice) CRRAH need to have ACL established.
7.5.5 | Auction Clearing Methodology | 2010-10-20
7.5.5.1 | Creditworthiness | 2010-11-09 | ERCOT assigns credit limit as lower of submitted or 90%ACL two business days before end of bid submission window
7.5.5.2 | Ownership Posting | 2010-12-07 | Post ownership by fifth business day of month. 12/7 is the first fifth business day that will have any data (IMHO CRRs are not owned until paid for)
7.5.5.3 | Auction Process | 2010-11-11 | Cutover plan - Run Dec 2010 CRR Auction
7.5.5.4 | Simultaneous Feasibility Test | 2010-11-11 | Cutover plan - Run Dec 2010 CRR Auction
7.5.6 | CRR Auction Settlements | 2010-11-17
7.5.7 | Method for Distributing CRR Auction Revenues | 2010-12-01
7.6 | CRR Balancing Account | 2010-12-01
7.7 | [Reserved] | N/A
7.8 | Bilateral Trades and ERCOT CRR Registration System | 2010-11-17
7.9 | CRR Settlements | 2010-12-01
8 (except 8.1.3.1-8.1.3.3) | Performance Monitoring | 2010-12-01
8.1.3.1; 8.1.3.2; 8.1.3.3 | Performance Criteria for EILS Loads; Testing of EILS Loads; Suspension of Qualification of EILS Loads and/or their QSEs | 2011-02-01 | Coincide with EILS Contract period
9 | Settlement Metering | See Below
9.1 | General | 2010-11-11
9.2 | Settlement Statements for the Day-Ahead Market | 2010-12-01
9.3 | Settlement Invoices for the DAM | 2010-12-01
9.4 | Payment Process for the DAM | 2010-12-01
9.5 | Settlement Statements for Real-Time Market | 2010-12-01
9.6 | Settlement Invoices for the Real-Time Market | 2010-12-01
9.7 | Payment Process for the RTM | 2010-12-01
9.8 | CRR Auction Award Invoices | 2010-11-11
9.9 | Payment Process for CRR Auction Invoices | 2010-11-11
9.10 | CRR Auction Revenue Distribution Invoices | 2010-12-01
9.11 | Payment Process for CRR Auction Revenue Distribution | 2010-12-01
9.12 | CRR Balancing Account Invoices | 2010-12-01
9.13 | Payment Process for the CRR Balancing Account | 2010-12-01
9.14 (except 9.14.5) | Settlement and Billing Dispute Process | 2010-11-01 | NPRR253 adds CRR Auction Invoice to dispute notices; effectuate 11/1 to be available for CRR Auction.
9.14.5 | Settlement of Emergency Interruptible Load Service (EILS) | 2011-02-01 | Coincide with EILS Contract period
9.15 (except 9.15.1) | Settlement Charges | 2010-12-01
9.15.1 | Settlement Matrix | 2010-11-21 | Must post 10 days prior to implementation of change
9.16 | Administrative Fees | 2010-12-01
9.17 | Transmission Billing Determinant Calculation | 2010-12-01
9.18 | Profile Development Cost Recovery Fee for Non-ERCOT Sponsored Load Profile Segment | 2010-12-01
9.19 | Partial Payments by Invoice Recipients | 2010-12-01
10 | Metering | 2010-12-01
11 | Data Acquisition and Aggregation | 2010-12-01
12 | Market Information System | 2010-12-01
13 | Transmission and Distribution Losses | 2010-12-01
14 | State of Texas Renewable Energy Credit Trading Program | 2010-12-01
15 | Customer Registration | 2010-12-01
16 (except 16.5; 16.8) | Registration and Qualification of MPs | 2010-12-01
16.5 | Registration of a Resource Entity | 2010-09-01
16.8 | Registration and Qualification of Congestion Revenue Rights Account Holders | 2010-10-01 | Recommend 10/1 to acknowledge preparation for November auction.
17 | Market Monitoring and Data Collection | See Below
17.1 | Overview | 2010-12-01
17.2 | Objectives and Scope of Market Monitoring and Data Collection | 2010-11-24
17.3 | Market Data Collection and Use | 2010-11-24
17.3.1 | Information System Data Collection and Retention | 2010-11-24
17.3.2 | Data Categories and Handling Procedures | 2010-12-01
17.3.3 | Accuracy of Data Collection | 2010-12-01
17.3.4 | PUCT Staff and IMM Review of Data Collection | 2010-12-01
17.3.5 | Data Retention | 2010-12-01
17.4 | Provision of Data to Individual Market Participants | 2010-12-01
17.5 (1) | Reports to the PUCT Staff, IMM, and the FERC | 2010-11-30
17.5 (2) | Reports to the PUCT Staff, IMM, and the FERC | 2010-12-01
17.6 | Changes to Facilitate Market Operation | 2010-12-01
18 | Load Profiling | 2010-12-01
19 | Texas Standard Electronic Transaction | 2010-12-01
20 | Alternative Dispute Resolution Procedure | 2010-12-01
21 | Process for Nodal Protocol Revision | 2010-12-01
22A | Standard Form Market Participant Agreement | 2010-12-01
22B | Standard Form Reliability Must-Run | 2010-12-01
22C | Amendment to Standard Form Market Participant Agreement | 2010-12-01
22D | Standard Form Black Start Agreement | 2010-12-01
22E | Notification of Suspension of Operations | 2010-12-01
22F | Standard Form Synchronous Condenser Agreement | 2010-12-01
22G | Standard Form Emergency Interruptible Load Service (EILS) Agreement | 2010-12-01
22H | Notification of Change of Generation Resource Designation | 2010-12-01
23 | Texas Test Plan Team - Retail Market Testing | 2010-12-01 | Note: NPRR247 deletes Section 23
24 | Retail Point to Point Communications | 2010-12-01
N/A | ERCOT Fee Schedule | 2010-12-01
*Notes: The Texas Nodal Market Implementation Date applies to entire subsection unless otherwise indicated. Please reference the ERCOT Market Information List under Key Documents at http://nodal.ercot.com/readiness/reports/index.html for Market Information System posting information.

## Zonal Protocol Retire Dates
Zonal Protocol Section | Zonal Protocol Title | Retirement Date* | Notes
1 (except 1.3) | Overview | 2010-11-30
1.3 | Confidentiality | 2011-11-30 | Expire 365 days after last Zonal Op Day
2 | Definitions and Acronyms | 2011-12-13 | Remain until last Zonal Protocol Retired
3 | Open Access to the ERCOT Transmission Grid | 2010-11-30
4 | Scheduling | See Below
4.1 | Overview of the Scheduling Process | 2010-11-30
4.2 | Scheduling-Related Duties of ERCOT | 2010-11-30
4.3 | Scheduling-Related Duties of Qualified Scheduling Entities | 2011-01-01
4.4 | Day Ahead Scheduling Process | 2010-12-07
4.5 | Adjustment Period Scheduling Process | 2010-11-30
4.6 | Operating Period Process | 2010-12-07
4.7 | Validation and Correction of Schedule Data | 2010-11-30
4.8 | Temporary Deviations from Scheduling Procedures | 2010-12-07
4.9 | Dynamic Schedules | 2010-11-30
4.1 | Resource Plan Performance Metrics | 2010-11-30
5 | Dispatch | 2010-11-30
6 (except as noted below) | Ancillary Services | 2010-11-30
6.5.12 | Emergency Interruptible Load Service (EILS) | 2011-01-31 | Coincide with EILS Contract period
6.8.6 | Capacity Payments for Emergency Interruptible Load Service (EILS) | 2011-01-31 | Coincide with EILS Contract period
6.9.4.4 | Settlement Obligation for Emergency Interruptible Load Service | 2011-01-31 | Coincide with EILS Contract period
6.10.13 | Emergency Interruptible Load Service Qualification, Testing and Performance Standards | 2011-01-31 | Coincide with EILS Contract period
7 (except 7.5) | Congestion Management | 2010-11-30
7.5 | Transmission Congestion Rights | 2010-12-31
8 | Planned Outages and Maintenance Outages of Transmission and Resource Facilities | 2010-12-07 | maybe up to one week later based on cut over.
9 | Settlement and Billing | See Below
9.1 | Overview | 2011-12-13 | Coincide with last effective date for Section 9.
9.1.1 | Settlement Statement Process | 2011-05-31 | Last statement
9.1.2 | Settlement Calendar | 2011-06-16 | Reflects calendar through payments for last invoice - assuming no uplift
9.2 | Settlement Statements | 2011-05-31 | True-Up Statement for TD 11/30/2010 will post 5/31/2011
9.3 | Settlement Invoice | 2011-06-09 | True-Up for TD 11/30/2010 will be invoiced 6/9/2011
9.4 (except 9.4.5) | Payment Process | 2011-12-13 | Payment due date for TD 11/30/2010 is 6/16/2011. 9.4.4 (5) allows for an additional 180 days following a short payment of a Settlement Invoice
9.4.5 | Enforcing the Security of a Defaulting QSE | 2010-11-30 | Based on Operating Day
9.5 (except 9.5.5) | Settlement and Billing Dispute Process | 2011-06-14
9.5.5 | Settlement of Emergency Interruptible Load Service | 2011-01-31 | Coincide with EILS Contract period; Nodal 9.14.5 language same.
9.6 | Settlement Charges | 2011-06-09 | This references the charge type matrix, which should be posted through final settlement
9.6.1 | Balancing Energy Neutrality Adjustment | 2010-11-30 | OpDay-centric
9.6.2 | Equalization Adjustment | 2010-11-30
9.7 | Administrative Fees | 2010-11-30 | OpDay-centric
9.8 | Transmission Billing Determinant Calculation | 2010-11-30
9.9 | Profile Development Cost Recovery Fee for a Non-ERCOT Sponsored Load Profile Segment | 2010-11-30
10 | Metering | 2010-11-30
11 | Data Acquisition and Aggregation | See Below
11.1 | Data Acquisition And Aggregation From ERCOT Polled Settlement (EPS) Metered Entities | 2010-11-30
11.2 | Data Acquisition From TDSPs | 2010-11-30
11.3 | ESI ID Synchronization | 2010-11-30
11.4 | Load Data Aggregation | 2011-05-31 | Tentative: Stays active until after true up settlements have run for 11/30/10.
11.4.1 | Estimation of Missing Data | 2010-11-30
11.4.2 (1st paragraph - (9) | Non-Interval Missing Consumption Data Estimation | 2011-05-31 | Tentative: Stays active until after true up settlements have run for 11/30/10.
11.4.2 (2nd paragraph - end 11.4.2) |  | 2010-11-30 | Beginning with "Estimates of missing data are based on Profile ID, which includes:…." through end of 11.4.2 retire 11/30
11.4.3 | Interval Consumption Data Estimation | 2010-11-30
11.4.4 | Data Aggregation Processing for Actual Data | 2010-11-30
11.4.4.1 (1st paragraph thru (9) | Application of Profiles to Non-Interval Data | 2011-05-31 | Tentative: Stays active until after true up settlements have run for 11/30/10.
11.4.4.1 (2nd paragraph - end 11.4.4.1) | Application of Profiles to Non-Interval Data | 2010-11-30 | Beginning with "Profile application will take aggregated non-interval…." through end of 11.4.4.1 retires 11/30
11.4.4.2 | Load Reduction for Excess Photo Voltaic Renewable Generation | 2010-11-30
11.4.4.3 | Load Reduction for Excess Non-Photo Voltaic Renewable Generation | 2010-11-30
11.4.5 | Adjustment of Consumption Data for Losses | 2010-11-30
11.4.6 | Unaccounted for Energy Calculation (UFE) and Allocation | 2010-11-30
11.5 | Data Aggregation | See Below
11.5.1 | Aggregate Retail Load Data | 2011-05-31 | Tentative: Stays active until after true up settlements have run for 11/30/10.
11.5.1.1 | Aggregated Load Data Posting/Availability | 2011-05-31 | Tentative: Stays active until after true up settlements have run for 11/30/10.
11.5.2 (1) | Generation Meter Data Aggregation | 2010-11-30
11.5.2(2) | Generation Meter Data Aggregation | 2011-05-31 | Tentative: Stays active until after true up settlements have run for 11/30/10.
11.5.2.1 | Participant Specific Generation Data Posting/Availability | 2010-11-30
11.5.2.2 | General Public Generation Data Posting/Availability | 6/2011
11.6 | Unaccounted For Energy (UFE) Analysis | 2010-11-30
12 | Market Information System | See Below
12.1 | Overview | 2010-11-30
12.2 | ERCOT Obligation to Provide Information | 2010-11-30
12.3 | Transmission-Related Information | 2010-11-30
12.4 (except as noted below) | Market-Related Information | 2010-11-30
12.4.4.2.3.2 (1)-(12) | Public ERCOT Posting | 2010-11-30
12.4.4.2.3.2 (13) | Public ERCOT Posting | 2010-12-03 | 2 days after last Operating Day
12.4.4.2.3.3 (1)-(4) | Public Posting of Entity-Specific Market Reports | 2011-01-31 | 60 days after last Operating Day
12.4.4.2.3.3 (5)-(6) | Public Posting of Entity-Specific Market Reports | 2011-05-31 | 180 days after last Operating Day
12.5 | Applicable Reliability Standards | 2010-11-30
13 | Transmission and Distribution Losses | 2010-11-30
14 | State of Texas Renewable Energy Credit Trading Program | 2010-11-30
15 | Customer Registration | 2010-11-30
16 (except 16.8) | Registration and Qualification of Market Participants | 2010-11-30
16.8 | Registration of TCR Account Holders | 2010-12-31
17 | Market Monitoring and Data Collection | 2010-11-30
18 | Load Profiling | 2010-11-30
19 | Texas Standard Electronic Transaction | 2010-11-30
20 | Alternative Dispute Resolution Procedure | 2010-11-30
21 | Process for Protocol Revision | See Below
21.1-21.6 | Introduction; Submission of a Protocol Revision Request; Protocol Revision Subcommittee; Protocol Revision Procedure; Urgent Requests; Protocol Revision Implementation | 2011-12-13 | Remain until last Zonal Protocol Retired
21.7-21.11 | Submission of a System Change Request; Process for Nodal Protocol Revisions System Change Request Procedure; Review of Project Prioritization, Review of Unfunded Project List, and Annual Budget Process; Review of Guide Changes; Process for Nodal Protocol Revisions | 2010-11-30
21.12 | Process for Transition to Nodal Market Protocol Sections | 2011-12-13 | Remain until last Zonal Protocol Retired
22A | Standard Form Black Start Agreement | 2010-11-30
22B | Intentionally left blank | N/A
22C | Intentionally left blank | N/A
22D | Intentionally left blank | N/A
22E | Intentionally left blank | N/A
22F | Standard Form Reliability Must-Run Agreement | 2010-11-30
22G | Intentionally left blank | N/A
22H | Standard Form TCR Account Holder Agreement | 2010-11-30
22I | Notification of Suspension of Operations | 2010-11-30
22J | Standard Form Synchronous Condenser Agreement | 2010-11-30
22K | Standard Form Emergency Interruptible Load Service (EILS) Agreement | 2010-11-30
22L | Standard Form Market Participant Agreement | 2010-11-30
22M | Notification of Change of Generation Resource Designation | 2010-11-30
22N | Amendment to Standard Form Market Participant Agreement | 2010-11-30
23 | Texas Test Plan Team - Retail Market Testing | 2010-11-30
24 | Retail Point to Point Communications | 2010-11-30
N/A | ERCOT Fee Schedule | 2010-11-30
*Notes: The Retirement Date applies to entire subsection unless otherwise indicated. Please reference the ERCOT Market Information List under Key Documents at http://nodal.ercot.com/readiness/reports/index.html for Market Information System posting information.

## Nodal Op Guide Effective Dates
Nodal Op Guide Section | Nodal Operating Guide Title | Texas Nodal Market Implementation Date* | Notes
1 (except 1.4) | Overview | 2010-12-01
1.4 | Definitions | 2010-09-01 | Coincide with first NOG Section.
2 | System Operations and Control Requirements | See Below
2.1 | Operational Duties | 2010-12-01
2.2 | System Monitoring and Control | See Below
2.2.1 | Overview | 2010-12-01
2.2.2 | Security Criteria | 2010-11-29
2.2.3 | Response to Transient Voltage Disturbance | 2010-12-01
2.2.4 | Load Frequency Control | 2010-12-01
2.2.5 | Automatic Voltage Regulators | 2010-12-01
2.2.6 | Power System Stabilizers | 2010-12-01
2.2.7 | Turbine Speed Governors | 2010-12-01
2.2.8 | Performance/Disturbance/Compliance Analysis | 2010-11-30
2.2.9 | Time Error and Time Synchronization | 2010-12-01
2.3 | Ancillary Services | 2010-12-01
2.4 | Outage Coordination | 2010-11-01 | For Outages related to Dec 2010
2.5 | Reliability Unit Commitment (RUC) | 2010-11-24 | WRUC starts week ahead
2.6 | Requirements for Under-Frequency Relaying | 2010-11-30
2.7 | System Voltage Profile | See Below
2.7.1 | Introduction | 2010-12-01
2.7.2 | Maintaining Voltage Profile | 2010-12-01
2.7.3 | Special Consideration for Nuclear Power Plants | 2010-11-30 | Early date to obtain COP info for go-live OpDay
2.7.4 | Reactive Considerations for Generation Resources | 2010-11-30
2.8 | Operation of Direct Current Ties (DC Ties) | 2010-12-01
2.9 | Voltage Ride-Through Requirements | 2010-12-01 | NOGRR043 adds 2.9
3 (except 3.9.4) | Resource Testing and Qualification Procedures | 2010-12-01
3.9.4 | Responsibility for Equipment Ratings | 2010-09-01
4 (except 4.3;4.4) | Emergency Operation | 2010-12-01
4.3 | Operation To Maintain Transmission System Security | 2010-11-30
4.4 | Block Load Transfers between ERCOT and Non-ERCOT System | 2010-11-30
5 (except 5.1.2) | Planning | 2010-12-01
5.1.2 | Real-Time and Short Term Planning | 2010-11-29 | Early date to obtain COP info for go-live OpDay
6 | Disturbance Monitoring and System Protection | 2010-12-01
7 | Telemetry and Communication | 2010-12-01
8 | Attachments | 2010-12-01
9 | Monitoring Programs | See Below
9.1 | QSE and Resource Monitoring Program | 2010-12-01
9.1.1 | Testing | 2010-12-01
9.1.2 | Reactive Testing for Generation Resources | 2010-12-01
9.1.3 | Real-Time Data | 2010-12-01
9.1.4 | Compliance with Valid Dispatch Instructions | 2010-12-01
9.1.5 | Resource Facilities Network Operations Model Update Implementation Monitor | 2010-12-01
9.1.6 | Resource Outage Reporting | 2010-11-30
9.1.7 | Backup Control for Resource Energy Deployment | 2010-11-30
9.1.8 | Qualified Staffing Requirement | 2010-12-01
9.1.9 | Automatic Voltage Regulator (AVR) | 2010-12-01
9.1.10 | Current Operating Plan Metrics for QSEs | 2010-11-30
9.2 | TSP Monitoring Program | See Below
9.2.1 | Rating Methodology Reporting Program | 2010-12-01
9.2.2 | Real-Time Data Monitor | 2010-12-01
9.2.3 | Transmission Outage Reporting | 2010-11-30
9.2.4 | Transmission Service Provider (TSP) Network Operations Model Update Implementation Monitor | 2010-12-01
9.2.5 | Backup Control for TSPs | 2010-11-30
9.3 | ERCOT Monitoring Program | See Below
9.3.1 | Transmission Control | 2010-12-01
9.3.2 | System and Resource Control | 2010-12-01
9.3.3 | Forecasting | 2010-12-01
9.3.4 | System Operating Constraints | 2010-11-30
9.3.5 | Network Operations Model Update Implementation Statistics | 2010-12-01
9.3.6 | Back-up Control Plan | 2010-11-30
9.3.7 | ERCOT Black Start Plan | 2010-12-01
9.3.8 | Computer and Communication Systems Real-Time Availability and Systems Security | 2010-12-01
9.3.9 | Voltage and Reactive Control Performance Monitoring | 2010-12-01
9.4 | Ancillary Services Monitoring Program | 2010-12-01
*Notes: The Texas Nodal Market Implementation Date applies to entire subsection unless otherwise indicated. Please reference the ERCOT Market Information List under Key Documents at http://nodal.ercot.com/readiness/reports/index.html for Market Information System posting information.

## Zonal Op Guide Reitre Dates
Zonal Op Guide Section | Zonal Operating Guide Title | Retirement Date* | Notes
1 (except 1.3; 1.6) | Introduction | 2010-11-30
1.3 | Process for Operating Guide Revision | 2010-12-07 | Remain until last Op Guide Section is retired.
1.6 | Operating Definitions | 2010-12-07 | Remain until last Op Guide Section is retired.
2 (except 2.7) | System Operations | 2010-11-30
2.7 | Outage Coordination | 2010-12-07
3 | Operational Interfaces | 2010-11-30
4 | Emergency Operation | 2010-11-30
5 | Planning | 2010-11-30
6 | Reports and Forms | 2010-11-30
7 | Disturbance Monitoring and System Protection | 2010-11-30
8 | Operational Metering and Communication | 2010-11-30
*Notes: The Retirement Date applies to entire subsection unless otherwise indicated. Please reference the ERCOT Market Information List under Key Documents at http://nodal.ercot.com/readiness/reports/index.html for Market Information System posting information.