## Market Design
Texas Renewables Implementation Plan
Quarterly Update for the Period Ending June, 2010
List of Market Design Issues
Issue Category | Issue No. | Title | Description | Current Group | Priority | Impact | Solution Implemented by | Revision Mechanism | Status | Other REF No. | RTWG Last Action/Next Step
MD | 1 | Ancillary Services Cost Allocations Applicable to Wind | Develop any ancillary services cost allocations applicable to wind generation resources. | TAC | Near Term | Medium | Market Participants | PRR/NPRR | The Board received a presentation from ERCOT staff at the April 20 Board meeting and requested additional information to be reported at the July 2010 Board Meeting.
MD | 4 | New Ancillary Service Products Needed for Reliability | Determine if new ancillary services are needed to reliably integrate the large amounts of wind generation coming into the ERCOT market. | ROS | Long Term | Medium | ERCOT | PRR/NPRR | This issue is part of the DOE Study. Reference to new SP issue. Links to SO-5
MD | 5 | Benefits of Storage Technologies | Determine benefit and potential applications of storage technologies in the ERCOT market. | RTWG | Long Term | Low | Market Participants | Other | RTWG will look for input from the Board at the May Board meeting related to the April 13, 2010 Storage Workshop.
MD | 7 | Wind Generating Resources Providing Ancillary Services | Determine possible changes in the ERCOT Nodal Protocols to allow Wind Generation Resources to provide ancillary services. | QMWG | Long-Term | Medium | Market Participants | NPRR | List of issues has been circulated; Walter Reid will be developing a NPRR to address market facilitation issues. |  | Circulated prior to Jan 29 meeting
MD | 9 | Wind Generation Dispatch in the Nodal Protocols | Review of Nodal Protocols to ensure proper treatment of wind generation in regard to dispatch response. | QMWG | Near Term | Medium | Market Participants | NPRR | NPRR 214 was approved by the ERCOT Board on May 18, 2010 | Under active discussion by Nodal Wind Generation discussion group. | White paper to be presented in March
MD | 10 | Wind Generation Performance Metrics in the Nodal Protocols | Review of Nodal Protocols to ensure proper treatment of wind generation in regard to performance metrics when negative pricing exists. | QMWG | Near Term | Medium | ERCOT | NPRR | Under discussion at QMWG. | Under active discussion by Nodal Wind Generation discussion group. | White paper to be presented in March
MD | 11 | Wind Generation and Base Point Deviation in the Nodal Protocols | Review of Nodal Protocols to ensure proper treatment of wind generation in regard to Base Point deviation. | QMWG | Near Term | Medium | ERCOT | NPRR | Under discussion at QMWG. | Under active discussion by Nodal Wind Generation discussion group. | White paper to be presented in March

## System Ops
Texas Renewables Implementation Plan
Quarterly Update for the Period Ending June, 2010
List of System Operations Issues
0
Issue Category | System Ops Issue No. | Title | Description | Current Group | Priority | Impact | Solution Implemented by | Revision Mechanism | Status | Other Ref No.
SO | 1 | Inventory of Wind Generation Facilities | Develop forms and collect wind turbine data from Wind Generation Resources to improve ERCOT's modeling and operations databases. | ERCOT/Consultant | Near Term | Low | ERCOT | Other | Much of the data from wind farms has been collected and reviewed. Changes to the RARF to accommodate new wind farm data will not occur until after Nodal Go-Live. ROS will be asked to address the list of items of data for post Go-Live implementation.
SO | 4 | Smart Grid Implications for Renewable Resources | Determine how development of a "smart grid" could benefit and improve integration of renewable resources into the ERCOT grid. | RTWG | Long Term | Low | Market Participants | Other | Steve Isser will develop a white paper to be presented to RTWG.
SO | 5 | Operational Studies Related to Wind Generation | Operational studies re: Wind (ramp rate, low load situations, forecasting) to identify if new ancillary services are needed. | RTWG | Long Term | Medium | ERCOT | NPRR | Some discussion of incorporating some of these issues in the DOE Study (see SP-10). Other issues may be discussed in other venues.
SO | 6 | Testing Reactive Capability of Wind Generation | Determine the appropriate testing methodology to measure the reactive capability of wind generation. | ERCOT Operations | Near Term | Medium | ERCOT | OGRR | See MD-8 (follow up activities associated with implementation of PRR 830)
SO | 10 | Voltage Management Practices Applicable to Wind Generation | Develop appropriate voltage management practices for ERCOT and Transmission Service Providers that would apply to wind generation resources. | ERCOT | Near Term | High | ERCOT/TSPs | NPRR | ERCOT reactive study of West Texas is scheduled for completion by 2nd quarter 2010. ABB provided a status report at the March RPG meeting.
SO | 14 | Impact of Transmission Outage Planning on Wind Generation | Examine possible ways to improve transmission outage planning to better coordinate with wind generation operations. | RPG | Long Term | High | ERCOT/TSPs | PRR | PRR 795 was approved by the Board on 02/17/2009 - Policy issues still open
SO | 23 | Impact of Advanced Meters/ Smart Grid on Integration of Renewable Resources | Examine impact of advanced metering / Smart Grid capabilities on integration and deployment of renewable resources and demand-side management technologies. | DSWG | Long Term | Low | Market Participants | PRR/NPRR | Steve Isser to develop a white paper to be presented to RTWG.
SO | 26 | Impact of Solar Generation on System Operations | Determine potential impact of new solar generation on ERCOT system operations through appropriate studies of solar ramp rate capabilities, forecasting of solar energy production, voltage and reactive control capabilities. | RTWG | Long Term | Medium | Market Participants | NPRR | Steve Isser to develop a white paper to be presented to RTWG.
SO | 30 | Application of Wind Generation Forecast to PASA | Determine how the ERCOT wind generation output forecast could be used to improve the Projected Assessment of System Adequacy (PASA). | ERCOT Operations | Near Term | Medium | ERCOT | Other | To be discussed at a future RTWG meeting
SO | 31 | Tension Monitors on Transmission Lines | Determine the need (if any) to install tension monitors on certain existing transmission lines that will be affected by construction of CREZ transmission facilities. | RPG | Near Term | Low | Market Participants | Other | Pending potential Market Participant project submissions.
SO | 32 | Real-Time Wind Generation Capacity | Determine the value of having a real-time value of available wind generating capacity for use by ERCOT operations. | QMWG | Near Term | Medium | ERCOT | PRR | Complete: PRR 811 was approved by the Board in February 2009. Additional follow-up activity is necessary to address issues associated with the re-definition of WGR in PRR 830 and to evaluate the utility of such information to ERCOT.
SO | 33 | Real-Time Wind Turbine Availability | Determine the value of having a real-time indication of the availability of each wind turbine for use by ERCOT operations. | QMWG | Near Term | Medium | ERCOT | PRR | The portion of PRR 830 related to reporting of status has been approved and will be in effect on June 1, 2010 pending resolution of the appeal of PRR 830 to the PUCT.
SO | 34 | SCED Line Ratings | Increase the frequency of SCED's consideration of dynamic line ratings to better model current system conditons. | ROS | Long Term | Medium | ERCOT | Other | Changed priority to Medium since it cannot be implemented for Nodal Go-Live; to be discussed at a later RTWG meeting.

## System Planning
Texas Renewables Implementation Plan
Quarterly Update for the Period Ending June, 2010
List of System Planning Issues
Issue Category | Issue No. | Title | Description | Current Group | Priority | Impact | Solution Implemented by | Revision Mechanism | Status | Other Ref. No.
SP | 2 | Wind Turbine Computer Models | Collect and verify accuracy of computer models for each type of wind turbine installed on the ERCOT grid. | ERCOT Planning | Near Term | Low | ERCOT | Other | Included in ERCOT's VRT Study
SP | 3 | Wind Turbine Fault Tolerance | Prepare a study of the fault tolerance of wind turbines installed on the ERCOT grid. | ERCOT Planning | Near Term | Medium | ERCOT | OGRR | Included in ERCOT's VRT Study
SP | 4 | Voltage Transient and Small Signal Stability Study | Update ERCOT voltage transient and small signal stability study and prepare a West Zone to North Zone transfer study. | ERCOT Operations | Near Term | Medium | ERCOT | Other | Phase I of the study has been completed and Phase II is underway.
SP | 5 | Impact of Wind Turbines on System Inertia | Determine the potential impact on system reliability of large amounts of wind turbine generating capacity on ERCOT's system inertia requirements. | ERCOT Planning | Long Term | Medium | ERCOT | Other | Will be undertaken following completion of VRT study
SP | 7 | Voltage Control Process | Develop a process to better control voltage in areas with large amounts of wind generation. | ERCOT Planning | Long Term | Medium | ERCOT | OGRR/NOGRR | See SO-10
SP | 8 | Voltage Ride-Through (VRT) Study | Prepare a study of the system reliability and associated requirements applicable to all generators for voltage ride-through capability. | ERCOT Planning | Near Term | High | ERCOT | Other | Phase I of the study was reported to ROS in December 2009, all study results due to ROS no later than June 2010.
SP | 9 | Wind Turbine Model Validation | Validation of wind turbine non-steady-state planning models - WECC/EPRI has done some work in this area that might be useful to examine. | RTWG | Near Term | Medium | ERCOT | Unknown | Project 173 was approved at EPRI in February 2010, field measurements will be done on 4 different wind turbines; looking for partners for tests (esp. ERCOT)
SP | 10 | DOE Long-Term Planning Study | Long-term transmission planning study and increased participation with state agencies, Non-governmental organizations and other interested parties. (See ERCOT presentation on March 23) | LTSTF | Long Term | High | ERCOT Planning | Unknown | First TF meeting on April 29, 2010
SP | 11 | Sub-Synchronous Interactions | Evaluate impact of series-compensated transmission lines which can result in interactions with generators at very low frequencies that can be damaging to the generators | ERCOT Planning | Near Term | High | ERCOT Planning, TSPs and Market Participants | Unknown | Reactive Study performed by ABB is investigating design alternatives.

## WT
Texas Renewables Implementation Plan
Quarterly Update for the Period Ending June, 2010
List of Workshop/Training Opportunities
Issue Category | Issue No. | Title | Description | Current Group | Priority | Impact | Solution Implemented by | Revision Mechanism | Status | Revision Mechanism | Other Ref. No.
WT | 1 | Resource Plan and Schedule Update Process | Determine potential improvements to the Resource Plan and Resource Schedule update process to improve performance and reliability. | RTWG/ERCOT Operations | Undetermined | Low | Market Participants | Other | Potential topic for future Wind Workshop | Other
WT | 3 | Wind Turbine Operator Training | Develop list of topics for use in development of a training session for wind turbine generator operators. | ROS | Long Term | Low | Market Participants | Other | RTWG to work with ROS to add Wind Operator Training in the Nodal Market to the ERCOT Operator Training Session of 2011. | Other
WT | 5 | Wind Workshop IV | Workshop to focus on turbine vendors and facility engineers and requirements in ERCOT that might impact their products and/or facilities. | RTWG | Short-Term | Medium | Market Participants | N/A | Walter Reid will develop a tentative agenda, list of topics and speakers to discuss at the May 2010 RTWG meeting.
WT | 6 | Solar Workshop | Workshop to focus on existing market rules and how those rules might impact particiular solar technologies. Target audience: manufactuers, developers, operators, other ISOs that have solar on-line. Schedule: First Quarter 2011 | RTWG | Short-Term | Medium | Market Participants | N/A | Mark Bruce will develop a tentative list of topics/speakers to discuss at the May 2010 RTWG meeting.
WT | 7 | Storage Workshop I | Workshop to focus on existing market rules and how those rules might impact particiular storage technologies. Target audience: manufactuers, developers, operators, other ISOs that have storage. Schedule: 2nd Quarter 2011 | RTWG | Short-Term | Medium | Market Participants | N/A | COMPLETE: Storage Workshop 1 was held on April 13, 2010. RTWG is developing a list of follow-up items.
WT | 8 | Ancillary Services Evaluation Workshop | Post Nodal Implementation Date (4-6 months) focusing on the effectiveness of ancillary service products in the nodal market design. Discussion of whether additional services or ancillary products are desirable or necessary. See also MD-04 and SO-5 | RTWG | Long Term | Medium | Market Participants | N/A | To be addressed at a future RTWG meeting (3rd Quarter 2010)
WT | 9 | Storage Workshop II | Workshop to focus on storage technologies issues. | RTWG | Short-Term | Medium | Market Participants | N/A | Coordinate with PUCT Staff on Project No. 38118

## COMPLETED
Texas Renewables Implementation Plan
Quarterly Update for the Period Ending June, 2010
List of All Completed Issues
Issue Category | Issue No. | Title | Description | Current Group | Priority | Impact | Solution Implemented by | Revision Mechanism | Status | Other Ref No.
MD | 2 | Ancillary Services Procurement Optimization for 2009 | Develop any ancillary services cost allocations applicable to wind generation resources (see also MD-6). | QMWG | Complete | Medium | ERCOT | Other | COMPLETE: ERCOT Board approved the 2009 Ancillary Services Procurement methodology at the February Board Meeting
MD | 3 | Non-Spin Requirements | Determine if additional Non-Spin Service procurements are required to accommodate increased amounts of wind generation in ERCOT. | WMS | Complete | Medium | ERCOT | Other | COMPLETE:
MD | 6 | Ancillary Service Procurement Methodology | Determine impact and possible changes in amounts of ancillary services to be procured to ensure reliability with increasing amounts of wind generation being installed in the ERCOT market. | WOTF | Complete | Medium | ERCOT | Other | COMPLETE: WOTF reviewed draft procedure method and made comments that were incorporated in the AS methodology approved for 2009 | WOTF 3c
MD | 8 | Reactive and Voltage Requirements Applicable to Wind Generators | Review of current ERCOT Protocols to ensure reactive and voltage control requirements are applicable to all generating technologies, including wind generation. | WOTF | Near Term | Low | ERCOT | PRR | COMPLETE: PRR 830 "Reactive Power Capability Requirement" has been approved by the ERCOT Board. RTWG is examining the need for follow-up activities related to PRR 830. | WOTF 2a
MD | 12 | Wind Generation Resource LSL as a Percentage of HSL | Establish a minimum percentage for the Low Sustained Limit (LSL) of the High Sustained Limit (HSL) for a wind generation resource. | QMWG | Complete | Medium | Market Participants and ERCOT | PRR | COMPLETE: PRR 773 approved by the ERCOT Board | WOTF 3b
MD | 13 | Use of State of the Art Wind Forecast | Requires Wind Generation Resources to use of a state-of-the-art wind production forecast (AWS Truewind) in their daily resource plan submittals. | N/A | Complete | Medium | Market Participants | PRR | COMPLETE: PRR 763 approved by the ERCOT Board
SO | 2 | Nodal Tools to Integrate Wind Generation | Determine tools applicable to the Nodal Protocols to successfully integrate wind generation into the ERCOT markets. | RTWG | Complete | Medium | Market Participants and ERCOT | NPRR | COMPLETE: (pending completion of Nodal market trials) - open issues are addressed in other specific issues. Review and discussion of the Nodal Protocols indicates that wind is addressed adequately.
SO | 3 | Wind Generation Response and SCE | Determine proper wind generation response to down balancing instructions from ERCOT and also address SCE issues. | QMWG | Near Term | Low | Market Participants | PRR | COMPLETE - PRR 812 has been approved by BOD and went into effect on October 1. | WOTF 1e
SO | 7 | Wind Generation and High System Frequency | Determine impact of wind generation on high system frequency events and develop possible solutions. | WOTF | Near Term | Medium | Market Participants | PRR/NPRR | COMPLETE: PRR 833 was approved by the ERCOT Board on May 20, 2010. | WOTF 5
SO | 8 | Wind Generation and System Inertia | Determine impact of wind generation on system inertia and develop possible solutions. | PDCWG | Complete | Low | Market Participants | Other | COMPLETE: PDCWG report to ROS in October 2008
SO | 9 | SCADA Control of Generator Circuit Breakers | Develop guidelines for better control of generator circuit breakers via SCADA. | OGRR TF | Near Term | Low | Market Participants | OGRR | COMPLETE: OGRR 226 "Generation Resource Response Time Requirements" was approved by TAC in December 2009. | WOTF 1b
SO | 11 | Technology-Specific Procedures and Protocols Changes | Develop renewable technology-specific changes in existing ERCOT Protocols, Operating Guides, Interconnection Agreements and interconnection procedures to recognize unique characteristics of various renewable generation technologies. | ROS | Near Term | Low | Market Participants | Other | COMPLETE - This issue is covered by other individual issues in System Operations, Market Design and System Planning
SO | 12 | Low-Voltage-Ride-Through for Wind Generators | Develop low-voltage-ride-through requirements for wind generators. | N/A | Complete | Medium | Market Participants | OGRR | COMPLETE: ROS approved OGRR 208
SO | 13 | Performance Metrics for Wind Generation | Develop appropriate operational performance metrics for wind generation. | QMWG | Complete | Medium | Market Participants | PRR | COMPLETE: PRR793 approved by the ERCOT Board | WOTF 3a
SO | 15 | Communications between Wind Farms and TSPs | Examine possible improvements in real-time communications between wind farms and transmission service providers (TSPs). | WOTF | Near Term | Medium | Market Participants | OGRR | COMPLETE: OGRR 226 "Generation Resource Response Time Requirements" was approved by TAC in December 2009. | WOTF 2a
SO | 16 | Wind Generation Ramp Limits | Develop appropriate ramp rate limits for wind farms | ROS | Complete | Medium | Market Participants | PRR | COMPLETE: PRRs 771 and 788 approved by the ERCOT Board | WOTF 3b
SO | 17 | Mid-Term and Short-Term Load Forecast Weather Sensitivity | WOTF determined that this was not a determining factor in the Februrary 26, 2008 event. | WOTF | Complete | Low | Market Participants and ERCOT | Other | COMPLETE: Issue resolved as result of ERCOT Operations response to SDWG comments. WOTF recommended no further action. | WOTF 3f
SO | 19 | Improve Competitively Sensitive Constraints (CSC) Process | Evaluate increasing the frequency of ERCOT CSC studies to more accurately determine congestion problems that affect wind generation. | WOTF | Complete | Medium | Market Participants and ERCOT | Other | COMPLETE: ERCOT implemented hourly limits effective June 10, 2008 | WOTF 3g
SO | 20 | Dynamic Transmission Line Ratings | Evaluate cost and benefits of using dynamic transmission line ratings in ERCOT's planning processes to allow more efficient use of transmission lines serving wind farms. | WOTF | Complete | Low | Market Participants | Other | COMPLETE: RPG has agreed to consider dynamic line rating solutions to congestion problems | WOTF 3h
SO | 21 | Evaluate Emergency Electric Curtailment Plan (EECP) Steps | Determine if the existing EECP steps need to be modified to take into account the increasing amount of variable wind generation in the ERCOT system. | OWG | Complete | Low | Market Participants | PRR/NPRR | COMPLETE: PRR 769 approved by BOD and NPRR 142 at January 20 BOD meeting
SO | 24 | Settlement of Advanced Meters in the Nodal Market | Determine appropriate settlement timeline to accommodate use of advanced meters in the Nodal Market design. | AMIT | Complete | Medium | Market Participants | Other | COMPLETE: Go-live date is November 2009; all provisioned advanced meters will be settled on a 15-minute basis.
SO | 25 | Generator Governor Response for Wind Generators | : Determine proper generator governor response requirements for wind generators in the Nodal Market design. | WOTF | Short Term | Medium | Market Participants | NPRR | COMPLETE: PRRs 824 and 833 have been approved by the ERCOT Board on 12-15-2009 (PRR 824) and 05-18-2010 (PRR 833). | WOTF 1e
SO | 27 | Manual Curtailment of Wind Generation to Resolve Local Congestion | Determine if changes can be made in the existing zonal systems to allow for automating curtailment of wind to resolve local congestion problems. | CMWG | Complete | High | ERCOT | Other | COMPLETE: ERCOT Operations discussed this issue extensively at February 2009 CMWG meeting; no reasonable, timely or cost-effective solution is available in the existing zonal market, issue is resolved by the Nodal market design.
SO | 28 | SPS Actuation for N-0 Conditions | Determine possible changes to eliminate actuation of special protection systems (SPS) caused by variable output of wind farms. | CMWG | Near Term | Medium | ERCOT | OGRR | COMPLETE: OGRR 224 has been approved by TAC in September, 2009
SO | 29 | Transmission Outage Planning for CREZ | Determine ways to accommodate large amounts of transmission outages associated with the CREZ buildout while still providing adequate transmission service to existing wind farms and maintaining adequate system reliability. | RPG | Near Term | High | ERCOT | Other | COMPLETE: PRR 795 was approved by the Board on 02/17/2009. This issue has been looked at in depth by RPG, CMWG RTWG and ROS, but no clear definition of the issue or resolution of the issue has occurred.
SP | 1 | Verify Wind Turbine Technical Data | Create and maintain an inventory of installed wind turbine characteristics. | ERCOT Operations | Complete | Medium | ERCOT | Other | COMPLETE: Survey has been completed
WT | 2 | Wind Workshop III - Summer 2009 | Develop list of topics and speakers for the ERCOT Wind Workshop III to be held in the summer of 2009. | RTWG/ERCOT Operations | Near Term | Low | Market Participants | Other | COMPLETE - Workshop held on June 26, 2009
WT | 4 | Wind in the Nodal Market | Develop presentation for use in the Wind Workshop explaining how wind generation will be treated in the Nodal Market design. | RTWG/ERCOT Operations | Complete | Low | Market Participants | Other | COMPLETE: Presentation included in ERCOT On-Line Training Course for Wind

## Menus
Priority
| Near-Term | Within a year
| Long-Term | Year out or longer
Complete
Undetermined
Est. Impact
| High | Has a major cost/benefit to MP; major resource requrement for ERCOT to implement; a major impact when implemented
Medium
Low
Area Affected | Delete column | Already covered in our division of issues (Mkt, Operations, etc.)
Reliability
| Open Access | Market Design Wholesale Tab
| Customer Choice | Market Design Retail Tab
Implementer
ERCOT
ERCOT/TSPs
Market Participants
Market Participants and ERCOT
To be determined
Revision Mechanism
PRR
NPRR
PRR/NPRR
OGRR
NOGRR
OGRR/NOGRR
Other