SSWG REPORT TO ROS

August 2010

- SSWG has met twice since the July ROS meeting, July 21 and Aug 4.

Nodal items

- SSWG members have completed PMCR/MOD training.

- SSWG is still correcting Connectivity Node Groups.  As of July 30, 147 Connectivity Node Groups need to be given appropriate PSSE bus numbers.  SSWG members are working toward an Aug 15 deadline.  ERCOT reports that these CNGs that have yet to be fixed are causing confusion during the CRR process.

- SSWG submitted Phase 2 of Information Model Management (IMM) corrections/updates by August 6.  This will include correcting PSSE Area and Zone #s, PSSE Load, Branch, Generator IDs, and mileage.  ERCOT agreed to allow spreadsheet changes and create batch NOMCRs for SSWG members.

- A new version of the Topology Processor has been delivered to ERCOT and is currently being tested.  We expect to use this version of the Topology Processor to create the case we will be working off of for our test case later this month.

- SSWG and ERCOT are working on a NPRR related to data needs for wind generator RARF submittals.

- SSWG is targeting August for a test of the new case building process to create a 2010 Summer Peak case and November to create a 2012 Summer Peak case as first proposed in the Planning Go-Live Procedure document.  This test should help identify what issues and deficiencies exist with the new process prior to the current plan of using the process to create cases in 2011.

Other items

- ERCOT concerns about out of range voltages in the DSA cases are being addressed.

- SSWG continues to work with the PLWG to determine the portions of the SSWG Procedure Manual that need to be included in the future Planning Guides.

- SSWG discussed potentially altering the 2014 minimum case slightly this fall to create a high wind / high transfer case as suggested by the Dynamics Working Group at the July ROS meeting.

- Calendar with all SSWG activities included (Nodal Planning Model related):

  - July – August	TSPs Complete changes based on TP enhancements

  - Aug 6	ERCOT sends Pass 1 to SSWG

  - Aug 13	TSPs send Pass1 changes to ERCOT

  - Aug 20	ERCOT sends Pass 2 to SSWG

  - Aug 27	TSPs send Pass 2 changes to ERCOT

  - Aug 18	SSWG meeting to prepare for 2010 test case

  - Aug	Compare 2010 test case to SSWG 2010 summer peak case

  - Sept 1	TPIT spreadsheet updates due to ERCOT

  - Sept 3	ERCOT sends Pass 3 to SSWG

  - Sept 10	TSPs send Pass 3 changes to ERCOT

  - Sept 21-23	SSWG meeting to finalize DSB cases

  - Sept – Oct	TPIT update work – 11 win & 11 DSA only

  - Nov	Create 2012 summer peak case using TP and MOD

  - Dec – Feb 	Review, update, and modify TP/MOD process for case creation

  - Dec 1	TPIT spreadsheet updates due to ERCOT

  - Dec 1	Nodal Go-Live

  - Dec – Jan 2011	TPIT update work

  - Mar 1 2011 	ALDR due to ERCOT

  - Mar-April 2011	Assuming Nov test meets SSWG approval, begin work to create 12DSA using Nodal method

Wes Woitt

2010 SSWG Chair