## Slide 1: Nodal Program Update to Cops 08-10-2010
Jim Galvin

## Slide 2: CRR
No new issues reported
  All known defects to CRR application have been fixed
Market Trial Auctions continue
  September Auction bid window Aug 23-24, credit lockdown will be Aug 23
  September Auction execution Aug 25-27
  Results posted Aug 27
  CRR Invoices published Aug 30

## Slide 3: DAM
DAM results continue to show approximately 40% to 75% of the load clearing with continued high participation
Market prices reaching as high as $500 for periods (generally afternoon peak)
RUC commitments still remain high between 40-80 commitments
No new identified issues for consideration

## Slide 4: DAM
Upcoming activities:
  DAM will execute everyday during the week of Aug 9 and Aug 16
    No “guardrails” ERCOT is requesting reasonable bids and offers and COPs reflecting Zonal for RUC process
  WRUC, DRUC and HRUC will execute
  Operational scenarios include:
    VDI commitments and RUC cancellations
    Ancillary Service Insufficiency
    DAM credit requirements begin simulation under NPRR 206 with “e-factor” utilization

## Slide 5: DAM
ERCOT is undergoing in conjunction with market participants a deep dive on DAM results and issues as identified during market trials
Goal is to better understand the results in the form of pricing, DA congestion, RUC commitments
Next discussion to be determined

## Slide 6: RTM/LFC
Real Time metrics on State Estimator convergence remains strong
Offer cap price ($2250) was reached 150 intervals during the past week, down from 381 the previous week
Warm summer conditions and peak demand is testing the Nodal systems

## Slide 7: RTM/LFC
ERCOT completed the 24-hour LFC test on August 4-5 with the following preliminary results:
  19 constraints activated with 7 at one time active
  2 instances where resources were released from their regulation obligation to be available for SCED (correct operator action, scenario not seen before)
  One instance of CPS1 (Control Performance Standard) score of -34, however, overall CPS1 performance for the entire test period was above the standard

## Slide 8: RTM/LFC
Issues of note:
  ERCOT still working with market participants on incorporating “Quick Start” Non-spin
  Telemetry inconsistencies
  Resource Status for testing units not using “ONTEST”
  Ramping down of units coming off line
  Shift factors being sent to SCED
Analysis of SPPs
  Zonal MCPEs exceeded SPPs in some intervals and SPPs exceeded MCPEs in others
  Refer to last Friday’s RTM/LFC presentation for comparison analysis

## Slide 9: Settlements/Coms/Credit
Statements, Invoices and Extracts continue to be delivered under protocol timelines for Market Trial activity
ERCOT provides a total dollar breakdown by charge type of settlement activity on the weekly call
All Settlement algorithms will be tested by August, please consult the latest presentation on Settlements/Credit for an update
SPPs continue to erratic and offer cap still frequently clearing for some settlement points

## Slide 10: Settlements/Coms/Credit
ERCOT will begin using Verifiable Costs for market trials where QSEs have approved submittals
Settlement of VDIs and De-commitments will take place in August
EILS settlement utilizing Miscellaneous Debit/Credit function will be simulated this month
New Issues:
  SFT results not making it to S&B systems, therefore no derated CRRs
  RTMG being incorrect with GSSPLITSCA having too much precision (fix will be migrated 8-13-10)

## Slide 11: Settlement/COMS/Credit
Credit
  Reports are still being generated and posted for MPs
  NPRR 206 will be tested in August and current “e-factors” are posted
  Market participants can request specific “e-factors” that may be more representative of their expected “e-factors” for Nodal operation
  Training for NPRR206 and “e-factors” takes place on the same day as COPS and is highly encouraged that market participants have their representatives in attendance

## Slide 12: Questions?