## Slide 1: PMO Update to PRS
Troy Anderson
ERCOT Program Management Office
August 19, 2010
Notes: <number>

## Slide 2: PMO Update – Agenda
  2010 Project Spending Update
    As of 8/13/2010
    YTD Actual added
  Nodal Parking Deck
    As of 8/13/2010
  Project Implementations
    July 2010
  2011 Project Prioritization
    Details of funding request
    Request for Approval/Endorsement
Notes: <number>

## Slide 3: 2010 Project Spending Update – 8/13/2010
Program Area | Initial Budget | Current Budget | Forecast | YTD Actual
CO | $ 1,150,000 | $ 1,150,000 | $ 1,077,422 | $ 421,609
IO | $ 1,450,000 | $ 765,000 | $ 881,575 | $ 679,968
MO | $ 1,500,000 | $ 1,297,649 | $ 1,168,738 | $ 563,019
RO | $ 1,900,000 | $ 1,892,118 | $ 1,527,999 | $ 1,146,141
SO | $ 150,000 | $ 144,068 | $ 113,711 | $ 80,918
Minor Cap | $ 750,000 | $ 1,435,000 | $ 1,435,000 | $ 958,362
Released but Not Yet Reallocated | $ 0 | $ 5,932 | $ 0 | $ 0
Subtotals | $ 6,900,000 | $ 6,689,767 | $ 6,204,445 | $ 3,850,017
Met Center Replacement | $ 31,900,000 | $ 37,600,000 | $ 37,290,537 | $ 28,449,677
Data Center Hardware | $ 7,500,000 | $ 7,900,000 | $ 8,264,441 | $ 1,876,436
Grand Totals | $ 46,300,000 | $ 52,189,767 | $ 51,759,423 | $ 34,176,130
* $685k from IO to Minor Cap for software licenses ** $400k from Met Center to DC Hardware for telecom equip.
*** Includes Board-authorized carryover of $5.9M in unspent 2009 funds
***
**
**
*
*

## Slide 4: Nodal Parking Deck – Posting on Nodal.ERCOT.com
Parking Deck – Now Posted !!
http://nodal.ercot.com/docs/po/index.html
Updated Multiple Times per Month

## Slide 5: Nodal Parking Deck – Approved
Source | Title | Priority | Current Status
NPRR208 | Registration and Settlement of Distributed Generation (DG) Less Than One MW | Critical | BoD Approved 7/20/2010
SCR756 | Enhancements to the MarkeTrak Application | Critical | BoD Approved 7/20/2010
NPRR131 | Ancillary Service Trades with ERCOT | High | BoD Approved 1/19/2010
NPRR146 | ICCP Telemetry Information Submittals | High | BoD Approved 6/15/2010
NPRR181 | FIP Definition Revision | High | BoD Approved 1/19/2010
NPRR207 | Unit Deselection | High | BoD Approved 7/20/2010
NPRR210 | Wind Forecasting Change to P50, Synch PRR841 | High | BoD Approved 6/15/2010
NPRR222 | Half-Hour Start Unit RUC Clawback | High | BoD Approved 7/20/2010
NPRR153 | Generation Resource Fixed Quantity Block Offer | Medium | BoD Approved 1/19/2010
NPRR164 | Resubmitting Ancillary Service offers in SASM | Medium | BoD Approved 1/19/2010
SCR755 | ERCOT.com Website Enhancements | Medium | BoD Approved 2/16/2010

## Slide 6: Nodal Parking Deck – Pending
Source | Title | Suggested Priority | Current Status
NPRR240 | Proxy Energy Offer Curve | TBD | Pending PRS Impact Analysis Approval
NPRR241 | Aggregate Incremental Liability (AIL) Calculation and Credit Reports Publish Corrections | TBD | Pending PRS Impact Analysis Approval
NPRR251 | Sync of PRR845, Definition for IDR Meters and Optional Removal of IDR Meters at a Premise Where an Advanced Meter Can be Provisioned | High | Pending at PRS RMS approved 7/14/2010
NPRR256 | Synchronize Nodal Protocols with PRR787, Add Non-Compliance Language to QSE Performance Standards | TBD | Pending at PRS
NOGRR034 | Rescind Telemetry Performance Calculation Exclusions | Medium | Pending at Board TAC approved 8/5/2010
SCR759 | acLineSegment Name Length Increase in Information Model Manager | High | Pending at PRS ROS approved 8/12/2010
The following items were removed from the Parking Deck in the past month:
None

## Slide 7: Nodal Parking Deck – Additional Items for Consideration
Title | Current Status / Description
Wind Cost Allocation | High level impact assessment of two options is near completion
Deferred NOGRR025 Reports | Draft NPRR in progress to gray-box reports planned for delivery after Nodal go-live
NMMS API | Functionality to be considered for post-go-live development
CRR API | Functionality to be considered for post-go-live development
MMS Multiple Network Models | Functionality to be considered for post-go-live development
Add PSS Status to RARF | Automation of manual process as a result of NPRR156
Automated Default Uplift Invoice | Automation of manual process as a result of NPRR221
EILS Enhancements | Automation of manual process
Load Participation in SCED | Functionality to be considered for post-go-live development
EMS Upgrade | Upgrade EMS system from v2.3 to v2.5/v2.6
Deferred Defects | Defects not addressed during Nodal stabilization period Approximately 700 deferred defects as of July 2010 Review underway to confirm issues and confirm acceptable workarounds

## Slide 8: Nodal Parking Deck – Additional Items for Consideration
Title | Current Status / Description
Large Wind Power Production Ramp Forecasting Phase 2 | Phase 2 of the project that built a display for ERCOT operators to indicate periods of time within the next 6 hours during which there is a high risk for a large wind power production ramp to occur
TML Transition to MIS | Upon go live, most applications that are currently available through TML will migrate to MIS and will only be accessible to MPs through the MIS portal. RMS has requested that Zonal Reports, Find ESI ID, Find Transactions, and Transaction submission be accessed through TML until MIS has had sufficient time to stabilize.
Decommission of Zonal Wholesale | After go-live of the redesigned ERCOT wholesale market, certain ERCOT systems and components that were only applicable to zonal wholesale operations will become disposable and need to be decommissioned.
Nodal Cutover Cleanup | Remove pre-go-live data from Nodal systems
Move Price Validation Tool (PVT) to a Server Application | Functionality to be considered for post-go-live development
PVT Enhancements | Enhancements to be identified during market testing and Nodal implementation
PVT Reporting Tools | Functionality to be considered for post-go-live development

## Slide 9: Nodal Parking Deck – Prioritization Guidelines
19 April 2010
Priority | Definition
Critical | Required by Statute, PUCT Order, NERC compliance or critical reliability of: Grid Operations IT Infrastructure Commercial Settlement
High | High value for a majority of market segments or ERCOT
High / Medium | High value to one or two segments, or Medium value for a majority of market segments or ERCOT
Medium | Medium value for only one segment

## Slide 10: PMO Update – YTD 2010 Project Implementations
January 2010
  None
February 2010
  CO PR-80047_02 DAM Control Center
  IO PR-90009_01 Infrastructure Monitoring Enhancement (Remedy Phase 3)
March 2010
  RO PR-90024_01 POLR Rule and Expedited Switch
      POLR Rule portion
      Expedited Switch delivered in August 2009
  SO PR-90002_01 Large Wind Power Production Ramp Forecasting
April 2010
  RO PR-90011_01 AMS Meter Flag
  RO PR-50088_01 Data Research and Reporting (Phase 1)
  SO PR-50029_01 Improvements to VSA/DSA Phase II
  CO PR-60029_01 Enterprise Records Management Framework
May 2010
  None
Dates represent project go-live dates, not project completion dates.
Notes: <number>

## Slide 11: PMO Update – YTD 2010 Project Implementations
June 2010
  IO PR-90010_01 Monitoring & Reporting Tools
  MO PR-90006_01 Information Lifecycle Management (Phase 1)
July 2010
  None
August - September 2010 (projected)
  IO PR-80001_01 Met Center Disposition
  CO PR-10028_01 Physical Security project
October- December 2010 (projected)
  DC PR-10015_01 Telcom Equipment (Phase 1)
  DC PR-10016_01 Network Gear (Phase 1)
  DC PR-10016_02 Network Gear (Phase 2)
  IO PR-10018_01 Annual Storage Growth
Dates represent project go-live dates, not project completion dates.
Notes: <number>

## Slide 12: 2011 Project Prioritization Schedule – Revised
April 2010 - CARTs develop draft 2011 project lists
May 2010
  Initial review at market subcommittees
    MO - COPS (May 11)
    RO - RMS (May 12)
    SO - ROS, WMS (May 13 / May 19)
June 2010
  Approval/endorsement by market subcommittees
    MO - COPS (June 8)
    RO - RMS (June 9)
July 2010 – status update
August 2010
  Approval/endorsement by remaining market subcommittees
    SO - ROS, WMS (August 12 / August 18)
    CO, IO, MO, RO, SO – PRS (August 19)
September 2010
  Approval/endorsement by TAC (September 2)
  Available for F&A and Board review (September 21)
Notes: <number>

## Slide 13: 2011 Project Prioritization – Stabilization Reminder
Nodal System Stabilization will be the primary focus in 2011 (especially during the January-June timeframe)
  Stabilization is estimated to cost $12M-$16M
    Not funded by project funds
  Code freeze will likely extend into Q2 2011
    Exception process will continue
  Parking deck items will be assessed for impact prior to the start of release planning
  First major release planned for 2012

## Slide 14: 2011 Project Prioritization – Primary Components
There are 3 primary components to ERCOT’s 2011 project funding request:
1 – Nodal Release Planning (Parking Deck items) $ 5M
2 – Data Center Hardware Purchase and Installation $37M*
3 – Other critical and high priority projects that have
limited resource impacts on items 1 and 2 $ 8M
Total $50M
ERCOT is reviewing options to reduce the funding requirement for Data Center Hardware (potentially as much as $20M)
  Authorize carryover of excess 2010 ERCOT revenue to 2011
  Accelerate purchases to Q4 2010 and fund with excess 2010 ERCOT revenue
Notes: <number>

## Slide 15: 2011 Project Prioritization – Funding Estimate
Basis of $5M Release Planning Estimate
Applying our experience from recent Nodal development and testing activities, ERCOT has projected the staffing needs for Nodal release planning. This activity is expected to start in July 2011 and will involve both ERCOT and vendor resources. These resources are in addition to staff allocated to the Nodal stabilization effort and the base level of Nodal system operations support.
Release planning will take into consideration items on the Parking Deck as well as other issues that are discovered prior to Nodal go-live and during the stabilization period.
Notes: <number>

## Slide 16: 2011 Project Priority List / Funding Level Review
2011 Project Budgets and Project Counts by Program Area
Program Area | Budget Request | Projects Started in 2008/2009 | New 2010 Projects
CO | $ 450,000 | 1 | 1
IO | $ 1,450,000 | 0 | 3
MO | $ 2,900,000 | 1 | 1
RO | $ 2,700,000 | 1 | 2
SO | $ 0 | 0 | 0
Minor Cap | $ 500,000 | 0 | 1
Subtotal | $ 8,000,000 | 3 | 8
Nodal Release Planning | $ 5,000,000 | 0 | 1
Data Center Refresh (IO) | $ 37,000,000 | 1 | 0
Grand Total | $ 50,000,000 | 4 | 9
Nodal Release Planning replaces the estimate from SO in 2011.
*
*

## Slide 17: 2011 Project Priority List / Funding Level Review
2011 Project Prioritization Notes by Program Area
  Nodal Release Planning ($ 5,000,000)
    Planning funds for Parking Deck and other Nodal enhancements
  Data Center Refresh (IO) ($37,000,000)
    Continuing effort to purchase and install hardware in new data centers
    Effort underway to reduce 2011 funding need
  CO ($ 450,000)
    1 carryover project and 1 security project
  IO ($ 1,450,000)
    2 infrastructure projects and 1 security project
  MO ($ 2,900,000)
    Continuation of Information Lifecycle Management project
    Settlement System Upgrade project
  RO ($ 2,700,000)
    2 PUCT/market projects and Data Research & Reporting project
  Minor Cap ($ 500,000)

## Slide 18: 2011 Project Prioritization – Motion
Suggested Motion
Motion to approve/endorse ERCOT’s proposal to fund 2011 projects in the amount of $50M.
This includes $5M for Nodal Release Planning as well as $1M-$2M to support PUCT and Market requests.
It is understood that requested amounts for the Data Center Hardware projects may be revised based on a change in funding approach. Other ERCOT projects are also subject to change as the ERCOT budget process nears completion.
Notes: <number>