|  |  |  |  | System Planning Division |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report to Reliability and Operations Subcommittee for August 2010 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
| Item |  |  |  |  |  |  |  |  |
| 1. | - ERCOT is currently tracking 186 active generation interconnection requests totaling over 65,000 MW. This includes over 38,000 MW of wind generation. |  |  |  |  |  |  |  |
| 2. | - Mid-Term Planning is currently reviewing proposed transmission improvements with a total cost of $80.8 Million - Transmission Projects approved in 2010 total $230.4 Million - All projects (in engineering, routing, licensing and construction) total approximately $9.6 Billion - Transmission Projects energized in 2010 total about $435 million |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	New Generation Registering for Commercial Operations	1

1.2	Publicly Disclosed Generation Interconnection Projects	4

1.3	Generation Projects Undergoing Full Interconnection Studies (not otherwise public)	6

1.4	Wind Generation	7

Wind Capacity Installed by Year	7

2.	Regional Planning Group Project Reviews	9

3.	Congestion Costs	10

4.	Wind Generation as a Percent of Load	15

5.	Other Notable Activities	15

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## New Generation Registering for Commercial Operations

## Texas Solar (Blue Wing)  8 MW  of Photovoltaic Solar in Bexar County

The total installed wind capacity remains at 9,317 MW, of which 7,958 MW (85%) is located within the Western Congestion Management Zone.

New Generation Interconnection Agreements  - none

Summary of Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |  |  |  |  |
| --- | --- | --- | --- | --- |
| Currently tracking 186 active generation interconnection or change requests |  |  |  |  |
| As of August 31, 2010 | North | South | West | Total |
| Security Screening Study | 1 | 3 | 7 | 11 |
| SSS Completed | 2 | 5 | 7 | 14 |
| Full Interconnect Study | 19 | 13 | 93 | 125 |
| FIS Completed | 3 | 14 | 2 | 19 |
| Interconnect Agreement Completed | 8 | 5 | 4 | 17 |
| Capacity under Interconnection Agreements | 5,192 | 2,575 | 506 | 8,273 |
| Capacity for Grid, MW | 19,200 | 13,833 | 32,239 | 65,272 |
| Wind Capacity, MW | 3,907 | 4,823 | 29,930 | 38,660 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Projects w/ Interconnect Agreement/Public Letter (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- |
| Gas-CC |  |  | 3,972 | 12,048 |
| Gas-CT |  |  |  | 547 |
| Total Gas | 650 | 7,973 | 3,972 | 12,595 |
| Nuclear |  |  | 5,900 | 5,900 |
| Coal |  | 1,740 | 3,213 | 4,953 |
| Wind | 3,672 | 29,370 | 5,618 | 38,660 |
| Solar | 290 | 639 |  | 929 |
| Biomass |  | 50 | 145 | 195 |
| Other |  | 740 | 1,300 | 2,040 |
| Grand Total | 4,612 | 40,512 | 20,148 | 65,272 |

## Publicly Disclosed Generation Interconnection Projects

The table below summarizes the publicly disclosed generation projects for the ERCOT region.

(Status: IA=Interconnect Agreement, PL=Public Letter, XX= cancelled)

| Generation Interconnections as of August 31, 2010 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR | SiteName | Status | County | Region | COD | Fuel Type |  | MW For Grid | Change from Last Report |
| 12INR0003 | Throckmorton Wind Farm | PL | Throckmorton | West | Dec-10 |  | Wind | 400 |  |
| 08INR0033 | Lufkin | IA | Angelina | North | Dec-10 |  | Biomass | 45 |  |
| 05INR0015b | Gulf Wind 2 | PL | Kenedy | South | Jan-11 |  | Wind | 400 | Date |
| 05INR0015c | Gulf Wind 3 | PL | Kenedy | South | Jan-11 |  | Wind | 400 | Date |
| 08INR0065 | Buffalo Gap 4 and 5 | PL | Nolan | West | Mar-11 |  | Wind | 465 |  |
| 09INR0029 | CFB Power Plant Units 11&12 | IA | Calhoun | South | Mar-11 |  | Coal | 263 |  |
| 10INR0010 | Jack County 2 | IA | Jack | North | Jun-11 |  | Gas-CC | 620 |  |
| 08INR0011 | Senate Wind Project | IA | Jack | North | Nov-11 |  | Wind | 150 |  |
| 08INR0038 | M Bar Wind | PL | Andrews | West | Dec-11 |  | Wind | 194 |  |
| 09INR0082 | Cedro Hill Wind | IA | Webb | South | Dec-11 |  | Wind | 150 | Date |
| 09INR0034 | Gatesville Wind Farm | PL | Coryell | North | Dec-11 |  | Wind | 200 |  |
| 08INR0025 | Pistol Hill Energy Center | PL | Ector | West | Dec-11 |  | Wind | 300 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Feb-12 |  | Coal | 925 |  |
| 09INR0007 | Nacogdoches Project | IA | Nacogdoches | North | Apr-12 |  | Biomass | 100 |  |
| 07INR0004 | Pampa Energy Center | PL | Gray | West | May-12 |  | Coal | 165 |  |
| 09INR0024 | B&B Panhandle Wind | PL | Carson | West | Jun-12 |  | Wind | 1,001 |  |
| 09INR0037 | Scurry County Wind III | PL | Scurry | West | Jun-12 |  | Wind | 350 |  |
| 12INR0004 | Fort Concho Wind Farm | PL | Tom Green | West | Jul-12 |  | Wind | 400 |  |
| 06INR0012b | Sherbino Mesa Wind Farm 2 | IA | Pecos | West | Jul-12 |  | Wind | 150 |  |
| 09INR0036 | McAdoo Energy Center II | PL | Dickens | West | Dec-12 |  | Wind | 500 |  |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Dec-12 |  | Wind | 120 |  |
| 06INR0022c | Penascal Wind Farm 3 | IA | Kenedy | South | Dec-12 |  | Wind | 202 |  |
| 06INR0006 | Cobisa-Greenville | IA | Hunt | North | May-13 |  | Gas-CC | 1,792 |  |
| 10INR0020a | Panda Temple Power | IA | Bell | North | May-13 |  | Gas-CC | 780 |  |
| 04INR0011b | Cedar Elm | IA | Shackelford | West | Jun-14 |  | Wind | 136 |  |
| 04INR0011c | Cottonwood Wind | IA | Shackelford | West | Jun-14 |  | Wind | 100 |  |
| 14INR0005 | White Stallion Energy Center | PL | Matagorda | South | Jul-14 |  | Coal | 1,200 |  |
| 12INR0016 | Las Brisas Energy Center | IA | Nueces | South | Sep-14 |  | Other | 1,300 |  |
| 14INR0002 | Coleto Creek Unit 2 | IA | Goliad | South | Nov-14 |  | Coal | 660 |  |
| 10INR0020b | Panda Temple Power | IA | Bell | North | Dec-14 |  | Gas-CC | 780 |  |
| 15INR0008 | STP 3 and 4 | PL | Matagorda | South | Jun-16 |  | Nuclear | 2,700 | Date |
| 15INR0002 | Comanche Peak 3 and 4 | PL | Somervel | North | Dec-18 |  | Nuclear | 3,200 | Date |
| 06INR0026 | Wild Horse Mountain | XX | Howard | West | Dec-12 |  | Wind | 120 | Cancelled |
|  |  |  |  |  |  |  | TOTAL | 20,148 |  |

County Location of Installed Generation and Interconnection Requests (all fuels)

## Generation Projects Undergoing Full Interconnection Studies (not otherwise public)

| INR | County | Capacity | COD | Fuel |  | INR | County | Capacity | COD | Fuel |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 08INR0049 | Clay | 50 | TBD | Wind |  | 09INR0054 | Stonewall | 149 | TBD | Wind |
| 09INR0061 | Kent | 258 | TBD | Wind |  | 10INR0048 | Hardeman | 1,000 | TBD | Wind |
| 10INR0016 | Childress | 150 | TBD | Wind |  | 10INR0054 | Palo Pinto | 36 | TBD | Wind |
| 10INR0079 | Nolan | 60 | TBD | Wind |  | 10INR0029 | Hood | 810 | TBD | Gas |
| 10INR0013 | Upton | 400 | TBD | Wind |  | 10INR0052a | Knox | 21 | TBD | Wind |
| 09INR0074 | Motley | 70 | TBD | Wind |  | 10INR0015 | Mitchell | 350 | TBD | Wind |
| 10INR0041 | Floyd | 135 | TBD | Wind |  | 10INR0089 | Harris | 40 | TBD | Other |
| 11INR0029 | Throckmorton | 200 | Nov-10 | Wind |  | 07INR0013 | Coke | 200 | Dec-10 | Wind |
| 07INR0015 | Foard | 180 | Dec-10 | Wind |  | 07INR0035 | Tom Green | 270 | Dec-10 | Wind |
| 08INR0062 | Archer | 249 | Dec-10 | Wind |  | 10INR0008 | Pecos | 500 | Dec-10 | Wind |
| 10INR0019 | Deaf Smith | 609 | Dec-10 | Wind |  | 10INR0032 | Navarro | 775 | Dec-10 | Gas |
| 10INR0033 | Armstrong | 399 | Dec-10 | Wind |  | 10INR0042 | Mason | 170 | Dec-10 | Wind |
| 10INR0051 | Brazoria | 200 | Dec-10 | Wind |  | 10INR0056 | Borden | 249 | Dec-10 | Wind |
| 10INR0060 | Willacy | 401 | Dec-10 | Wind |  | 10INR0077 | Callahan | 101 | Dec-10 | Wind |
| 10INR0080 | Presidio | 144 | Dec-10 | Solar |  | 10INR0082 | Travis | 30 | Dec-10 | Solar |
| 11INR0076 | Archer | 94 | Jan-11 | Wind |  | 11INR0050 | Crosby | 149 | Mar-11 | Wind |
| 11INR0081 | Live Oak | 72 | Mar-11 | Wind |  | 11INR0082A | Val Verde | 50 | Mar-11 | Wind |
| 11INR0083A | Crockett | 50 | Mar-11 | Wind |  | 11INR0071 | Harris | 7 | Apr-11 | Gas |
| 11INR0075 | Fort Bend | 15 | Apr-11 | Coal |  | 11INR0084 | Ector | 45 | Apr-11 | Wind |
| 11INR0086 | Travis | 60 | Apr-11 | Solar |  | 10INR0009 | Castro | 300 | May-11 | Wind |
| 11INR0037 | Smith | 50 | May-11 | Biomass |  | 11INR0048 | Harris | 300 | May-11 | Gas |
| 11INR0058 | Pecos | 135 | May-11 | Solar |  | 11INR0060 | Tom Green | 90 | May-11 | Solar |
| 11INR0061 | Presidio | 90 | May-11 | Solar |  | 11INR0062 | Nueces | 149 | May-11 | Wind |
| 11INR0033a | Cameron | 200 | May-11 | Wind |  | 11INR0033b | Cameron | 200 | May-11 | Wind |
| 08INR0020 | Eastland | 200 | Jun-11 | Wind |  | 09INR0050 | Fannin | 1,200 | Jun-11 | Gas |
| 10INR0023 | Haskell | 386 | Jun-11 | Wind |  | 10INR0057 | Taylor | 200 | Jun-11 | Wind |
| 11INR0019 | Upton | 200 | Jun-11 | Wind |  | 11INR0054 | San Patricio | 161 | Jun-11 | Wind |
| 11INR0057 | Cameron | 165 | Jun-11 | Wind |  | 11INR0065 | Nueces | 240 | Jun-11 | Wind |
| 11INR0006 | Lamar | 579 | Jul-11 | Gas |  | 11INR0040 | freestone | 640 | Aug-11 | Gas |
| 11INR0039 | Starr | 201 | Sep-11 | Wind |  | 11INR0047 | Deaf Smith | 600 | Sep-11 | Wind |
| 11INR0079a | Clay | 200 | Sep-11 | Wind |  | 07INR0014a | Wilbarger | 140 | Oct-11 | Wind |
| 07INR0014b | Wilbarger | 70 | Oct-11 | Wind |  | 10INR0062a | Pecos | 80 | Oct-11 | Wind |
| 10INR0081b | Clay | 19 | Oct-11 | Wind |  | 10INR0021 | Grayson | 646 | Nov-11 | Gas |
| 11INR0005 | Upton | 500 | Dec-11 | Wind |  | 11INR0013 | Mills | 150 | Dec-11 | Wind |
| 11INR0025 | Crockett | 400 | Dec-11 | Wind |  | 11INR0043 | Coke | 300 | Dec-11 | Wind |
| 11INR0067 | Cameron | 78 | Dec-11 | Wind |  | 11INR0070 | Reeves | 50 | Dec-11 | Solar |
| 12INR0034 | Borden | 342 | Dec-11 | Wind |  | 09INR0048 | Jack | 150 | Dec-11 | Wind |
| 09INR0075 | Kinney | 248 | Dec-11 | Wind |  | 10INR0085 | Ector | 40 | Jan-12 | Solar |
| 12INR0021 | Edwards | 165 | Jan-12 | Wind |  | 12INR0033 | Motley | 150 | Jan-12 | Wind |
| 10INR0018 | Madison | 550 | Mar-12 | Gas |  | 12INR0042 | Deaf Smith | 400 | Mar-12 | Wind |
| 09INR0031 | Ector | 275 | May-12 | Gas |  | 10INR0081a | Clay | 30 | May-12 | Wind |
| 11INR0049 | Wharton | 275 | May-12 | Gas |  | 12INR0007 | Lamar | 296 | May-12 | Gas |
| 08INR0031 | Childress | 100 | Jun-12 | Wind |  | 10INR0022 | Harris | 1,380 | Jun-12 | Gas |
| 12INR0006 | Limestone | 875 | Jun-12 | Coal |  | 08INR0041 | Coke | 200 | Oct-12 | Wind |
| 12INR0026 | Randall | 400 | Oct-12 | Wind |  | 08INR0044 | Concho | 200 | Nov-12 | Wind |
| 12INR0035 | Nueces | 249 | Nov-12 | Wind |  | 12INR0043 | Ector | 290 | Nov-12 | Wind |
| 08INR0042 | Coke | 200 | Dec-12 | Wind |  | 08INR0054 | Comanche | 401 | Dec-12 | Wind |
| 09INR0025 | Concho | 180 | Dec-12 | Wind |  | 12INR0005 | Floyd | 1,100 | Dec-12 | Wind |
| 12INR0022 | Hidalgo | 200 | Dec-12 | Wind |  | 12INR0029 | Swisher | 500 | Dec-12 | Wind |
| 10INR0024 | Briscoe | 2,940 | Jan-13 | Wind |  | 12INR0027 | Gray | 200 | Jan-13 | Wind |
| 09INR0058 | Howard | 250 | Mar-13 | Wind |  | 11INR0082B | Val Verde | 150 | Mar-13 | Wind |
| 11INR0083B | Crockett | 100 | Mar-13 | Wind |  | 12INR0018 | Gray | 500 | Apr-13 | Wind |
| 10INR0062b | Pecos | 220 | May-13 | Wind |  | 13INR0020 | Glasscock | 350 | May-13 | Wind |
| 09INR0041 | Mitchell | 300 | Jun-13 | Wind |  | 09INR0051 | Borden | 249 | Jun-13 | Wind |
| 13INR0023 | Ector | 240 | Jul-13 | Gas |  | 13INR0016 | Deaf Smith | 251 | Aug-13 | Wind |
| 13INR0004 | Deaf Smith | 500 | Oct-13 | Wind |  | 13INR0005 | Carson | 600 | Oct-13 | Wind |
| 08INR0022 | Floyd | 100 | Dec-13 | Wind |  | 08INR0023 | Floyd | 100 | Dec-13 | Wind |
| 09INR0077 | Reagan | 500 | Dec-13 | Wind |  | 12INR0002a | Briscoe | 200 | Dec-13 | Wind |
| 13INR0007 | Pecos | 200 | Dec-13 | Wind |  | 13INR0017 | Childress | 200 | Dec-13 | Wind |
| 09INR0073 | Scurry | 200 | Dec-13 | Wind |  | 13INR0010 | Parmer | 1,200 | Dec-13 | Wind |
| 08INR0019a | Gray | 250 | Jan-14 | Wind |  | 08INR0019b | Gray | 250 | Jan-14 | Wind |
| 08INR0019c | Gray | 250 | Jan-14 | Wind |  | 13INR0006 | Gray | 750 | Jan-14 | Wind |
| 14INR0003 | Nolan | 850 | Jun-14 | Coal |  | 12INR0002b | Briscoe | 200 | Dec-14 | Wind |
| 14INR0001 | Pecos | 500 | Dec-14 | Wind |  | 12INR0002c | Briscoe | 350 | Dec-15 | Wind |
| 16INR0002 | Brazoria | 700 | Jun-17 | Other |  |  |  |  |  |  |

## Wind Generation

## Wind Capacity Installed by Year

County Location of Installed Capacity and Interconnection Requests (Wind only)

# Regional Planning Group Project Reviews

- Oncor submitted a project to relieve congestion related to new wind units in the Lamesa area.  The project will upgrade the Lamesa to Bluff Creek 138 kV line, rebuild the Bluff Creek to China Grove 138 kV line, rebuild the Lamesa to Ackerly Vealmoor 69 kV line to 138/69 kV double circuit, rebuild the Lamesa 138 kV switching station, build a new 138 kV Ackerly Vealmoor station, add second circuits to all rebuilt lines and include station upgrades at China Grove and Big Spring.  The cost of this project is $ 80.8 M.  This project will be reviewed to ensure that the improvements fit into the likely CREZ transmission solution for the area.  This project is in ERCOT Independent Review.

- Pattern Energy has submitted a project to construct an HVDC tie with a capacity of up to 3000 MW between ERCOT and SERC.  This project is in the comment phase.  ERCOT is currently developing a process for evaluating asynchronous ties with other grids.

# Congestion Costs

Dollars shown in graphs are settlement quality.

OOMC – last 13 months in million$

OOM Down – last 13 months in million$

Local Balancing Energy Down – last 13 months in million$

OOM Up – last 13 months in million$

Local Balancing Energy Up – last 13 months in million$

Replacement Reserve – last 13 months in thousand$

Binding Constraints & Capacity Shortages– July, 2010

| Contingency | Binding Element | Estimated Costs | Transmission Project | Clearance |
| --- | --- | --- | --- | --- |
| Watermill Switch - West Levee Switch & Sargent Road 345kV | Duncanville South - Cedar Hill 138kV | $ 5,552,283 | Cedar Hill Switch second 345/138 kV autotransformer [13TPIT0062 | Outage on Cedar Hill Switch 345kVAT2 |
| Graham SES - Parker Switch 345kV | Flat Creek - Leon Switch 138kV | $ 786,902 | Leon - Flat Creek 138 kV line rebuild [08TPIT0107] | Outage on Jacksboro Switching to Willow Creek 345kV |
| Meadow - PH Robinson 345kV | North Alvin - Hastings 138kV | $ 579,396 | Upgrade North Alvin-Hastings [14TPIT0018] | Outage on Oasis-WA Parish 345kV |
| Greens Bayou – Gable & Hardy-Crockett 138kV | Garrott – Midtown 138kV | $ 539,619 |  | Insufficient generation in East Houston. |
| Zorn-Marion-Clear Springs 345kV | Clear Springs 345/138kV Autotransformer | $ 429,998 |  | Outage on Marion CB 6950_CB |
| Fort Bend-East Bernard 138kV | Flewellen – Peters 138kV | $ 220,790 |  | Outage on Peters to Raccoon Bend 69 kV |
| Capacity |  | $ 195,434 |  |  |
| Austrop Switch – Sandow Switch 345kV | Round Rock NE – Round Rock 138kV | $ 193,227 |  | High north to south flow |
| Houston Import |  | $ 179,961 |  |  |
| Ingleside – Whitepoint 138kV | Rincon – White Point 138kV | $ 114,398 |  |  |

Inter-zonal Congestion

# Wind Generation as a Percent of Load

One-hour average Settlement quality data shown.

# Other Notable Activities

- Work on the 2010 Five-Year Transmission Plan is underway.  The initial set of projects needed to reliably serve load in 2015 has been identified and comments have been received.  The analysis is currently focused on finalizing reliability projects for the years 2011-2014 and projects to relieve congestion for 2011 through 2015.

- Nodal Network Model Management System Topology Processor base case building modernization work continues with bi-weekly meetings/calls with SSWG and weekly ERCOT topology processor output.  ERCOT is working on the MOD sandbox system and will populate with a topology processor output case with a build date of late September.  ERCOT and SSWG will create generation, load, and voltage profiles to create a solvable case respresenting summer peak load.  This will be compared to the current 2010 Summer Peak case.

- ERCOT created a spreadsheet showing impedance and branch ratings differences that need to be reconciled between the current 2010 Fall Peak SSWG case and Topology Processor output case with a November build date.  The purpose of this comparison is to confirm that impedances and ratings in the NMMS have been crosschecked against the SSWG database.

- Studies to determine the ERCOT System Voltage Profile have begun.  Market Participants should participate in these to make sure that their interests and unit capabilities are taken into consideration.

- Blackstart testing has begun.  ERCOT staff are witnessing the required tests.

- The CREZ Reactive Study, being performed by ABB and led jointly by ERCOT and the CREZ TSPs, to optimize the reactive support equipment required to implement the CREZ plan is ongoing.  This study will define the size, type and location of the equipment as well as study any associated subsynchronous issues.

- Work on the Long-Term System Assessment/DOE Study has begun.  A separate subgroup of RPG has been established to focus on this study and is meeting monthly.  The current focus is on background information that will be used for developing the scenarios to be studied.  The next meeting is July 23rd.

- Transient Stability Study for 2010 Summer on-peak conditions: As part of the annual reliability assessment of the network, a transient stability study is being performed on the DWG 2010 case.

- Transient Stability Study for 2013 Summer on-peak conditions: As part of the annual reliability assessment of the network, a transient stability study is being performed on the DWG 2013 case.