## Slide 1: PMO Update to PRS
Troy Anderson
ERCOT Program Management Office
September 23, 2010

## Slide 2: PMO Update – Agenda
  2010 Project Spending Update 3
    As of 9/17/2010
  Nodal Parking Deck 4-8
    As of 9/5/2010
  Project Implementations 9-10
    August 2010
  2011 Project Prioritization 11-18
    Approval schedule
    Recent changes in overall funding approach
    Summary of 2011 Project Priority List (PPL)
    Request for approval/endorsement

## Slide 3: 2010 Project Spending Update – 9/17/2010
Program Area | Initial Budget | Current Budget | Forecast | YTD Actual
CO | $ 1,150,000 | $ 1,150,000 | $ 1,063,712 | $ 457,019
IO | $ 1,450,000 | $ 765,000 | $ 882,137 | $ 693,412
MO | $ 1,500,000 | $ 1,297,649 | $ 1,029,607 | $ 600,508
RO | $ 1,900,000 | $ 1,892,118 | $ 1,491,896 | $ 1,204,111
SO | $ 150,000 | $ 144,068 | $ 101,223 | $ 81,373
Minor Cap | $ 750,000 | $ 1,435,000 | $ 1,435,000 | $ 1,012,450
Released but Not Yet Reallocated | $ 0 | $ 5,932 | $ 0 | $ 0
Subtotals | $ 6,900,000 | $ 6,689,767 | $ 6,003,575 | $ 4,048,873
Met Center Replacement | $ 31,900,000 | $ 37,600,000 | $ 36,556,194 | $ 29,854,119
Data Center Hardware | $ 7,500,000 | $ 7,900,000 | $ 8,226,440 | $ 2,542,415
Grand Totals | $ 46,300,000 | $ 52,189,767 | $ 50,786,209 | $ 36,445,407
* $685k from IO to Minor Cap for software licenses ** $400k from Met Center to DC Hardware for telecom equip.
*** Includes Board-authorized carryover of $5.9M in unspent 2009 funds
***
**
**
*
*

## Slide 4: Nodal Parking Deck – Approved
Source | Title | Priority | Approval Date
NPRR208 | Registration and Settlement of Distributed Generation (DG) Less Than One MW | Critical | BoD Approved 7/20/2010
SCR756 | Enhancements to the MarkeTrak Application | Critical | BoD Approved 7/20/2010
NPRR131 | Ancillary Service Trades with ERCOT | High | BoD Approved 1/19/2010
NPRR146 | ICCP Telemetry Information Submittals | High | BoD Approved 6/15/2010
NPRR181 | FIP Definition Revision | High | BoD Approved 1/19/2010
NPRR207 | Unit Deselection | High | BoD Approved 7/20/2010
NPRR210 | Wind Forecasting Change to P50, Synch PRR841 | High | BoD Approved 6/15/2010
NPRR222 | Half-Hour Start Unit RUC Clawback | High | BoD Approved 7/20/2010
NPRR153 | Generation Resource Fixed Quantity Block Offer | Medium | BoD Approved 1/19/2010
NPRR164 | Resubmitting Ancillary Service offers in SASM | Medium | BoD Approved 1/19/2010
SCR755 | ERCOT.com Website Enhancements | Medium | BoD Approved 2/16/2010
Total Approved = 11
The items above are sorted by Priority then by Source
µ
µ
On Parking Deck due to resource impact only. Separately funded on 2011 PPL.

## Slide 5: Nodal Parking Deck – Pending
Source | Title | Suggested Priority | Current Status
NPRR240 | Proxy Energy Offer Curve | High / Medium | Pending at Board TAC approved 9/2/2010
NPRR241 | Aggregate Incremental Liability (AIL) Calculation and Credit Reports Publish Corrections | Medium | Pending at Board TAC approved 9/2/2010
NPRR251 | Sync of PRR845, Definition for IDR Meters and Optional Removal of IDR Meters at a Premise Where an Advanced Meter Can be Provisioned | High | Pending at Board TAC approved 9/2/2010
NPRR256 | Sync Nodal Protocols with PRR787, Add Non-Compliance Language to QSE Performance Standards | TBD | Pending at NATF
NPRR257 | Synchronization with Nodal Operating Guide Section 9, Monitoring Programs | TBD | Pending at PRS
NPRR258 | Sync with PRR824 and PRR833 and Additional Clarifications | TBD | Pending at PRS
NPRR260 | Providing Access to MIS Secure Area to MIS Registered Users | TBD | Tabled at PRS
NOGRR034 | Rescind Telemetry Performance Calculation Exclusions | Medium | Pending at Board TAC approved 8/5/2010
NOGRR050 | Resolution of Reporting Issues Related to NPRR219 | TBD | Pending at PRS ROS approved 8/12/2010
SCR759 | acLineSegment Name Length Increase in Information Model Manager | High | Pending at Board TAC approved 9/2/2010
Total Pending = 10
The items above are sorted by Source

## Slide 6: Nodal Parking Deck – Additional Items for Consideration
Title | Current Status / Description
Deferred NOGRR025 Reports | Draft NPRR in progress to gray-box reports planned for delivery after Nodal go-live
NMMS API | Functionality to be considered for post-go-live development
CRR API | Functionality to be considered for post-go-live development
MMS Multiple Network Models | Functionality to be considered for post-go-live development
Add PSS Status to RARF | Automation of manual process as a result of NPRR156
Automated Default Uplift Invoice | Automation of manual process as a result of NPRR221
EILS Enhancements | Automation of manual process
Load Participation in SCED | Functionality to be considered for post-go-live development
EMS Upgrade | Upgrade EMS system from v2.3 to v2.5/v2.6
Deferred Defects | Defects not addressed prior to go-live or during Nodal stabilization period Approximately 700 deferred defects as of July 2010 Review underway to confirm issues and confirm acceptable workarounds
Total “Other” = 19

## Slide 7: Nodal Parking Deck – Additional Items for Consideration
Title | Current Status / Description
Large Wind Power Production Ramp Forecasting Phase 2 | Phase 2 of the project that built a display for ERCOT operators to indicate periods of time within the next 6 hours during which there is a high risk for a large wind power production ramp to occur
TML Transition to MIS | Upon go live, most applications that are currently available through TML will migrate to MIS and will only be accessible to MPs through the MIS portal. RMS has requested that Zonal Reports, Find ESI ID, Find Transactions, and Transaction submission be accessed through TML until MIS has had sufficient time to stabilize.
Decommission of Zonal Wholesale | After go-live of the redesigned ERCOT wholesale market, certain ERCOT systems and components that were only applicable to zonal wholesale operations will become disposable and need to be decommissioned.
Nodal Cutover Cleanup | Remove pre-go-live data from Nodal systems
Move Price Validation Tool (PVT) to a Server Application | Functionality to be considered for post-go-live development
PVT Enhancements | Enhancements to be identified during market testing and Nodal implementation
PVT Reporting Tools | Functionality to be considered for post-go-live development
Update Credit PFE Model (Potential Future Exposure) | Enhance PFE model to include the following risk factors: • Price volatility analysis for the Day Ahead Market, • Bid and offer volume analysis in the Day Ahead Market, and • Value of Congestion Revenue Rights
Automate Identification of PUNs for Reporting | NPRR202 required that Private Use Networks (PUNs) be excluded from State Estimator postings of transmission flows and voltages. This requirement is being met by adding a static table to the reporting infrastructure to store the list of known PUNs. This Parking Deck item would create a method to dynamically derive the population of PUNs for this reporting.

## Slide 8: 2011 Project Prioritization – Parking Deck Prioritization
High Level Steps to Assess Parking Deck Items
In the first half of 2011, Parking Deck items will be assessed for impact and evaluated for implementation timing
  Some items will be considered for implementation in the Stabilization period
  Others will be targeted for the 1st major release (or future releases)
  The market will be included in these prioritization discussions
Release planning is targeted to begin in July 2011
  Specific items in the release must be identified at this point
1st major release is planned to go live in 2012
During the Execution phase of the 1st release, a separate effort to plan the 2nd release will begin
The details of this process are still under development

## Slide 9: PMO Update – YTD 2010 Project Implementations
January 2010 – None
February 2010
  CO PR-80047_02 DAM Control Center
  IO PR-90009_01 Infrastructure Monitoring Enhancement (Remedy Phase 3)
March 2010
  RO PR-90024_01 POLR Rule and Expedited Switch
      POLR Rule portion
      Expedited Switch delivered in August 2009
  SO PR-90002_01 Large Wind Power Production Ramp Forecasting
April 2010
  RO PR-90011_01 AMS Meter Flag
  RO PR-50088_01 Data Research and Reporting (Phase 1)
  SO PR-50029_01 Improvements to VSA/DSA Phase II
  CO PR-60029_01 Enterprise Records Management Framework
May 2010 – None
June 2010
  IO PR-90010_01 Monitoring & Reporting Tools
  MO PR-90006_01 Information Lifecycle Management (Phase 1)
Months represent project go-live dates, not project completion dates

## Slide 10: PMO Update – YTD 2010 Project Implementations
July / August 2010
  None
September 2010 (projected)
  IO PR-80001_01 Met Center Disposition
  CO PR-10028_01 Physical Security project
October 2010 (projected)
  DC PR-10016_02 Network Gear (Phase 2)
November 2010 (projected)
  None planned
December 2010 (projected)
  DC PR-10015_01 Telcom Equipment (Phase 1)
  DC PR-10016_01 Network Gear (Phase 1)
  IO PR-10018_01 Annual Storage Growth
Months represent project go-live dates, not project completion dates

## Slide 11: 2011 Project Prioritization Schedule – Revised
April 2010 - CARTs develop draft 2011 project lists
May 2010
  Initial review at market subcommittees
    MO - COPS (May 11)
    RO - RMS (May 12)
    SO - ROS, WMS (May 13 / May 19)
June 2010
  Approval/endorsement by market subcommittees
    MO - COPS (June 8)
    RO - RMS (June 9)
July / August 2010 – status updates
September 2010
  Update remaining market subcommittees
    SO - ROS, WMS (September 16 / September 22)
    CO, IO, MO, RO, SO – PRS (September 23)
October 2010
  Approval/endorsement by TAC (October 7)
  Available for F&A and Board review (October 19)

## Slide 12: 2011 Project Prioritization – Stabilization
Nodal System Stabilization is the primary focus in 2011
  Stabilization is the period after Nodal go-live where additional resources are allocated to address urgent issues and increased levels of business activity
  Stabilization funding is being re-evaluated in the overall context of the 2011 ERCOT budget submission
    Work components to be included in Stabilization
    Duration of Stabilization (6-12 months)
  Release planning funding is also being re-evaluated
    Potential component of Stabilization
    This is the item that was originally planned for consideration as an item on the PPL
  The above items will be a topic of discussion at the September Board meeting

## Slide 13: 2011 Project Prioritization – Nodal System Support
Major work categories being planned to support the Nodal systems
1/1/2011
7/1/2011
1/1/2012
Resource Level
Stabilization Support
Components:
Supplemental staff
Emergency fixes/enhancements
High priority deferred defects
Decommissioning efforts
Release Planning
Cost estimate in progress
Steady State Nodal Systems Support
Ongoing O&M Cost
2012 Release Execution

## Slide 14: 2011 Project Prioritization – Current Questions
Q – How can a change be considered in Stabilization?
  See slide 8. More details forthcoming.
Q – Define steps to prioritize items for Stabilization
  Still under development
Q – How can the market have confidence that ERCOT is appropriately staffed for post-Go-Live activities?
    See slide 13
      Steady state staffing levels are budgeted in department O&M budgets
      Incremental resources are being budgeted for Stabilization

## Slide 15: 2011 Project Prioritization – Primary Components
There are now 2 components to ERCOT’s 2011 project funding request:
1 – Data Center Hardware Purchase and Installation $37.0M*
2 – Other critical and high priority projects that have
limited resource impacts on items 1 and 2 $ 8.2M
Total $45.2M
ERCOT is reviewing options to reduce the funding requirement for Data Center Hardware (potentially as much as $20M)
  Authorize carryover of excess 2010 ERCOT revenue to 2011
  Accelerate purchases to Q4 2010 and fund with excess 2010 ERCOT revenue

## Slide 16: 2011 Project Priority List / Funding Level Review
2011 Project Budgets and Project Counts by Program Area
Program Area | Budget Request | Projects Started in 2008/2009 | New 2010 Projects
CO | $ 375,000 | 1 | 1
IO | $ 765,000 | 0 | 2
MO | $ 3,360,000 | 3 | 0
RO | $ 2,700,000 | 1 | 2
SO | $ 0 | 0 | 0
Minor Cap | $ 1,000,000 | 0 | 1
Subtotal | $ 8,200,000 | 5 | 6
Nodal Release Planning | $ 0 | 0 | 0
Data Center Refresh (IO) | $ 37,000,000 | 1 | 0
Grand Total | $ 45,200,000 | 6 | 6
Nodal Release Planning replaces the estimate from SO in 2011
Nodal Release Planning is now being budgeted as part of Nodal Stabilization
*
*
**
**

## Slide 17: 2011 Project Priority List / Funding Level Review
2011 Project Prioritization Notes by Program Area
  Nodal Release Planning ($ 0)
    Planning funds for Parking Deck and other Nodal enhancements
    Now a component of Nodal Stabilization
  Data Center Refresh (IO) ($37,000,000)
    Continuing effort to purchase and install hardware in new data centers
    Effort underway to reduce 2011 funding need
  CO ($ 375,000)
    1 carryover project and 1 security project
  IO ($ 765,000)
    1 infrastructure project and 1 security project
  MO ($ 3,360,000)
    Continuation of Information Lifecycle Management project
    2 internal software enhancement projects that recently initiated
  RO ($ 2,700,000)
    2 PUCT/market projects and Data Research & Reporting project
  Minor Cap ($ 1,000,000)

## Slide 18: 2011 Project Prioritization – Motion
Suggested Motion
Motion to approve/endorse ERCOT’s proposal to fund 2011 projects in the amount of $45.2M.
This includes $1M-$2M to support PUCT and Market requests.
It is understood that requested amounts for the Data Center Hardware projects may be revised based on a change in funding approach. Other ERCOT projects are also subject to change as the ERCOT budget process nears completion.