- DRAFT MINUTES OF THE ERCOT

Nodal advisory task force (NATF) MEETING

ERCOT Austin Office

- 7620 Metro Center Drive

- Austin, TX 78744

- August 31, 2010

- Meeting Attendance:

Segment Representatives in Attendance:

| Name | affiliation | Market Segment |
| --- | --- | --- |
| Bivens, Danny | OPUC | Consumers - Residential |
| Blackburn, Don | Luminant | Investor Owned Utility (IOU) |
| Jackson, James | CPS Energy | Municipal |
| Kroskey, Tony | Brazos | Cooperative (Alt.) |
| Lovelace, Russell | Shell Energy | Independent Power Marketer (IPM) |
| McEvoy, Kevin | Exelon Generation | IPM (Alt.) |
| McMurray, Mark | Direct Energy | Independent Retail Electric Provider (IREP) (Alt.) (Via Teleconference) |
| Ögelman, Kenan | CPS Energy | Municipal (Alt.) |
| Reynolds, Jim | StarTex Power | IREP |
| Richard, Naomi | LCRA | Cooperative |
| Seymour, Cesar | Suez | Independent Generator (Alt.) |
| Wardle, Scott | Occidental Chemical | Consumer – Industrial |

Non-voting Attendees:

| Name | Affiliation |  |
| --- | --- | --- |
| Aguirre, T. | CPS Energy | Via Teleconference |
| Alford, Anthony | CenterPoint Energy | Via Teleconference |
| Allen, Thresa | Iberdrola Renewables | Via Teleconference |
| Ankalm, Rob | Cargill | Via Teleconference |
| Ashley, Kristy | Exelon |  |
| Bailey, Dan | Garland Power and Light |  |
| Barrow, Les | CPS Energy | Via Teleconference |
| Basaran, Harika | Austin Energy | Via Teleconference |
| Bevill, Jennifer | AEP | Via Teleconference |
| Bogen, David | Oncor |  |
| Brandt, Adrianne | Austin Energy |  |
| Briscoe, Judy | BP | Via Teleconference |
| Brown, Jack | Garland Power and Light | Via Teleconference |
| Brown, Jeff | Shell Energy |  |
| Cannon, Maribeth | Edison Mission | Via Teleconference |
| Carter, Kevin | Duke Energy | Via Teleconference |
| Clemenhagen, Barbara | Topaz |  |
| Clevenger, J. |  | Via Teleconference |
| Cochran, Seth | RBS Sempra | Via Teleconference |
| Coffing, Timothy | Luminant | Via Teleconference |
| Crozier, Richard | Brownsville |  |
| De La Rosa, Lewis | PUCT |  |
| Detelich, David | CPS Energy | Via Teleconference |
| Doll, Laura | ERCOT Board |  |
| Ebby, John | CenterPoint Energy | Via Teleconference |
| English, Rock | Luminant | Via Teleconference |
| Fahey, Matt | ANP/IPA | Via Teleconference |
| Fogarty, Audrey | EON | Via Teleconference |
| Galliguez, Percy | Brazos Electric | Via Teleconference |
| Galvin, Jim | Luminant | Via Teleconference |
| Garza, Beth | Potomac Economics | Via Teleconference |
| Geinzer, Jay | AES | Via Teleconference |
| Goff, Eric | Reliant |  |
| Grimes, Mike | Horizon | Via Teleconference |
| Hampton, Brenda | Luminant |  |
| Hassouni, Daniel | DC Energy | Via Teleconference |
| Hebert, Jason | PCI | Via Teleconference |
| Hellinghausen, Bill | EDF |  |
| Hess, Stephen | Edison Mission | Via Teleconference |
| Hughes, Darren | Optim Energy | Via Teleconference |
| Huynh, Thuy | Potomac Economics | Via Teleconference |
| Jacoby, Jim | AEP |  |
| Janssen, John | Sunguard | Via Teleconference |
| Jeev, Kumar | DC Energy | Via Teleconference |
| Jones, Dan | Potomac Economics |  |
| Jones, Liz | Oncor | Via Teleconference |
| Jones, Randy | Calpine |  |
| Kolodziej, Eddie | Customized Energy Solutions |  |
| Lange, Clif | STEC | Via Teleconference |
| Lewis, W. | Cirro Energy | Via Teleconference |
| Li, Y. | Potomac Economics |  |
| Looney, Sherry | Luminant |  |
| Martin, Javier | PCI |  |
| Mathews, Michael | Bryan Texas Utilities | Via Teleconference |
| McLamb, Darryl | Constellation | Via Teleconference |
| McNamara, Grace | LDH Energy | Via Teleconference |
| Morris, Sandy | LCRA | Via Teleconference |
| Munoz, Manny | CenterPoint Energy | Via Teleconference |
| Nikazm, Tamila | Austin Energy | Via Teleconference |
| O’Leary, Paul | EDF Trading | Via Teleconference |
| Palani, Anath | Optim Energy | Via Teleconference |
| Pieniazek, Adrian | NRG |  |
| Priestley, Vanus | Macquarie |  |
| Sandidge, Clint | Sempra Solutions | Via Teleconference |
| Satkowski, Ned | PSEG Texas | Via Teleconference |
| Siddiqi, Shams | LCRA |  |
| Soutter, Mark | Invenergy |  |
| Starr, Lee | Bryan Texas Utilities | Via Teleconference |
| Stephenson, Randa | Luminant |  |
| Thomas, Wayne | Bryan Texas Utilities | Via Teleconference |
| Thompson, Bobby | Luminant | Via Teleconference |
| Tomlinson, Brian | Rayburn Electric Cooperative |  |
| Troell, Mike | STEC | Via Teleconference |
| Varnell, John | TENASKA |  |
| Vo, Trieu | CPS Energy |  |
| Wagner, Marguerite | PSEG TX |  |
| Wan, Josephine | Austin Energy | Via Teleconference |
| Watson, Mark | Platts Oilgram | Via Teleconference |
| Wheeler, Ron | Optim Energy |  |
| Wittmeyer, Bob | DME |  |
| Woodard, Stacy | LCRA | Via Teleconference |
| Zang, H. | Potomac Economics | Via Teleconference |
| Zarnikau, Jay | Frontier | Via Teleconference |

ERCOT Staff:

| Name |  |
| --- | --- |
| Allen, Sean | Via Teleconference |
| Bauld, Mandy | Via Teleconference |
| Boren, Ann | Via Teleconference |
| DiPastena, Phil | Via Teleconference |
| Dumas, John |  |
| Geer, Ed | Via Teleconference |
| Gonzalez, Ino | Via Teleconference |
| Hanson, Chuck | Via Teleconference |
| Kasparian, Ken | Via Teleconference |
| Landin, Yvette | Via Teleconference |
| Landry, Kelly |  |
| Madden, Terry | Via Teleconference |
| Maggio, David |  |
| Manz, Laura |  |
| Matlock, Robert | Via Teleconference |
| McElfresh, Brandon |  |
| Middleton, Scott | Via Teleconference |
| Natoli, Anthony | Via Teleconference |
| Opheim, Calvin | Via Teleconference |
| Ragsdale, Ken |  |
| Rajagopal, Raj | Via Teleconference |
| Reedy, Steve |  |
| Roark, Dottie | Via Teleconference |
| Shaw, Pamela | Via Teleconference |
| Sills, Alex | Via Teleconference |
| Spangler, Bob | Via Teleconference |
| Surendran, Resmi |  |
| Trefny, Floyd | Via Teleconference |
| Wise, Joan | Via Teleconference |
| Yager, Cheryl | Via Teleconference |

Unless otherwise indicated, all Market Segments were present for a vote.

Don Blackburn called the meeting to order at 9:30 a.m.

Antitrust Admonition

Mr. Blackburn read the Antitrust Admonition, which was displayed.  He asked those who had not yet reviewed the Antitrust Guidelines to do so.  Copies of the Antitrust Guidelines were available.

Consider Approval of Meeting Minutes

Naomi Richard moved to approve the 06/23/2010 and 07/08/2010 NATF meeting minutes as presented.  Cesar Seymour seconded the motion.  The motion carried unanimously.

Market Reform Report

Laura Manz reviewed the Market Reform report previously presented to the ERCOT Board.  She noted that the report provided a high-level risk analysis of the ERCOT Nodal Protocols and observed one serious issue needing resolution before Texas Nodal Market implementation.  Steve Reedy stated that the issue is with system performance, not design.  He explained that when there are an excessive number of unique source/sink pairs of Congestion Revenue Right (CRR) Offers in combination with contingencies, a performance issue arises in the power flow and Contingency Analysis Module (NSM) due to the sheer volume of computations necessary.  He noted that the amount of time needed to complete the calculations may exceed the three and one half hours allotted to provide the results of the Day-Ahead Market (DAM), and that currently approximately 150 Point to Point Options can be calculated in a timely manner.  Mr. Reedy stated that potential action plans for immediate implementation would include potential software and hardware improvements and the use of new math libraries.  He noted that a long term solution would include enhancements to parallel computation capabilities of the NSM.  Mike Cleary stated ERCOT Staff would be meeting with Non-Opt-In Entities (NOIEs) to discuss the issue and would provide NATF with an update as soon as possible.

DAM Available Credit Limit (ACL)

Eric Goff noted that during recent market trials testing, DAM was run over non-business days for the first time with credit constraints and that a significant amount of credit was consumed such that some Market Participants were constrained from full participation in the DAM on the following Business Day due to their ACL.  Mr. Goff stated that the Credit Working Group (CWG) and Market Credit Working Group (MCWG) convened a meeting to examine this issue and provided several recommendations.  Mr. Blackburn directed that a Special NATF meeting be scheduled for 09/02/2010 to further review and provide a recommendation on this issue.

Review Modeling Expectations White Paper and Comments

Woody Rickerson reviewed Modeling Expectations White Paper version 5.0, and the comments that had been incorporated and rejected.  Randa Stephenson noted that the approval to energize process included in the White Paper was intended to be the official process and that future revisions of the White Paper would be reviewed and documented by the Network Data Support Working Group (NDSWG) and the Reliability and Operations Subcommittee (ROS).

Cesar Seymour moved to endorse the Modeling Expectations White Paper version 5.0 as revised by NATF 08/31/2010.  James Jackson seconded the motion.  The motion carried unanimously.

Ancillary Services Capacity Monitor

Bill Hellinghausen observed that ERCOT Protocols require ERCOT to provide Market Participants with Real-Time summaries of available capacity that can be used to increase or decrease Base Points in the Security Constrained Economic Dispatch (SCED), and noted confusion regarding the meaning of this requirement.  He stated that ERCOT intends to publish the difference between the Base Point and the High Dispatch Limit or Low Dispatch Limit respectively.  Mr. Hellinghausen stated that his interpretation was that ERCOT should publish the difference between the Base Point and the High Ancillary Services Limit (HASL) or Low Ancillary Services Limit (LASL) representing the SCED up and SCED down reserve.

Qualified Scheduling Entity (QSE) List of Nodal Issues/Critical Items

Naomi Richard noted that a list of severity one issues affecting Texas Nodal Market implementation has been collected and that ERCOT had provided comments to each of the items.  She reviewed the criteria for classification of the issues and ERCOT comments, and Market Participants discussed each issue individually to ensure proper categorization and that ERCOT had identified a plan for resolution.  Mr. Blackburn stated that NATF would continue to review and update the list as necessary.

Nodal Protocol Revision Requests (NPRRs) Referred by the Protocol Revision Subcommittee (PRS)

NPRR256, Synchronize Nodal Protocols with PRR787, Add Non-Compliance Language to QSE Performance Standards

Ms. Stephenson recommended that discussion of this item be postponed until the next NATF to allow time for additional comments to be submitted.  Market Participants agreed.

NPRR257, Synchronization with Nodal Operating Guide Section 9, Monitoring Programs

Yvette Landin noted that NPRR257 gray-boxes multiple sections of the Nodal Protocols to align them with Nodal Operating Guide Section 9, Monitoring Programs.  Sherry Looney opined that NPRR257 removes the requirement for ERCOT to post some reports that are critical to Market Participant’s ability to monitor their performance.  Alex Sills observed that the operational reports needed by Market Participants will be delivered in spite of NPRR257 as part of the Telemetry Performance Report.  Ms. Looney stated that she would withdraw Luminant’s comments to NPRR257.

Danny Bivens moved to recommend approval of NPRR257 as submitted by ERCOT.  Ms. Richard seconded the motion.  The motion carried unanimously.

NPRR119, Resource Limit Calculator

Modifications as a Result of the Latest Full System Market and Reliability Test

David Maggio reviewed a graph indicating the dates between 08/15/2010 and 08/29/2010 when a high number of Resource Limit Calculator (RLC) alerts were dispatched and noted the importance of Market Participant’s attention to them.  He observed that there were some legitimate reasons for the alerts, but that market trials may have identified potential inaccuracies with regard to some Generation Resources telemetered High sustained Limits (HSLs).

Preview Market Readiness Criteria for Remaining Parts of the Nodal Program

Brandon McElfresh reviewed readiness criteria and metric totals, and noted that 26 metrics are planned, 23 metrics remain active, and 26 metrics are complete.  Mr. McElfresh noted that of the 26 completed metrics, 7 were previously acknowledged by NATF as complete.  Market Participants acknowledged the remaining 19 metrics as complete and agreed that it was no longer necessary for ERCOT to track associated performance.

Russell Lovelace expressed concern with issues with Nodal Implementation that are not tracked by metrics, and observed the Point to Point Options issue as an example.  He opined that the Point to Point Options issue is a system performance problem and not a defect, and is therefore not being tracked through metrics.  Ken Ragsdale noted that the QSE Issues list is tracking this and similar issues and stated that he would consider alternatives for better tracking.

Competitive Constraints List for Nodal Market Implementation

Decision-Making Entities (DMEs) and Common Control

Beth Garza stated that DMEs should not be affiliated with one another and that the current list should be updated as necessary to indicate that no such affiliations exist.  She noted that the Independent Market Monitor would not be constructing a new list.  Ms. Stephenson recommended that a Market Notice be distributed advising Market Participants of the need for review of their respective DME and to submit updates as necessary.

Draft Business Practices for ERCOT and QSE Operations During the Operating Hour

Review Business Practice – ERCOT and QSE Operations Practices During the Operating Hour

Mr. Maggio noted that discussion of this item should be postponed until the next NATF meeting to allow more time for Market Participant comments.  Randy Jones stated that he would be submitting comments supporting an “on-ramp” status similar to the “on-test” status proposed by ERCOT.  He noted that the recommendation would be for post Texas Nodal Market implementation.  Mr. Blackburn encouraged interested Market Participants to submit comments and directed that this item be added the agenda for the next NATF meeting.

Adjournment

Mr. Blackburn noted that the next NATF meeting would be 09/07/2010 and that the 09/14/2010 meeting was rescheduled to 09/16/2010.  He adjourned the meeting at 4:35 p.m.

Some attendees may not have been present for the entire meeting.