## 10-1
TSP Issue List Summary Updated 10/1/2010 | NMMS - Changes to Interim Update definition | NMMS - Operational Updates as Interim updates | NMMS system performance issues | NMMS - OS coordination Process | NMMS - Updated process for SPSs | NMMS - Transparancy into ERCOT Validation Changes | NMMS - ME process burden for TSPs | NMMS - ERCOT introduced NOMCRs responsibilities | NMMS - 15th of the month deadline for model changes | NMMS - Ratings in multiple places | NMMS - Process to prevent broken outages | NMMS - Visibility into future operations cases | NMMS - NPRR146 resolution | NMMS - Gray box implementation timeline | NMMS - Pseudo equipment | SE metrics and reports | SE -- solution not getting better | SE -- Telemetry Standards exclusion | OS - Executing the A2E process | OS - A2E Process Definition and Training | OS use for relocation process | OS - Explanation of Nov. 1 binding deadline for OS | OS - CNP lines with extra "1" in OS | OS exclusion for energization outages | OS - each tap station has to be entered | OS - historical tracking | OS - selecting time method | OS - Req Company | OS - lines not selectable from both ends | OS - NPRR219 burden on TSPS | PL - roll up of all SSWG Recommend Changes | PL - go-live prior IMM changes effective | PL - SCR759 | PL - process for building models is unknown | PL - TSP review of RARF data | PL - SVCs | PL - FACTS | PL - assigning cap banks to CNG | PL - assigning loads to right CNG | PL - zero impedance lines | PL - Load ownership | PL - Pmax and Pmin | PL - distribution Cap banks | PL - distributive gen | PL - Special Planning Models | PL - Allow adding 30 deg phase shift to Autos | PL - Phase shifting TSF | PL - TP radial line reduction problems | PL - SPS pseudo equipment | PL - Ability to support future PSSE versions | PL - TSP with no access to MOD | PL - documentation for TOP
POTENTIAL PROJECTS | 1 | 2 | 3 | 5 | 8 | 10 | 12 | 13 | 14 | 15 | 16 | 17 | 44 | 46 | 47 | 18 | 19 | 45 | 4 | 6 | 7 | 9 | 11 | 20 | 21 | 22 | 23 | 24 | 25 | 43 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 48 | 49 | 50 | 51 | 52 | Row Totals
FOD modifications |  | 1 | [50 empty] | 1
Outage Scheduling enhancements | [20 empty] | 1 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | [22 empty] | 7
Forward looking SOTE environment | [11 empty] | 1 | [40 empty] | 1
MOD/ TP enhancement | [52 empty] | 11 | bar: 26 to 27; 29; 31 to 38; 41 to 48; 50
CIM Schema Change | [22 empty] | 1 | [29 empty] | 10 | 30 | bar: 26; 28; 31 to 35; 38; 41 to 42
NPRRs and SCRs | 1 | 2 | 3 | 5 | 8 | 10 | 12 | 13 | 14 | 15 | 16 | 17 | 44 | 46 | 47 | 18 | 19 | 45 | 4 | 6 | 7 | 9 | 11 | 20 | 21 | 22 | 23 | 24 | 25 | 43 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 48 | 49 | 50 | 51 | 52
Waiting on SCR759 | [22 empty] | 1 | [29 empty] | 2 | bar: 1 28
Waiting on NPRR146 gray box | [8 empty] | 1 |  |  |  | 1 | [39 empty] | 2
Waiting on NPRR219 | [29 empty] | 1 | [22 empty] | 1
Waiting on Future documentation | [9 empty] | 1 | [42 empty] | 4 | bar: 1 29; 1 49; 1 52
Waiting on Future NPRR | 1 | 1 |  |  |  | 1 | [7 empty] | 1 | [38 empty] | 6 | bar: 1 29 to 1 30
Needs SCR Submitted | [11 empty] | 1 | [5 empty] | 1 | [34 empty] | 11 | 26 | bar: 1 26; 1 32 to 1 35; 1 38; 1 40 to 1 42; 1 50 to 1 51
CURRENT STATUS | 1 | 2 | 3 | 5 | 8 | 10 | 12 | 13 | 14 | 15 | 16 | 17 | 44 | 46 | 47 | 18 | 19 | 45 | 4 | 6 | 7 | 9 | 11 | 20 | 21 | 22 | 23 | 24 | 25 | 43 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 48 | 49 | 50 | 51 | 52
Monitor and Evaluate |  |  |  | 1 | [11 empty] | 1 | 1 |  | 1 | 1 | 1 | [31 empty] | 12 | bar: 1 27; 1 35; 1 37; 1 48 to 1 49; 1 51 to 1 52
Resolved |  |  | 1 |  |  | 1 | 1 | [7 empty] | 1 |  |  |  |  | 1 |  | 1 |  | 1 | [28 empty] | 10 | bar: 1 31; 1 36; 1 39
Deferred | 1 | 1 |  |  | 1 |  |  | 1 | 1 | 1 | 1 | 1 | [5 empty] | 1 |  |  |  |  | 1 |  | 1 | 1 | 1 | 1 | 1 | [23 empty] | 15 | 37
Waiting on NPRR or SCR | 1 | 1 |  |  | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | 1 |  |  |  |  | 1 |  | 1 | 1 | 1 | 1 | 1 | [23 empty] | 29 | bar: 1 26; 1 28 to 1 30; 1 32 to 1 35; 1 38; 1 40 to 1 42; 1 50 to 1 51
REQUESTED DELIVERY | 1 | 2 | 3 | 5 | 8 | 10 | 12 | 13 | 14 | 15 | 16 | 17 | 44 | 46 | 47 | 18 | 19 | 45 | 4 | 6 | 7 | 9 | 11 | 20 | 21 | 22 | 23 | 24 | 25 | 43 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 48 | 49 | 50 | 51 | 52
Needed early 2011 | 1 | 1 | [5 empty] | 1 |  |  |  | 1 | [16 empty] | 1 | [23 empty] | 15 | bar: 26; 28 to 30; 35; 38; 40; 42 to 48; 50 to 51
Needed mid 2011 |  |  |  |  | 1 |  |  |  | 1 |  | 1 |  | 1 | [39 empty] | 5 | bar: 26
Needed late 2011 | [52 empty] | 1 | bar: 26; 36
Needed in 2012 | [24 empty] | 1 | 1 | 1 | 1 | [24 empty] | 5 | 26 | bar: 42
| 1 | 2 | 3 | 5 | 8 | 10 | 12 | 13 | 14 | 15 | 16 | 17 | 44 | 46 | 47 | 18 | 19 | 45 | 4 | 6 | 7 | 9 | 11 | 20 | 21 | 22 | 23 | 24 | 25 | 43 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 48 | 49 | 50 | 51 | 52

## 9-30
TSP Issue List Summary Updated 9/30/2010 | NMMS - Changes to Interim Update definition | NMMS - Operational Updates as Interim updates | NMMS system performance issues | NMMS - OS coordination Process | NMMS - Updated process for SPSs | NMMS - Transparancy into ERCOT Validation Changes | NMMS - ME process burden for TSPs | NMMS - ERCOT introduced NOMCRs responsibilities | NMMS - 15th of the month deadline for model changes | NMMS - Ratings in multiple places | NMMS - Process to prevent broken outages | NMMS - Visibility into future operations cases | NMMS - NPRR146 resolution | NMMS - Gray box implementation timeline | NMMS - Pseudo equipment | SE metrics and reports | SE -- solution not getting better | SE -- Telemetry Standards exclusion | OS - Executing the A2E process | OS - A2E Process Definition and Training | OS use for relocation process | OS - Explanation of Nov. 1 binding deadline for OS | OS - CNP lines with extra "1" in OS | OS exclusion for energization outages | OS - each tap station has to be entered | OS - historical tracking | OS - selecting time method | OS - Req Company | OS - lines not selectable from both ends | OS - NPRR219 burden on TSPS | PL - roll up of all SSWG Recommend Changes | PL - go-live prior IMM changes effective | PL - SCR759 | PL - process for building models is unknown | PL - TSP review of RARF data | PL - SVCs | PL - FACTS | PL - assigning cap banks to CNG | PL - assigning loads to right CNG | PL - zero impedance lines | PL - Load ownership | PL - Pmax and Pmin | PL - distribution Cap banks | PL - distributive gen | PL - Special Planning Models | PL - Allow adding 30 deg phase shift to Autos | PL - Phase shifting TSF | PL - TP radial line reduction problems | PL - SPS pseudo equipment | PL - Ability to support future PSSE versions | PL - TSP with no access to MOD | PL - documentation for TOP
POTENTIAL PROJECTS | 1 | 2 | 3 | 5 | 8 | 10 | 12 | 13 | 14 | 15 | 16 | 17 | 44 | 46 | 47 | 18 | 19 | 45 | 4 | 6 | 7 | 9 | 11 | 20 | 21 | 22 | 23 | 24 | 25 | 43 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 48 | 49 | 50 | 51 | 52 | Row Totals
FOD modifications |  | 1 | [50 empty] | 1
Outage Scheduling enhancements | [20 empty] | 1 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | [22 empty] | 7
Forward looking SOTE environment | [11 empty] | 1 | [40 empty] | 1
MOD/ TP enhancement | [52 empty] | 14 | bar: 26 to 27; 29; 31 to 38; 41; 48; 50
CIM Schema Change | [22 empty] | 1 | [29 empty] | 10 | 33 | bar: 26; 28; 31 to 34; 38; 41 to 42
NPRRs and SCRs | 1 | 2 | 3 | 5 | 8 | 10 | 12 | 13 | 14 | 15 | 16 | 17 | 44 | 46 | 47 | 18 | 19 | 45 | 4 | 6 | 7 | 9 | 11 | 20 | 21 | 22 | 23 | 24 | 25 | 43 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 48 | 49 | 50 | 51 | 52
Waiting on SCR759 | [22 empty] | 1 | [29 empty] | 2 | bar: 1 28
Waiting on NPRR146 gray box | [8 empty] | 1 |  |  |  | 1 | [39 empty] | 2
Waiting on NPRR219 | [29 empty] | 1 | [22 empty] | 1
Waiting on Future documentation | [9 empty] | 1 | [42 empty] | 3 | bar: 1 49; 1 52
Waiting on Future NPRR | 1 | 1 |  |  |  | 1 | [7 empty] | 1 | [38 empty] | 6 | bar: 1 29 to 1 30
Needs SCR Submitted | [11 empty] | 1 | [5 empty] | 1 | [34 empty] | 13 | 27 | bar: 1 26; 1 32 to 1 35; 1 38; 1 40 to 1 42; 1 50 to 1 51
CURRENT STATUS | 1 | 2 | 3 | 5 | 8 | 10 | 12 | 13 | 14 | 15 | 16 | 17 | 44 | 46 | 47 | 18 | 19 | 45 | 4 | 6 | 7 | 9 | 11 | 20 | 21 | 22 | 23 | 24 | 25 | 43 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 48 | 49 | 50 | 51 | 52
Monitor and Evaluate |  |  |  | 1 | [11 empty] | 1 | 1 |  | 1 | 1 | 1 | [31 empty] | 8 | bar: 35; 37
Resolved |  |  | 1 |  |  | 1 | 1 | [7 empty] | 1 |  |  |  |  | 1 |  | 1 |  | 1 | [28 empty] | 8 | bar: 39
Deferred | 1 | 1 |  |  | 1 |  |  | 1 | 1 | 1 | 1 | 1 | [5 empty] | 1 |  |  |  |  | 1 |  | 1 | 1 | 1 | 1 | 1 | [23 empty] | 15 | 31
Waiting on NPRR or SCR | 1 | 1 |  |  | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | 1 |  |  |  |  | 1 |  | 1 | 1 | 1 | 1 | 1 | [23 empty] | 29 | bar: 26; 29 to 30; 32 to 34; 38; 40 to 42; 50 to 51
REQUESTED DELIVERY | 1 | 2 | 3 | 5 | 8 | 10 | 12 | 13 | 14 | 15 | 16 | 17 | 44 | 46 | 47 | 18 | 19 | 45 | 4 | 6 | 7 | 9 | 11 | 20 | 21 | 22 | 23 | 24 | 25 | 43 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 48 | 49 | 50 | 51 | 52
Needed early 2011 | 1 | 1 | [5 empty] | 1 |  |  |  | 1 | [16 empty] | 1 | [23 empty] | 16 | bar: 26; 28 to 30; 35; 38; 40; 42 to 48; 50 to 51
Needed mid 2011 |  |  |  |  | 1 |  |  |  | 1 |  | 1 |  | 1 | [39 empty] | 5 | bar: 26
Needed late 2011 | [52 empty] | 2 | bar: 26; 36
Needed in 2012 | [24 empty] | 1 | 1 | 1 | 1 | [24 empty] | 4 | 27
| 1 | 2 | 3 | 5 | 8 | 10 | 12 | 13 | 14 | 15 | 16 | 17 | 44 | 46 | 47 | 18 | 19 | 45 | 4 | 6 | 7 | 9 | 11 | 20 | 21 | 22 | 23 | 24 | 25 | 43 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 48 | 49 | 50 | 51 | 52

## 9-24
TSP Issue List Summary Updated 9/24/2010 | NMMS - Changes to Interim Update definition | NMMS - Operational Updates as Interim updates | NMMS system performance issues | NMMS - OS coordination Process | NMMS - Updated process for SPSs | NMMS - Transparancy into ERCOT Validation Changes | NMMS - ME process burden for TSPs | NMMS - ERCOT introduced NOMCRs responsibilities | NMMS - 15th of the month deadline for model changes | NMMS - Ratings in multiple places | NMMS - Process to prevent broken outages | NMMS - Visibility into future operations cases | NMMS - NPRR146 resolution | NMMS - Gray box implementation timeline | NMMS - Pseudo equipment | SE metrics and reports | SE -- solution not getting better | SE -- Telemetry Standards exclusion | OS - Executing the A2E process | OS - A2E Process Definition and Training | OS use for relocation process | OS - Explanation of Nov. 1 binding deadline for OS | OS - CNP lines with extra "1" in OS | OS exclusion for energization outages | OS - each tap station has to be entered | OS - historical tracking | OS - selecting time method | OS - Req Company | OS - lines not selectable from both ends | OS - NPRR219 burden on TSPS | PL - roll up | PL - go-live prior IMM changes effective | PL - SCR759 | PL - process for building models is unknown | PL - TSP review of RARF data | PL - SVCs | PL - FACTS | PL - assigning cap banks to CNG | PL - assigning loads to right CNG | PL - zero impedance lines | PL - Load ownership | PL - Pmax and Pmin | PL - distribution Cap banks | PL - distributive gen | PL - SPWG cases | PL - AutoTsf modeling differences | PL - Phase shifting TSF | PL - TP radial line reduction problems | PL - SPS pseudo equipment | PL - Ability to support future PSSE versions | PL - TSP with no access to MOD | PL - documentation for TOP
POTENTIAL PROJECTS | 1 | 2 | 3 | 5 | 8 | 10 | 12 | 13 | 14 | 15 | 16 | 17 | 44 | 46 | 47 | 18 | 19 | 45 | 4 | 6 | 7 | 9 | 11 | 20 | 21 | 22 | 23 | 24 | 25 | 43 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 48 | 49 | 50 | 51 | 52 | Row Totals
FOD modifications |  | 1 | [50 empty] | 1
Outage Scheduling enhancements | [20 empty] | 1 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | [22 empty] | 7
Forward looking SOTE environment | [11 empty] | 1 | [40 empty] | 1
MOD/ TP enhancement | [52 empty] | 14 | bar: 26 to 27; 29; 31 to 38; 41; 48; 50
CIM Schema Change | [22 empty] | 1 | [29 empty] | 10 | 33 | bar: 26; 28; 31 to 34; 38; 41 to 42
NPRRs and SCRs | 1 | 2 | 3 | 5 | 8 | 10 | 12 | 13 | 14 | 15 | 16 | 17 | 44 | 46 | 47 | 18 | 19 | 45 | 4 | 6 | 7 | 9 | 11 | 20 | 21 | 22 | 23 | 24 | 25 | 43 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 48 | 49 | 50 | 51 | 52
Waiting on SCR759 | [22 empty] | 1 | [29 empty] | 2 | bar: 1 28
Waiting on NPRR267 | [52 empty] | 0 | bar: 1 42
Waiting on NPRR146 gray box | [8 empty] | 1 |  |  |  | 1 | [39 empty] | 2
Waiting on NOGR034 | [52 empty] | 0
Waiting on NPRR219 | [29 empty] | 1 | [22 empty] | 1
Waiting on Telemetry Standards | [52 empty] | 0
Waiting on Future documentation | [9 empty] | 1 | [42 empty] | 3 | bar: 1 49; 1 52
Waiting on Future NPRR | 1 | 1 |  |  |  | 1 | [7 empty] | 1 | [38 empty] | 6 | bar: 1 29 to 1 30
Needs SCR Submitted | [11 empty] | 1 | [5 empty] | 1 | [34 empty] | 13 | 27 | bar: 1 26; 1 32 to 1 35; 1 38; 1 40 to 1 42; 1 50 to 1 51
CURRENT STATUS | 1 | 2 | 3 | 5 | 8 | 10 | 12 | 13 | 14 | 15 | 16 | 17 | 44 | 46 | 47 | 18 | 19 | 45 | 4 | 6 | 7 | 9 | 11 | 20 | 21 | 22 | 23 | 24 | 25 | 43 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 48 | 49 | 50 | 51 | 52
Monitor and Evaluate |  |  |  | 1 | [11 empty] | 1 | 1 |  | 1 | 1 | 1 | [31 empty] | 8 | bar: 35; 37
Resolved |  |  | 1 |  |  | 1 | 1 | [7 empty] | 1 |  |  |  |  | 1 |  | 1 |  | 1 | [28 empty] | 8 | bar: 39
Deferred | 1 | 1 |  |  | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  |  | 1 |  |  | 1 |  |  |  |  | 1 |  | 1 | 1 | 1 | 1 | 1 | [23 empty] | 16 | 32
Waiting on NPRR or SCR | 1 | 1 |  |  | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 |  |  |  |  | 1 |  | 1 | 1 | 1 | 1 | 1 | [23 empty] | 30 | bar: 26; 29 to 30; 32 to 34; 38; 40 to 42; 50 to 51
REQUESTED DELIVERY | 1 | 2 | 3 | 5 | 8 | 10 | 12 | 13 | 14 | 15 | 16 | 17 | 44 | 46 | 47 | 18 | 19 | 45 | 4 | 6 | 7 | 9 | 11 | 20 | 21 | 22 | 23 | 24 | 25 | 43 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 48 | 49 | 50 | 51 | 52
Needed early 2011 | 1 | 1 | [5 empty] | 1 |  |  |  | 1 | [16 empty] | 1 | [23 empty] | 16 | bar: 26; 28 to 30; 35; 38; 40; 42 to 48; 50 to 51
Needed mid 2011 |  |  |  |  | 1 |  |  |  | 1 |  | 1 |  | 1 | [39 empty] | 5 | bar: 26
Needed late 2011 | [52 empty] | 2 | bar: 26; 36
Needed in 2012 | [24 empty] | 1 | 1 | 1 | 1 | [24 empty] | 4 | 27
| 1 | 2 | 3 | 5 | 8 | 10 | 12 | 13 | 14 | 15 | 16 | 17 | 44 | 46 | 47 | 18 | 19 | 45 | 4 | 6 | 7 | 9 | 11 | 20 | 21 | 22 | 23 | 24 | 25 | 43 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 48 | 49 | 50 | 51 | 52
All changes noted in this sheet were discussed and agreed upon during the 9-29-10 Nodal Engagement Call -- dwr

## 9-22a
TSP Issue List Summary Updated 9/22/2010a | NMMS - Changes to Interim Update definition | NMMS - Operational Updates as Interim updates | NMMS system performance issues | NMMS - OS coordination Process | NMMS - Updated process for SPSs | NMMS - Transparancy into ERCOT Validation Changes | NMMS - ME process burden for TSPs | NMMS - ERCOT introduced NOMCRs responsibilities | NMMS - 15th of the month deadline for model changes | NMMS - Ratings in multiple places | NMMS - Process to prevent broken outages | NMMS - Visibility into future operations cases | NMMS - NPRR146 resolution | NMMS - Gray box implementation timeline | NMMS - Pseudo equipment | SE metrics and reports | SE -- solution not getting better | SE -- Telemetry Standards exclusion | OS - Executing the A2E process | OS - A2E Process Definition and Training | OS use for relocation process | OS - Explanation of Nov. 1 binding deadline for OS | OS - CNP lines with extra "1" in OS | OS exclusion for energization outages | OS - each tap station has to be entered | OS - historical tracking | OS - selecting time method | OS - Req Company | OS - lines not selectable from both ends | OS - NPRR219 burden on TSPS | PL - roll up | PL - go-live prior IMM changes effective | PL - SCR759 | PL - process for building models is unknown | PL - TSP review of RARF data | PL - SVCs | PL - FACTS | PL - assigning cap banks to CNG | PL - assigning loads to right CNG | PL - zero impedance lines | PL - Load ownership | PL - Pmax and Pmin | PL - distribution Cap banks | PL - distributive gen | PL - SPWG cases | PL - AutoTsf modeling differences | PL - Phase shifting TSF | PL - TP radial line reduction problems | PL - SPS pseudo equipment | PL - Ability to support future PSSE versions | PL - TSP with no access to MOD | PL - documentation for TOP
POTENTIAL PROJECTS | 1 | 2 | 3 | 5 | 8 | 10 | 12 | 13 | 14 | 15 | 16 | 17 | 44 | 46 | 47 | 18 | 19 | 45 | 4 | 6 | 7 | 9 | 11 | 20 | 21 | 22 | 23 | 24 | 25 | 43 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 48 | 49 | 50 | 51 | 52 | Row Totals
FOD modifications |  | 1 | [50 empty] | 1
Outage Scheduling enhancements | [20 empty] | 1 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | [22 empty] | 7
Forward looking SOTE environment | [11 empty] | 1 | [40 empty] | 1
MOD/ TP enhancement | [52 empty] | 14 | bar: 26 to 27; 29; 31 to 38; 41; 48; 50
CIM Schema Change | [22 empty] | 1 | [29 empty] | 10 | 33 | bar: 26; 28; 31 to 34; 38; 41 to 42
NPRRs and SCRs | 1 | 2 | 3 | 5 | 8 | 10 | 12 | 13 | 14 | 15 | 16 | 17 | 44 | 46 | 47 | 18 | 19 | 45 | 4 | 6 | 7 | 9 | 11 | 20 | 21 | 22 | 23 | 24 | 25 | 43 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 48 | 49 | 50 | 51 | 52
Waiting on SCR759 | [22 empty] | 1 | [29 empty] | 2 | bar: 1 28
Waiting on NPRR267 | [6 empty] | 1 | [7 empty] | 1 | [37 empty] | 3 | bar: 1 42
Waiting on NPRR146 gray box | [8 empty] | 1 |  |  |  | 1 | [39 empty] | 2
Waiting on NOGR034 | [17 empty] | 1 | [34 empty] | 1
Waiting on NPRR219 | [29 empty] | 1 | [22 empty] | 1
Waiting on Telemetry Standards | [17 empty] | 1 | [34 empty] | 1
Waiting on Future documentation | [9 empty] | 1 | [42 empty] | 3 | bar: 1 49; 1 52
Waiting on Future NPRR | 1 | 1 |  |  |  | 1 | [7 empty] | 1 | [38 empty] | 6 | bar: 1 29 to 1 30
Needs SCR Submitted | [11 empty] | 1 | [40 empty] | 12 | 31 | bar: 1 26; 1 32 to 1 35; 1 38; 1 40 to 1 42; 1 50 to 1 51
CURRENT STATUS | 1 | 2 | 3 | 5 | 8 | 10 | 12 | 13 | 14 | 15 | 16 | 17 | 44 | 46 | 47 | 18 | 19 | 45 | 4 | 6 | 7 | 9 | 11 | 20 | 21 | 22 | 23 | 24 | 25 | 43 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 48 | 49 | 50 | 51 | 52
Monitor and Evaluate |  |  |  | 1 | [11 empty] | 1 | 1 |  | 1 | 1 | 1 | [31 empty] | 8 | bar: 35; 37
Resolved |  |  | 1 |  |  | 1 | [13 empty] | 1 |  | 1 |  | 1 | [28 empty] | 6 | bar: 39
Deferred | 1 | 1 |  |  | 1 |  |  | 1 | 1 | 1 | 1 | 1 | [10 empty] | 1 |  | 1 | 1 | 1 | 1 | 1 | [23 empty] | 14
Waiting on NPRR or SCR | 1 | 1 |  |  | 1 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 1 |  |  |  |  | 1 |  | 1 | 1 | 1 | 1 | 1 | [23 empty] | 30 | 58 | bar: 26; 29 to 30; 32 to 34; 38; 40 to 42; 50 to 51
REQUESTED DELIVERY | 1 | 2 | 3 | 5 | 8 | 10 | 12 | 13 | 14 | 15 | 16 | 17 | 44 | 46 | 47 | 18 | 19 | 45 | 4 | 6 | 7 | 9 | 11 | 20 | 21 | 22 | 23 | 24 | 25 | 43 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 48 | 49 | 50 | 51 | 52
Needed early 2011 | 1 | 1 | [5 empty] | 1 |  |  |  | 1 | [16 empty] | 1 | [23 empty] | 16 | bar: 26; 28 to 30; 35; 38; 40; 42 to 48; 50 to 51
Needed mid 2011 |  |  |  |  | 1 |  |  |  | 1 |  | 1 |  | 1 | [39 empty] | 5 | bar: 26
Needed late 2011 | [52 empty] | 2 | bar: 26; 36
Needed in 2012 | [24 empty] | 1 | 1 | 1 | 1 | [24 empty] | 4 | 27
| 1 | 2 | 3 | 5 | 8 | 10 | 12 | 13 | 14 | 15 | 16 | 17 | 44 | 46 | 47 | 18 | 19 | 45 | 4 | 6 | 7 | 9 | 11 | 20 | 21 | 22 | 23 | 24 | 25 | 43 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 48 | 49 | 50 | 51 | 52