SSWG REPORT TO ROS

October 2010

- SSWG has met twice since the September ROS meeting, Sept 21-23, and Sept 29.

- Version 9 of the Topology Processor has been delivered to ERCOT.  It is being used, but there are still outstanding issues that need to be addressed before next spring.

- ERCOT Planning has taken the lead on creating the NPRR related to data needs for wind generator RARF submittals.

- SSWG is currently testing the new nodal case building process by creating a 2010 Summer Peak case.  An initial MOD case was created and TSPs are now uploading Planning Model Change Requests (PMCRs) to modify the case.  We will complete this test within the next month.  Afterward, we will test the creation of a 2012 summer peak case.

- SSWG members want to report to ROS ongoing concern with the process of RARF submittals feeding into planning cases in the new nodal case building process.  Recent Topology Processor case downloads contain bus number problems created by RARF submittals with incorrect or missing bus numbers.  TSPs are not being contacted to provide correct bus numbers before the NOMCRs are submitted by the ERCOT Network Modeling group.  TSPs then have to correct these problems afterward.

- SSWG reviewed the TSP Combined Issues list.  Currently, SSWG members are preparing a System Change Request to address many of these issues.  As soon as SSWG has reviewed the SCR, SSWG will formally submit into the review process which is expected to happen before the November ROS meeting.  As directed at a previous ROS meeting, it is understood that this SCR does not need formal ROS approval before being submitted.

- SSWG is going to alter the 2014 minimum case slightly in the Data Set B cases expected to be posted in the next three weeks.  The dispatch will be applied that will create a high power transfer from wind resources in West Texas to the rest of ERCOT.

- Data Set B is currently being created.  The cases are expected to be posted in early November.  A short delay from the original schedule is needed to ensure that the cases 2014 and beyond contain the correct CREZ reactive resources.

- Calendar with all SSWG activities included (Nodal Planning Model related):

  - Sept – Oct	TPIT update work – 11 win & 11 DSA only

  - Oct	Compare TP output to SSWG 2010 summer peak case

  - Oct 8	Pass 1: TSPs to import PMCRs to fix issues

  - Oct 8	DSB Pass 8 due to TSPs

  - Oct 15	DSB Pass 8 changes due to ERCOT

  - Oct 22	DSB Pass 9 due to TSPs

  - Oct 29	DSB Pass 9 changes due to ERCOT

  - Oct 29	Download TP case with energization date of 7/1/2012

  - Nov 5	DSB cases posted

  - Nov 5	Pass 0: TSPs to import profiles and PMCRs

  - Nov	Create 2012 summer peak case using TP and MOD

  - Dec – Feb 	Review, update, and modify TP/MOD process for case creation

  - Dec 1	TPIT spreadsheet updates due to ERCOT

  - Dec 1	Nodal Go-Live

  - Dec – Jan 2011	TPIT update work

  - Mar 1 2011 	ALDR due to ERCOT

  - Mar-April 2011	Assuming Nov test meets SSWG approval, begin work to create 12DSA using Nodal method

Wes Woitt

2010 SSWG Chair