## Slide 1: PMO Update to TAC
Troy Anderson
ERCOT Program Management Office
October 7, 2010
Notes: <number>

## Slide 2: PMO Update – Agenda
  2011 Project Prioritization 3-7
    Request for TAC endorsement
  Nodal Parking Deck 8-15
    As of 9/27/2010
  Nodal Stabilization 16-17
Notes: <number>

## Slide 3: 2011 Project Prioritization Schedule – Revised
April 2010 - CARTs develop draft 2011 project lists
May 2010
  Initial review at market subcommittees
    MO - COPS (May 11)
    RO - RMS (May 12)
    SO - ROS, WMS (May 13 / May 19)
June 2010
  Approval/endorsement by market subcommittees
    MO - COPS (June 8)
    RO - RMS (June 9)
July / August 2010 – status updates
September 2010
  Update remaining market subcommittees
    SO - ROS, WMS (September 16 / September 22)
    CO, IO, MO, RO, SO – PRS (September 23)
October 2010
  Consideration by TAC (October 7)
  Available for F&A and Board review (October 19)
Notes: <number>

## Slide 4: 2011 Project Prioritization – Primary Components
There are 2 components to ERCOT’s 2011 project funding request:
1 – Data Center Hardware Purchase and Installation $33.715M*
    Reduced from $37M due to Board approval of
      accelerated purchase of servers
2 – Other critical and high priority projects $ 8.185M
Total $41.900M
* ERCOT is reviewing options to reduce the funding requirement for Data Center Hardware (potentially as much as $20M)
  Authorize carryover of excess 2010 ERCOT revenue to 2011
  Accelerate purchases to Q4 2010 and fund with excess 2010 ERCOT revenue
Notes: <number>

## Slide 5: 2011 Project Priority List / Funding Summary
2011 Project Budgets and Project Counts by Program Area
Program Area | Budget Request | Projects Started in 2008/2009 | New 2010 Projects
CO | $ 370,000 | 1 | 1
IO | $ 680,000 | 0 | 2
MO | $ 3,360,000 | 3 | 0
RO | $ 2,775,000 | 1 | 2
SO | $ 0 | 0 | 0
Minor Cap | $ 1,000,000 | 0 | 1
Subtotal | $ 8,185,000 | 5 | 6
Data Center Refresh (IO) | $ 33,715,000 | 1 | 0
Grand Total | $ 41,900,000 | 6 | 6
The SO project budget is replaced by Nodal Release Planning in 2011
Nodal Release Planning is being budgeted as part of Nodal Stabilization
*
*

## Slide 6: 2011 Project Priority List / Funding Summary
2011 Project Prioritization Notes by Program Area
  Nodal Release Planning ($ 0)
    Planning funds for Parking Deck and other Nodal enhancements
    Component of Nodal Stabilization
  Data Center Refresh (IO) ($33,715,000)
    Continuing effort to purchase and install hardware in new data centers
    Effort underway to reduce 2011 funding need
  CO ($ 370,000)
    1 carryover project and 1 security project
  IO ($ 680,000)
    1 infrastructure project and 1 security project
  MO ($ 3,360,000)
    Continuation of Information Lifecycle Management project
    2 internal software enhancement projects that recently initiated
  RO ($ 2,775,000)
    2 PUCT/market projects and Data Research & Reporting project
  Minor Cap ($ 1,000,000)

## Slide 7: 2011 Project Prioritization – Motion
Suggested Motion
Motion to approve/endorse ERCOT’s proposal to fund 2011 projects in the amount of $41.9M.
This includes $1M-$2M to support PUCT and Market requests.
The requested amount for the Data Center Hardware project may be revised based on a change in funding approach. Other ERCOT-proposed projects are also subject to change as the 2011 budget process nears completion.
Notes: <number>

## Slide 8: Nodal Parking Deck – Posting on Nodal.ERCOT.com
Parking Deck – Posted at the following URL:
http://nodal.ercot.com/docs/po/index.html
Updated Multiple Times per Month

## Slide 9: Nodal Parking Deck – Prioritization Guidelines
Priority | Definition
Critical | Required by Statute, PUCT Order, NERC compliance or critical reliability of: Grid Operations IT Infrastructure Commercial Settlement
High | High value for a majority of market segments or ERCOT
High / Medium | High value to one or two segments, or Medium value for a majority of market segments or ERCOT
Medium | Medium value for only one segment

## Slide 10: Nodal Parking Deck – Approved page 1 of 2
Source | Title | Priority | Approval Date
NPRR208 | Registration and Settlement of Distributed Generation (DG) Less Than One MW | Critical | BoD Approved 7/20/2010
SCR756 | Enhancements to the MarkeTrak Application | Critical | BoD Approved 7/20/2010
NPRR131 | Ancillary Service Trades with ERCOT | High | BoD Approved 1/19/2010
NPRR146 | ICCP Telemetry Information Submittals | High | BoD Approved 6/15/2010
NPRR181 | FIP Definition Revision | High | BoD Approved 1/19/2010
NPRR207 | Unit Deselection | High | BoD Approved 7/20/2010
NPRR210 | Wind Forecasting Change to P50, Synch PRR841 | High | BoD Approved 6/15/2010
NPRR222 | Half-Hour Start Unit RUC Clawback | High | BoD Approved 7/20/2010
NPRR251 | Sync of PRR845, Definition for IDR Meters and Optional Removal of IDR Meters at a Premise Where an Advanced Meter Can be Provisioned | High | BoD Approved 9/21/2010
SCR759 | acLineSegment Name Length Increase in Information Model Manager | High | BoD Approved 9/21/2010
Total Approved = 16


On Parking Deck due to resource impact only. Separately funded on 2011 PPL.

## Slide 11: Nodal Parking Deck – Approved page 2 of 2
Source | Title | Priority | Approval Date
NPRR240 | Proxy Energy Offer Curve | High / Medium | BoD Approved 9/21/2010
NPRR153 | Generation Resource Fixed Quantity Block Offer | Medium | BoD Approved 1/19/2010
NPRR164 | Resubmitting Ancillary Service offers in SASM | Medium | BoD Approved 1/19/2010
NPRR241 | Aggregate Incremental Liability (AIL) Calculation and Credit Reports Publish Corrections | Medium | BoD Approved 9/21/2010
NOGRR034 | Rescind Telemetry Performance Calculation Exclusions | Medium | BoD Approved 9/21/2010
SCR755 | ERCOT.com Website Enhancements | Medium | BoD Approved 2/16/2010

## Slide 12: Nodal Parking Deck – Pending
Source | Title | Suggested Priority | Current Status
NPRR244 | Clarification of Other Binding Documents | High / Medium | Pending at PRS
NPRR256 | Sync Nodal Protocols with PRR787, Add Non-Compliance Language to QSE Performance Standards | TBD | Pending at PRS
NPRR257 | Synchronization with Nodal Operating Guide Section 9, Monitoring Programs | TBD | Pending at PRS
NPRR258 | Sync with PRR824 and PRR833 and Additional Clarifications | TBD | Pending at PRS
NPRR260 | Providing Access to MIS Secure Area to MIS Registered Users | TBD | Tabled at PRS
NPRR272 | Definition and Participation of Quick Start Generation Resources | TBD | Pending at PRS
NOGRR050 | Resolution of Reporting Issues Related to NPRR219 | TBD | Pending at PRS ROS approved 8/12/2010
Total Pending = 7

## Slide 13: Nodal Parking Deck – Additional Items for Consideration
Title | Current Status / Description
Deferred NOGRR025 Reports | Draft NPRR in progress to gray-box reports planned for delivery after Nodal go-live
NMMS API | Functionality to be considered for post-go-live development
CRR API | Functionality to be considered for post-go-live development
MMS Multiple Network Models | Functionality to be considered for post-go-live development
Add PSS Status to RARF | Automation of manual process as a result of NPRR156
Automated Default Uplift Invoice | Automation of manual process as a result of NPRR221
EILS Enhancements | Automation of manual process
Load Participation in SCED | Functionality to be considered for post-go-live development
EMS Upgrade | Upgrade EMS system from v2.3 to v2.5/v2.6
Deferred Defects | Defects not addressed prior to go-live or during Nodal stabilization period Approximately 700 deferred defects as of July 2010 Review underway to confirm issues and confirm acceptable workarounds
Total “Other” = 17

## Slide 14: Nodal Parking Deck – Additional Items for Consideration
Title | Current Status / Description
Large Wind Power Production Ramp Forecasting Phase 2 | Phase 2 of the project that built a display for ERCOT operators to indicate periods of time within the next 6 hours during which there is a high risk for a large wind power production ramp to occur
TML Transition to MIS | Upon go live, most applications that are currently available through TML will migrate to MIS and will only be accessible to MPs through the MIS portal. RMS has requested that Zonal Reports, Find ESI ID, Find Transactions, and Transaction submission be accessed through TML until MIS has had sufficient time to stabilize.
Decommission of Zonal Wholesale | After go-live of the redesigned ERCOT wholesale market, certain ERCOT systems and components that were only applicable to zonal wholesale operations will become disposable and need to be decommissioned.
Nodal Cutover Cleanup | Remove pre-go-live data from Nodal systems
Move Price Validation Tool (PVT) to a Server Application | Functionality to be considered for post-go-live development
Update Credit PFE Model (Potential Future Exposure) | Enhance PFE model to include the following risk factors: • Price volatility analysis for the Day Ahead Market, • Bid and offer volume analysis in the Day Ahead Market, and • Value of Congestion Revenue Rights
Automate Identification of PUNs for Reporting | NPRR202 required that Private Use Networks (PUNs) be excluded from State Estimator postings of transmission flows and voltages. This requirement is being met by adding a static table to the reporting infrastructure to store the list of known PUNs. This Parking Deck item would create a method to dynamically derive the population of PUNs for this reporting.

## Slide 15: 2011 Project Prioritization – Parking Deck Prioritization
High Level Steps to Assess Parking Deck Items
In the first half of 2011, Parking Deck items will be assessed for impact and evaluated for implementation timing
  Some items will be considered for implementation in the Stabilization period
  Others will be targeted for the 1st major release (or future releases)
  The market will be included in these prioritization discussions
Release planning is targeted to begin in July 2011
  Specific items in the release must be identified at this point
1st major release is planned to go live in 2012
During the Execution phase of the 1st release, a separate effort to plan the 2nd release will begin
The details of this process are still under development

## Slide 16: 2011 Project Prioritization – Stabilization
Nodal System Stabilization is the primary focus in 2011
  Stabilization is the period after Nodal go-live where additional resources are allocated to address urgent issues and increased levels of business activity
  Stabilization funding has been re-evaluated as a component of the 2011 ERCOT budget submission
    Work components to be included in Stabilization
    Duration of Stabilization (6-12 months)
    See next slide
  Release planning funding has also been re-evaluated
    Now a component of Stabilization
    This was originally planned for consideration as an item on the PPL
  The above items will be a topic of discussion at the October and November Board meetings

## Slide 17: 2011 Project Prioritization – Nodal System Support
Major work categories being planned to support the Nodal systems
1/1/2011
7/1/2011
1/1/2012
Stabilization Support
Components:
Supplemental staff
Emergency fixes/enhancements
High priority deferred defects
Decommissioning efforts
Release Planning
Cost estimate in progress
Steady State Nodal Systems Support
Ongoing O&M Cost
2012 Release Execution
This diagram is not drawn to scale
Notes: <number>

## Slide 18: PMO Update
  Questions?
Notes: <number>