ERCOT Process for Evaluating Transmission Projects Related to Asynchronous Ties

Applicability

This process shall apply to the evaluation of all ERCOT-system transmission projects associated with asynchronous ties between ERCOT and other transmission networks.  This process will not apply to emergency load transfers between ERCOT and other networks that are not simultaneously connected to both networks, such as block load transfers.  The process may be modified as deemed necessary by ERCOT to meet the unique circumstances associated with each specific proposed tie, while maintaining the non-discriminatory nature of the process.

Limitations

This process is intended to cover the transmission system engineering studies that would be necessary for evaluating an asynchronous tie between ERCOT and another transmission network.  It does not address the process for obtaining regulatory approval (from FERC, PUCT, etc.) that may be necessary for such projects.

Notification

The entity, “Proposer,” that would construct and/ or own the interconnection facilities (that is, facilities to interconnect the ERCOT grid to a system outside the ERCOT grid) for a proposed new asynchronous tie or expansion of an existing tie shall submit notification to ERCOT (via the rpg@ercot.com mailbox) describing the proposed facilities.  Within five (5) business days of receiving the notification and resolving any questions ERCOT will notify the Regional Planning Group (RPG) about the request along with any relevant information. ERCOT will then designate a TSP to lead the reliability study and contact that TSP to schedule a reliability study scope meeting.  ERCOT will select the lead TSP based upon its preliminary analysis with respect to the most likely point of interconnection, but may defer to alternative arrangements agreed upon by the TSPs when multiple TSPs are involved.  The lead TSP may be the same as the Proposer.

Concurrently, ERCOT will send notification of the project to all other TSP(s) via the confidential Transmission Owner Generation Interconnection email list.  It is the responsibility of each TSP to determine if the proposed project would have a material impact on its transmission facilities and to what extent they should participate in the reliability study.  Each TSP desiring to participate in the reliability study should notify the lead TSP.  The lead TSP will have the responsibility to involve all other TSP(s) that have expressed an interest in the reliability study as appropriate for their expressed level of involvement to the extent that such involvement is reasonable.

Reliability Study

A reliability study will be performed for all proposed new asynchronous ties or the expansion of existing ties based on the ERCOT Planning Criteria, NERC Reliability Standards and other ERCOT requirements.  The Proposer will fully fund the reliability study in accordance with the tariffs of the TSP(s) performing the study.  The reliability study shall consist of the following elements:

- Steady state analysis

- Short circuit analysis

- Stability analysis including (as necessary):

  - Angular stability analysis

  - Voltage stability analysis

  - Small signal stability analysis

  - Frequency stability analysis (testing of loss of the tie, consistent with Table 1 of the NERC TPL standards, during both maximum import and maximum export conditions)

  - Subsynchronous resonance/ Subsynchronous interaction analysis testing the impact on nearby generation that may be affected

These analyses may be performed in stages as the project develops.

The lead TSP shall present the study scope to ERCOT and the TSPs.  ERCOT and the TSPs will have ten (10) days to provide comments.

Following the completion of the reliability study, the lead TSP will present the results to ERCOT and other TSPs via the confidential Transmission Owner Generation Interconnection email list.  ERCOT and TSPs will have thirty (30) days to provide comments.  The proposed transmission project set identified during the reliability studies shall undergo the RPG review process according to the appropriate Tier classification of the project after the interconnection agreement has been signed.

The Proposer shall provide data sufficient to accurately model the tie for the steady state, short circuit and stability studies.

RPG Review

Transmission projects that are proposed for export or import of power for an asynchronous tie, whether for a proposed tie or to increase the capability of an existing tie, shall go through the RPG review process.  Tier 1 and 2 projects shall include an economic study to be used by ERCOT in determining the project set to include in an independent report.  The scope of the economic study may include an assessment of the overall economic impact of the asynchronous tie to the ERCOT market; however, this assessment will not be considered by ERCOT unless needed to evaluate the economics of any incremental transmission system improvements that are warranted by the addition of the tie and that would be included in transmission cost of service paid for by ERCOT loads, or unless ERCOT is so directed by the PUCT.

ERCOT shall develop the economic study scope, in consultation with the Proposer, and will forward the study scope to the RPG, which will have 21 days to provide comments.  If all of the comments cannot be resolved, ERCOT will determine the approach that should be included in the economic study to address the comments.  The economic study should include modeling of system limitations and constraints on the non-ERCOT transmission system.

At the end of the RPG review period ERCOT will contract with an independent consultant to perform the economic study as described in the economic study scope, and the Proposer will fund this study  ERCOT will provide periodic study updates to the RPG and the RPG may provide comments throughout the study process.  To the extent practicable, ERCOT and the consultant will post models for use by the RPG members for their own analysis.

Ancillary Services Study

If deemed necessary by ERCOT, ERCOT will contract with an independent consultant to perform a study to assess the tie’s impact on ancillary services in the ERCOT market including the economic impact due to potentially increased or decreased ancillary services.  The Proposer will fund this study.

ERCOT Review

ERCOT will not recommend or endorse commercial asynchronous ties or associated AC transmission system improvements.  However, ERCOT will provide an independent report that:

- assesses how well the study addressed the comments of ERCOT and the RPG,

- provides independent comments on the economic study,

- provides a contingent assessment of the incremental transmission projects on the ERCOT system that are indicated by the economic study,

- provide an assessment on the ancillary service impact to the ERCOT market, and

- provides an opinion on the reliability benefits (if any) of the asynchronous tie even if the tie is primarily intended to accommodate commercial transactions.  Benefits may include, but are not limited to, generation adequacy, storm hardening, and emergency support.

Notice to Proceed

The project will be added to the base case models once the following conditions have been met:

- An interconnection agreement with notice to proceed has been executed between the interconnecting ERCOT TSP(s) and the Proposer for the asynchronous tie facilities,

- an interconnection agreement with notice to proceed has been executed between the interconnecting entities on the other transmission network and the Proposer, and,

- if necessary, FERC has issued an order stating that the tie be constructed in accordance with sections 210 and 211 of the Federal Power Act.

The Proposer shall inform ERCOT and the interconnecting TSP(s) when each of these conditions has been met.  At this time ERCOT will post all of the studies on the ERCOT website.