|  |  |  |  | System Planning Division |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report to Reliability and Operations Subcommittee for September 2010 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
| Item |  |  |  |  |  |  |  |  |
| 1. | - ERCOT is currently tracking 188 active generation interconnection requests totaling over 65,000 MW. This includes almost 39,000 MW of wind generation. |  |  |  |  |  |  |  |
| 2. | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $80.8 Million - Transmission Projects endorsed in 2010 total $230.4 Million - All projects (in engineering, routing, licensing and construction) total approximately $9.4 Billion - Transmission Projects energized in 2010 total about $791.7 million |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	New Generation Registering for Commercial Operations	1

1.2	Publicly Disclosed Generation Interconnection Projects	4

1.3	Generation Projects Undergoing Full Interconnection Studies (not otherwise public)	6

1.4	Wind Generation	7

Wind Capacity Installed by Year	7

2.	Regional Planning Group Project Reviews	9

3.	Congestion Costs	10

4.	Wind Generation as a Percent of Load	16

5.	Other Notable Activities	17

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## New Generation Registering for Commercial Operations

## Texas Solar (Blue Wing 2)  7 MW  of Photovoltaic Solar in Bexar County

The total installed wind capacity remains at 9,317 MW, of which 7,958 MW (85%) is located within the Western Congestion Management Zone.

New Generation Interconnection Agreements  - none

Summary of Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |  |  |  |  |
| --- | --- | --- | --- | --- |
| Currently tracking 188 active generation interconnection or change requests |  |  |  |  |
| As of September 30, 2010 | North | South | West | Total |
| Security Screening Study | 1 | 1 | 8 | 10 |
| SSS Completed | 2 | 4 | 9 | 15 |
| Full Interconnect Study | 19 | 13 | 93 | 125 |
| FIS Completed | 3 | 15 | 3 | 21 |
| Interconnect Agreement Completed | 8 | 5 | 4 | 17 |
| Capacity under Interconnection Agreements | 5,192 | 2,575 | 506 | 8,273 |
| Capacity for Grid, MW | 19,325 | 13,347 | 32,454 | 65,126 |
| Wind Capacity, MW | 3,756 | 4,641 | 30,310 | 38,707 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Projects w/ Interconnect Agreement/Public Letter (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- |
| Gas-CC |  |  | 3,972 | 12,043 |
| Gas-CT |  |  |  | 247 |
| Total Gas | 600 | 7,718 | 3,972 | 12,290 |
| Nuclear |  |  | 5,900 | 5,900 |
| Coal |  | 1,740 | 3,213 | 4,953 |
| Wind | 3,628 | 29,127 | 5,953 | 38,708 |
| Solar | 340 | 699 |  | 1,039 |
| Biomass |  | 50 | 145 | 195 |
| Other |  | 740 | 1,300 | 2,040 |
| Grand Total | 4,568 | 40,074 | 20,483 | 65,125 |

## Publicly Disclosed Generation Interconnection Projects

The table below summarizes the publicly disclosed generation projects for the ERCOT region.

(Status: IA=Interconnect Agreement, PL=Public Letter, XX= cancelled)

| Generation Interconnections as of September 30, 2010 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR | SiteName | Status | County | Region | COD | Fuel Type |  | MW For Grid | Change from Last Report |
| 09INR0082 | Cedro Hill Wind | IA | Webb | South | Oct-10 |  | Wind | 150 | Date |
| 12INR0003 | Throckmorton Wind Farm | PL | Throckmorton | West | Dec-10 |  | Wind | 400 |  |
| 08INR0033 | Lufkin | IA | Angelina | North | Dec-10 |  | Biomass | 45 |  |
| 05INR0015b | Gulf Wind 2 | PL | Kenedy | South | Jan-11 |  | Wind | 400 |  |
| 05INR0015c | Gulf Wind 3 | PL | Kenedy | South | Jan-11 |  | Wind | 400 |  |
| 08INR0065 | Buffalo Gap 4 and 5 | PL | Nolan | West | Mar-11 |  | Wind | 465 |  |
| 09INR0029 | CFB Power Plant Units 11&12 | IA | Calhoun | South | Mar-11 |  | Coal | 263 |  |
| 10INR0010 | Jack County 2 | IA | Jack | North | Jun-11 |  | Gas-CC | 620 |  |
| 08INR0011 | Senate Wind Project | IA | Jack | North | Nov-11 |  | Wind | 150 |  |
| 08INR0038 | M Bar Wind | PL | Andrews | West | Dec-11 |  | Wind | 194 |  |
| 09INR0034 | Gatesville Wind Farm | PL | Coryell | North | Dec-11 |  | Wind | 200 |  |
| 08INR0025 | Pistol Hill Energy Center | PL | Ector | West | Dec-11 |  | Wind | 300 |  |
| 06INR0012b | Sherbino Mesa Wind Farm 2 | IA | Pecos | West | Jan-12 |  | Wind | 150 | Date |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Feb-12 |  | Coal | 925 |  |
| 11INR0084 | 2W Whatley Phase 1 | PL | Ector | West | Mar-12 |  | Wind | 45 | New |
| 09INR0007 | Nacogdoches Project | IA | Nacogdoches | North | Apr-12 |  | Biomass | 100 |  |
| 07INR0004 | Pampa Energy Center | PL | Gray | West | May-12 |  | Coal | 165 |  |
| 09INR0024 | B&B Panhandle Wind | PL | Carson | West | Jun-12 |  | Wind | 1,001 |  |
| 09INR0037 | Scurry County Wind III | PL | Scurry | West | Jun-12 |  | Wind | 350 |  |
| 12INR0004 | Fort Concho Wind Farm | PL | Tom Green | West | Jul-12 |  | Wind | 400 |  |
| 12INR0043 | 2W Whatley Phase 2 | PL | Ector | West | Aug-12 |  | Wind | 290 | New |
| 09INR0036 | McAdoo Energy Center II | PL | Dickens | West | Dec-12 |  | Wind | 500 |  |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Dec-12 |  | Wind | 120 |  |
| 06INR0022c | Penascal Wind Farm 3 | IA | Kenedy | South | Dec-12 |  | Wind | 202 |  |
| 06INR0006 | Cobisa-Greenville | IA | Hunt | North | May-13 |  | Gas-CC | 1,792 |  |
| 10INR0020a | Panda Temple Power | IA | Bell | North | May-13 |  | Gas-CC | 780 |  |
| 04INR0011b | Cedar Elm | IA | Shackelford | West | Jun-14 |  | Wind | 136 |  |
| 04INR0011c | Cottonwood Wind | IA | Shackelford | West | Jun-14 |  | Wind | 100 |  |
| 14INR0005 | White Stallion Energy Center | PL | Matagorda | South | Jul-14 |  | Coal | 1,200 |  |
| 12INR0016 | Las Brisas Energy Center | IA | Nueces | South | Sep-14 |  | Other | 1,300 |  |
| 14INR0002 | Coleto Creek Unit 2 | IA | Goliad | South | Nov-14 |  | Coal | 660 |  |
| 10INR0020b | Panda Temple Power | IA | Bell | North | Dec-14 |  | Gas-CC | 780 |  |
| 15INR0008 | STP 3 and 4 | PL | Matagorda | South | Jun-16 |  | Nuclear | 2,700 |  |
| 15INR0002 | Comanche Peak 3 and 4 | PL | Somervel | North | Dec-18 |  | Nuclear | 3,200 |  |
|  |  |  |  |  |  |  | TOTAL | 20,483 |  |

County Location of Installed Generation and Interconnection Requests (all fuels)

## Generation Projects Undergoing Full Interconnection Studies (not otherwise public)

| INR | County | Capacity | COD | Fuel |  | INR | County | Capacity | COD | Fuel |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 09INR0054 | Stonewall | 149 | TBD | Wind |  | 09INR0061 | Kent | 258 | TBD | Wind |
| 10INR0048 | Hardeman | 1,000 | TBD | Wind |  | 10INR0016 | Childress | 150 | TBD | Wind |
| 10INR0054 | Palo Pinto | 36 | TBD | Wind |  | 10INR0079 | Nolan | 60 | TBD | Wind |
| 10INR0029 | Hood | 810 | TBD | Gas |  | 10INR0013 | Upton | 400 | TBD | Wind |
| 10INR0052a | Knox | 21 | TBD | Wind |  | 09INR0074 | Motley | 70 | TBD | Wind |
| 10INR0041 | Floyd | 135 | TBD | Wind |  | 11INR0029 | Throckmorton | 200 | TBD | Wind |
| 07INR0013 | Coke | 200 | Dec-10 | Wind |  | 07INR0015 | Foard | 180 | Dec-10 | Wind |
| 07INR0035 | Tom Green | 270 | Dec-10 | Wind |  | 08INR0062 | Archer | 249 | Dec-10 | Wind |
| 10INR0008 | Pecos | 500 | Dec-10 | Wind |  | 10INR0019 | Deaf Smith | 609 | Dec-10 | Wind |
| 10INR0032 | Navarro | 775 | Dec-10 | Gas |  | 10INR0033 | Armstrong | 399 | Dec-10 | Wind |
| 10INR0042 | Mason | 170 | Dec-10 | Wind |  | 10INR0051 | Brazoria | 200 | Dec-10 | Wind |
| 10INR0056 | Borden | 249 | Dec-10 | Wind |  | 10INR0060 | Willacy | 401 | Dec-10 | Wind |
| 10INR0077 | Callahan | 101 | Dec-10 | Wind |  | 10INR0080 | Presidio | 144 | Dec-10 | Solar |
| 10INR0082 | Travis | 30 | Dec-10 | Solar |  | 11INR0076 | Archer | 94 | Jan-11 | Wind |
| 11INR0050 | Crosby | 149 | Mar-11 | Wind |  | 11INR0081 | Live Oak | 72 | Mar-11 | Wind |
| 11INR0082A | Val Verde | 50 | Mar-11 | Wind |  | 11INR0083A | Crockett | 50 | Mar-11 | Wind |
| 11INR0088 | Brazos | 45 | Mar-11 | Gas |  | 11INR0071 | Harris | 7 | Apr-11 | Gas |
| 11INR0075 | Fort Bend | 15 | Apr-11 | Coal |  | 11INR0086 | Travis | 60 | Apr-11 | Solar |
| 10INR0009 | Castro | 300 | May-11 | Wind |  | 11INR0037 | Smith | 50 | May-11 | Biomass |
| 11INR0058 | Pecos | 135 | May-11 | Solar |  | 11INR0060 | Tom Green | 90 | May-11 | Solar |
| 11INR0061 | Presidio | 90 | May-11 | Solar |  | 11INR0062 | Nueces | 149 | May-11 | Wind |
| 11INR0033a | Cameron | 200 | May-11 | Wind |  | 11INR0033b | Cameron | 200 | May-11 | Wind |
| 08INR0020 | Eastland | 200 | Jun-11 | Wind |  | 09INR0050 | Fannin | 1,200 | Jun-11 | Gas |
| 10INR0023 | Haskell | 386 | Jun-11 | Wind |  | 10INR0057 | Taylor | 200 | Jun-11 | Wind |
| 10INR0089 | Harris | 40 | Jun-11 | Other |  | 11INR0019 | Upton | 200 | Jun-11 | Wind |
| 11INR0054 | San Patricio | 161 | Jun-11 | Wind |  | 11INR0057 | Cameron | 165 | Jun-11 | Wind |
| 11INR0065 | Nueces | 240 | Jun-11 | Wind |  | 11INR0091 | Webb | 92 | Jun-11 | Wind |
| 11INR0006 | Lamar | 579 | Jul-11 | Gas |  | 11INR0040 | Freestone | 640 | Aug-11 | Gas |
| 11INR0039 | Starr | 201 | Sep-11 | Wind |  | 11INR0047 | Deaf Smith | 600 | Sep-11 | Wind |
| 11INR0079a | Clay | 200 | Sep-11 | Wind |  | 07INR0014a | Wilbarger | 140 | Oct-11 | Wind |
| 07INR0014b | Wilbarger | 70 | Oct-11 | Wind |  | 10INR0062a | Pecos | 80 | Oct-11 | Wind |
| 10INR0081b | Clay | 19 | Oct-11 | Wind |  | 10INR0021 | Grayson | 646 | Nov-11 | Gas |
| 11INR0090 | Howard | 60 | Nov-11 | Solar |  | 08INR0049 | Clay | 50 | Dec-11 | Wind |
| 11INR0005 | Upton | 500 | Dec-11 | Wind |  | 11INR0013 | Mills | 150 | Dec-11 | Wind |
| 11INR0025 | Crockett | 400 | Dec-11 | Wind |  | 11INR0043 | Coke | 300 | Dec-11 | Wind |
| 11INR0067 | Cameron | 78 | Dec-11 | Wind |  | 11INR0070 | Reeves | 50 | Dec-11 | Solar |
| 12INR0034 | Borden | 342 | Dec-11 | Wind |  | 09INR0048 | Jack | 150 | Dec-11 | Wind |
| 09INR0075 | Kinney | 248 | Dec-11 | Wind |  | 10INR0085 | Ector | 40 | Jan-12 | Solar |
| 12INR0021 | Edwards | 165 | Jan-12 | Wind |  | 12INR0033 | Motley | 150 | Jan-12 | Wind |
| 10INR0018 | Madison | 550 | Mar-12 | Gas |  | 12INR0042 | Deaf Smith | 400 | Mar-12 | Wind |
| 09INR0031 | Ector | 275 | May-12 | Gas |  | 10INR0081a | Clay | 30 | May-12 | Wind |
| 11INR0049 | Wharton | 275 | May-12 | gas |  | 12INR0007 | Lamar | 296 | May-12 | Gas |
| 08INR0031 | Childress | 100 | Jun-12 | Wind |  | 10INR0022 | Harris | 1,380 | Jun-12 | Gas |
| 12INR0006 | Limestone | 875 | Jun-12 | Coal |  | 08INR0041 | Coke | 200 | Oct-12 | Wind |
| 12INR0026 | Randall | 400 | Oct-12 | Wind |  | 08INR0044 | Concho | 200 | Nov-12 | Wind |
| 12INR0035 | Nueces | 249 | Nov-12 | Wind |  | 08INR0042 | Coke | 200 | Dec-12 | Wind |
| 08INR0054 | Comanche | 401 | Dec-12 | Wind |  | 09INR0025 | Concho | 180 | Dec-12 | Wind |
| 12INR0005 | Floyd | 1,100 | Dec-12 | Wind |  | 12INR0022 | Hidalgo | 200 | Dec-12 | Wind |
| 12INR0029 | Swisher | 500 | Dec-12 | Wind |  | 10INR0024 | Briscoe | 2,940 | Jan-13 | Wind |
| 12INR0027 | Gray | 200 | Jan-13 | Wind |  | 09INR0058 | Howard | 250 | Mar-13 | Wind |
| 11INR0082B | Val Verde | 150 | Mar-13 | Wind |  | 11INR0083B | Crockett | 100 | Mar-13 | Wind |
| 12INR0018 | Gray | 500 | Apr-13 | Wind |  | 10INR0062b | Pecos | 220 | May-13 | Wind |
| 13INR0020 | Glasscock | 350 | May-13 | Wind |  | 09INR0041 | Mitchell | 300 | Jun-13 | Wind |
| 09INR0051 | Borden | 249 | Jun-13 | Wind |  | 13INR0023 | Ector | 240 | Jul-13 | Gas |
| 13INR0016 | Deaf Smith | 251 | Aug-13 | Wind |  | 13INR0004 | Deaf Smith | 500 | Oct-13 | Wind |
| 13INR0005 | Carson | 600 | Oct-13 | Wind |  | 08INR0022 | Floyd | 100 | Dec-13 | Wind |
| 08INR0023 | Floyd | 100 | Dec-13 | Wind |  | 09INR0077 | Reagan | 500 | Dec-13 | Wind |
| 12INR0002a | Briscoe | 200 | Dec-13 | Wind |  | 13INR0007 | Pecos | 200 | Dec-13 | Wind |
| 13INR0017 | Childress | 200 | Dec-13 | Wind |  | 09INR0073 | Scurry | 200 | Dec-13 | Wind |
| 13INR0010 | Parmer | 1,200 | Dec-13 | Wind |  | 08INR0019a | Gray | 250 | Jan-14 | Wind |
| 08INR0019b | Gray | 250 | Jan-14 | Wind |  | 08INR0019c | Gray | 250 | Jan-14 | Wind |
| 13INR0006 | Gray | 750 | Jan-14 | Wind |  | 10INR0015 | Mitchell | 350 | May-14 | Wind |
| 14INR0003 | Nolan | 850 | Jun-14 | Coal |  | 12INR0002b | Briscoe | 200 | Dec-14 | Wind |
| 14INR0001 | Pecos | 500 | Dec-14 | Wind |  | 12INR0002c | Briscoe | 350 | Dec-15 | Wind |
| 16INR0002 | Brazoria | 700 | Jun-17 | Other |  |  |  |  |  |  |

## Wind Generation

## Wind Capacity Installed by Year

County Location of Installed Capacity and Interconnection Requests (Wind only)

# Regional Planning Group Project Reviews

- Oncor submitted a project to relieve congestion related to new wind units in the Lamesa area.  The project will upgrade the Lamesa to Bluff Creek 138 kV line, rebuild the Bluff Creek to China Grove 138 kV line, rebuild the Lamesa to Ackerly Vealmoor 69 kV line to 138/69 kV double circuit, rebuild the Lamesa 138 kV switching station, build a new 138 kV Ackerly Vealmoor station, add second circuits to all rebuilt lines and include station upgrades at China Grove and Big Spring.  The cost of this project is $ 80.8 M.  This project will be reviewed to ensure that the improvements fit into the likely CREZ transmission solution for the area.  This project is in ERCOT Independent Review.

- Pattern Energy has submitted a project to construct an HVDC tie with a capacity of up to 3000 MW between ERCOT and SERC.  This project is in study mode.  ERCOT is currently developing a process for evaluating asynchronous ties with other grids.

# Congestion Costs

Dollars shown in graphs are settlement quality.

OOMC – last 13 months in million$

OOM Down – last 13 months in million$

Local Balancing Energy Down – last 13 months in million$

OOM Up – last 13 months in million$

Local Balancing Energy Up – last 13 months in million$

Replacement Reserve – last 13 months in thousand$

Average MCPE

Binding Constraints & Capacity Shortages– August, 2010

| Contingency | Binding Element | Estimated Costs | Transmission Project | Clearance |
| --- | --- | --- | --- | --- |
| Watermill Switch - West Levee Switch 345kV | Duncanville South - Cedar Hill 138kV | $ 2,555,729 | Cedar Hill Switch second 345/138 kV autotransformer [13TPIT0062 | Outage on Cedar Hill Switch 345kVAT2 |
| Barney Davis - Holly 138kV West Side - Airline 138kV | Airline - Cabaniss 138kV | $ 1, 639,144 |  | High generation |
| Lytton Springs - Zorn & Austrop - Zorn 345kV | Zorn - Pooley 138kV | $ 671,998 | Zorn/Clear Springs-Gilleland Creek-Hutto Switch 345-kV line [08TPIT0020] | High load in the area and S-N flow |
| Big Brown - Venus 345kV | Richland Chambers - Trinidad 345kV | $ 569,438 | Trinidad - Watermill 345 kV line [07TPIT0140] | High load in North |
| Watermill - Limestone 345 kV | Jewett - Rattlesnake Road Switch 345kV | $ 465,102 | Rattlesnake Road Switch - Lake Creek 345 kV line [09TPIT0150] | High load in North, but units in North having issues. MCSES derated & HLSES tripping/running back. |
| Austrop - Sandow 345kV | Round Rock - Round Rock Northeast 138kV | $ 357,861 | Hutto Switch - Round Rock NE - Round Rock 138 kV line [08TPIT0009] | High N-S zonal transfer |
| RPRS |  | $ 340,696 |  |  |
| Lytton Springs - Zorn & Austrop - Zorn 345kV | Victoria - Thomaston - Cuero 138kV | $ 221,167 | Thomaston: Install 138 kV PST, Add 3-28.8 MVAR Cap Banks, Reterminate 138 kV Line [10TPIT0069] | Line derated per NOMCR 7339_1 |
| Martin Lake SES - Elkton & Tyler Grande | Delek POI - Tyler Northeast 138kV | $ 209,706 |  | High generation |
| Tricorner - Tyler Grande & Martin Lake SES - Elkton 345kV | Tyler Grande - Elkton 138kV | $ 184,334 | Elkton - Tyler West 138 kV line [06TPIT0047] | High load in the area |

Inter-zonal Congestion

# Wind Generation as a Percent of Load

One-hour average Settlement quality data shown.

# Other Notable Activities

- Work on the 2010 Five-Year Transmission Plan is underway.  The set of projects needed to reliably serve load in 2011 through 2015 has been identified and comments have been received.  The analysis is currently focused projects to relieve congestion for 2011 through 2015.

- Nodal Network Model Management System Topology Processor base case building modernization work continues with bi-weekly meetings calls with SSWG and weekly ERCOT topology processor output.  ERCOT and SSWG have created a planning case by adding generation, load, and voltage profiles to the Topology Processor output in Model On Demand (MOD).  This case, once completed, will be compared to the current 2010 Summer Peak case.

- ERCOT created a spreadsheet in September showing impedance and branch ratings differences that need to be reconciled between the current 2010 Fall Peak SSWG case and Topology Processor output case with a November build date.  The purpose of this comparison is to confirm that impedances and ratings in the NMMS have been crosschecked against the SSWG database.  The deadline for submitting the spreadsheet back to ERCOT and submitting NOMCRs to change the NMMS model was October 1, 2010.  ERCOT will create another spreadsheet showing remaining differences and report this metric to ROS at their next meeting.

- Studies to determine the ERCOT System Voltage Profile continue.  Market Participants should participate in these to make sure that their interests and unit capabilities are taken into consideration.

- Blackstart testing has begun.  ERCOT staff are witnessing the required tests.

- The CREZ Reactive Study, being performed by ABB and led jointly by ERCOT and the CREZ TSPs, to optimize the reactive support equipment required to implement the CREZ plan is nearly complete.  Findings from this study will be discussed at the Regional Planning Group meeting on 10/15.  A final report will be available in late October.

- Work on the Long-Term System Assessment/DOE Study has begun.  A separate subgroup of RPG has been established to focus on this study and is meeting monthly.  The current focus is on background information that will be used for developing the scenarios to be studied.

- Transient Stability Study for 2010 Summer on-peak conditions: As part of the annual reliability assessment of the network, a transient stability study study has been performed on an ERCOT 2010 case that included wind modeling.  Presentation of results is being prepared for DWG’s Oct. meeting.

- Transient Stability Study for 2013 Summer on-peak conditions: As part of the annual reliability assessment of the network, a transient stability study has been performed on an ERCOT 2013 case that included wind modeling.  Presentation of results is being prepared for DWG’s Oct. meeting.