## Project Summary
ERCOT Fiscal Year 2011 Budget
Project Summary
($ in Thousands)
[5 empty] | Timeline |  | Labor Estimate
Line | Task | 2009 Actual | 2010 Budget | 2010 Forecast | 2011 Preliminary Budget | 2012 Projected Budget | 2013 Projected Budget | 2014 Projected Budget | 2015 Projected Budget | 2016 Projected Budget
1 | Project Priority List (PPL) | 43660.5 | 46300 | 54092.131 | 41896 | 20000 | 20000 | 25000 | 25000 | 20000
2 | Nodal Stabilization | 0 | 0 | 0 | 7532 | 0 | 0 | 0 | 0 | 0
3 | Parking Deck | 0 | 0 | 0 | 3250 | 0 | 0 | 0 | 0 | 0
4 | Deferred Defects & Workarounds | 0 | 0 | 0 | 2509 | 0 | 0 | 0 | 0 | 0
5 | Total - Project Costs | 43660.5 | 46300 | 54092.131 | 55187 | 20000 | 20000 | 25000 | 25000 | 20000
6
7 | Revenue-Fund Percentage | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40%
8
9 | Revenue -Funded Project Costs | 17464.2 | 18520 | 21636.8524 | 22074.8 | 8000 | 8000 | 10000 | 10000 | 8000

## 2011 PPL
ERCOT Fiscal Year 2011 Budget
Project Priority List (PPL)
2011 Priority | 2011 Rank | Program Area | Source | Project Number | Capital Projects | 2011 Budget Range | Cumulative Budget Range | Current Status | Description
1- Critical | 1 | DC | ERCOT | Various | Data Center Buildout | $30M-$40M | $30M-$35M | Planning / Execution | Data Center Buildout Project - 8 subprojects addressing storage, servers, tape backup, telecommunication, and network gear
1- Critical | 2 | CO | ERCOT | 99911 | Minor Cap - Critical | $500k-$1M | $30M-$35M | Not Started | Critical priority Minor Cap purchases
1- Critical | 3 | RO | Market | 11002_01 | Texas SET 4.0 | $1M-$2M | $35M-$40M | Not Started | TX SET project to include reconnect / disconnect, AMS, Acquisitions, Meter Tampering
1- Critical | 4 | MO | ERCOT | 90006_02 | Information Lifecycle Mgmt – Mkt Systems, Archive, Reporting | $1M-$2M | $35M-$40M | Planning | Subproject of 90006_01 - optimizing data storage requirements for our commercial systems
1- Critical | 5 | IO | ERCOT | 11003_01 | Cyber Security Project #1 | $500k-$1M | $35M-$40M | Not Started | Enhance a specific area of ERCOT's cyber security capability
1- Critical | 6 | MO | ERCOT | 10052_01 | Settlement System Upgrade | $1M-$2M | $35M-$40M | Planning | Replace the current application code with an optimized, self-supported solution. Includes only the conversion of code -- no enhancements.
1- Critical | 7 | CO | ERCOT | 11004_01 | Cyber Security Project #2 | $250k-$500k | $35M-$40M | Not Started | Enhance a specific area of ERCOT's cyber security capability
1- Critical | 8 | IO | ERCOT | 11005_01 | IT Security Infrastructure Upgrade | $100k-$250k | $35M-$40M | Not Started | Upgrade a specific component of the IT security infrastructure
1- Critical | 9 | RO | PUCT / Market | 11006_01 | MarkeTrak Upgrade and Enhancements (PLANNING) | $100k-$250k | $40M-$45M | Not Started | Enhance MarkeTrak application for new PUCT requirements and other enhancements requested by market participants. Examples: new subtypes for Expedited Switch Rescission and Meter Tampering, improved data validation, and AMS usage parameters
2-High | 10 | RO | ERCOT | 50088_01 | Data Research and Reporting | $1M-$2M | $40M-$45M | Execution | Transition of ETS reporting from Data Archive to Enterprise Data Warehouse - Final stage of project
2-High | 11 | MO | ERCOT | 10055_01 | Data Agg Performance Improvements | $250k-$500k | $40M-$45M | Initiation | New project to address data aggregation processing performance risk Expected to start in 2010 and conclude in 2011
2-High | 12 | CO | ERCOT | 10031_01 | Enterprise Records Management Automation (ERMA) | <$50k | $40M-$45M | Execution | Provide a centralized record management repository for ERCOT with email integration.
Cutline
ERCOT Fiscal Year 2011 Budget
Project Priority List (PPL)
2011 Priority | 2011 Rank | Program Area | Source | Project Number | Capital Projects | 2011 Budget Range | Cumulative Budget Range | Current Status | Description
2-High | 13 | IO | ERCOT | New | IDM (databases only) | $500k-$1M | $40M-$45M | Not Started | Eliminate maintenance of two systems to control access to ERCOT systems.
2-High | 14 | MC | ERCOT | New | Minor Cap - High | $250k-$500k | $40M-$45M | Not Started | High priority Minor Cap purchases
2-High | 15 | CO | ERCOT | New | Cyber Security Project #3 | $250k-$500k | $40M-$45M | Not Started | Enhance a specific area of ERCOT's cyber security capability
2-High | 16 | IO | ERCOT | New | Oracle Access Management | $250k-$500k | $40M-$45M | Not Started | Replace a manual effort carried out by the DBA’s.
2-High | 17 | IO | ERCOT | New | Cyber Security Project #4 | $100k-$250k | $40M-$45M | Not Started | Enhance a specific area of ERCOT's cyber security capability
2-High | 18 | MO | Market/ ERCOT | 90015_01 | Web-enabled Registration | $100k-$250k | $40M-$45M | Not Started | Create an interface that MPs (and potential MPs) can use to electronically submit and update registration data post nodal go-live.
2-High | 19 | IO | ERCOT | New | Tripwire | $100k-$250k | $40M-$45M | Not Started | Tripwire has been deployed for approximately 3 years. To garner further benefit to our investment we would like to deploy a new utility Tripwire has available called Log Center.
2-High | 20 | IO | ERCOT | New | Storage Replication Strategies | $50k-$100k | $40M-$45M | Not Started | Resize Ptest and Itest environments
2-High | 21 | MO | ERCOT | 90017_01 | ERCOT.com CMS Replacement | $250k-$500k | $45M-$50M | Not Started | Replace the Serena Collage application and Market Information Repository (MIR)
2-High | 22 | MO | ERCOT | 10006_01 | EPS Meter DB Redesign | $500k-$1M | $45M-$50M | Not Started | Move departmental EPS Meter database and web views due to unsupported compatibility.
2-High | 23 | IO | ERCOT | New | Secure Storage Bldg | $250k-$500k | $45M-$50M | Not Started | Facilities secured storage and shop
2-High | 24 | IO | ERCOT | New | Blue Bldg Reconfig | $100k-$250k | $45M-$50M | Not Started | Blue Building reconfiguration
2-High | 25 | CO | ERCOT | 10039_01 | Physical Security Project #1 | $250k-$500k | $45M-$50M | Not Started | Enhance a specific area of ERCOT's physical security
ERCOT Fiscal Year 2011 Budget
Project Priority List (PPL)
2011 Priority | 2011 Rank | Program Area | Source | Project Number | Capital Projects | 2011 Budget Range | Cumulative Budget Range | Current Status | Description
3-High/Med | 26 | MC | ERCOT | New | Minor Cap - Other | $250k-$500k | $45M-$50M | Not Started | Lower priority Minor Cap items
3-High/Med | 27 | IO | ERCOT | New | OS Upgrades | $250k-$500k | $45M-$50M | Not Started | Upgrade Windows, Linux, AIX and other supporting applications to the latest versions.
3-High/Med | 28 | MO | ERCOT | New | AppWorx Upgrade | TBD | $45M-$50M | Not Started | Upgrade to newer version.
3-High/Med | 29 | RO | ERCOT | New | Rearchitecture of Zonal TIBCO Framework (to be consistent with Nodal) | TBD | $45M-$50M | Not Started | Upgrade to Zonal TIBCO to be consistent with Nodal TIBCO
3-High/Med | 30 | RO | ERCOT | 10004_01 | Retail Testing Website Enhancement | $250k-$500k | $45M-$50M | Not Started | ERCOT upgrade to transition to Enterprise Architecure approved infrastructure. No functional changes planned.
3-High/Med | 31 | RO | ERCOT | New | Siebel Table Split | TBD | $45M-$50M | Not Started | The objective of this project is to make modifications to the Siebel data model to gain performance efficiencies and comply with Siebel technical data architecture guidelines.
3-High/Med | 32 | RO | ERCOT | New | Siebel Upgrade | TBD | $45M-$50M | Not Started | The objective of this project is to upgrade Siebel to the latest Siebel release.
3-High/Med | 33 | RO | ERCOT | 10050_01 | TIBCO Upgrade | $100k-$250k | $45M-$50M | Not Started | This project will upgrade ERCOT’s TIBCO infrastructure and underlying Linux Operating System (Zonal only).
3-High/Med | 34 | IO | ERCOT | New | TCC2 Delivery Room Reconfig | $250k-$500k | $45M-$50M | Not Started | TCC2 Delivery Room reconfiguration
3-High/Med | 35 | IO | ERCOT | New | TCC2 Cube Reconfig | $500k-$1M | $50M-$55M | Not Started | TCC2 Cube reconfiguration
3-High/Med | 36 | IO | ERCOT | New | TCC2 Hope Room Reconfig | $250k-$500k | $50M-$55M | Not Started | TCC2 Hope Room reconfiguration
3-High/Med | 37 | IO | ERCOT | New | TCC1 Cube Reconfig | $500k-$1M | $50M-$55M | Not Started | TCC1 1st floor cubicle reconfiguration
3-High/Med | 38 | IO | ERCOT | New | Windows 7 | $100k-$250k | $50M-$55M | Not Started | Windows 7 upgrade
4-Medium | 39 | MO | Market | New | Default Uplift Process | TBD | $50M-$55M | Not Started | Modify the existing Lodestar uplift functionality to support uplift of defaults on DAM Invoices and RTM Invoices through a Default Uplift Invoice, in an automated fashion.
4-Medium | 40 | MO | Market | 10008_01 | Enhancements to API for Disputes | TBD | $50M-$55M | Not Started | Enhance the API Disputes functionality for updates, search and other functions post nodal go-live.
4-Medium | 41 | MO | ERCOT | 90006_03 | System Right-Sizing for ILM | TBD | $50M-$55M | Not Started | All systems coming online with Nodal - need to establish ongoing maintenance activities. Replication from Nodal systems. CRR, CMM sources only.
ERCOT Fiscal Year 2011 Budget
Project Priority List (PPL)
2011 Priority | 2011 Rank | Program Area | Source | Project Number | Capital Projects | 2011 Budget Range | Cumulative Budget Range | Current Status | Description
4-Medium | 42 | CO | ERCOT | 70015_01 | Cyber Security Project #5 | $100k-$250k | $50M-$55M | Not Started | Enhance a specific area of ERCOT's cyber security capability
4-Medium | 43 | RO | ERCOT | New | Test Automation Tool Upgrade | TBD | $50M-$55M | Not Started | Affects anything using WinRunner today
4-Medium | 44 | CO | ERCOT | 10030_01 | Vendor Contract Information Database Review | <$50k | $50M-$55M | Not Started | Move the management of vendors and vendor contracts from the current, in-house developed application to a best-practice model application
4-Medium | 45 | CO | ERCOT | New | Cyber Security Project #6 | TBD | $50M-$55M | Not Started | Enhance a specific area of ERCOT's cyber security capability
4-Medium | 46 | CO | ERCOT | New | Cyber Security Project #7 | TBD | $50M-$55M | Not Started | Enhance a specific area of ERCOT's cyber security capability
4-Medium | 47 | CO | ERCOT | 10049_01 | Collateral Calculation Enhancement | $100k-$250k | $50M-$55M | Not Started
9-Parking Lot |  | RO | PUCT | 90007_01 | Advanced Metering – Long-Term Settlement Solution | TBD | TBD | Not Started
9-Parking Lot |  | MO | Market | 10007_01 | Verifiable Cost Management System (VCMS) | TBD | TBD | Not Started
9-Parking Lot |  | CO | ERCOT | 10029_01 | Governance, Risk & Compliance (GRC) | TBD | TBD | Not Started
9-Parking Lot |  | CO | ERCOT | 10032_01 | App Log Centralization | TBD | TBD | Not Started
9-Parking Lot |  | CO | ERCOT | 10043_01 | BOD Material Preparation & BOD Resolution Tracking | TBD | TBD | Not Started
9-Parking Lot |  | CO | ERCOT | 10045_01 | Document Preparation Software - Legal | TBD | TBD | Not Started
9-Parking Lot |  | CO | ERCOT | 10046_01 | Lawson Pcard Module | TBD | TBD | Not Started
9-Parking Lot |  | CO | ERCOT | New | Open Enrollment | TBD | TBD | Not Started
9-Parking Lot |  | IO | ERCOT | New | Oracle Upgrade | TBD | TBD | Not Started
9-Parking Lot |  | MO | ERCOT | New | Rewrite REC Program | TBD | TBD | Not Started

## Stabilization Cost Summary
ERCOT Fiscal Year 2011 Budget
Proposed Nodal Post Go-Live Charges
|  | Timeline |  | Labor Estimate
Line | Task | 2011 Budget Estimate | HW/SW | Vendor | FTE | Staff Augmentation | Notes
1 | Nodal Stabilization - Operational Response, Production Issues and Stability | 11263816.85 | 0 | 6817500 | 2783284 | 1663032.85
2 | Daylight Savings Time & Planning Model Functionality | 41276 | 0 | 0 | 41276 | 0
3 | Zonal Decommissioning Efforts | 307008 | 0 | 0 | 307008 | 0
4 | Deferred Defects & Workarounds | 2509110 | 0 | 1044147 | 1220396 | 244567 | 50% defects delivered in 2011
5 | Parking Deck - Initial Release Impact Analysis/Requirements/Design | 3250000 | 0 | 650000 | 1300000 | 1300000 | Planning/Design activities in 2011
6 | Hardware & Software Maintenance | 7820047 | 7820047 | 0 | 0 | 0
7 | Post Go-Live Support Total | 25191257.85 | 7820047 | 8511647 | 5651964 | 3207599.85

## DST_MOD defects
ERCOT Fiscal Year 2011 Budget
Nodal Post Go-Live Support - Daylight Saving Time & Planning Model Defects
Time and Cost Estimate - Project Information and Summary
PART A Project Information
Project Number: | TBD
Project Title: | Nodal Deferred Defects | Sponsor's Name: |  | Cleary
Estimator's Name: | Martinez/Lowe | Estimate Date: |  | 2010-08-30
Department: | Nodal PMO - Integration and Systems
What are We Doing: DST and MOD (Planning Model) defects before Q111 end. This document provides a bottom up estimate of the effort it requires to resolve these before Mar 2011.
Why are We Doing This: These are required to be resolved before DST (short day) and 2011 Planning Model Go-Live.
Why Now: These were originally deferred to 2011 since they were not needed on Operating Day 1 - 12/01/2010, but will be needed before DST happens in Mar 2011.
Estimated Cost |  | Estimated Effort (Hrs)
Internal Labor | 38720 |  | Internal | 352
External Labor | 0 |  | External | 0
Hardware | 0
Licenses | 0 | Estimated Project Duration
Maintenance | 0 |  | Weeks | 12
Other | 0
Sub-Total | 38720 | Labor Rates
Est. Finance Charges | 2556 |  | Internal | 100
TOTAL | 41276 |  | External
Key Risks
1.) | Nodal go-live emergencies may consume business and development resources which will delay and incur costs from staff augmentation
2.) | Nodal Operations and Dispute volumes require more external resources than estimated for test planning and execution
3.) | Environment availability and coordination with other mandated or business required efforts could cause delays
4.) | Infrastructure projects need careful coordination with code releases
Key Assumptions
1.) | Based on $100 blended rate to account for incremental staff aug. as needed
2.) | Assumes 10% Contingency for bug iterations

## Decommision
ERCOT Fiscal Year 2011 Budget
Nodal Post Go-Live Support - Zonal Decommission
Time and Cost Estimate - Project Information and Summary
PART A Project Information
Project Number: | TBD
Project Title: | Decommission of Zonal Wholesale Systems | Sponsor's Name:
Estimator's Name: | Martinez/Lowe | Estimate Date: |  | 2010-09-07
Department: | TBD
What are We Doing: The objective is to eliminate zonal wholesales systems and components that will no longer be used post nodal go-live.
Why are We Doing This: Decommissioning of the zonal systems will be necessary in order to eliminate the cost overhead of support, maintenance and storage required to continue to service these systems that are no longer used. Leaving these systems active too long may risk interference with daily operations and eat into support resources better used for nodal operations or other projects.
Why Now: After go-live of the redesigned ERCOT wholesale market (Nodal), certain ERCOT systems and components that were only applicable to zonal wholesale operations will become disposable and need to be decommissioned.
Estimated Cost |  | Estimated Effort (Hrs)
Internal Labor | 288000 |  | Internal | 2880
External Labor | 0 |  | External | 0
Hardware | 0
Licenses | 0 | Estimated Project Duration
Maintenance | 0 |  | Weeks | 15
Other | 0
Sub-Total | 288000 | Labor Rates
Est. Finance Charges | 19008 |  | Internal | 100
TOTAL | 307008 |  | External | 150
Key Risks
1.) | Clean up of some extracts, reports, files, etc, may be constrained by the need to retain records (as defined by the Records Retention Schedule) for a longer period of time.
Key Assumptions
1.) | Assumes 3.5 month effort
2.) | Assumes systems on scope tab

## Deferred Defects
ERCOT Fiscal Year 2011 Budget
Nodal Post Go-Live Support - Deferred Defects
System | Defects to be Resolved by Go-Live | Deferred Defects | Comments
MMS | Total : 17 | Total: 63 | Delivery Schedule
·17 Defects to be resolved by 11/05
Deferred Defects
·51 Deferred defects require a workaround, 48 workarounds in place and exercised. 3 in progress to complete by 10/05
EMS | Total: 19 | Total: 347 | Delivery Schedule
·19 Defects to be resolved by 11/05
Deferred Defects
·119 Deferred defects require a workaround, 116 workarounds in place and exercised. 3 in progress to complete by 10/05
COMS | Total: 2 | Total: 62 | Delivery Schedule
·2 Defects to be resolved by 10/17 (test completion on 10/08, must migrate on Retail Outage Cycle)
Deferred Defects
·34 Deferred defects require a workaround, all 34 workarounds in place and exercised
CMM | Total: 1 | Total: 51 | Delivery Schedule
·1 Defect to be resolved by 10/08
Deferred Defects
·12 Deferred defects require a workaround, all 12 workarounds in place and exercised
MIS | Total: 24 | Total: 9 | Delivery Schedule
·24 Defects to be resolved by 10/15/2010
Deferred Defects
·2 Deferred defects require a workaround, both workarounds in place and exercised
NMMS | Total: 0 | Deferred: 10 | Delivery Schedule
·None
Deferred Defects
·9 Deferred defects require a workaround, all 9 workarounds in place and exercised
OS | Total: 1 | Total: 125 | Delivery Schedule
·1 Defect to be resolved by 10/08
Deferred Defects
·39 Deferred defects require a workaround, all 39 workarounds in place and exercised
CRR | Total: 3 | Total: 5 | Delivery Schedule
·3 Defects to be resolved by 10/08
Deferred Defects
·3 Deferred defects require a workaround, all 3 workarounds in place and exercised
EIP | Total: 4 | Total: 62 | Delivery Schedule
·4 Defects to be resolved by 10/15
Deferred Defects
·7 Deferred defects require a workaround, all 7 workarounds in place and exercised
CDR | Total: 16 | Total: 7 | Delivery Schedule
·16 Defects to be resolved by 10/15
Deferred Defects
·4 Deferred defects require a workaround, all 4 workarounds in place and exercised
EIS | Total: 17 | Total: 8 | Delivery Schedule
·12 Defects to be resolved by 10/15
· 5 defects to be resolved by 11/19
Deferred Defects
·5 Deferred defects require a workaround, all 5 workarounds in place and exercised

## Nodal Parking Deck
ERCOT Fiscal Year 2011 Budget
Nodal Post Go-Live Support - Parking Deck
| Item | Desc | Status | Priority | Impacted Systems | Details
Board Approved Items | NPRR208 | Registration and Settlement of Distributed Generation (DG) Less Than 1 MW | Board approved 7/20/10 | Critical | COMS | Revises the formula for Settlement of electricity consumption and out-flow by Customers with renewable Distributed Generation (DG). The revised formula fulfills the provisions of PUC Rule 25.213 that requires ERCOT to develop DG Settlement processes that “reflect the time of generation.” In order to fully synchronize the Protocols with the intent of the Rule as soon as practicable, ERCOT supports implementation of the grey-boxed language in NPRR208 as a “Critical” priority.
| NPRR131 | Ancillary Service Trades with ERCOT | Board approved 1/19/10 | High | MMS, CMM, COMS, EIP, EDW, CDR | Allows QSEs representing resources to procure A/S in the DAM
| NPRR146 | ICCP Telemetry Information Submittals | Board approved 6/15/10 | High | NMMS | Allows NOMCRs that modify only ICCP data object names to be submitted within 15 days of the network model load date Possible resolution with business process changes
| NPRR181 | FIP Definition Revision | Board approved 1/19/10 | High | MMS, COMS, EIP | Revises the definition of Fuel Index Price (FIP) to correctly account for the timing difference between ERCOT’s application of FIP in its systems (midnight to midnight) and the timing of natural gas prices reflected by the index (i.e., hour ending 1000 to 0900).
| NPRR207 | Unit Deselection | Board approved 7/20/10 | High | MMS | Defers two changes: 1 – hourly RUC notification of recommended but deselected resources in RUC 2 – prevent QSEs from increasing Energy Offer Curves after a RUC Notification
| NPRR210 | Wind Forecasting Change to P50, Sync with PRR841 | Board approved 6/15/10 | High | COMS | This NPRR changes the wind forecast from the 80% probability to 50%. This change is also effective in determining if a QSE is capacity short. The boxed language changes the capacity short calculation back to the 80% forecast.
| NPRR222 | Half-Hour Start Unit RUC Clawback | Board approved 7/20/10 | High | MMS, COMS | Removed from original NPRR207 language. Removes RUC clawback on Half-Hour Start Units in certain circumstances. Also changes the RUC Clawback on Half-Hour Start Units that did not participate in the DAM to 50%.
| NPRR153 | Generation Resource Fixed Quantity Block Offer | Board approved 1/19/10 | Medium | MMS, EIP, EDW, CDR | Allows a fixed quantity and time block bid for Offline Non-Spin with the contingency that all hours be purchased in the block
| NPRR164 | Resubmitting Ancillary Service offers in SASM | Board approved 1/19/10 | Medium | MMS, EIP, EDW, CDR | Allows QSEs to take full advantage of A/S and energy co-optimization in the DAM and participate in the Supplemental Ancillary Service Market (SASM) by being able to resubmit A/S Offers at the higher of DAM MCPC or its offer price in the DAM.
| SCR755 | ERCOT.com Website Enhancements | Board approved 2/16/10 | Medium | ERCOT.com, Web Services, Collage | Implementation of 10 improvements to ERCOT.com received in the 2008 Market Participant Survey. Includes document archiving, search improvements, training, meeting calendar enhancements, and RSS feeds.
In-flight Items | NPRR240 | Proxy Energy Offer Curve | Pending at Board | High / Medium | MMS, CDR (possibly others) | One grey-box section: “Energy Offer Curves that were constructed in whole or in part with proxy Energy Offer Curves shall be so marked in all ERCOT postings or references to the energy offer.”
| NPRR241 | Aggregate Incremental Liability (AIL) Calculation and Credit Reports Publish Corrections | Pending at Board | Medium | TBD | One grey-box section: Changes the alternate posting format for 3 reports from XLS to XML (in addition to PDF).
| NPRR251 | Sync of PRR845, Definition for IDR Meters and Optional Removal of IDR Meters at a Premise Where an Advanced Meter Can be Provisioned | Pending at Board | High | TBD | Grey-boxes language requiring IDR meters if usage warrants. Current language exempts situations where Advanced Meters have been installed. Also gray-boxes related reporting requirements for ERCOT.
| NPRR256 | Synchronize Nodal Protocols with PRR787, Add Non-Compliance Language to QSE Performance Standards | Pending at NATF | TBD | EMS, EDW | Seeks to exempt generation resources from GREDP calculation during testing and qualification periods. Not really a sync because additional exemptions to GREDP (Generation Resource Energy Deployment Performance) calculation are included
| NPR257 | Synchronization with Nodal Operating Guide Section 9, Monitoring Programs | Pending at PRS | TBD | CDR, EDW (possibly others) | Grey-boxes multiple sections of the Nodal Protocols to align with Nodal Operating Guide Section 9, Monitoring Programs. Through NOGRR025, ERCOT agreed to provide certain reports either during market trials, on a limited basis for specific intervals as requested by the PUCT, TRE and the IMM, or after TNMID.
| NPRR258 | Sync with PRR824 and PRR833 and Additional Clarifications | Pending at PRS | Critical | TBD | Grey-boxes language to change the calculation of GREDP PDCWG suggests priority of “critical”
| NPRR260 | Providing Access to MIS Secure Area to MIS Registered Users | Tabled at PRS | TBD | Siebel, MPIM | Makes it possible for consultants, power marketers, aggregators, consumers and universities to get access to the MIS Secure area (without doing so by getting a digital certificate through a registered Market Participant)
| NOGRR034 | Rescind Telemetry Performance Calculation Exclusions | Pending at Board | Medium | TBD | Grey-boxes language that allows QSE and TSPs to request removal of telemetry from Telemetry Standard performance metrics when certain situations exist.
| NOGRR050 | Resolution of Reporting Issues Related to NPRR219 | Pending at PRS | TBD | TBD | Grey-boxes several transmission Outage scheduling data elements from ERCOT reports until such time ERCOT systems can be modified to include only Transmission Service Provider’s (TSP’s) Outages in the reports
| SCR759 | acLine Segment Name Length Increase in Information Model Manager (IMM) | Pending at TAC | High | IMM, CRR, MMS (possibly others) | Increases the character size of the acLine Segment type under the Line Equipment Container from 2 to 14 in the IMM. Allows modeling of multi-section line segments. Not a major impact to IMM but cascading impacts to CRR and MMS Desire expressed at ROS to have this implemented for Planning Go-Live (~March 2011) Primarily requested by Centerpoint.
Additional Items for Consideration |  | Wind Cost Allocation |  |  | TBD | Multiple discussions at TAC / Board from 1/20/2009 to 3/16/2010 WMS endorsed “Wind Plus Load Ratio Share” proposal (wind generators receive a hedgeable A/S obligation for responsive reserves, non-spinning reserves, regulation up and regulation down.)
|  | Deferred NOGRR025 Reports |  |  | Various | Completion of NOGRR025 reports targeted for post-go-live development – synchronization effort underway to grey-box deferred reports in Nodal Operating Guide
|  | NMMS API |  |  | NMMS | System to system interactions for the uploading and possible future downloading of data between ERCOT and Market Participants with minimal manual intervention. NOMCR submittals (upload) including data submittals, one-line submittals and CIM XML submittal. Various other submittals such as Rating Methodologies, SPS documents, etc.
|  | CRR API |  |  | CRR | System to system interactions for the uploading and downloading of data between ERCOT and Market Participants without manual intervention. Nomination submittals (upload), Auction bid/offer submittals (upload), CRR Network Model files (download), CRR ownership records (download), CRR Auction results (download).
|  | MMS Multiple Network Models |  |  | MMS | MMS does not currently have the capability to concurrently support separate network models for Operating Day and Day-Ahead MMS processes (DAM & RUC)
|  | Add PSS Status to RARF |  |  | TBD | Automation of manual reporting process created by NPRR156. Current process involves the posting of a spreadsheet on PSS status when operators are notified of a change in PSS status.
|  | Automated Default Uplift Invoice |  |  | COMS | Automation of uplift invoice in the event of a market participant default. Current approach is manual.
|  | EILS Enhancements |  |  | TBD | Automate the ERCOT Energy Interruptible Load Service reporting process in expectation of higher volumes with AMI.
|  | Load Participation -SCED |  |  | TBD | Functionality to be considered for post-go-live development
|  | EMS Upgrade |  |  | EMS | Upgrade EMS from v2.3 to v2.5/v2.6 - Change operating system from Windows to Linux AREVA ceases support of v2.3 in June 2011 (extended support can be negotiated) NERC CIP-007-1 R3 requires that ERCOT assess all security patches within 30 days of a patch release for all critical cyber assets, including EMS servers. ERCOT has taken the stance that to meet this requirement it must set a goal of deploying all patches within 30 days. The current number of Windows servers within the CCA perimeter makes this unmanageable due to the number of patches issued for Windows and its peripheral applications, and the relative severity of security breaches with Windows. The current zonal EMS system in production has received Technical Feasibility Exception (TFE) from NERC based on our commitment to Nodal migration. However, since the Nodal EMS system may become unsupported, we need to reapply for a TFE for which we may need to demonstrate that an upgrade project is underway.
|  | Deferred Defects |  |  | Various | Defects not addressed during Nodal stabilization period (Approx. 770 deferred defects as of Aug) Review underway to confirm issues and confirm acceptable workarounds
|  | Lg. Wind Power Prod - Ramp Forecasting Ph 2 |  |  | TBD | Phase 2 of the project that built a display for ERCOT operators to indicate periods of time within the next 6 hours during which there is a high risk for a large wind power production ramp to occur
|  | TML Transition to MIS |  |  | MIS | Upon go live, most applications that are currently available through TML will migrate to MIS and will only be accessible to MPs through the MIS portal. RMS has requested that Zonal Reports, Find ESI ID, Find Transactions, and Transaction submission be accessed through TML until MIS has had sufficient time to stabilize.
|  | Move Price Validation Tool (PVT) to Svr App |  |  | TBD | Functionality to be considered for post-go-live development
|  | PVT Enhancements |  |  | TBD | Enhancements needed based on results of market testing and Nodal implementation: reporting, user interface changes, etc.
|  | PVT Reporting Tools |  |  | TBD | Functionality to be considered for post-go-live development
|  | Update Credit PFE (Potential Future Exposure) Model |  |  | TBD | With the implementation of Nodal, ERCOT’s portfolio credit risk analysis for the Nodal market will include the following risk factors: (1) Price volatility analysis for the Day Ahead Market, (2) Bid and offer volume analysis in the Day Ahead Market, and (3) Value of Congestion Revenue Rights
Subtotal for Items 31 - 37
| David Troxtell |  |  |  |  | Totals
Cagle Lowe
| Hope Parrish |  | Estimating Elements |  |  | #REF!
| Adam Martinez |  | Planning |  | 25%
| Jerry Dreyer |  | Development |  | 50%
| Troy Anderson |  | Test & Deploy |  | 25%
Recommendation by estimating team is to work all Critical and High priority items that have been Board approved and selected Other Items.
There will be one integrated release prior to September 2012 with some smaller releases starting in Q1 2012.
The smaller releases will include independent functionality from the parking deck items and/or small enhancements/defects .
No contingency included.
Other projects on the PPL (i.e. DC project) may impact the start of execution for releases.
Complete estimating ranges for all items.
Determine what to do about EMS Upgrade. Does it need to start in 2011?