## NATF list Legend and History
LEGEND
1 = Show stopper; Needs resolution before Go-live can be accomplished.
2 = High priority issue that should be resolved by Go-live. Work-Arounds could be developed but for a very short time frame.
3 = Needed but can be implemented post Go-live. Will not affect safety, operational reliability or validated work-arounds exist.
4 = Needed by Planning Go-Live (approximately March 2011)
5 = Not an issue. (Could be an answer to a question or a discussion item.)
1) Started with the file from the 09-17-10 NATF meeting
2) Provided updates to a few items on 09-21-10.
3) Includes updates from the 9-22-10 NATF meeting.
3) Includes updates to a few items on 9-28-10 in prepartion for 9-30-10 NATF.
4) The 10-18-10 version includes updates from the 10-5-10 NATF meeting and items provided by email after the meeting. It also has some updates provided by ERCOT after the 10-5-10 NATF meeting.
5) The 10-29-10 version includes updates from the 10-26-10 NATF meeting. It also has some updates provided by ERCOT after the 10-26-10 NATF meeting. There are no open Priority 1 items. There are 10 open items. There are 5 deferred items.

## QSE Issues List
Source: NATF Issues List
Source: NATF Issues List |  |  | last updated 10-29-10 1623
REF # | COMPANY | ISSUE CATEGORY | DESCRIPTION | PRIORITY provided by MP | ERCOT Lead | Status | ERCOT / MP Comments | ERCOT Ranking
1 | PSEG | Competitive Constraints | Detailed discussion from ERCOT on how they plan to manage the generic constraints-- (W-->N and Hou import) | 1 | John Adams | closed | 8-30-10: ERCOT will calculate Generic Constraints two (2) days ahead of the operating period using power flow study cases for voltage stability constraints, and looking up limits from previously performed small signal stability constraints for known small signal stability issues (currently West-North). ERCOT plans to create these study power flow cases using COP data for the study period. Our intention is to use WRUC results to create these power flow cases, but this capability is not yet functional. Currently we are capturing a real-time case to exercise the generic constraint procedure. For voltage stability constraints, we calculate maximum transfer across the interface using the VSAT application, and then pass these limits to TCM (Transmission Constraint Manager) through manual entry with effective dates and times. For small signal stability (W-N) ERCOT examines the cases built for voltage stability constraints, and uses the generation units and lines in service data to look up in a table the small signal stability limit for that scenario based upon historic studies. TCM transfers these limits to market systems, where the execution of DAM captures these limits and incorporates them in the DAM run. The manual portions of this process are documented in ERCOT’s “Generic Constraint Limit Calculation Practice”. 9-15-10: ERCOT will use the best available information to build its study cases. Closed 9-15-10.
2 | PSEG | Competitive Constraints | Comparison of load flow cases with and without competitive constraints--we have no information on how this works yet. None of the competitive constraints were binding in the most recent test (24 hrs). So we still have no clue as to how the Step 1 and Step 2 SCED results differ. | 1 | Resmi Surendran/ Isabel Flores/Steve Reedy | closed | 8-30-10: Comparison of load flow cases is not in scope. ERCOT plans to use the "existing CSCs/CREs (See section 3.19) "Unless the Board approves changes, the Competitive Constraints" are the "existing CSCs/CREs ……. " Note that the W_TO_N generic constraint was active as competitve constraint during the recent 24 hr LFC test, from 11 P.M. on 19th to 6:45 A.M. on the 20th and then from 10:45 A.M. to 12:30 P.M. on 20th. Note that from 12:35 AM to 1:30 A.M. the price separation was due to W_TO_N since that was the only constraint that was binding during that time. Also, during the recent 40 hr LFC test the N-H generic constraint was active.
3 | CPS | DAM & RT Credit | If a QSE has a negative credit limit and submits a TPO, then the system will not allow for the cancellation of the TPO if this action would result in the credit line remaining negative. | 2 | Sai Moorty | closed | 8-30-10: Implemented as per NPRR 206. Can discuss further - Not a defect. 9-3-10: This was discusssed at the 8-31-10 NATF. Sai to research. 9-16-10: This is working as designed. If a CP's current available credit limit is already negative , cancelling an existing 3PO will further push the available credit limit into more negative direction - this is not allowed. In order to cancel a 3PO in this scenario, the QSE must cancel all the bids that are contributing to the negative available credit limit first until the credit limit reaches positive vaule before cancelling their 3PO. This behaviour, is due to changes in the manner by which 3PO credit exposure actually increases available credit limit as per NPRR 206. Closed. 9-22-10: Reopened and marked as a 2. 9-28-10: Sai and James discussed after the 9-22-10 NATF meeting. James to check a few things before possibly closing. Expect to close at 9-30-10 NATF.
4 | LCRA | Settlement Price Calculations | Irrational settlement point prices are a concern seen in Market Trials and not acceptable for go-live. Settlement point prices were reported as zero or negative market wide. There have also been large price swings from a high positive number to a large negative number and back to a high positive number in the span of five 15-minute intervals. These results do not seem to be logical or reasonable. | 1 | Jeff Gilbertson | closed | 8-30-10: ERCOT has not observed irrational Settlement Point Prices. Specific issues observed in the past have been addressed and have been explained. Output data from SCED has been consistant with the input data. If you need explanations for specific intervals, please send in specifics to MarketTrials@ERCOT.com. 9-16-10: ERCOT has since researched a question from LCRA about OD 7-29-10 and provided an acceptable answer. Item still closed.
5 | CALPINE | LFC | During LFC's we would like to see ERCOT using a CPS1 minimum of 125% rather than 100% | 1 | Kenneth Ragsdale | closed | 8-30-10: NERC criteria is 100%, ERCOT will continue to report the CPS1 scores from the LFC tests.
6 | Luminant | DAM Clearing Engine | If number of source/sink pairs for CRR PTP Options carried to Real-Time exceed 100, increases iteration time for DAM. Prohibits correct modeling of Phase Shifters as in the field. | 1 | Sai Moorty | closed | 8-30-10: DAM optimization cannot solve for both Phase Shifters optimization and PtP Options (complex solution that was not considered years ago during design when there were no PSTs). As discussed in DeepDive mtgs, ERCOT working on procedure to improve PST with 1) Moving off of neutral position based on weather forecast from Operations. 2) "Monitor Only" those lines affected by the PSTs. Note there is only 1 setting for each PST for the 24-hour period. 9-15-10: Method 2 was adopted during the 168 hour test. 22 lines have been identified as impacted by the existing PSTs and are currently tagged to be monitored only (as opposed to secured). Additionally, the DAM performance issues associated with NOIE CRR PTP Option Offers exceeding 175 unique source to sink pairs is anticipated to be resolved with a shorter contingency list and hardware upgrade.
7 | Luminant | Network Modeling | The network model used for DAM should be consistent with the real time model with regard to all mitigation plans, SPSs, etc. and there should be a verifications process to check for consistency prior to go-live. | 1 | John Adams | closed | 8-30-10: John Adams is finalizing procedures. Draft Procedures to be provided by 9-8-10. 9-15-10: The approach is to have the Operations Engineers calculating generic limits notify the DAM operators of the contingencies to be disabled to approximate the affect of anticipated RAPS (which includes PCAPs TOAPS, and Mitigation Plans). RAPS and SPS's that are in the model are automatically taken into consideration by DAM (by not securing certain elements). Also, developing a script that would outage the equipment as proposed by the PCAP. 10-05-10 Luminant believes a draft procedure for the process described above is being prepared by ERCOT staff. Luminant understands that ERCOT hopes to have a draft version of the procedure ready for distribution on the 10-7-10 DAM Deep Dive Conf. Call. The intent is to then solict feedback from Market Participants on the draft proposal prior to the 10-14-10 DAM Deep Dive Conf. Call, which will allow ERCOT to interate once or twice on this procedure and bring a final copy back to TAC for endorsement at their early Nov. 2010 meeting.
8 | NRG | Real-Time Operations | Discussion from ERCOT on the XML messages utilized when deploying non-spin. Are the XML messages the same for off-line generation resources, on-line generation resources, controllable load resources and non-controllable load resources? Will market participants get an opportunity to test the non-spin deployment messages? | 1 | Resmi Surendran | closed | 8-30-10: This item came in separate from the original list. As part of Market Trials, we had done some open loop testing of the NSRS deployment. Also, during the 40 hour LFC test, NSRS was deployed. If still needed by NRG or others, additional tests can be scheduled.
9 | Luminant | DAM Clearing Engine | ERCOT needs a proven methodology for load distribution factors and allocation of non conforming loads. | 2 | Sai Moorty/ John Adams/ Matt Mereness | open | 8-30-10: Currently using data from 7 days ago as discussed in protocols and seeded with State Estimator data. ERCOT is working on establishing an alternative procedure for establishing LDF. In DAM, every submission at the Load Zone is distributed down to individual loads as conforming load as per the protocols. 9-15-10: ERCOT has seeded Load Distribution Factors with a static set using historic State Estimator data to achive stable DAM results. It is ERCOT's intent to present to NATF in September and to TAC in October our procedure for generating these static LDF distributions for future months. 9-22-10: Presentation made at NATF 9-22-10. Leave open at least until 9-30-10. 9-28-10: ERCOT plans to review methodology at 9-30-10 NATF and take methodology to TAC on 10-7-10. 10-05-10 Luminant believes ERCOT has the draft methodology posted on the TAC calendar for a vote on 10-7-10. Luminant plans to share the analysis that we prepared internally in mid-September to analyze how ERCOT draft proposal was improving LDFs over what we had seen in late August. This analysis will suggest that progress has definitely been made and that ERCOT's LDF methodogy proposal is definitely a step in the right direction. Luminant plans to ask ERCOT to commit to come back to TAC at the early Nov. 2010 TAC meeting with a similar analysis from the DAM market trials that are planned for the end of October to show how the LDFs are tracking at that time and talk about any further improvements that they have made to the methodology.
10 | Luminant | DAM Clearing Engine | Due to rounding AS quantities awarded to the nearest tenth, the awarded quantities actually exceeded offers by 0.10 to 0.20 MW | 2 | Sai Moorty | closed | 8-30-10: Investigating the following change (details to be provided in September NATF): 1) Adjust the individual block awards sent to market participants from MMS to match total that S&B recieves. 2) Need to check if this type of adjustment does not break something else - AS OFFER CAP management. Working to correct this, but ERCOT does not consider this item as absolutely necessary for go-live. 9-21-10: Progress has been made with the approach described above. ETC not yet available. 9-28-10: Fix is part of MMS5 patch 10 which is scheduled to be migrated into NPROD 10-1-10. 10-29-10: Closed
11 | Luminant | DAM Clearing Engine | Is there a need for a protocol revision to create shadow price limits in DAM equal to Real Time? | 2 | Sai Moorty | deferred | 8-30-10: Not necessary for go-live.
12 | Luminant | Network Modeling | Network model used for DAM must include PCAPS used in Real Time model. | 2 | John Adams | closed | 8-30-10: ERCOT agrees. See the answer for REF # 7. 9-15-10: See the answer for REF # 7.
13 | Luminant | Network Modeling | ERCOT has provided redacted operations model files and evaluation is ongoing concerning review of operations model files. | 2 | Sai Moorty | closed | 8-30-10: Per NPRR202 redacted model is posted for each model load, and PSSe file being provided for market trials.
14 | Luminant | Network Modeling | Is there a different methodology or set of ratings being used between the nodal (reported as RTM) and zonal (reported as Daily Ops) models. Is ERCOT working with the TDSPs to match/correct these differences? | 2 | Matt Mereness/ Anthony Natoli | closed | 8-30-10: Each TSP is required to submit to ERCOT its rating methodology. There is no provision for different methodologies between Zonal and Nodal. Nodal to Zonal comparisons have been made. Any reports of discrepancies are passed on to TSPs by ERCOT.
15 | Luminant | Network Modeling | Luminant tracking approximately 12 active Modeling issues on DAM Deep Dive calls. ERCOT Ownership of the quality of the data based on the Current Network Model for DAM and RT. | 2 | Matt Mereness/ Woody Rickerson | closed | 8-30-10: Covered on DAM Deep Dive list. ERCOT has developed a model quality assurance process prior to model first use. This process is part of the 90 day model review process described in the protocols. 9-16-10: During the 9-16-10 DAM Deep Dive call these items were marked as closed. Closed. Note however that there is on-going work as new items are discovered. Currently, working to correct incorrect contingency definitions for some of the auto transformer contingencies. Closed.
16 | Luminant | Line Ratings | Luminant tracking approximately 19 active ratings issues on DAM Deep Dive calls. ERCOT Ownership of the quality of the data based on the Current Network Model for DAM and RT. | 2 | Matt Mereness/ Woody Rickerson/Anthony Natoli | Closed | 8-30-10: Covered on DAM Deep Dive list. ERCOT has developed a model quality assurance process prior to model first use. This process is part of the 90 day model review process described in the protocols. 9-16-10: During the 9-16-10 DAM Deep Dive call these items were marked as closed. Closed.
17 | Luminant | Real Time Operations | All questions, comments, and observations dealing with start up and shut down of units. | 2 | Dave Maggio | closed | 8-30-10: ERCOT Business Practices for "ERCOT and QSE Operations During the Operating Hour" should address these issues. First Draft scheduled to be reviewed at 8-31-10 NATF. 9-16-10: Comments on the document have been received and the plan is to review a revised version (that incorporates the appropriate comments) at the 9-22-10 NATF meeting. The go-live approach will be to use "ONTEST" for start-ups and shut-downs. An NPRR has been drafted by ERCOT to allow this approach. Left open until at least 9-22-10.
18 | Luminant | Real Time Operations | Questions and comments regarding the real time telemetry of AS responsibility on units varying during the Operating Hour. | 2 | Dave Maggio | Open | 8-30-10: ERCOT Business Practices for "ERCOT and QSE Operations During the Operating Hour" should address these issues. First Draft scheduled to be reviewed at 8-31-10 NATF. 9-16-10: Comments on the document have been received and the plan is to review a revised version (that incorporates the appropriate comments) at the 9-22-10 NATF meeting. Left open until at least 9-22-10. 9-28-10: NPRR 275 was rejected by PRS on 9-23-10. Business Practice Manual has been not been revised. ERCOT considering to appeal PRS decision. Left as open for now. 10-26-10: Plan to take up at 11-2-10 NATF.
19 | Luminant | Real Time Operations | QSE AS Capacity Compliance Monitoring Notification: ERCOT will supply a notification to QSEs when the comparison between the QSEs AS Supply Responsibility in the EMS system with the AS Supply Responsibility in the MMS system indicates that the QSE is not providing sufficient capacity Question: will the notification also be available through XML form, similar to EIP 1.19, section 5.3.1.2? Outstanding question. | 2 | Colleen Frosch | deferred | 8-30-10: ERCOT notifies Participants in advance of capacity shortages based on COP info with XML messages. ERCOT performs RT notification with phone calls until XML notification is added post go-live. ERCOT also provides a 5 minute report.
20 | Luminant | Market Data/Reports | Question: When will QSE Ancillary Services Capacity Monitor report on the MIS or through Get Reports be available? Response: report is not active at this time, release data is not yet established. The Report will only work when Telemetry is required for DAM awards | 2 | Jamie Lavas | closed | 8-30-10: Though required by Market Trials, we have had several outstanding defects with this report. It is currently back in development and will be re-released to itest next week for further testing. Once through itest, it will need to be validated by business before it can be released in nprod. If business or itest find additional defects, it will be remanded back to development again. Still working to get an estimate for the delivery date. 9-16-10: Currently in business validation. Suspect it is a data issue. 9-28-10: Determined it is not a data issue. New views have been created in DEV environment. Pending ITEST and business validation before NPROD delivery. On track to be fixed by go-live. 10-05-10 Luminant requests that ERCOT get this fixed prior to the Nodal LFC test at the end of October so that they can demostrate to Market Participants that this is working as intended. 10-26-10: Migrated into NPROD on 10-22-10. Closed.
21 | Luminant | Protocol Revision | When DAM is aborted, ERCOT will not have AS to meet their obligations. ERCOT will abort the DRUC and run a SASM, in which offers can be revised. Need approval of NPRR255. | 2 | Matt Mereness | closed | 8-30-10: Yes. On 8/19/10, PRS unanimously voted to recommend approval of NPRR255 as submitted. 9-22-10: NPRR is scheduled to be reviewed at PRS 9-23-10 and possibly could be at October TAC. 9-28-10: Scheduled to be reviewed at the October 4 PRS meeting. 10-26-10: NPRR 255 approved by BOD on 10-19-10. Closed.
22 | Luminant | Settlement | The ERCOT settlement system is incorrectly using HSL from the COP to detect curtailed intervals. Needs a system change or work around. Settlement of BPD not right for non-IRR units. Calculation is wrong. | 2 | Mandy Bauld | open | 8-30-10: BPD for IRR: ERCOT system is coded per protocol. The issue (can the market go-live per that protocol) is open at QMWG/WMS. ERCOT's slides for QMWG update at the 8/18 WMS offered options for an interim solution; options would require a protocol change, but not a system change. ERCOT is still investigating whether or not there are other viable options. BPD for non-IRR: ERCOT system AABP calcluation is coded per protocol. Luminant submitted a question to market trials concernign the validity of the protocol calculation, under a scenario when any of the SCED intervals in the 15-minute settlement interval are less than 5 minutes. ERCOT staff is currently addressing this question. Luminant has been asked to provide data to backup their concern. ERCOT does not believe there is an issue with BPD for non-IRR. More discussion is needed. Absent a timely NPRR the current Protocols will be in effect. 9-16-10: BPD for IRR: NPRR has been drafted to disable the BPD charge for IRRs. BPD for non IRR: At this point in time it appears this is a non-issue. Luminant needs to provide more information. Any changes to the calculation would require an NPRR. 9-21-10: Issue has been discussed at QMWG and SEWG. Settlement System is coded per protocol. QMWG has a draft NPRR going to WMS. No change to the Settlement System until there is an approved NPRR. 10-26-10: NPRR 285 is scheduled to go to TAC on 11-4-10.
23 | Luminant | Compliance Criteria | Anticipating some questions will be answered in ERCOT Real Time Business Practices document. | 2 | Kenneth Ragsdale | closed | 8-30-10: Document to be posted and reviewed at 8-31-10 NATF meeting. 9-16-10: Comments on the document have been received and the plan is to review a revised version (that incorporates the appropriate comments) at the 9-22-10 NATF meeting. Left open until at least 9-22-10.
24 | Luminant | Real Time Operations | Need submittal and approval of NPRR to add protocol language for real time dispatch of units in SCED | 2 | Kenneth Ragsdale | open | 8-30-10: Need better description of the issue. 9-22-10: Related to Quick starts. NPRR 272 covers this issue. ERCOT believes that this NPRR is NOT necessary for go-live. 9-28-10: NPRR 272 is scheduled to be discussed at the 10-4-10 PRS meeting. 10-29-10: NPRR 272 (Definition and Participation of Quick Start Generation Resources) is scheduled to to TAC on 11-4-10 TAC.
25 | Luminant | Resource Parameters | Would like ERCOT to: 1) Provide QSEs ability to view the values ERCOT is using in their modeling. 2) Provide a method of correcting this number should the ERCOT value get out of sync with the units actual status | 3 | Kenneth Ragsdale | open | 8-30-10: Need better description of the issue. QSEs have the ability to update operational resource parameters and can view most of the values. 9-28-10: Suggest that this be deferred. Need to identify the specific values that need improved visability.
26 | Luminant | Planned Telemetry Outages | ERCOT compliance criteria for telemetry does not take into account planned outages. | 2 | John Dumas/ Alex Sills | closed | 8-30-10: NOGR 34 is scheduled to be reviewed at the September BOD meeting. 9-22-10: Board revised the standard to 92% to account for planned outages.
27 | Luminant | Compliance Criteria | The language in the NPRR for telemetry of WGR HSL is overly restrictive; may need modifications. | 2 | Dave Maggio | closed | 8-30-10: See answer to REF # 30 below.
28 | LCRA | Market Data/Reports | Future Credit Exposure for CRR PTP Options (FCEOPT) Detail Report | 2 | Cheryl Yager | open | 8-30-10: This detailed report is not currently being provided and is not expected to be provided as it takes too long to run. NPRR 241 (going to TAC next week) allows ERCOT to not provide this report and/or allows ERCOT to provide an extract instead. ERCOT is working on an extract of the data. 9-22-10: Need to confirm extracts will be available before go-live. NPRR 241 was approved by TAC. 9-28-10: NPRR 241 was approved by the Board on 9-21-10.
29 | LCRA | Market Data/Reports | Future Credit Exposure for CRR PTP Obligations (FCEOBL) Detail Report | 2 | Cheryl Yager | open | 8-30-10: This detailed report is not currently being provided and is not expected to be provided as it takes too long to run. NPRR 241 (going to TAC next week) allows ERCOT to not provide this report and/or allows ERCOT to provide an extract instead. ERCOT is working on an extract of the data. 9-22-10: Need to confirm extracts will be available before go-live. NPRR 241 was approved by TAC. 9-28-10: NPRR 241 was approved by the Board on 9-21-10.
30 | E.ON Climate & Renewables | Protocol Revision | Issue of ERCOT producing a curtailment flag for Wind Resources to the list with a priority of #2? There was an NPRR that stated that if your basepoint is 2 MW less than your HSL sent into ERCOT, the resource is curtailed, but it has become evident during the LFC testing that a curtailment flag is truly the only reliable way a wind resource can be assured of a curtailment. We have a few QSEs for our many wind farms and each QSE has their own calculation for when a wind resource is curtailed and each method is different. If wind QSE's formula for calculating a curtailment is wrong, there could be reliability issues on the system. | 2 | Dave Maggio | closed | 8-30-10: The language in the protocols (as a result of approved NPRR 214) is clear. ERCOT is not planning to submit NPRRs to change the approach.
31 | CALPINE | RUC | Calpine would like the ability to move AS onto a unit that has been committed for RUC. Currently ERCOT allows this by calling ERCOT and the operator can turn down the request. If a unit trips, then ERCOT has no choice but to accept the request. Calpine would like a rules based response to any request to move AS and would prefer that the request be handled systematically via an electronic transaction as opposed to simply operator judgement. | 2 | Colleen Frosch | closed | 8-30-10: Per Section 3.9(4), moving AS to a Resource RUCed on is not permitted . Not required for go-live.
32 | CALPINE | DAM | Request for all Combined Cycle resources to be allowed to change their offer curve in the adjustment period. We realize this is an item that was discussed at length in past years, however, we believe the market has learned a lot about CC resources since then and it would be productive to re-open this issue. As a middle ground the request could be softened to allow any Co-gen (QF) to change their offer curve in the adjustment period and disallow any other type of resource to make changes. Two other alternatives for consideration are changes during the Adjustment Period and Inter-Hour again for Co-gen purposes. | 2 | Steve Reedy | closed | 8-30-10: Implemented according to protocol.
33 | CALPINE | Competitive Constraints | We want to be able to verify the classification of non-competitive constraints. Right now we see the results but not the process. The list of competitive constraints seems too small. | 2 | Resmi Surendran | closed | 8-30-10: See answer to item 2 above.
34 | CALPINE | Protocol Revision | NPRR200 was approved in Feb 2010 and essentially says that DC-Tie schedule data will be sourced from the OATI system. ERCOT has been very slow to respond with details regarding how QSE's will access DC-Tie data. As of August 2010, ERCOT is now pulling DC-Tie schedules from the OATI zonal system and settling them in Nodal settlements. However, ERCOT has indicated no plans to provide any type of download for QSE systems to determine trade positions or for shadow settlements purposes. | 2 | Scott Middleton/ Mandy Bauld | closed | 8-30-10: QSE's should access DC-Tie data through OATI. Settlement extracts (RTM CODE) contain the DC Tie data used in settlment, which is sourced from the OATI system. The published DC Tie-related billing determinants include: RTDCEXP, RTDCIMP, DCIMPSNAP, and DCIMPADJ. The LSEGUFE for approved import tags will be included in the RTAML at the DCTIE Settlement Point and will also be in the RTM CODE extract.
35 | CALPINE | AS on a RUCed Resource | If the ERCOT Operator RUCs a Combined Cycle Resource to a different configuration and the Resource was already carrying AS on the train ----- can they continue to carry AS on the train? Can a resource holding AS be committed for RUC? Can a resource be RUCed that is already holding AS? Section 5.5.2(7) seems to indicate that a resource already holding AS cannot be committed for RUC. However, we’re not sure to what extent ERCOT could use the “infeasibility” exception in this paragraph. Furthermore, if the configuration committed for RUC was not carrying AS, would we be allowed to move the AS to that config (see separate question next that references section 3.9(4)). What if the config confirmed for RUC could not provide the AS, would ERCOT relieve us of the obligation to provide AS? | 2 | Colleen Frosch | closed | 8-30-10: This item came in separate from the original list. A Resource will be RUCed to a different configuration only by an ERCOT Operator (ie not by the software). If the grid needs additional capacity, then ERCOT could direct a different configuration which would provide this additional capacity. If ERCOT asks for a configuration which would yield an increase in capacity without directing that this capacity be used to provide AS, then the AS should be moved to a different Resource. Section 5.5.2(7) indicates that a RUCed Resource cannot carry AS unless it was RUCed on to provide AS.
36 | Luminant | Market Data/Reports | Forecasted Temp. Adj. Dynamic Ratings Duplicate Data: Each timestamp row of data is duplicated | 3 | Jamie Lavas | closed | 8-30-10: This is an open defect. Expected to be fixed in NPROD by dd/mm/yy. 9-16-10: This has been corrected in Itest. Expected to be in NPROD September 17. 9-22-10: Need Jamie to confirm before it is closed. 9-28-10: No longer have duplicate data, however the latest fix resulted in broken sort order for the report. On track to be fixed before go-live. 10-29-10: Fix released into NPROD on 10-22-10. Closed
37 | Luminant | Market Data/Reports | Shift Factors Rpt Duplicate Records: Each timestamp row of shift factor data is duplicated | 3 | Jamie Lavas | closed | 8-30-10: This is an open defect. Expected to be fixed in NPROD by dd/mm/yy. 9-16-10: Have been unable to recreate the issue and are continuing to monitor. Marking as Closed.
38 | Luminant | Compliance Criteria | Whether the PUC intends to change its QWETR rule in any way to reflect the nodal market. New PUC project was opened. | 3 | Kenneth Ragsdale | closed | 8-30-10: This is not within ERCOT's scope. (Quarterly Wholesale Electricity Transaction Reports.)
39 | Luminant | Systems I/O | It seems that messages of type = TELEMETRY do not have milliseconds and type = Market Message do have milliseconds. Is this the intended behavior for alerts? Can we expect this to be how this field is populated? | 3 | Jeff Gilbertson | closed | 8-30-10: While the format of the timestamps are inconsistent, they are valid formats. Yes, the timestamps will continue to be populated in this manner.
40 | Luminant | Real Time Operations | Advocate to change SCED to use an integrated value on the ramp rate curve. The way SCED behaves now, if the unit is currently at 5 MW/min rr and on the cusp of the next ramp rate at 10 MW/min rr, SCED will continue to use 5 MW/min rr even though the unit is capable of providing more than 5 MW/min. | 3 | Kenneth Ragsdale | closed | 8-30-10: Could be considered post go-live. This would be a change in scope.
41 | Luminant | RUC | HRUC notices are received after the COP deadline has passed. Possibly solved. | 2 | Scott Middleton | closed | 8-30-10: There was a one time occurance of this from the HRUC software during Market Trials, the root cause was a late web report, and the issue was resolved. It is possible for this to occur in the case of RUC VDIs; this issue will be added to the COP Expectations Business Practices. 9-22-10: Restatement of issue. Not enough time to update COP after getting RUC instruction. For example, a Resource with a 2 hour start up time is only getting 1.25 hour notice. ERCOT needs to confirm how it handles startup-time. 9-28-10: The deadline for ERCOT to approve an HRUC study is "50 minutes after the top of the hour". COPs will not be able to be updated for instructions for the first hour of the study period. Instructions could still be issued for the first hour of the study period. (for example, for a don't shutdown, stay on-line instruction) Here is another example: ERCOT approves the RUC study at 0750. Any Resource that takes more than 15 minutes to start should NOT recieve an instruction to be on for Hour Ending 0900. A resource with a start time of 1 hour could be instructed to be on for hour ending 1000. The RUC software has a parameter ----- the time for the study to complete and the time for approval ---- to ensure Resources are not instructed to be on sooner than they can be on. Expect to close this issue at the 9-30-10 NATF.
42 | Luminant | Systems I/O | Do “Emergency Notice” alerts only show up on the MMS? | 3 | Jamie Lavas | closed | 8-30-10: Assume the question was MIS not MMS?. Public alerts are posted to the MMS UI, MIS and the EIP listener.
43 |  | Additional resource status for resource startup/shutdown | ERCOT published guidelines for telemetry and resource statuses during resource startup and shutdown. We would like additional resource statuses for conditions below LSL rather than using workarounds with existing resource statuses. | 2 | Kenneth Ragsdale | deferred | 8-31-10: This was added at the 8-31-10 NATF meeting. 9-16-10: NPRR required. This is generally agreed upon, but something that can be implemented after go-live.
44 |  | Trade Confirmation Timestamp | ERCOT has not implemented a trade confirmation timestamp in the Trades area on the MMS. Although notifications provides a timestamp of when each QSE submits or confirms this can provide conflicting timestamps particularly when confirmation is done around 1430. A single timestamp record is needed on the Trades tab to confirm which RUC capacity will be treated in. This leaves a hole for shadow settlements to determine whether a trade was confirmed pre or post 1430. | 2 | Jeff Gilbertson | deferred | 8-31-10: This was added at the 8-31-10 NATF meeting. 9-16-10: ERCOT is investigating. The DRUC snapshot information should provide info on whether or not the trade was confirmed before or after 1430. Not absolutely necessary before go-live.
45 |  | DA/RT SPP Price files only available for 3 days on MIS | The RT SPP Price files are only available for 3 days on MIS and DA SPP Price Files for 5 days. We have asked ERCOT to increase this to at least 7 days to ensure if there are download errors sufficient time is allowed to correct the issue. Other ISO's observe posting times of 7 days and greater for prices. This becomes the greatest issue over weekends when reduced vendor and technical staff cannot realistically solve a technical issue in time before data rolls off the MIS. | 2 | Kenneth Ragsdale | closed | 8-31-10: This was added at the 8-31-10 NATF meeting. 9-3-10: ERCOT has increased the holding time for 5 & 15 min LMP/SPP files to 5 days.
46 |  | PRDE Files only on MIS for 2 days | Currently the PRDE files are only out on the portal for 2 days. We have asked ERCOT to increase this to at least 7 days to ensure if there are download errors sufficient time is allowed to correct the issue. This becomes the greatest issue over weekends when reduced vendor and technical staff cannot realistically solve a technical issue in time before data rolls off the MIS. | 2 | Kenneth Ragsdale | closed | 8-31-10: This was added at the 8-31-10 NATF meeting. 9-3-10: The historical PRDE files are not necessary for loading historical extracts.
47 |  | Approval of the procedure describing how to set shadow price caps and power balance penalities in SCED | Per Nodal Protocols 6.5.7.1.11, ERCOT shall determine the methodology for setting maximum Shadow Prices for network constraints and for the power balance constraint. Following review and recommendation by TAC, the ERCOT Board shall review the recommendation and approve a final methodology. Many market participants believe this procedure needs to finalized before one can vote on a go-live decision. | 2 | Resmi Surendran | closed | 8-31-10: This was added at the 8-31-10 NATF meeting. 9-16-10: Comments on the document have been received and the plan is to review a revised version (that incorporates the appropriate comments) at the 9-22-10 NATF meeting. 9-22-10: WMS approved this Business Practice today. This is no longer an issue. TAC to address. Closed today.
48 |  | Approval of the procedure which sets the x,y, and z variables for the GREDP compliance claculation. | Per Nodal Protocols 8.1.1.4.1,the GREDP/CLREDP performance criteria in paragraphs (7) through (9) shall be reviewed and set by the TAC two months before the Texas Nodal Market Implementation Date (TNMID). The performance criteria will be subject to review by TAC beginning two months after the TNMID and as deemed necessary. The GREDP/CLREDP performance criteria variables X, Y, and Z shall be posted to the MIS Public Area no later than three Business Days after TAC approval. | 2 | Dave Maggio | closed | 8-31-10: This was added at the 8-31-10 NATF meeting. 9-16-10: ERCOT is in the process of preparing this analysis and plans to provide the information at the October TAC meeting. 9-22-10: NATF could recommend something ---- but that is not required. Make sure it is on the TAC agenda. 9-28-10: Kristi has this earmarked as a TAC agenda item. Brief discussion planned for the 9-30-10 NATF.
49 | LCRA | TBD | In order to test our software implementation which calculates the Startup Offer Cap and Minimum Energy Offer Cap, ERCOT needs to start incorporating the FIP adder and Proxy Heat Rate when validating Offers. | 1 | Kenneth Ragsdale | closed | 9-3-10: This was added 9-3-10. 9-16-10: ERCOT has provided an opportunity for the MPs shadow the calculations next week. Only those QSEs or REs with approved verifiable costs will be able to see the changes.
50 | CALPINE | TBD | Proposal to use telemetered Ramp Rates instead of Ramps Rates provided through MMS UI/EWS. | 1 | Kenneth Ragsdale | deferred | 9-16-10: This was added based on discussion at NATF
51 | J ARON |  | Missing intervals for posting RTSPPs | 2 | Jamie Lavas | open | 9-16-10: Two defects have been created. The prices are right, the problem is with the postings. 17405: When the electrical bus LMP report retry functionality is automatically triggered, the retry report contains a SCED interval that has already been posted instead of a missing SCED interval. This has been observed in NPROD for the past three days. 17620: RT SPP data is generated in MMS every 15 minutes, regardless if SCED has run or not. This report needs to be posted via MMS every 15 minutes as well, in a timely fashion. Currently the report trigger depends on a SCED completion event message somehow. Therefore if SCED is not running, the report is not generated. The trigger must be modified such that it posts the SPP report when new data is stored in the SCED_SPP table in MMS/MIDB. 9-22-10: ERCOT needs to confirm that this will be fixed before go-live. 9-28-10: We have developed a manual workaround that could be implemented. Also, plan to revisit the retry logic. On track to have fixed by go-live. 10-29-10: The fix for this item is scheduled to be released into Itest 10-29-10 (today).
52 | NRG |  | NRG’s question was for real time, not DAM. The energy offer curves are being rejected because the system can’t find credit exposure values. NRG believes this is a serious problem and apparently Sai does too because he started working on it immediately. I do not understand why the ERCOT system is looking for credit exposure values in real time on units with EOCs? | 1 | Sai Moorty | closed | 9-16-10: This has been identified as a defect and should be corrected with MMS5 patch 10. 9-28-10: Confirmed that the fix for this issue is in MMS5 patch 10. This can be tested after the migration into NPROD (which is scheduled for 10-1-10). DAM does not need to be executed. We just need offer curve submitted close to the closing time of the window for sumbissions. This should remain open until tested in NPROD. Target date to close is 10-6-10.
53 | LCRA |  | Available credit on non-business days When DAM was run over the weekend in August, a significant amount of credit was consumed | 1 | Cheryl Yager | closed | 9-16-10: Two possible solutions DAM system improvements ERCOT credit staff to update ACLs on non-business days ERCOT staff will update ACLs on non-business days at go-live until a long term solution can be finalized.
54 | LCRA |  | CRR to RT Settlemetn Issue: In recent market trial activity there are days in which the offer price was above the Day-Ahead settlement point price, but the CRR was settled in Day-Ahead instead of going to Real-Time settlement. There are also days in which there were not any CRR offers, but some CRRs still went to Real-Time settlement. Below is a list of a few sample days where there has been an issue with the proper CRR settlement: • 8/18 – Some CRR’s settled in RT when all should have cleared in DA because there were no DA offers • 8/20 – Some CRR’s settled in RT when all should have cleared in DA because there were no DA offers • 8/24 – Some CRR’s settled in RT when all should have cleared in DA because there were no DA offers • 8/30 – All settled in DA when all should have gone to RT • 8/31 - Some CRR’s settled in DA that should have gone to RT (some CRR’s have correctly gone to RT) • 9/1 – Some CRR’s settled in DA that should have gone to RT (some CRR’s have correctly gone to RT) • 9/9 - All settled in DA when all should have gone to RT | 1 | Sai Moorty | closed | 9-16-10: This item was sent in 9-16-10. ERCOT is still investigating. 9-21-10: Fix is being worked on and is expected to be migrated into NPROD with MMS5 patch 10. Issue related to multiple updates to PTP offers. 9-28-10: Test conducted in ITEST 9-24-10 indicates the defect (data transfer within MMS) has been fixed. The code has been migrated to NPROD and tests are ongoing in NPROD. Based on 9-23-10 email from LCRA --- issued closed 9-28-10.
55 | Shell |  | Need update on Dashboards. Concern is that different MPs get data at different times. 9-24-10: Additional info: The dashboards that are of particular interest are the following: DA and RT LMP’s/SPP’s LMP Contour Map Load Forecast vs Actual SCED Up/Down Weather In addition to this information, we would like to see the same market information that is provided today in zonal and is available in the nodal market via ICCP be made available via the dashboards. This includes data such as: Total Gen, Total Load, Capacity available for SCED, total A/S by A/S type and total wind output. | 2 | Jamie Lavas | open | 9-22-10: Added at NATF 9-22-10. 9-28-10: Jackie Ashbaugh provided an update at PRS on 9-23-10 and more info to K. Ashley on 9-24-10. ERCOT plans to provide an update at the 9-30-10 NATF meeting. System Ancillary Service Capacity Monitor Status: Live in NPROD during Market Trials SCED Up/Down Day-Ahead & Real-Time LMPs LMP Contour Map Load Forecast vs. Actual LMP Ticker Status: Currently in integration testing. Scheduled for 10/12 MIS go-live date in production. Frequency, Weather and DC Ties Status: Still have outstanding work to be done. 10-05-10 Luminant shares Shell's desire to see this data shared prior to Go Live 10-26-10: Still working on new scope (4 new price dashboards). Load Forecast vs, Actual is still not available. RT system conditions covers Frequency and DC ties. Weather is post go-live.
56 | Tenaska |  | Inablility to move Demand Response from Group 1 to Group 2 as needed | 3 | Brandon McElfresh | closed | 9-22-10: Added at NATF 9-22-10. 9-28-10: Nodal Protocols allow QSEs to deploy process dependent Load Resources from Group 2 with the Group 1 deployments. Refer to Nodal Protocols 6.5.9.4.2(2)(a)(ii)(A), “QSEs shall deploy Load Resources according to the group designation and will be given some discretion to deploy additional Load Resources from Group 2 if Load Resource operational considerations require such.” Beyond that QSEs do not have the ability to move Load Resources from Group 1 to Group 2 or vice versa. The Group 1 and Group 2 designations are determined via the “random sampling” process referenced in Nodal Protocols 6.5.9.4.2(2)(a)(ii)(A). Since the random sampling process only looks at one operating hour of the day, not all Resources are actually assigned to Group 1 or Group 2. All Resources not assigned to Group 1 or Group 2 will automatically be deployed with Group 1 by the AS Deployment Management tool. Plan to try to close at 9-30-10 NATF meeting. 10-29-10: Closed.
57 |  |  | General concerns about credit management and credit processes during the first 45-60 days after nodal go-live. How will extremely high credit calls be handled? | 2 | Cheryl Yager | closed | 9-30-10: Added this today. 10-15-10: Cheryl Yager presented an overview of the approach planned to be used by ERCOT to make Credit Adjustments as necessary in the early months of Nodal. The same presentation was made the Joint CWG/MCWG meeting on 10-6-10. ERCOT recommends this issue be closed at the 10-26-10 NATF meeting. 10-29-10: Closed due to Cheryl's presentations.
58 |  |  | Misinterprtation of null SU and min energy offers by RUC software | 1 | Sai Moorty | closed | 9-30-10: Issue known before but added to this list today. Fix migrated into NPROD last week.
59 | Luminant |  | NEW ITEM Luminant feels that ERCOT must provide Market Participants the ability to audit and validate that the QSE credit calculations for NPRR206 are working as intended. | 2 | Carrie Tucker | closed | 10-13-10: This issue was added to the list on 10-5-10. After it was added, Carrie Tucker stepped through the calculations and sent out an analysis to the NATF exploder last week. She plans to present a summary of the analysis and answer questions at the 10-26-10 NATF meeting. ERCOT believes this item should be closed at the 10-26-10 NATF meeting. 10-29-10: Closed due to completion of Carrie Tucker's walk through at 10-26-10 NATF.
60 | NRG |  | Add actual load by weather zone to the data available via ICCP. It is my understanding that this is a fairly simple change to make from ERCOT’s end and it is important to several of our internal systems. At the moment I believe total ERCOT load is all that is available via ICCP. And strangely enough, we are able to get this data in zonal, but it got left out of nodal. | 2 | Stacy Bridges Bill Blevins | open | 10-13-10: Issue added via email 10-13-10. 10-26-10: ERCOT is investigating. 10-29-10 Added Bill Blevins to the owner cell.
61 | Constellation |  | Want published a comprehensive list of constraints that are unenforced/enforced on a daily basis (as this list is changing continously during testing and perhaps into go-live as well) | 1 |  | closed | 10-18-10: Issue added via email 10-06-10. Currently these are posted in the Deep Dive list. ERCOT is working on long term plan to provide the information. (62) 10-26-10: Closed at the 10-26-10 NATF meeting. |  | 62
62 | Constellation |  | Requesting that DAM network model continue to be sent out after go-live. Also requesting a mapping between bus names, line names, etc in the DAM, crr, and planning models. | 2 |  | closed | 10-18-10: Issue added via email 10-06-10. For the go-live model, similar to what has been provided during Market Trials, the CD with the PSSE files will be provided. After go-live, there still is ongoing discussion. A protocol change most likely required. (66) 10-26-10: Closed at the 10-26-10 NATF meeting. |  | 66
63 | Constellation |  | Concerned about DST transitions--many problems reported. | 2 |  | closed | 10-18-10: Issue added via email 10-06-10. Additional DST testing is scheduled in ITEST. The first DST encountered in production will be in the Spring of 2011. (67) 10-26-10: Closed at the 10-26-10 NATF meeting. |  | 67
64 | Constellation |  | Finding many occasions when data (such as bill determinant components) have to be pulled manually or tables backed out manually (i.e. CSI defect #17214). We are worried that manually pulling data could cause errors in settlement calculations. | 1.5 |  | closed | 10-18-10: Issue added via email 10-06-10. This effects the Emergency Energy Payment when ERCOT operators issue a dispatch instruction to a resource to move to a specific output level. (6.5.9). While this hasn't been automated, there is a manual process to pull this data daily and check for base point overrides. This defect has been deferred. (68) 10-26-10: Closed at the 10-26-10 NATF meeting. |  | 68
65 | Constellation |  | There are many EDW defects related to reports that we don't know what the reports are used for. i.e. EDW defect #16269 says that 'a report' does not capture controllable load resource RRS data--which report is this and how is that report used? Does it affect settlements? i.e. EDW defect #16238 what is data mart and how is it used? Does it affect settlements? i.e. Many report errors related to DRP2.0--what is DRP2.0? | 2 |  | closed | 10-18-10: Issue added via email 10-06-10. Defect #16238 is closed. Defect #16269 is scheduled to be fixed in NPROD 10-27-10. (69) 10-26-10: Closed at the 10-26-10 NATF meeting. |  | 69
66 | Constellation |  | There are many issues that relate to incorrect settlements with RUC. For example: COMS-S&B 13290 "If a Resource is DAM committed, then that DAM commitment is decomitted and after the decommitment the Resource is then RUC committed, the code does not evaluate the commitments on a chronological order and produces a result that is different than expected." What is the different than expected? "'Process put in place to identify and correct using Manual adjustment steps documented in existing procedures." COMS-S&B 17632: RUC settlements correctly determining start-type? | 1 |  | closed | 10-18-10: Issue added via email 10-06-10. 17632 is resolved. 13290 only occurs when a QSE requests decommitment for a DAM committed resource and the resource is then RUC committed (A situation that should be very rare). In this case the resource should not be eligible for a makewhole payment. A work around is in place to identify these instances and correct the eligbility outcome. Remaining eligibility defects also have work arounds and should occur in very rare circumstances. (74) 10-26-10: Closed at the 10-26-10 NATF meeting. |  | 74
67 | Constellation |  | RUC AS: 1. If an online CC supplying AS is RUC'd to a higher-capacity configuration, then the AS has to be moved to another plant. NATF issue #35/31 RUC decommitments: 1. Forced to buyback DAM-sold energy at RT prices--exposing you to RT volatility 2. Was told in Settlements 301: You don't get paid nor capacity credit if you were scheduled to turn off during the operating day (e.g. a CC that runs during peak hours can't recover it's start costs unless running for a certain time period). 3. Was told in RUC workshop: You don't get capacity credit if decommitted 4. Protocols do not clarify the capacity credit during decommits 5. You don't get a credit for the AS If a unit is decommitted--that unit is left on the hook for covering energy, capacity, and AS--resulting in future RUC charges. | 1 |  | closed | 10-18-10: Issue added via email 10-06-10. Items 2, 3 and 4. You do receive a Capacity Credit if the decommitment was issued within the two hours before the operating hour (Nodal Protocols 5.7.4.1.1(2)). It is correct that if ERCOT decommits a QSE-committed Resource during the RUC process earlier than its scheduled shutdown within the Operating Day, then no compensation is due to the affected QSE from ERCOT. This has been implemented per nodal protocols section 5.7.3 (1). (75) 10-26-10: Closed at the 10-26-10 NATF meeting. |  | 75
68 | Constellation |  | Mrk Facing Known Issues: * "DAM is not properly handing outages that close a breaker. If an outage opens some breakers while closing others, DAM is not closing the breaker but is opening the others. This can cause the network to split and can cause high prices in certain areas " * "During Aug 4th-5th 24-Hour Test, shift factors were observed to not be passing to SCED for specific constraints with unresolved contingencies. The vendor is working on an emergency patch." * "COP validation logic that is looking at whether or not the resource is RUC-committed when attempting to submit a resource status of ‘ONRUC’ is falsely looking only at the latest RUC process, rather than all RUC processes. For example, if DRUC committed the resource for hours 14-18, and a subsequent HRUC committed it for hour 19 only, then the system will only let you update the COP to a status of ONRUC for hour 19. " * "Day-ahead self-commitment logic not working for combined cycles – if different CC configurations are self-committed for different hours, DAM is not properly handling the CC as self-committed." * Online unit start times not correctly considered in RUC--lead time not correct? line 42 * "QCLAW - A SELF - RUC -DAM commit with the SELF being in later RUC process than the RUC should yield the SELF commits as QCLAW intervals" "RUC transition created in error when SELFCOMMIT to different configuration in HE1 and RUC in HE24 prev OD" COMS S&B6587 | 1 |  | closed | 10-18-10: Issue added via email 10-06-10. All of these issues have been addressed. (76) 10-26-10: Closed at the 10-26-10 NATF meeting. |  | 76
69 | Constellation |  | Complete list of DAM-derated CRRs not published | 1 |  | closed | 10-18-10: Issue added via email 10-06-10. Certified data is available after the DAM in extracts. NOIEs can see the DAM results and determine which of the CRR offers were derated. (78) 10-26-10: Closed at the 10-26-10 NATF meeting. |  | 78
70 | Constellation |  | Does the datafeed for RT binding constraints (INSERT TABLE NAME) include both constraints that bound in step 1 AND constraints that bound in step 2? (There may be constraints that bind in step 1, but not step 2.) | 3 |  | closed | 10-18-10: Issue added via email 10-06-10. The answer is "yes". (79) 10-26-10: Closed at the 10-26-10 NATF meeting. |  | 79
71 | Constellation |  | MMS 12022 "different price within one hour block for CRR offer, PTP bid should be rejected. but MPI let it pass. xml files are attached. Suggest put price, quantity at one xml area,like AS offer and energy only offer, instead of at seperate areas." | 2 |  | closed | 10-18-10: Issue added via email 10-06-10. Deferred. The fix would be a validation rule that would make submittals clearer. As is, there is no impact to prices or the clearing. (80) 10-26-10: Closed at the 10-26-10 NATF meeting. |  | 80
72 | Constellation |  | MMS 16528: "'SCED process should read shift factors (Resources and electrical buses) from a consistent set in EMS" | 1:3 depending on response |  | closed | 10-18-10: Issue added via email 10-06-10. Deferred. Some changes were made in MMS5 patch 10 that mitigate the issue. Monitoring will continue until defect is addressed. Not required for go-live. (85) 10-26-10: Closed at the 10-26-10 NATF meeting. |  | 85
73 | Constellation |  | MMS 17594: 'RUC - manual commitment before RUC execution - issues in handling temporal constraints. Seems like there is error in the logic (temporal constraint) in determining a unit's eligibility/ineligibility to be committed in RUC. Impact if not fixed? What is the effect of a correct/incorrect detection of infeasibility for a resource? | 1 |  | closed | 10-18-10: Issue added via email 10-06-10. As of 10-15-10, this issue is still open with a resolution target date of 11-5-10 (and is in patch 11). (91) 10-26-10: Closed at the 10-26-10 NATF meeting. |  | 91
74 | Constellation |  | EMS 17484: Request response to Luminant's request for explanation on how this issue effects compliance www.ercot.com/.../08_luminant_questions_concerning_nodal_reliability_performan.doc | 3 |  | closed | 10-18-10: Issue added via email 10-06-10. Closed. Scheduled to be migrated into NPROD by 11-5-10. (98) 10-26-10: Closed at the 10-26-10 NATF meeting. |  | 98
75 | Constellation |  | DAM market report--protocols state awarded energy offers and bids should be published specifying MWh, Settlement Point, and SPP for each hour of the awarded bid. |  |  | closed | 10-18-10: Issue added via email 10-06-10. Need more info on this item. (100) 10-26-10: Closed at the 10-26-10 NATF meeting. |  | 100