## Slide 1: Nodal Program Update
Technical Advisory Committee
4 November 2010

## Slide 2: Today’s Agenda
Program Status
Cutover Update
24 Hour LFC Test Update
  Nodal Issues Update
  Defect Delivery Update
Prioritization Process Overview
4 November 2010
Technical Advisory Committee

## Slide 3: Integrated Nodal Timeline – Go-Live December 1, 2010
Technical Advisory Committee
4 November 2010

## Slide 4: 26 Days to Go-Live
Technical Advisory Committee
Market Trials has Concluded
Upcoming Milestones:
  Load Frequency Control(LFC)Tests
    LFC test is scheduled for the week of November 8, 2010
    In support of the Soft Launch, the next LFC test will occur on 11/28/2010 and become binding with Go-Live
  Market Trials
    October 30, 2010: ERCOT concluded the October testing window:
    10/18 – 10/30 Day Ahead Market, DRUC and HRUC tested daily
    10/18 – 10/30 SCED published LMPs and base points
    10/25 – 10/29 Focused input from the Market (e.g. realistic COPs, telemetry, offers and bids)
    10/27 – 10/28 24-Hour LFC Test
    November 15, 2010 - November 29, 2010 Go-Live Soft Launch:
    Note that ERCOT has updated the start of the Soft Launch to 11/15 (previously 11/23)
    Soft Launch will include a ramp into Go-Live bringing systems online, but non-binding over the stated 2-week period
4 November 2010

## Slide 5: Cut-Over Monthly Outlook – Go-Live Sequence of Events
Date | Action | Comments
11/15/2010 – 11/29/2010 | ERCOT Initiates “Soft Launch” to Nodal Market Go-Live | ERCOT will run non-binding DAM, RUC daily per Nodal protocol timelines. RTM will remain Open Loop, but continue to publish base points and LMPs. Note that credit will be set high on 11/15
11/15/2010 | Credit posts ACLs and TPEs for non-binding DAM | For Operating Day 11/15 credit will be manually set to high limits
11/16/2010 | First Credit Operating Day 11/16/2010 | Credit reflects actual limits
11/17/2010 | Market now able to submit transactions for first Nodal Operating Day (T-14d) | 12/01/2010 Operating now available for Market submissions
11/23/2010 | QSEs with Resources required to submit 7 days of rolling COPs | 12/01/2010 required on 11/23/2010
11/28/2010 2:00 PM – 11/28/2010 3:00 PM | Generation and Frequency Control switched to Nodal systems for final LFC test | QSEs will begin following Nodal base points Settlements will continue to be Zonal
11/28/2010 2:00 PM – 11/30/2010 11:59:59 | QSEs remain on Nodal Control while settling Zonally during the LFC test | 
11/29/2010 | Last Non- Binding DAM for operating day 11/30/2010 | 
4 November 2010
Technical Advisory Committee

## Slide 6: Cut-Over Monthly Outlook – Go-Live Sequence of Events
Time | Action | Comments
up to 10:00 | Bids and Offer submission | QSE submit bids and offers
10:00 | Close DAM | 
10:00 | Execute Dam Clearing Process | 
13:30 | Approve DAM results | Day Ahead results posted to MIS
13:30-14:30 | Submit Post DAM COP updates | 
14:30 | Close for RUC | 
14:30 | Begin Execution of DRUC | 
16:00 | Approve DRUC Results | 
16:00 | Post DRUC Results | 
18:00 | HRUC Begins Hourly Runs | 
11/30/2010 Go-Live Sequencing
4 November 2010
Technical Advisory Committee

## Slide 7: Cut-Over Monthly Outlook – Go-Live Sequence of Events
Key Zonal Notes for 11/30/2010 and 12/01/2010
  QSEs will maintain:
    Balancing Energy Offers through Operating Day 12/01/2010
      Submitted on 11/30 for OD 12/1
    Resource Plans through Operating Day 12/01/2010
      Maintained continuously through 12/01 to reflect actual Resource Plan
    Zonal Outages effective on Operating Day 12/01/2010
      Examples: Actual Start / End, Forced Outages, etc
  On 11/30/2010 ERCOT will run:
    Zonal Ancillary Service Market
      Zonal awards will be published
    Zonal RPRS
      Run as a study only
      Zonal commitments will not be published
  Zonal prices will not be generated for 12/01/2010
  No Zonal Submissions or Markets for Operating Day 12/02/2010 or later
  Note that all Zonal systems (ERCOT and MP) must remain in place until 1/1/2011
4 November 2010
Technical Advisory Committee

## Slide 8: Cut-Over Update - October
MP Activities / Impacts
CRRAH able to retrieve ACLs from CRR system each business day.
MPs can post additional collateral until 11/08/2010 for Dec 2010 CRR Auction
Dec 2010 CRR Model available on MIS
Dec 2010 Monthly Auction Notice available on MIS
Functional Area
Network Model
Outage Scheduler
Congestion Revenue Rights
Credit
MIS
May
June
July
Aug
Sept
Oct
Nov
Dec
Key Cut-Over Activities for October 2010
  Complete (10/14-10/19) CRR: ERCOT begins accepting PCRR Nominations for December Monthly Auction (updated)
  (10/15-11/15) Model: Network Operations Model posted to TSP Citrix location and TSPs begin validation process
  Complete (10/26) CRR: ERCOT shall allocate PCRRs to NOIEs for the 2010 December Monthly Auction and publish to MIS
  Complete (10/26) CRR: ERCOT shall post CRR Network Model for the 2010 December Monthly Auction to MIS
  (10/28-11/08) Credit: ERCOT posts ACLs daily for CRR December monthly auction to CRR
  Complete (10/29) CRR: ERCOT to post December 2010 Monthly Auction Notice to MIS
4 November 2010
Technical Advisory Committee

## Slide 9: Cut-Over Update - November
MP Activities / Impacts
Available Credit Limit is locked for CRRAHs
CRR Auction Invoice via the API or MIS
CRRAHs can receive postings on MIS
QSEs can begin DAM Bid submission (15 submission items)
Market checkpoint calls begin to facilitate issues and readiness
Daily Market Conference Bridge starts 11/23
Functional Area
Settlements
Credit
Congestion Revenue Rights
Disputes
Market Management
May
June
July
Aug
Sept
Oct
Nov
Dec
Key Cut-Over Activities for November 2010
(11/8/2010 12:00pm) Credit: Collateral Posting Deadline (Dec Auction)
(11/8/2010 5:00pm) CRR: Credit Lock for Dec CRR Auction
(11/9/2010 – 11/11/2010) CRR: December CRR Auction Bid Open/Close
(11/12/2010) CRR: December CRR Auction Executes
(11/15/2010) CRR: December CRR Auction Results published
(11/16/2010) Settlements: December CRR Auction Invoice published
(11/19/2010) Credit: Payment Due for December CRR Auction Invoices
(11/22/2010) Settlements: Payments to CRRAH (Dec Auction)
(11/23/2010) Market Submission Opens (Remaining Protocol Go-Live)
(11/24/2010) Model: Network Model Load
(11/29/2010) Credit: ERCOT to Publish ACL for the initial Day-Ahead Market execution by ERCOT
4 November 2010
Technical Advisory Committee

## Slide 10: Cut-Over Monthly Outlook – December
MP Activities / Impacts
Daily Market Calls continue for issue facilitation
Settlement Calendar Extracts (See Emil for full list of postings)
MPs receive 1st Nodal Invoice for DAM and RTM via MIS
MPs can submit Disputes via MIS or API
Functional Area
Network Model
Settlements
Congestion Revenue Rights
Credit
Market Management System
May
June
July
Aug
Sept
Oct
Nov
Dec
Key Cut-Over Activities for December 2010
(12/01/10) Nodal Program: Nodal Go-Live (Operating Day 1)
(12/3/2010) Settlements: Nodal Day Ahead Market Statement & Invoice Available
(12/8/2010) Credit: Nodal Payment Due for OD12/01/2010
(12/9/2010) Credit: Nodal Payout for OD12/01/2010
(12/15/2010) Model: Network Model Load
(12/13/2010) Settlements: Nodal Real-Time Statement Available
(12/16/2010) Settlements: Nodal Real-Time Invoice Available
(12/27/2010) Credit: Nodal Payment Due for Real-Time Invoice 12/16/10
(12/28/2010) Credit: Nodal Payout for Real-Time Invoice 12/16/10
4 November 2010
Technical Advisory Committee

## Slide 11: 24 Hour LFC Test Update
Kenneth Ragsdale
Principal Market Operations

## Slide 12: 24 Hour LFC Test (Highlights) – Completion Criteria
Initial assessment of Completion Criteria:
  The rolling CPS1 one minute average score must equal or exceed 100% during the test period
    Note that the CPS1 average will not take into account the periods where ERCOT is transitioning to Nodal and then back to Zonal
    Note that the CPS1 average will not take into account the periods where ERCOT is performing system tuning
      Hourly CPS1 Scores:
        Max: 166, Min: 88, Average: 137
  Zonal Commercially Significant Constraints (CSCs) and Closely Related Elements (CREs) managed below thermal limits: Yes
  Local Congestion managed below thermal limits : Yes
  Stability limits managed below transfer limits : Yes
  No NERC Disturbance Control Standard (DCS) failure if applicable: None
  No LFC-SCED system issues that result in termination of the test : None
4 November 2010
Technical Advisory Committee

## Slide 13: 24 Hour LFC Test (Highlights) – Observations
Observation | What / When | Cause | Resolution
SCED Stopped | Intervals 12:05, 12:10, 15:55 | Issue occurs when DSR telemetered Output Schedule = 0 MW and RST = ONDSR | Code fix targeted for 11/5/2010 release
Updated Desired Base Points | UDBPs were observed to cease updating for 5 units | Problem related to SCED stopping. | Code fix targeted for 11/5/2010 release
EMS Alert Issues | Large volume of EMS alerts seen by MPs, including stale alerts and duplicates | Root Cause under investigation | Implemented parameter updates and purged database at approximately 11:30 AM on 10/27 to clear stale alerts and eliminate duplicates
Incorrect Base Points, LMPs, HUB Prices, Load Zone Prices | Interval impacted 13:15, 18:05, 18:55 | Shift factor transfer issue | Code fix targeted for 11/5/2010 release
4 November 2010
Technical Advisory Committee

## Slide 14: 24 Hour LFC Test (Highlights) – Observations (continued)
Observation | What / When | Cause | Resolution
High / Low Prices | Throughout peak period of the test | Multiple outages (common this time of year) Resource limit constraints (AS, ONTEST) Nodal prices are not incentivized Conservative Operations | Not a software problem
Incorrect Real-Time Metered Prices (Note: this did not impact Base Points or other prices) | Missing EPS data between 12:00 and 13:30 on 10/27 | Under investigation | Improved monitoring of data transfer processes
4 November 2010
Technical Advisory Committee

## Slide 15: Nodal Issues & Defect Delivery Update
Kenneth Ragsdale
Principal Market Operations

## Slide 16: Defect Summary (slide 1 of 3) [as of 10-29-10]
Technical Advisory Committee
System | Defects to be resolved by Quarter 4 | Deferred Defects | Comments
MMS | Total : 30 | Total: 84 | Delivery Schedule 1 Defects to be resolved by 11/01 29 Defects to be resolved by 11/05 Deferred Defects 51 Deferred defects require a workaround, all 51 workarounds in place and exercised
EMS | Total: 5 | Total: 360 | Delivery Schedule 5 Defects to be resolved by 11/05 Deferred Defects 129 Deferred defects require a workaround, all 129 workarounds in place and exercised.
COMS | Total: 0 | Total: 71 | Delivery Schedule NA Deferred Defects 36 Deferred defects require a workaround, all 36 workarounds in place and exercised.
CMM | Total: 0 | Total: 54 | Delivery Schedule NA Deferred Defects 12 Deferred defects require a workaround, all 12 workarounds in place and exercised
4 November 2010
Notes: <number>

## Slide 17: Defect Summary (slide 2 of 3) [as of 10-29-10]
Technical Advisory Committee
System | Defects to be resolved by Quarter 4 | Deferred Defects | Comments
MIS | Total: 14 | Total: 10 | Delivery Schedule 1 Defects to be resolved by 10/29 10 Defects to be resolved by 11/05 1 Defects to be resolved by 11/10 2 Defects to be resolved by 11/19 Deferred Defects 3 Deferred defects require a workaround, all 3 workarounds in place and exercised
NMMS | Total: 0 | Deferred: 10 | Delivery Schedule NA Deferred Defects 9 Deferred defects require a workaround, all 9 workarounds in place and exercised
OS | Total: 0 | Total: 128 | Delivery Schedule NA Deferred Defects 40 Deferred defects require a workaround, all 40 workarounds in place and exercised
CRR | Total: 0 | Total: 7 | Delivery Schedule NA Deferred Defects 4 Deferred defects require a workaround, all 4 workarounds in place and exercised
4 November 2010
Notes: <number>

## Slide 18: Defect Summary (slide 3 of 3) [as of 10-29-10]
Technical Advisory Committee
System | Defects to be resolved by Quarter 4 | Deferred Defects | Comments
EIP | Total: 2 | Total: 64 | Delivery Schedule 2 Defects to be resolved by 11/05 Deferred Defects 10 Deferred defects require a workaround, all 10 workarounds in place and exercised
CDR | Total: 16 | Total: 5 | Delivery Schedule 16 Defects to be resolved by 11/05 Deferred Defects 3 Deferred defects require a workaround, all 3 workarounds in place and exercised
EIS (EDW) | Total: 2 | Total: 13 | Delivery Schedule 2 Defects to be resolved by 11/05 Deferred Defects None Required
4 November 2010
Notes: <number>

## Slide 19: Critical Defects to be resolved by Go-Live (12/1/10)
4 November 2010
Technical Advisory Committee

## Slide 20: Nodal Defects Target Completion dates (as of 10/29/10)
4 November 2010
Technical Advisory Committee

## Slide 21: Next 60-days of Nodal Classes/Workshops
Enrollment at: http://nodal.ercot.com/training/courses/index.html
Course | Start Date | Location
Load Serving Entity 201 | November 8 | Liberty Power (Florida)
Nodal Market Workshop for Retail Electric Providers | November 9 | Omni Austin Hotel at Southpark
Load Serving Entity 201 | November 19 | ERCOT MET Center (Austin)
4 November 2010
Technical Advisory Committee

## Slide 22: Prioritization Process Overview
Troy Anderson
Manager, Enterprise Project Portfolio Management

## Slide 23: It’s Time to Look Forward to 2011…
Nodal Stabilization will be the primary focus after Go-Live
A coordinated effort is needed to prioritize and implement future changes to the Nodal systems
  Deferred Defects will be worked as time allows during Stabilization
  Parking Deck items need an impact assessment before final prioritization can be completed
  Other lists of proposed changes have been compiled
    QSE / TSP / DAM Issues lists
    Potomac Economics Market Assessment
    ERCOT Risk Assessment
  New requests will come through existing channels
    NPRRs, SCRs, Revision Guide changes, etc.
Technical Advisory Committee
4 November 2010

## Slide 24: Nodal Stabilization Timeline
Technical Advisory Committee
4 November 2010

## Slide 25: Approach
Initial Prioritization Process
  The various issues lists will be centralized and managed by ERCOT
  ERCOT will propose an initial prioritization
  ERCOT will coordinate stakeholder review of the prioritized list
    ROS, WMS, COPS, PRS, TAC
  TAC and the Board will be asked to endorse the initial prioritization
  NPRRs or SCRs will need to be submitted for market requests to ensure stakeholder support (QSE / TSP / DAM issue lists)
Ongoing Prioritization Process
  New requests are considered through the usual process
    Revision Request submission
    ERCOT Review
    Market Subcommittee consideration
    TAC and Board approval
Technical Advisory Committee
4 November 2010

## Slide 26: Prioritization Timeline
November 2010
  Seek approval of approach
  ERCOT initial prioritization recommendation
December 2010
  Begin review of prioritized list with stakeholder groups
February 2011
  Seek TAC/Board approval of initial prioritized list
Nov 2010
Dec 2010
Jan 2011
Feb 2011
Mar 2011
Nodal Stabilization
Initial Prioritization Process
Impact Assessment of Parking Deck Items
Process Approval
Ongoing Prioritization Process
TAC Consideration
Board Consideration
Technical Advisory Committee
4 November 2010