## Slide 1: MARS Taskforce
COPS Update December 7, 2010
Notes: <number>

## Slide 2: Initial Settlement
As of December 2, 2010
  Operating Date: November 24, 2010
  AMC ESI ID Totals: 1,985,554
  AMDG ESI ID Totals: 289
  Estimated Percentage: 1.162%
<number>
Notes: <number>

## Slide 3: Final Settlement
As of December 2, 2010
  Operating Date: October 6, 2010
  AMC ESI ID Totals: 1,595,724 AMDG ESI ID Totals: 241
  Estimated Percentage: .2906%
<number>
Notes: <number>

## Slide 4: True-Up Settlement
As of December 2, 2010
  Operating Date: June 5, 2010
  AMC ESI ID Totals: 912,564
  AMDG ESI ID Totals: 112
  Estimated Percentage: .2093%
<number>
Notes: <number>

## Slide 5: Why more AMS meters Installed than Settled?
For AMS installs some TDSPs have designed their process to allow time for all meters on the cycle to be installed and this will also allow time needed for those installed meters to synchronize with the TDSP’s AMS communications and back-end systems before these meter(s) can be accepted by the TDSP for invoicing and replacement of field operations for activities such as Switches, Move-Ins, Move-Outs, Reconnects and Disconnects for non-payment.
  In these events, changes to load profiles for a newly installed AMS meter may take 45-60 days following the AMS meter installation. In short, AMS settlement numbers are running about 2 months behind AMS installation numbers
<number>
Notes: <number>

## Slide 6: AMS Meter Installation Status Report
Oncor (approximately):
Installed: 1,459,563 as of 11.30.2010
    Deployment Plan:
      2010 – 929,000 meters
      2011 – 902,000 meters
      2012 – 902,000 meters
<number>
Notes: <number>

## Slide 7: AMS Meter Installation Status Report
CNP (approximately):
Installed: 789,857 as of 10.31.2010
  Deployment Plan, includes projected growth:
      2010 – 756,684 meters
      2011 – 960,327 meters
      2012 – 373,423 meters
<number>
Notes: <number>

## Slide 8: AMS Meter Installation Status Report
AEP (approximately):
Installed: 172,502 as of 11.30.2010
  Deployment Plan schedule:
      2010 – 188,212 meters
      2011 – 251,571 meters
      2012 – 279,329 meters
      2013 – 278,280 meters
<number>
Notes: <number>

## Slide 9: Market AMS Installed Totals
<number>
Notes: <number>

## Slide 10: PUCT Project 34610
Advanced Metering Implementation Team (AMIT) Documentation & Meeting Schedules can be found on:
Public Utility Commission of Texas Project 34610 Website:
      http://www.puc.state.tx.us/electric/projects/34610/34610.cfm
<number>
Notes: <number>

## Slide 11: AMIT’s New Working Groups
Operations and Maintenance Working Group (OMWG)
    http://www.puc.state.tx.us/electric/projects/34610/AMITMtg111610/WorkgroupScopeandProcedures-OperationsandMaintenance.pdf
Project and Strategy Working Group (PSWG)
    http://www.puc.state.tx.us/electric/projects/34610/AMITMtg111610/WorkgroupScopeandProcedures-ProjectsandStrategy.pdf
<number>

## Slide 12: AMIT’s New Working Groups
Registration, Administration and Access Working Group (RAAWG)
  http://www.puc.state.tx.us/electric/projects/34610/AMITMtg111610/WorkgroupScopeandProcedures-RegistrationAdminstrationandAccess.pdf
Security Working Group (SWG)
  http://www.puc.state.tx.us/electric/projects/34610/AMITMtg111610/WorkgroupScopeandProcedures-Security.pdf
<number>

## Slide 13: Advanced Metering Implementation Team (AMIT)
DECEMBER
  16th (F2F)
    Tue: 9:30 AM -12:00 PM
      AMIT Operations and Maintenance Working Group (OWG) Kick-Off meeting
        Location: ERCOT MET Center Austin
    WebEx and Conference Bridge will be provided for those wanting to attend via teleconference.
<number>
Notes: <number>

## Slide 14: Advanced Metering Implementation Team (AMIT)
DECEMBER
  20th (F2F)
    Tue: 1:00 PM -5:00 PM
      AMIT Registration, Administration, and Access (RAAWG) Working Group Kick-Off meeting
        Location: ERCOT MET Center Austin
    WebEx and Conference Bridge will be provided for those wanting to attend via teleconference
End of the Year – No more meetings until 2011
<number>
Notes: <number>

## Slide 15: Questions?
<number>
Notes: <number>