| SCR Number | 759 | SCR Title | acLineSegment Name Length Increase in Information Model Manager |
| --- | --- | --- | --- |
| Impact Analysis Date |  | December 5, 2010 |  |
| Cost/Budgetary Impact |  | A project will be required to implement System Change Request (SCR) 759. This project will be in the range $1.7 million – $2.2 million |  |
| Estimated Project Time Requirements* *Unless otherwise indicated, project time requirements begin upon project initiation. |  | Implementation of SCR759 will be completed in approximately 12-15 months of ERCOT Board approval. |  |
| ERCOT Staffing Impacts (across all areas) |  | No full time equivalents (FTEs) required. |  |
| ERCOT Computer System Impacts |  | Topology Processor, Information Model Manager (IMM), Energy Management System (EMS), Market Management System (MMS), Enterprise Information Services (EIS) |  |
| ERCOT Business Function Impacts |  | This SCR will affect many ERCOT Business processes as detailed below. |  |
| Grid Operations & Practices Impacts |  | No impact to grid operations and practices. |  |

Alternatives for a More Efficient Implementation (include explanation of impacts)

TSPs should continue to use the MOD to implement these changes. Implementation Cost = $0. Functionality is currently available.

Evaluation of Interim Solutions (e.g., manual workarounds)

Prior to the ERCOT Alternative being fully implemented, ERCOT will load standard Planning Model Change Requests (PMCRs) that were created during testing and will work with TSPs to resolve discrepancies. Requires 1 full time equivalent (FTE) for the period from Planning Go-Live through final implementation of the ERCOT Alternative. This FTE will load PMCRs for both SCR759 and SCR760. Planning Go-live date of April 2011 does not change.

Feasibility of Implementation

Impact on Resource Availability: Not yet assessed. Impact on Other Projects: Not yet assessed.

| Comments |  |  |
| --- | --- | --- |
| This change impacts both EMS and MMS core applications. The changes to EMS are not recommended by the vendor. Additional Note: There are currently 150 occurrences of this in the Planning Model. |  |  |
| Cost Estimates |  |  |
| REQUIREMENTS: Annual Planning Models will have multi-section line group records output from the Topology Processor similar to how they are defined in current planning cases. Seamless transition for planning studies and cases from zonal to Nodal environment. No work required of TSPs and ERCOT to redefine multi-section lines in planning cases. PROPOSED RESOLUTION: Increase the allowable character size of the acLineSegment type under the Line Equipment Container from two to 14 in the Information Model Manager. |  |  |
| ASSUMPTIONS: 1. Solution is to change Line Segment to 14 characters from 2 and maintain Line Container at its current 14 character length. |  |  |
| IMPACTS: |  |  |
| Impacts | Preliminary Cost Estimate |  |
| EMS: - Requires a change to the field length - Requires extensive database, code and display changes to support the new field length in: - Netmom - SCADA - Generation applications - DTS applications - Network applications | $850K - $1.13M |  |
| MMS: - Requires a change to the field length - Requires nominal database, code and display changes to support the new field length in: - MA application - DAM - DRUC, HRUC and WRUC | $100K - $130K |  |
| Network Modeling Group tool development for: - Information Model Manager script/validation rules - Project Tracking Coordinator - Macomber Map - Macomber Map Loader - RUC displays tool - CIM comparison tool - SR dataform convertor | $65K -- $80K |  |
| Data Warehouse: - Requires changes to replication for both EMS and MMS because of the schema changes. | $35K -- $45K |  |
| Testing: - Business and system testing to ensure changes are correct within each system - Full integration test to ensure all impacts are identified and resolved - Impacts: - EMS - MMS - NMMS - CRR - OS - EIP - VSAT, TSAT - CDR - MIS - S&B - COMS - EWS | $500K -- $650K |  |
| Release Management - Coordinated for multiple applications | $15K – 20K |  |
| Project Management | $130K -- $170K |  |
| TOTAL | $1.7M – $2.2M |  |