## Slide 1: Nodal Program Update
Technical Advisory Committee
6 December 2010

## Slide 2: Today’s Agenda
General Notes
Soft Launch Activities Review
  Review of Live Nodal Market - First 2 Days

## Slide 3: General Notes
ERCOT support on 24x7 rotation from 11/28 – 12/03
  ERCOT is now on heightened on-call support based on the initial stability of the Nodal Systems
Market Calls
  ERCOT will continue to conduct two daily calls (10:30 AM and 4:30 PM) until 12/7
  ERCOT will conduct daily calls (Monday thru Friday) until the end of the year

## Slide 4: Nodal Market is Live!
Date | Action | Comments
11/15/2010 – 11/29/2010 | ERCOT Initiates “Soft Launch” to Nodal Market Go-Live | ERCOT will run non-binding DAM, RUC daily per Nodal protocol timelines. RTM will remain Open Loop, but continue to publish base points and LMPs. Note that credit will be set high on 11/15
11/15/2010 | Credit posts ACLs and TPEs for non-binding DAM | For Operating Day 11/15 credit will be manually set to high limits
11/16/2010 | First Credit Operating Day 11/16/2010 | Credit reflects actual limits
11/17/2010 | Market now able to submit transactions for first Nodal Operating Day (T-14d) | 12/01/2010 Operating now available for Market submissions
11/23/2010 | QSEs with Resources required to submit 7 days of rolling COPs | 12/01/2010 required on 11/23/2010
11/28/2010 2:00 PM – 11/28/2010 3:00 PM | Generation and Frequency Control switched to Nodal systems for final LFC test | QSEs will begin following Nodal base points Settlements will continue to be Zonal
11/28/2010 2:00 PM – 11/30/2010 11:59:59 | QSEs remain on Nodal Control while settling Zonally during the LFC test | 
11/29/2010 | Last Non- Binding DAM for operating day 11/30/2010 | 
Soft Launch in Review – Effectively prepared ERCOT and the Market for a smooth transition to Nodal

## Slide 5: Cut-Over Monthly Outlook – December
MP Activities / Impacts
Daily Market Calls continue for issue facilitation
Settlement Calendar Extracts (See Emil for full list of postings)
MPs receive 1st Nodal Invoice for DAM and RTM via MIS
MPs can submit Disputes via MIS or API
Functional Area
Network Model
Settlements
Congestion Revenue Rights
Credit
Market Management System
May
June
July
Aug
Sept
Oct
Nov
Dec
Key Cut-Over Activities for December 2010
(12/01/10) Nodal Program: Nodal Go-Live (Operating Day 1)
(12/3/2010) Settlements: Nodal Day Ahead Market Statement & Invoice Available
(12/8/2010) Credit: Nodal Payment Due for OD12/01/2010
(12/9/2010) Credit: Nodal Payout for OD12/01/2010
(12/15/2010) Model: Network Model Load
(12/13/2010) Settlements: Nodal Real-Time Statement Available
(12/16/2010) Settlements: Nodal Real-Time Invoice Available
(12/27/2010) Credit: Nodal Payment Due for Real-Time Invoice 12/16/10
(12/28/2010) Credit: Nodal Payout for Real-Time Invoice 12/16/10

## Slide 6: Review of Live Nodal Market - First 2 Days DAM 12/1 & 12/2 Electricity Prices

## Slide 7: Review of Live Nodal Market - First 2 Days DAM 12/1 & 12/2 Schedule Summary
This is the net additional usage of transmission
capacity by CRR/PTPs.
This is the net additional usage of transmission capacity by CRR/PTPs.
7

## Slide 8: Review of Live Nodal Market - First 2 Days DAM 12/1 & 12/2 Electricity and Ancillary Service Prices
8

## Slide 9
Review of Live Nodal Market - First 2 Days RTM 12/1 & 12/2 Load Zone Prices
9

## Slide 10
Review of Live Nodal Market - First 2 Days RTM 12/1 & 12/2 Constraint Shadow Prices

## Slide 11
Review of Live Nodal Market - First 2 Days RTM 12/1 SPPs (LZ and HUBs RTM vs. DAM)

## Slide 12
Review of Live Nodal Market - First 2 Days RTM 12/2 SPPs (LZ and HUBs RTM vs. DAM)

## Slide 13
Review of Live Nodal Market - First 2 Days RTM HUB Average SPPs
12/1/2010
12/2/2010

## Slide 14
Review of Live Nodal Market - First 2 Days RTM 12/2 HUB Average SPPs
Operating Day 12/01
  Executed DRUC in 8 minutes
  1 total resource commitments
Operation Day 12/02
  Executed DRUC in 8 minutes
  Executed 24 HRUCs in an average of 10.3 minutes
  5 total Resource commitments

## Slide 15
QUESTIONS