## Slide 1: Project Portfolio Update
Cagle Lowe
Director Business Integration (Interim)
Technical Advisory Committee
6 December 2010

## Slide 2: ERCOT Project Portfolio Delivery Timeline

## Slide 3: Nodal Stabilization Project
Scope
  Evaluate and remediate ERCOT Nodal Operational Issues including higher than normal: production outages, issue analysis, software defect remediation, stakeholder support, and request for information volumes
Objectives
  Maintain Nodal Operational Stability during the first months of System Operations
Duration
  7-month period, running 12/1/2010 – 6/30/2011
Current Status
  Hot patches continue to be migrated to production as issues are identified that cannot wait to be migrated in a scheduled release
  Issue triage process transitioning to Operations teams
Risks / Issues
  Issue volumes are higher than expected
  Complexity of issues is greater than expected
  System design changes are implemented before systems are fully stabilized

## Slide 4: Data Center Migration Project
Scope
  Replace data center hardware that is approaching end of life and migrate hardware to new Taylor and Bastrop data centers.
Objectives
  Reduce level of risk of hardware failure and resulting impact on critical business functions.
Current Status
  Procurement of hardware to begin December 6 for late 2010/early 2011 delivery.
  Migration schedule 90% complete for Q1 and Q2 2011.
  Resource plans 90% complete for Q1 and Q2 2011.
Duration
  27-month period, running October 2009 through December 2011.
Risks / Issues
  Resource availability and delivery timelines may be impacted by Stabilization efforts

## Slide 5: Planning Model Project
Scope
  Build Annual Planning Models from the NMMS Database also used to build Network Operations Model and models for the Market.
Objectives
  Attain much higher level of consistency between Operations and Planning models than experienced in the past.
Current Status
  Testing the Topology Processor and Model On Demand applications to retrieve data from NMMS Database to finished Planning model. Go-Live date set for April 1, 2011.
Duration
  5-month period, running 12/01/2010 – 4/01/2011
Risks / Issues
  TSP concerns about the amount of data that they need to add to Topology Processor output in Model On Demand to create satisfactory Planning model.

## Slide 6: Deferred Defects Project
Scope
  Evaluate and remediate the priority 3 defects that were deferred from the Nodal Project
Objectives
  Continue to improve the operational efficiency of the Nodal Applications and reduce the impact of workarounds for both ERCOT and Market Participants
Current Status
  Defect release bundles and estimates have been defined for delivery in 2011
  1st release mainly isolated to the individual application
Duration
  10-month period, running 12/1/2010 – 9/30/2011
Risks / Issues
  Resource availability and delivery timelines may be impacted by Stabilization efforts

## Slide 7: Summary of Defects by Target Delivery
Nodal Systems went live beginning Operating Day 12/1 with all Critical defects resolved and 29 Priority defects remaining. There were also 958 lower priority defects to be reviewed and resolved.
The focus now is on stabilization. As vendor and ERCOT resources are available, defects will be addressed in scheduled releases.

## Slide 8: Priority 1&2 Defects – Target To Be Resolved by 12/2010

## Slide 9: Lower Priority Defects (3, 4, 5)
NOTE: After NMMS went live last summer, deferred defects were only being tracked in the Siemens defect system, not in the Nodal project system. During the review of defects that were being bundled for future releases the differences between the Siemens defect system and EROCT system was discovered.

## Slide 10: Defects Breakdown by Priority and severity level (as of 12-03-10)

## Slide 11: Prioritization Timeline
Nodal Stabilization
December 2010
  Begin review of prioritized list with stakeholder groups
February 2011
  Seek approval from market subcommittees
March 2011
  Seek TAC/Board approval of initial prioritized list
Note: This is an aggressive timeline. If stabilization resource constraints arise that limit ERCOT’s ability to get an initial prioritization complete in December/January there will be a one month delay in the approval dates.
Dec 2010
Jan 2011
Feb 2011
Mar 2011
Initial Prioritization Process
TAC Consideration
Board Consideration
Apr 2011
Ongoing Prioritization Process
Impact Assessment of Parking Deck Items

## Slide 12: Project Approval & Prioritization Processes
ERCOT Assessment & Prioritization
60 days
Subcommittee
Review & Approval
PRS
TAC
Board of Directors
Parking Deck
Market Rules Processing
5 Business Days
Subcommittee
Language Consideration
PRS
Impact Analysis Review
TAC
Board of Directors
System Change Request
(SCR)
ERCOT Business Integration Processing
21 Day Comment Period
Impact Analysis
Analysis Period Varies Depending on subcommittee
Market Rules Processing
5 Business Days
PRS
Language Consideration
PRS
Impact Analysis Review
TAC
Board of Directors
Nodal Protocol Revision Request
(NPRR)
ERCOT Business Integration Processing
21 Day Comment Period
Impact Analysis
30 Day Analysis Period