## TX SET V4.0 Requirements
Change Control Number | Requested Priority | Implemented in Version | Description | Trans Set(s) | Requestor | Company | Date Requested | Disposition by Texas Standard Electronic Transactions | Market Testing Required? (Y/N) | Testing Flight # (Required when Testing is Required) | Approved Production Implementation date
2007-706 | N | Version 4.0 | Remove the EM Communicaton Number Qualifier from the 814_24 | 814_24 | Catherine Meiners | ERCOT | 2007-04-25 | Approved 3/28/07 change control | N
2008-718 | N | Version 4.0 | Change to ERCOT logic to use receipt of an 814_04 on a Move In in order to determine if the Move Out should be cancelled. | 814_24 | Kathy Scott | Centerpoint | 2008-02-14 | Approved 5/22/08 change control | N
2008-720 | N | Version 4.0 | Add code A78 "Item or Service already Established (Requested action has already completed)" as a valid reject reason to the 814_29. | 814_29 | Kathryn Thurman | ERCOT | 2008-04-15 | Approved 5/22/08 change control | Y
2008-722 | N | Version 4.0 | IG currently requires Originating Tran ID and Estimated Restoration Date whenever purpose code = "79". It is actually only required when purpose code = 79 AND Suspension/Reactivation code = RC001. Causing false rejection of a 650_04 Reactivate after disconnect for denial of access when Originating Transaction ID and Estimated Restoration Date is not also included. | 650_04 | Kathy Scott | Centerpoint | 2008-04-17 | Approved 10/12/10 Change Control Call | Y
2010-733 | N | Version 4.0 | Discontinue use of the following transactions submitted to ERCOT by a CR 814_07, 814_09, 814_13, 814_15, 814_19, 814_21, 814_23, & 814_29. | 814_07, 814_09, 814_10, 814_13, 814_15, 814_19, 814_21, 814_23, 814_29 | Kathryn Thurman | ERCOT | 2010-06-01 | Approved 10/12/10 Change Control Call | N
2010-734 | N | Version 4.0 | New REF Segment to the 814_20 with Switch Hold Add and Removal and new Reason for Change added to REF~TD segment to support Meter Tampering Rulemaking | 814_20 | Kathy Scott | Centerpoint | 2010-06-17 | Approved 10/12/10 Change Control Call | Y
2010-735 | N | Version 4.0 | In order to support Meter Tampering, in the event of a Mass Transition, the POLR CR will be notified that an ESI ID had a Switch Hold Prior to the Mass Transition. | 814_04, 814_20 | Kathy Scott | Centerpoint | 2010-06-17 | Approved 10/12/10 Change Control Call | Y
2010-736 | N | Version 4.0 | In order to reject a Move In or Switch which currently has a Switch Hold, a new reject code of SHF will be added to the appropriate transactions. | 814_04, 814_05 | Kathy Scott | Centerpoint | 2010-06-17 | Approved 10/12/10 Change Control Call | Y
2010-737 | N | Version 4.0 | In order to support the Meter Tampering Rulemaking, changes were added to the 650_01 and 650_02 to communicate Switch Hold Disconnect and Reconnect | 650_01, 650_02 | Kathy Scott | Centerpoint | 2010-06-28 | Approved 10/12/10 Change Control Call | N
2010-738 | N | Version 4.0 | New Critical Care status designations are required when Critical Care = Y and additional Contact information is required for certain Critical Care status. | 814_04, 814_05, 814_14, 814_22 | Kathy Scott | Centerpoint | 2010-06-28 | Approved 10/12/10 Change Control Call | Y
2010-739 | N | Version 4.0 | Changes are required to the 814_PC in order for the TDSPs to receive customer contact information for power outages and service restoration. | 814_PC | Kathy Scott | Centerpoint | 2010-06-28 | Approved 10/12/10 Change Control Call | Y
2010-740 | N | Version 4.0 | If the 814_27 is received with REF~1P~HUU (Status Reason) HISTORICAL USAGE UNAVAILABLE, ERCOT should close the Business Process Instance (BPI) and the 867_02 transaction should not be expected by the CR or ERCOT | 814_04, 814_05, 814_27 | Kathy Scott | Centerpoint | 2010-04-06 | Approved 10/12/10 Change Control Call | N
2010-741 | N | Version 4.0 | Adding a priority code to the 814_24 to allow for same day requests to be processed at a different level from standard Move Outs. | 814_24, 814_03 | Jennifer Frederick | Direct Energy | 2010-08-12 | Approved 10/12/10 Change Control Call | TBD
2010-742 | N | Version 4.0 | Addition of new reject code ACR - Acquisition Cancel Reject to be used when a CR submits an 814_08 on a Acquisition | 814_09 | Kathryn Thurman | ERCOT | 2010-08-13 | Approved 10/12/10 Change Control Call | Y
2010-743 | N | Version 4.0 | Addition of new reject code CW1 for use when a CR submits an 814_08 or 814_12 within 1 day of Scheduled Meter Read | 814_09, 814_13 | Kathryn Thurman | ERCOT | 2010-08-13 | Approved 10/12/10 Change Control Call | N
2010-745 | N | Version 4.0 | Add the ability for a TDSP to Complete Unexecutable a Switch | 814_28, 814_29 | Kathy Scott | Centerpoint | 2010-08-23 | Approved 10/12/10 Change Control Call | Y
2010-746 | N | Version 4.0 | TX SET Guide changes by transaction required to support Acquisition Transfer | 814_03, 814_04, 814_08, 814_09, 814_11, 814_14 | Kathryn Thurman | ERCOT | 2010-09-15 | Approved 10/12/10 Change Control Call | Y
2010-747 | N | Version 4.0 | In order to provide REPs information on whether an ESI ID has a provisioned Advanced Meter installed at the premise, a new REF segment will be added to the 814_04, 814_05, 814_14, 814_22 and 814_20. | 814_04, 814_05, 814_14, 814_22 and 814_20 | Jennifer Frederick | Direct Energy | 2010-09-21 | Approved 10/12/10 Change Control Call | Y
2010-748 | N | Version 4.0 | The purpose of this Change Control is to sync the names of the Texas SET Guide transactions, with the names of the transactions in Protocol and the Retail Market Guide. | 824, 650_02, 650_04, 650_05, 810_02, 810_03, 814_01, 814_02, 814_03, 814_04, 814_05, 814_06, 814_08, 814_09, 814_18, 814_19, 814_20, 814_21, 814_22, 814_26, 814_27, 814_29, 820_02, 820_03, 867_03, 867_04, T0, T1, T2, T3, T4 | Kathryn Thurman | ERCOT | 2010-09-22 | Approved 10/12/10 Change Control Call | N
2010-749 | N | Version 4.0 | Explanation of the 2 options for the REF~IK segment in the 810_03 transaction. | 810_03 | Chris Duncan | Nueces | 2010-09-22 | Approved 10/12/10 Change Control Call | Y
2010-751 | N | Version 4.0 | Adding new codes Force Majeure Event (FME) and Weather Moratorium (WTM) | 650_02, 814_04, 814_05, 814_13, 814_14, 814_23, 814_25, and 814_28 | Kathy Scott | Centerpoint | 2010-08-31 | Approved 10/12/10 Change Control Call | Y
2010-752 | N | Version 4.0 | Remove incorrect link for locating ISO country codes from TX SET implementation Guides. | 814_01, 814_10, 814_14, 814_16, 814_24 and 814_PC | Kathryn Thurman | ERCOT | 2010-09-30 | Approved 10/12/10 Change Control Call | N
2010-753 | N | Version 4.0 | Create a new code in both the 650_01 and 650_02 transactions that will allow a CR to notify a TDSP when a customer has installed some type of generation equipment at the premise | 650_01, 650_02 | Kathy Scott | Centerpoint | 2010-10-01 | Approved 10/12/10 Change Control Call | Y
2010-754 | Y | Version 4.0 | Add a new code to allow a CR to notify a TDSP when a customer has an Electric Vehicle as an end-use device at a premise. | 650_01, 650_02 | Ed Echols | Oncor | 2010-10-13 | Approved 10/21/10 Change Control Call | N
2010-755 | Y | Version 4.0 | In order for the TDSP to send discretionary charges due to tampering a new type code should be added to the 810_02. | 810_02 | Jonathan Landry | Gexa Energy | 2010-10-14 | Approved 10/21/10 Change Control Call | Y
2010-756 | Y | Version 4.0 | Cleanup after 3.0A to have off-cycle updated to reflect self selected | 814_03, 814_04, 814_05 & 814_11 | Kathryn Thurman | ERCOT | 2010-10-15 | Approved 10/21/10 Change Control Call | N
2010-757 | Y | Version 4.0 | Missed 814_20 transaction left out on CC 738 - New Critical Care status designations are required when Critical Care = Y and additional Contact information is required for certain Critical Care status. | 814_20 | Diana Rehfeldt | Texas-New Mexico Power | 2010-10-18 | Approved 10/21/10 Change Control Call | Y
2010-758 | Y | Version 4.0 | Proposes changes to MIMO rules (Solution to Stacking), which would allow the TDSP to reject an 814_08 cancel with cancel codes of A81, MPC and MOX. | 814_08 and 814_09 | Jane Eyanson | AEP | 2010-10-19 | Approved on 11/08/10 Change Control Call | Y
2010-759 | Y | Version 4.0 | Add a new REF segment to the 814_16 to provide key information to the TDSP about a condition that may affect the execution of a MVI, MVO or MVO to CSA. | 814_16, 814_03 and 814_24 | Johnny Robertson | TXU Energy | 2010-10-19 | Approved 10/28/10 Change Control Call | Y
2010-760 | Y | Version 4.0 | Add a new code in the ESIID attributes to specify LED bulb types for Unmetered Service type. | 814_04, 814_05, 814_14, 814_20 814_22 and 867_03 | Ed Echols | Oncor | 2010-10-21 | Approved 10/28/10 Change Control Call | N
2010-761 | Y | Version 4.0 | Add to the existing REF02 of the REF~PRT segment the "WF" code to represent Wi-Fi (Wireless Fidelity). | 814_04, 814_05, 814_14, 814_20 814_22 and 867_03 | Kathy Scott | Centerpoint | 2010-10-25 | Approved 10/28/10 Change Control Call | N
2010-762 | Y | Version 4.0 | Discontinue use of the 650_05 response transaction that doesn’t provide or require a response by the TDSP once received. | 650_05 | Kathy Scott | Centerpoint | 2010-10-26 | Approved 10/28/10 Change Control Call | N
2010-764 | Y | Version 4.0 | Add an expiration date to the Special Needs designation to allow CRs to audit these designations and ask TDSPs for clarification of whether a status has been removed if the expiration date has passed without receiving an update. | 814_04, 814_05, 814_14, 814_20, & 814_22 | Jennifer Fredrick | Direct Energy | 2010-10-27 | Approved 10/28/10 Change Control Call | Y
2010-765 | Y | Version 4.0 | The final rule language for Critical Care adopted the concept that TDSPs are required to provide notice to REPs when a Customer's ESIID is placed on Temporary Status for either Critical Care Residential or Chronic Care Residential. Adding 2 additional codes for the temporary Critical Care status | 814_04, 814_05, 814_14, 814_20 and 814_22 | Ed Echols | Oncor | 2010-11-01 | Approved 11/08/10 Change Control Call | N
2010-766 | Y | Version 4.0 | In order to provide codes that are more specific than "Other" with a text explanation, TX SET shall add a new code T023 to the REF~G7 for Move Out treated as a force off due to Move In scheduled for same date. | 814_28 | Kathy Scott | Centerpoint | 2010-10-28 | Approved 11/08/10 Change Control Call | Y
2010-767 | Y | Version 4.0 | In order to accommodate the reason for change when updating the expiration date for special needs customers add the REF02 code of the DTM036 to the REF~TD of the LIN loop. | 814_20 | Diana Rehfeldt | Texas-New Mexico Power | 2010-11-01 | Approved 11/08/10 Change Control Call | Y
2010-768 | N | Version 4.0 | Added clarifying language to gray box that was approved in CC 2010-735 to know which Switch Hold is required to be notified to the gaining POLR CR in a Mass Transistion according to the Tampering Rule | 814_04 and 814_14 | Kathy Scott | Centerpoint | 2010-11-19 | Recommended for RMS Approval 12/06/10 Change Control Call
2010-769 | N | Version 4.0 | Added clarifying language to CC 2010-737 to show the Switch Hold Add and Switch Hold Remove codes are only for Deferred Bill Payment Switch Holds that are applied by the TDSP at the request of the ROR | 650_01 and 650_02 | Kathy Scott | Centerpoint | 2010-11-19 | Recommended for RMS Approval 12/06/10 Change Control Call
2010-770 | Y | Version 4.0 | Add new code T024 to the REF~G7 segment in 814_28 for Switch or Move_in cannot be completed due to Switch Hold recently applied to this ESI ID | 814_28 | Kathy Scott | Centerpoint | 2010-11-19 | Recommended for RMS Approval 12/06/10 Change Control Call