|  |  |  |  | System Planning Division |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report to Reliability and Operations Subcommittee for November 2010 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
| Item |  |  |  |  |  |  |  |  |
| 1. | - ERCOT is currently tracking 194 active generation interconnection requests totaling over 65,000 MW. This includes almost 39,000 MW of wind generation. |  |  |  |  |  |  |  |
| 2. | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $51.1 Million - Transmission Projects endorsed in 2010 total $268.8 Million - All projects (in engineering, routing, licensing and construction) total approximately $9.4 Billion - Transmission Projects energized in 2010 total about $791.7 million |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	New Generation Registering for Commercial Operations	1

1.2	Publicly Disclosed Generation Interconnection Projects	4

1.3	Generation Projects Undergoing Full Interconnection Studies (not otherwise public)	6

1.4	Wind Generation	7

Wind Capacity Installed by Year	7

2.	Regional Planning Group Project Reviews	9

3.	Congestion Costs	10

4.	Wind Generation as a Percent of Load	16

5.	Other Notable Activities	17

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## New Generation Registering for Commercial Operations

## None

The total installed wind capacity is 9,467 MW, of which 7,958 MW (84%) is located within the Western Congestion Management Zone.

Summary of Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |  |  |  |  |
| --- | --- | --- | --- | --- |
| Currently tracking 194 active generation interconnection or change requests |  |  |  |  |
| As of November 30, 2010 | North | South | West | Total |
| Security Screening Study | 0 | 2 | 9 | 11 |
| SSS Completed | 2 | 3 | 11 | 16 |
| Full Interconnect Study | 19 | 13 | 93 | 125 |
| FIS Completed | 4 | 15 | 4 | 23 |
| Interconnect Agreement Completed | 8 | 6 | 5 | 19 |
| Capacity under Interconnection Agreements | 5,192 | 3,742 | 756 | 9,690 |
| Capacity for Grid, MW | 19,200 | 13,144 | 33,194 | 65,538 |
| Wind Capacity, MW | 3,907 | 4,491 | 30,243 | 38,641 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Projects w/ Interconnect Agreement/Public Letter (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- |
| Gas-CC |  |  | 5,352 | 12,054 |
| Gas-CT |  |  |  | 639 |
| Total Gas | 11 | 7,330 | 5,352 | 12,693 |
| Nuclear |  |  | 5,900 | 5,900 |
| Coal |  | 1,740 | 3,210 | 4,950 |
| Wind | 3,295 | 29,293 | 6,053 | 38,641 |
| Solar | 360 | 819 |  | 1,179 |
| Biomass |  | 50 | 145 | 195 |
| Other |  | 740 | 1,240 | 1,980 |
| Grand Total | 3,666 | 39,972 | 21,900 | 65,538 |

## Publicly Disclosed Generation Interconnection Projects

The table below summarizes the publicly disclosed generation projects for the ERCOT region.

(Status: IA=Interconnect Agreement, PL=Public Letter, XX= cancelled)

| Generation Interconnections as of November 30, 2010 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR | SiteName | Status | County | Region | COD | Fuel Type |  | MW For Grid | Change from Last Report |
| 08INR0033 | Lufkin | IA | Angelina | North | Dec-10 |  | Biomass | 45 |  |
| 12INR0003 | Throckmorton Wind Farm | PL | Throckmorton | West | Dec-10 |  | Wind | 400 |  |
| 05INR0015b | Gulf Wind 2 | PL | Kenedy | South | Jan-11 |  | Wind | 400 |  |
| 05INR0015c | Gulf Wind 3 | PL | Kenedy | South | Jan-11 |  | Wind | 400 |  |
| 08INR0065 | Buffalo Gap 4 and 5 | PL | Nolan | West | Mar-11 |  | Wind | 465 |  |
| 09INR0029 | CFB Power Plant Units 11&12 | IA | Calhoun | South | Mar-11 |  | Coal | 260 |  |
| 10INR0010 | Jack County 2 | IA | Jack | North | Jun-11 |  | Gas-CC | 620 |  |
| 08INR0011 | Senate Wind Project | IA | Jack | North | Nov-11 |  | Wind | 150 |  |
| 08INR0038 | M Bar Wind | PL | Andrews | West | Dec-11 |  | Wind | 194 |  |
| 09INR0034 | Gatesville Wind Farm | PL | Coryell | North | Dec-11 |  | Wind | 200 |  |
| 08INR0025 | Pistol Hill Energy Center | PL | Ector | West | Dec-11 |  | Wind | 300 |  |
| 06INR0012b | Sherbino Mesa Wind Farm 2 | IA | Pecos | West | Jan-12 |  | Wind | 150 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Feb-12 |  | Coal | 925 |  |
| 08INR0062 | Archer-Young | IA | Young | West | Mar-12 |  | Wind | 250 |  |
| 11INR0084 | 2W Whatley Phase 1 | PL | Ector | West | Mar-12 |  | Wind | 45 |  |
| 09INR0007 | Nacogdoches Project | IA | Nacogdoches | North | Apr-12 |  | Biomass | 100 |  |
| 07INR0004 | Pampa Energy Center | PL | Gray | West | May-12 |  | Coal | 165 |  |
| 09INR0024 | B&B Panhandle Wind | PL | Carson | West | Jun-12 |  | Wind | 1001 |  |
| 09INR0037 | Scurry County Wind III | PL | Scurry | West | Jun-12 |  | Wind | 350 |  |
| 12INR0004 | Fort Concho Wind Farm | PL | Tom Green | West | Jul-12 |  | Wind | 400 |  |
| 12INR0043 | 2W Whatley Phase 2 | PL | Ector | West | Aug-12 |  | Wind | 290 |  |
| 09INR0036 | McAdoo Energy Center II | PL | Dickens | West | Dec-12 |  | Wind | 500 |  |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Dec-12 |  | Wind | 120 |  |
| 06INR0022c | Penascal Wind Farm 3 | IA | Kenedy | South | Dec-12 |  | Wind | 202 |  |
| 10INR0020a | Panda Temple Power | IA | Bell | North | Feb-14 |  | Gas-CC | 780 | Date |
| 06INR0006 | Cobisa-Greenville | IA | Hunt | North | May-14 |  | Gas-CC | 1792 |  |
| 10INR0022 | Pondera King Power Project | IA | Harris | South | Jun-14 |  | Gas-CC | 1380 |  |
| 04INR0011b | Cedar Elm | IA | Shackelford | West | Jun-14 |  | Wind | 136 |  |
| 04INR0011c | Cottonwood Wind | IA | Shackelford | West | Jun-14 |  | Wind | 100 |  |
| 14INR0005 | White Stallion Energy Center | PL | Matagorda | South | Jul-14 |  | Coal | 1200 |  |
| 14INR0002 | Coleto Creek Unit 2 | IA | Goliad | South | Nov-14 |  | Coal | 660 | Date |
| 10INR0020b | Panda Temple Power | IA | Bell | North | Jan-16 |  | Gas-CC | 780 | Date |
| 12INR0016a | Las Brisas Energy Center | IA | Nueces | South | Jun-15 |  | Other | 620 |  |
| 12INR0016b | Las Brisas Energy Center | IA | Nueces | South | Jun-16 |  | Other | 620 |  |
| 15INR0008 | STP 3 and 4 | PL | Matagorda | South | Jun-16 |  | Nuclear | 2700 |  |
| 15INR0002 | Comanche Peak 3 and 4 | PL | Somervel | North | Dec-18 |  | Nuclear | 3200 |  |
|  |  |  |  |  |  |  | TOTAL | 21,900 |  |

County Location of Installed Generation and Interconnection Requests (all fuels)

## Generation Projects Undergoing Full Interconnection Studies (not otherwise public)

| INR | County | Capacity | COD | Fuel |  | INR | County | Capacity | COD | Fuel |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 09INR0061 | Kent | 258 | TBD | Wind |  | 09INR0054 | Stonewall | 149 | TBD | Wind |
| 10INR0048 | Hardeman | 1,000 | TBD | Wind |  | 10INR0079 | Nolan | 60 | TBD | Wind |
| 10INR0054 | Palo Pinto | 36 | TBD | Wind |  | 10INR0016 | Childress | 150 | TBD | Wind |
| 10INR0029 | Hood | 810 | TBD | Gas |  | 10INR0052a | Knox | 21 | TBD | Wind |
| 10INR0013 | Upton | 400 | TBD | Wind |  | 09INR0074 | Motley | 70 | TBD | Wind |
| 10INR0041 | Floyd | 135 | TBD | Wind |  | 11INR0029 | Throckmorton | 200 | TBD | Wind |
| 10INR0082 | Travis | 30 | TBD | Solar |  | 10INR0080 | Presidio | 144 | TBD | Solar |
| 10INR0077 | Callahan | 101 | TBD | Wind |  | 10INR0060 | Willacy | 401 | TBD | Wind |
| 10INR0056 | Borden | 249 | TBD | Wind |  | 10INR0051 | Brazoria | 200 | TBD | Wind |
| 10INR0042 | Mason | 170 | TBD | Wind |  | 10INR0033 | Armstrong | 399 | TBD | Wind |
| 10INR0032 | Navarro | 775 | TBD | Gas |  | 10INR0019 | Deaf Smith | 609 | TBD | Wind |
| 10INR0008 | Pecos | 500 | TBD | Wind |  | 07INR0035 | Tom Green | 270 | TBD | Wind |
| 07INR0015 | Foard | 180 | TBD | Wind |  | 07INR0013 | Coke | 200 | TBD | Wind |
| 11INR0076 | Archer | 94 | Jan-11 | Wind |  | 11INR0088 | Brazos | 45 | Mar-11 | Gas |
| 11INR0082A | Val Verde | 50 | Mar-11 | Wind |  | 11INR0083A | Crockett | 50 | Mar-11 | Wind |
| 11INR0081 | Live Oak | 72 | Mar-11 | Wind |  | 11INR0050 | Crosby | 149 | Mar-11 | Wind |
| 11INR0086 | Travis | 60 | Apr-11 | Solar |  | 11INR0075 | Fort Bend | 15 | Apr-11 | Coal |
| 11INR0071 | Harris | 7 | Apr-11 | Gas |  | 11INR0062 | Nueces | 149 | May-11 | Wind |
| 11INR0058 | Pecos | 135 | May-11 | Solar |  | 11INR0060 | Tom Green | 90 | May-11 | Solar |
| 11INR0061 | Presidio | 90 | May-11 | Solar |  | 11INR0037 | Smith | 50 | May-11 | Biomass |
| 10INR0009 | Castro | 300 | May-11 | Wind |  | 11INR0033a | Cameron | 200 | May-11 | Wind |
| 11INR0033b | Cameron | 200 | May-11 | Wind |  | 11INR0091 | Webb | 92 | Jun-11 | Wind |
| 10INR0089 | Harris | 40 | Jun-11 | Other |  | 11INR0065 | Nueces | 240 | Jun-11 | Wind |
| 11INR0057 | Cameron | 165 | Jun-11 | Wind |  | 11INR0054 | San Patricio | 161 | Jun-11 | Wind |
| 10INR0057 | Taylor | 200 | Jun-11 | Wind |  | 11INR0019 | Upton | 200 | Jun-11 | Wind |
| 10INR0023 | Haskell | 386 | Jun-11 | Wind |  | 09INR0050 | Fannin | 1,200 | Jun-11 | Gas |
| 08INR0020 | Eastland | 200 | Jun-11 | Wind |  | 11INR0006 | Lamar | 579 | Jul-11 | Gas |
| 11INR0040 | freestone | 640 | Aug-11 | Gas |  | 11INR0079a | Clay | 200 | Sep-11 | Wind |
| 11INR0047 | Deaf Smith | 600 | Sep-11 | Wind |  | 11INR0039 | Starr | 201 | Sep-11 | Wind |
| 10INR0081b | Clay | 19 | Oct-11 | Wind |  | 10INR0062a | Pecos | 80 | Oct-11 | Wind |
| 07INR0014b | Wilbarger | 70 | Oct-11 | Wind |  | 07INR0014a | Wilbarger | 140 | Oct-11 | Wind |
| 11INR0094 | Kent | 100 | Nov-11 | Solar |  | 11INR0090 | Howard | 60 | Nov-11 | Solar |
| 10INR0021 | Grayson | 646 | Nov-11 | Gas |  | 11INR0089 | Hays | 20 | Dec-11 | Solar |
| 12INR0034 | Borden | 342 | Dec-11 | Wind |  | 11INR0070 | Reeves | 50 | Dec-11 | Solar |
| 11INR0067 | Cameron | 78 | Dec-11 | Wind |  | 11INR0043 | Coke | 300 | Dec-11 | Wind |
| 11INR0025 | Crockett | 400 | Dec-11 | Wind |  | 11INR0013 | Mills | 150 | Dec-11 | Wind |
| 08INR0049 | Clay | 50 | Dec-11 | Wind |  | 11INR0005 | Upton | 500 | Dec-11 | Wind |
| 09INR0075 | Kinney | 248 | Dec-11 | Wind |  | 09INR0048 | Jack | 150 | Dec-11 | Wind |
| 10INR0085 | Ector | 40 | Jan-12 | Solar |  | 12INR0033 | Motley | 150 | Jan-12 | Wind |
| 12INR0021 | Edwards | 165 | Jan-12 | Wind |  | 12INR0042 | Deaf Smith | 400 | Mar-12 | Wind |
| 10INR0018 | Madison | 550 | Mar-12 | Gas |  | 10INR0081a | Clay | 30 | May-12 | Wind |
| 11INR0049 | Wharton | 275 | May-12 | gas |  | 12INR0007 | Lamar | 296 | May-12 | Gas |
| 09INR0031 | Ector | 275 | May-12 | Gas |  | 12INR0053 | Crockett | 615 | Jun-12 | Wind |
| 12INR0006 | Limestone | 875 | Jun-12 | Coal |  | 08INR0031 | Childress | 100 | Jun-12 | Wind |
| 12INR0026 | Randall | 400 | Oct-12 | Wind |  | 08INR0041 | Coke | 200 | Oct-12 | Wind |
| 12INR0035 | Nueces | 249 | Nov-12 | Wind |  | 08INR0044 | Concho | 200 | Nov-12 | Wind |
| 12INR0022 | Hidalgo | 200 | Dec-12 | Wind |  | 12INR0005 | Floyd | 1,100 | Dec-12 | Wind |
| 08INR0054 | Comanche | 401 | Dec-12 | Wind |  | 09INR0025 | Concho | 180 | Dec-12 | Wind |
| 08INR0042 | Coke | 200 | Dec-12 | Wind |  | 12INR0029 | Swisher | 500 | Dec-12 | Wind |
| 12INR0027 | Gray | 200 | Jan-13 | Wind |  | 10INR0024 | Briscoe | 2,940 | Jan-13 | Wind |
| 11INR0082B | Val Verde | 150 | Mar-13 | Wind |  | 11INR0083B | Crockett | 100 | Mar-13 | Wind |
| 09INR0058 | Howard | 250 | Mar-13 | Wind |  | 12INR0018 | Gray | 500 | Apr-13 | Wind |
| 13INR0020a | Glasscock | 200 | May-13 | Wind |  | 10INR0062b | Pecos | 220 | May-13 | Wind |
| 09INR0051 | Borden | 249 | Jun-13 | Wind |  | 09INR0041 | Mitchell | 300 | Jun-13 | Wind |
| 13INR0023 | Ector | 240 | Jul-13 | Gas |  | 13INR0016 | Deaf Smith | 251 | Aug-13 | Wind |
| 13INR0005 | Carson | 600 | Oct-13 | Wind |  | 13INR0004 | Deaf Smith | 500 | Oct-13 | Wind |
| 13INR0028 | Hale | 392 | Nov-13 | Gas |  | 13INR0017 | Childress | 200 | Dec-13 | Wind |
| 13INR0007 | Pecos | 200 | Dec-13 | Wind |  | 09INR0077 | Reagan | 500 | Dec-13 | Wind |
| 12INR0002a | Briscoe | 200 | Dec-13 | Wind |  | 13INR0010 | Parmer | 1,200 | Dec-13 | Wind |
| 09INR0073 | Scurry | 200 | Dec-13 | Wind |  | 13INR0006 | Gray | 750 | Jan-14 | Wind |
| 08INR0019a | Gray | 250 | Jan-14 | Wind |  | 08INR0019b | Gray | 250 | Jan-14 | Wind |
| 08INR0019c | Gray | 250 | Jan-14 | Wind |  | 13INR0020b | Glasscock | 150 | May-14 | Wind |
| 10INR0015 | Mitchell | 350 | May-14 | Wind |  | 14INR0003 | Nolan | 850 | Jun-14 | Coal |
| 13INR0021 | Llano | 600 | Dec-14 | Gas |  | 14INR0001 | Pecos | 500 | Dec-14 | Wind |
| 12INR0002b | Briscoe | 200 | Dec-14 | Wind |  | 12INR0002c | Briscoe | 350 | Dec-15 | Wind |
| 16INR0002 | Brazoria | 700 | Jun-17 | Other |  |  |  |  |  |  |

## Wind Generation

## Wind Capacity Installed by Year

County Location of Installed Capacity and Interconnection Requests (Wind only)

# Regional Planning Group Project Reviews

- Oncor submitted a project to relieve congestion related to new wind units in the Lamesa area.  The project consists of several 138 kV line upgrades in the Lamesa area and includes the creation of a new 345/ 138 kV substation.  The revised cost estimate of this project is $38.4 M.  The ERCOT Independent Review of this project has been completed.

- Pattern Energy has submitted a project to construct an HVDC tie with a capacity of up to 3000 MW between ERCOT and SERC.  This project has exited Regional Planning Group review at this time and is currently following the revised process for evaluating projects related to asynchronous ties.

- Brazos Electric Cooperative has submitted a project to move some load that is currently being served by the Entergy Texas system into the ERCOT system.  The project would involve disconnecting the subject load from the Entergy Texas system, constructing a new 345/ 138 kV substation in ERCOT, upgrading an existing 69 kV line in the ERCOT system and constructing two new 138 kV lines to serve the load from the ERCOT system.  The estimated cost of this project is $51.1 M.  The project is currently in study mode.

# Congestion Costs

Dollars shown in graphs are settlement quality.

OOMC – last 13 months in million$

OOM Down – last 13 months in million$

Local Balancing Energy Down – last 13 months in million$

OOM Up – last 13 months in million$

Local Balancing Energy Up – last 13 months in million$

Replacement Reserve – last 13 months in thousand$

Average MCPE

Binding Constraints & Capacity Shortages– September, 2010

| Contingency | Binding Element | Estimated Costs | Transmission Project | Clearance |
| --- | --- | --- | --- | --- |
| Roanoke Switch - West Denton - Lewisville Switch 345kV | West Denton - Ft Worth 138kV | $ 1,127,996 | Roanoke Tap to West Denton 345kV CREZ Circuit [10TPIT0133] | High W_N flow |
| Austrop - Sandow 345kV | Round Rock - Round Rock Northeast 138kV | $ 563,652861 | Hutto Switch - Round Rock NE - Round Rock 138 kV line [08TPIT0009] | High N-S zonal transfer Outage: Gabriel-Jarrell East |
| Santa Anna - Ballinger 138kV | Ballinger - Humble 69kV | $ 450,097 | Ballinger to Steamboat, Rebuild portions of 69 kV line [12TPIT0070] | Outage on Putnam 138 kV, 69 kV operating bus |
|  | Low Voltage - Valley | $ 235,763 |  | Forced outage on Ajo-Rio Hondo 345kV |
| Greens Bayou - Gable & Hardy - Crockett 138kV | Garrott - Midtown 138kV | $ 160,897 | Upgrade 138 kV underground Ckt. 90 Garrott to Midtown to Polk [11TPIT0072] | High Load and Insufficient generation in East Houston |
| Oklaunion - Fisher Road - Bowman 345kV | Bomarton TU - Baylor County Tap 69kV | $ 158,528 |  | Olney - Westover PCAP |
| Sandow Switch - Austrop 345kV | Hutto - Round Rock Southeast 138kV | $ 132,036 | Hutto Switch - Round Rock NE - Round Rock 138 kV line [08TPIT0009] | High N-S zonal transfer Outage: Gabriel-Jarrell East |
|  | Houston area planned transmission outages | $ 111,894 |  |  |
|  | Capacity Shortage | $ 84,824 |  |  |
| Graham - Parker 345kV | Leon Switch - Flat Creek 138kV | $ 53,264 |  | Outage: Willow Creek Switch- Parker Switch 345kV & Graham SES - Jacksboro Switching 345KV |

Inter-zonal Congestion

# Wind Generation as a Percent of Load

One-hour average Settlement quality data shown.

# Planning Model Activities

- ERCOT and SSWG continued work to create a 2010 planning case by adding generation, load, and voltage profiles to the Topology Processor output in Model On Demand (MOD).  Three passes have been completed for the 2010 case.  The case solves if islands are disconnected and generator MVar limits are ignored.  TSPs have not completed adding standard PMCRs in MOD that would provide additional reactive capability.

- Work will begin on the 2012 case using PSSE version 32 format starting Dec. 3, 2010.  All standard PMCR’s will be applied to this case and the case will be completed using PMCR’s to model transmission projects expected to by complete by July 1, 2012.  This case will be compared to the current DSB 2012SUM1 case completed in Nov. 2010.  The projected schedule is as follows:

  - Dec. 3 – ERCOT creates Topology Processor case and loads into MOD

  - Dec. 17 – TSPs submit Pass 1 PMCR’s (standard PMCR’s only)

  - Jan. 7 -  TSPs submit Pass 2 PMCR’s (standard PMCR’s and future project PMCR’s)

  - Jan. 21 - TSPs submit Pass 3 PMCR’s (standard PMCR’s and future project PMCR’s)

# Other Notable Activities

- Work on the 2010 Five-Year Transmission Plan is wrapping up.  The set of projects needed to reliably serve load in 2011 through 2015 has been identified and comments have been received.  The analysis is currently focused on projects to relieve congestion for 2011 through 2015.

- A draft process for evaluating projects related to new or upgraded asynchronous ties has been completed.  This process will be incorporated into the new Planning Guides in 2011.

- ABB has completed the CREZ Reactive Study.  This study was conducted to optimize the reactive support equipment required to implement the CREZ plan.  A final report will be available to market participants by mid-November.

- Work on the Long-Term System Assessment/DOE Study is ongoing.

- Transient Stability Study for 2011 Winter off-peak conditions: As part of the annual reliability assessment of the network, a transient stability study study is been performed on an ERCOT 2011 Winter off-peak case.