## 2011
No. | PWG 2011 Goals | Target Date | Complete
1 | LPGRR042 Annual Validation for AMS change (plus) IA and Comments | TBD | 0%
2 | LPGRR043 DG Profile implementation (NPRR208 gray box) | TBD | 0%
3 | Protocol Requirement Review 2010 UFE Analysis | 2011-04-30 | 0%
4 | 2010 Annual Validation. | 2011-11-01 | 0%
5 | LPGRR changes as needed | 2011-12-06 | 0%

## 2010
No. | PWG 2010 Goals | Target Date | Complete
1 | Review 2009 UFE Analysis (April 30, true-up in Aug) | 2010-08-31 | 100%
2 | 2009 Annual Validation. | 2010-11-01 | 90%
3 | Evaluate language changes for Annual Validation Process due to AMS (NPRR250) | 2010-12-02 | 100%
4 | Review Weather Sensitivity Correlation and Proxy Day Method in lieu of AMS | 2010-12-03 | Post Nodal
5 | Review of LPG concerning the future of Load Profiles, forecasted NIDR profiles, Business ID assignment, review of LPGRR Chapter 15 in conjuction with PUCT Load Research Rule in lieu of AMS metering. | 2010-12-04 | Post Nodal
6 | LPGRR per NOIE DRG PRR (NPRR208 gray box) | 2010-12-05 | 90%
7 | LPGRR changes as needed | 2010-12-06 | 90%
8 | Round 2 load research sample recalibration of ERCOT Load Profiles | 2010-12-07 | 100%
Changed with update in following slides
Post Nodal Postponed
Complete

## 2009
No. | PWG 2009 Goals | Target Date | % Complete
7 | IDR Analysis – 2 issues outstanding from original analysis. | 2009-04-30 | 100%
11 | Evaluate the methodology for profile scaling factors (per UFETF Nov. 16, 2007) | 2009-06-30 | 100%
16 | The shift in proportion of UFE to NIDR metered premises as AMS matures | 2009-07-18 | 100%
1 | Review 2008 UFE Analysis (April 30, true-up in Aug or Sept) | 2009-08-23 | 100%
15 | UFE allocation factors in lieu of AMS meter installations | 2009-08-23 | 100%
10 | Reevaluate distribution loss methodology due to advanced metering. | 2009-09-01 | 100%
17 | Distribution loss factors in relation to UFE | 2009-09-02 | 100%
2 | 2009 Annual Validation. | 2009-11-01 | 100% | Chg
14 | Evaluate language changes for Annual Validation Process due to AMS | 2009-10-01 | 80% | Chg
4 | Review Weather Sensitivity Correlation | 2009-12-01 | 0%
5 | Review Proxy Day Method | 2009-12-01 | 0%
12 | Update Long Term Strategy of Load Profiles including refreshed timeline | 2009-12-02 | 5%
6 | Evaluate Hurricane Ike affect on settlement for possible improvements | 2009-12-09 | 10%
3 | LPGRR language Chapter 15 for consistency with PUCT Load Research Rule | 2009-12-31 | 5%
8 | Review profile models using Round 2 load research data, review if having more weather stations adds accuracy, and review if the weighting of weather stations is appropriate. | 2009-12-31 | 0%
9 | Improve Business Profile ID assignment process (pending AMS Metering) | 2009-12-31 | 0%
13 | Demand Response LPG or PRR language changes as needed | 2009-12-31 | 0%
Complete
NEW
Carry over to 2010
Combined