## Slide 1
Business Integration Update to PRS
Troy Anderson
ERCOT
Enterprise Project Portfolio Management
December 16, 2010

## Slide 2: Business Integration Update – Agenda
  2010 Project Spending Update 3
    As of 12/15/2010
  Nodal Parking Deck 4-9
    As of 12/15/2010
  Project Implementations 10-11
    November 2010
  2011 Prioritization of Nodal Work 12
    Status

## Slide 3: 2010 Project Spending Update – 12/15/2010
Program Area | Initial Budget | Current Budget | Forecast | YTD Actual
CO | $ 1,150,000 | $ 1,150,000 | $ 965,778 | $ 634,643
IO | $ 1,450,000 | $ 765,000 | $ 812,333 | $ 722,039
MO | $ 1,500,000 | $ 1,297,649 | $ 1,148,131 | $ 709,708
RO | $ 1,900,000 | $ 1,892,118 | $ 1,420,068 | $ 1,300,178
SO | $ 150,000 | $ 144,068 | $ 100,801 | $ 81,601
Minor Cap | $ 750,000 | $ 1,435,000 | $ 1,435,000 | $ 1,049,805
Released but Not Yet Reallocated | $ 0 | $ 5,932 | $ 0 | $ 0
Subtotals | $ 6,900,000 | $ 6,689,767 | $ 5,882,111 | $ 4,497,974
Met Center Replacement | $ 31,900,000 | $ 37,600,000 | $ 32,565,590 | $ 32,217,891
Data Center Hardware | $ 7,500,000 | $ 26,500,000 | $ 25,467,215 | $ 7,384,316
Grand Totals | $ 46,300,000 | $ 70,789,767 | $ 63,914,916 | $ 44,100,181
* $685k from IO to Minor Cap for software licenses ** $400k from Met Center to DC Hardware for telecom equip.
*** Includes Board-authorized carryover of $5.9M in unspent 2009 funds
***
**
**
*
*
****
**** Includes Board-authorized acceleration of $18.315M from projected 2011 funds
Actuals as of 10/31/2010

## Slide 4: Nodal Parking Deck – Approved
Source | Title | Priority | Approval Date
NPRR208 | Registration and Settlement of Distributed Generation (DG) Less Than One MW | Critical | BoD Approved 7/20/2010
NPRR219 | Resolution of Alignment Items A33,A92,A106,A150 - TSPs Must Submit Outages for Resource Owned Equipment & Clarification of Changes in Status of Transmission Element Postings | Critical | BoD Approved 10/19/2010
NPRR285 | Generation Resource Base Point Deviation Charge Corrections | Critical | BoD Approved 11/16/2010
NOGRR050 | Resolution of Reporting Issues Related to NPRR219 | Critical | BoD Approved 10/19/2010
SCR756 | Enhancements to the MarkeTrak Application | Critical | BoD Approved 7/20/2010
NPRR131 | Ancillary Service Trades with ERCOT | High | BoD Approved 1/19/2010
NPRR146 | ICCP Telemetry Information Submittals | High | BoD Approved 6/15/2010
NPRR181 | FIP Definition Revision | High | BoD Approved 1/19/2010
NPRR207 | Unit Deselection | High | BoD Approved 7/20/2010
NPRR210 | Wind Forecasting Change to P50, Synch PRR841 | High | BoD Approved 6/15/2010
NPRR222 | Half-Hour Start Unit RUC Clawback | High | BoD Approved 7/20/2010
Total Approved = 25
µ
µ
On Parking Deck due to resource impact only. Separately funded on 2011 PPL.
page 1 of 3

## Slide 5: Nodal Parking Deck – Approved
Source | Title | Priority | Approval Date
NPRR251 | Sync of PRR845, Definition for IDR Meters and Optional Removal of IDR Meters at a Premise Where an Advanced Meter Can be Provisioned | High | BoD Approved 9/21/2010
NPRR272 | Definition and Participation of Quick Start Generation Resources | High | BoD Approved 11/16/2010
NPRR293 | Requirement to Post CRR Option and Obligation Quantities Cleared in DAM or Taken to Real Time | High | BoD Approved 12/14/2010
SCR759 | acLineSegment Name Length Increase in Information Model Manager | High | BoD Approved 9/21/2010
NPRR240 | Proxy Energy Offer Curve | High / Medium | BoD Approved 9/21/2010
NPRR244 | Clarification of Other Binding Documents | High / Medium | BoD Approved 10/19/2010
NPRR257 | Synchronization with Nodal Operating Guide Section 9, Monitoring Programs | High / Medium | BoD Approved 11/16/2010
NPRR258 | Sync with PRR824 and PRR833 and Additional Clarifications | High / Medium | BoD Approved 11/16/2010
page 2 of 3

## Slide 6: Nodal Parking Deck – Approved
Source | Title | Priority | Approval Date
NPRR153 | Generation Resource Fixed Quantity Block Offer | Medium | BoD Approved 1/19/2010
NPRR164 | Resubmitting Ancillary Service offers in SASM | Medium | BoD Approved 1/19/2010
NPRR241 | Aggregate Incremental Liability (AIL) Calculation and Credit Reports Publish Corrections | Medium | BoD Approved 9/21/2010
NPRR256 | Sync Nodal Protocols with PRR787, Add Non-Compliance Language to QSE Performance Standards | Medium | BoD Approved 11/16/2010
NOGRR034 | Rescind Telemetry Performance Calculation Exclusions | Medium | BoD Approved 9/21/2010
SCR755 | ERCOT.com Website Enhancements | Medium | BoD Approved 2/16/2010
page 3 of 3

## Slide 7: Nodal Parking Deck – Pending
Source | Title | Suggested Priority | Current Status
NPRR260 | Providing Access to MIS Secure Area to MIS Registered Users | Medium | Pending at Board TAC Approved 12/6/2010
NPRR282 | Dynamic Ramp Rates Use in SCED | Critical | Pending at Board TAC Approved 12/6/2010
NPRR290 | ERCOT Publication of DAM PSS/E Files | TBD | Pending at PRS
SCR760 | Recommended Changes Needed for Information Model Manager and Topology Processor for Planning Models | Critical | Pending at TAC PRS Approved 11/22/2010
Total Pending = 4

## Slide 8: Nodal Parking Deck – Additional Items for Consideration
Title | Current Status / Description
NMMS API | Functionality to be considered for post-go-live development
CRR API | Functionality to be considered for post-go-live development
MMS Multiple Network Models | Functionality to be considered for post-go-live development
Add PSS Status to RARF | Automation of manual process as a result of NPRR156
Automated Default Uplift Invoice | Automation of manual process as a result of NPRR221
EILS Enhancements | Automation of manual processes
Load Participation in SCED | Functionality to be considered for post-go-live development Demand Side Working Group (DSWG) currently looking into the feasibility of demand response being economically dispatched by SCED
EMS Upgrade | Upgrade EMS system from v2.3 to v2.5/v2.6
Deferred Defects | Defects not addressed prior to go-live Approximately 800 deferred defects as of October 2010 Review underway to confirm issues and confirm acceptable workarounds
Potomac Economics Market Assessment | Items not addressed prior to Nodal go-live
TSP / QSE / DAM Issue Lists | Items not addressed prior to Nodal go-live
Total “Other” = 19

## Slide 9: Nodal Parking Deck – Additional Items for Consideration
Title | Current Status / Description
Large Wind Power Production Ramp Forecasting Phase 2 | Phase 2 of the project that built a display for ERCOT operators to indicate periods of time within the next 6 hours during which there is a high risk for a large wind power production ramp to occur
TML Transition to MIS | After go-live, most applications that are currently available through TML will migrate to MIS and will only be accessible to Market Participants through the MIS portal. RMS has requested that Zonal Reports, Find ESI ID, Find Transactions, and Transaction submission be accessed through TML until MIS has had sufficient time to stabilize.
Decommission of Zonal Wholesale | After go-live, certain ERCOT systems and components that were only applicable to zonal wholesale operations will need to be decommissioned. This effort includes Nodal cutover cleanup (removal of pre-go-live data from the following Nodal systems : Lodestar, ISM, MIR, EIP, Siebel, and MIS.)
Move Price Validation Tool (PVT) to a Server Application | Functionality to be considered for post-go-live development
Update Credit PFE Model (Potential Future Exposure) | Enhance PFE model to include the following risk factors: • Price volatility analysis for the Day Ahead Market, • Bid and offer volume analysis in the Day Ahead Market, and • Value of Congestion Revenue Rights
Automate Identification of PUNs for Reporting | NPRR202 required that Private Use Networks (PUNs) be excluded from State Estimator postings of transmission flows and voltages. This requirement is being met by adding a static table to the reporting infrastructure to store the list of known PUNs. This Parking Deck item would create a method to dynamically derive the population of PUNs for this reporting.
MOTE for Outage Scheduler | The Nodal MOTE does not include providing an environment for Outage Scheduler. Without this environment, MPs will be unable to test their code when ERCOT makes changes to web services. Similarly, MPs who decide to use web services for the first time will not have a test environment to test their outage transactions with ERCOT.
RARF HUB Replication to ISM | Data replication to support information needed for use by IMM/PUCT

## Slide 10: YTD 2010 Project Implementations
January 2010 – None
February 2010
  CO PR-80047_02 DAM Control Center
  IO PR-90009_01 Infrastructure Monitoring Enhancement (Remedy Phase 3)
March 2010
  RO PR-90024_01 POLR Rule and Expedited Switch
      POLR Rule portion
      Expedited Switch delivered in August 2009
  SO PR-90002_01 Large Wind Power Production Ramp Forecasting
April 2010
  RO PR-90011_01 AMS Meter Flag
  RO PR-50088_01 Data Research and Reporting (Phase 1)
  SO PR-50029_01 Improvements to VSA/DSA Phase II
  CO PR-60029_01 Enterprise Records Management Framework
May 2010 – None
June 2010
  IO PR-90010_01 Monitoring & Reporting Tools
  MO PR-90006_01 Information Lifecycle Management (Phase 1)
Months represent project go-live dates, not project completion dates

## Slide 11: YTD 2010 Project Implementations
July / August 2010
  None
September 2010
  IO PR-80001_01 Met Center Disposition
October 2010
  DC PR-10016_02 Network Gear (Phase 2)
  CO PR-10028_01 Physical Security project
November 2010
  None planned
December 2010 (projected)
  DC PR-10015_01 Telcom Equipment (Phase 1)
  DC PR-10016_01 Network Gear (Phase 1)
  IO PR-10018_01 Annual Storage Growth
Months represent project go-live dates, not project completion dates

## Slide 12: 2011 Project Prioritization – Prioritization of 2011 Nodal Work
Prioritization of deferred Nodal work is underway
  ERCOT has begun impact assessment on many of the Board-approved Parking Deck items
  Subcommittees have been briefed on the approach and will be visited in January and February to review and discuss priorities
    Beginning with COPS on 1/11/2011
  Subcommittee endorsement will be requested in February
    Including PRS
  TAC and Board approval targeted for March
  These dates are 1 month later than originally communicated
    More time is needed to complete the recommended ERCOT prioritization