## Prioritized List
Priority | Rank | Current Status | Source Document | Description | Sort Char | Release Year | Systems Impacted | Target Release | Source | IA Phase | Estimated Cost | Estimated Effort | Estimated Duration | Work-arounds | Funding Source | Submitter | Submission Date | Actual Implementation Date | Prioritization Source | Additional Information
1 - Critical | 1 | Board Approved | NPRR208 | Registration and Settlement of Distributed Generation (DG) Less Than One MW | 7 | 2011 | S&B / Data Agg | Deferred Defects - G7 - Sept 11 | Parking Deck | 1 | $5k-$10k | 80-160 hours | 6 months |  | Parking Deck | NOIE DRG TF | 2010-01-25 |  |  | Revises the formula for Settlement of electricity consumption and out-flow by Customers with renewable Distributed Generation (DG). The revised formula fulfills the provisions of PUC RULE 25.213 that requires ERCOT to develop DG Settlement processes that “reflect the time of generation.” In order to fully synchronize the Protocols with the intent of the Rule as soon as practicable, ERCOT supports implementation of the grey-boxed language in NPRR208 as a “Critical” priority.
1 - Critical | 2 | Board Approved | NPRR285 | Generation Resource Base Point Deviation Charge Corrections | 4 | 2011 | COMS, MMS, Integration, EMS, Reg, CSI | Deferred Defects - G4 - Jun 11 | Parking Deck | 1 | $30k-$40k | 4-8 weeks | 3 months |  | Parking Deck | WMS | 2010-10-13 |  |  | Various greyboxes relating to Generation Resource Base Point Deviation Charge
1 - Critical | 3 | Board Approved | NPRR219 | Resolution of Alignment Items A33,A92,A106,A150 - TSPs Must Submit Outages for Resource Owned Equipment & Clarification of Changes in Status of Transmission Element Postings | 11 | TBD | Outage Scheduler, NMMS, Integration, Siebel, EIS, EWS, RARF | N/A | Parking Deck | 1 | $565k-$750k | 3,850-5,010 hours | 12-15 months | ERCOT staff entering data on behalf of MPs |  | ERCOT Staff | 2010-03-24 |  |  | Implement system change to allow Resources to submit Outages for Resource-owned transmission equipment
1 - Critical | 4 | Board Approved | NOGRR050 | Resolution of Reporting Issues Related to NPRR219 | 11 | TBD | Outage Scheduler, MIS, NMMS | N/A | Parking Deck | 1 | [5 empty] | CenterPoint Energy | 2010-08-12 |  |  | Grey-boxes several transmission Outage scheduling data elements from ERCOT reports until such time ERCOT systems can be modified to include only Transmission Service Provider’s (TSP’s) Outages in the reports
1 - Critical | 5 | Pending at Board | NPRR282 | Dynamic Ramp Rates Use in SCED | 99 | TBD | EMS, MMS | TBD | Parking Deck | [6 empty] | Calpine | 2010-09-28 |  |  | Proposes revisions that are intended to result in more reasonable Dispatch of Generation Resources when a telemetered Base Point requires the Resource to employ technologies that in turn change the Resource’s ramp rate.
1 - Critical | 6 | Tabled at TAC | SCR760 | Recommended Changes Needed for Information Model Manager and Topology Processor for Planning Models | 99 | TBD | NMMS | TBD | Parking Deck | 1 | $2.1M-$2.7M |  | 24-30 months | TBD |  | SSWG | 2010-11-04 |  |  | Proposes 8 changes to the Information Model Manager and Topology Processor
1 - Critical | 7 | Board Approved | SCR756 | Enhancements to the MarkeTrak Application | 99 | 2012 | MarkeTrak | TBD | Parking Deck |  | $200k-$250k (Planning) |  |  | Multiple ERCOT workarounds in place |  | RMS | 2009-05-06 |  |  | Enhance MarkeTrak application for new PUCT requirements and other enhancements requested by market participants. 8 specific issue areas identified - Examples: new subtypes for Expedited Switch Rescission and Meter Tampering, improved data validation, AMS usage parameters.
2 - High | 1 | Board Approved | NPRR293 | Requirement to Post CRR Option and Obligation Quantities Cleared in DAM or Taken to Real Time | 3 | 2011 | MMS, CDR, MIS | Deferred Defects - G3 - May 11 | Parking Deck | 1 | $12k-$15k | 175-195 hours | 2 months | ERCOT posting daily report until automated | Parking Deck | Luminant | 2010-11-04 |  |  | Adds language to specify the need for ERCOT to post the hourly energy bought and sold in the DAM at each Settlement Point for each hour in the Operating Day
2 - High | 2 | Board Approved | NPRR251 | Sync of PRR845, Definition for IDR Meters and Optional Removal of IDR Meters at a Premise Where an Advanced Meter Can be Provisioned | 99 | TBD | Lodestar, EIS | TBD | Parking Deck | 1 | [5 empty] | RMWG | 2010-07-08 |  |  | Grey-boxes language requiring IDR meters if usage warrants. Current language exempts situations where Advanced Meters have been installed. Also gray-boxes related reporting requirements for ERCOT.
2 - High | 3 | Board Approved | SCR759 | acLineSegment Name Length Increase in Information Model Manager | 99 | TBD | NMMS, MMS, CRR, EMS, OS | TBD | Parking Deck | 1 | $1M |  | 8-10 months |  |  | SSWG | 2010-05-27 |  |  | Increases the character size of the acLineSegment type under the Line Equipment Container from 2 to 14 in the IMM. Allows modeling of multi-section line segments. Not a major impact to IMM but cascading impacts to CRR and MMS Desire expressed at ROS to have this implemented for Planning Go-Live (~March 2011)
2 - High | 4 | Board Approved | NPRR181 | FIP Definition Revision | 99 | 2013+ | MMS, COMS, Integration | TBD | Parking Deck | [6 empty] | Luminant | 2009-06-10 |  |  | Revises the definition of Fuel Index Price (FIP) to correctly account for the timing difference between ERCOT’s application of FIP in its systems (midnight to midnight) and the timing of natural gas prices reflected by the index (i.e., hour ending 1000 to 0900).
2 - High | 4 | Board Approved | NPRR210 | Wind Forecasting Change to P50, Synch PRR841 | 99 | 2012 | COMS | TBD | Parking Deck | [6 empty] | Morgan Stanley | 2010-02-09 |  |  | Changes the wind forecast from the 80% probability to 50%. This change is also effective in determining if a QSE is capacity short. The boxed language changes the capacity short calculation back to the 80% forecast.
2 - High | 4 | Board Approved | NPRR272 | Definition and Participation of Quick Start Generation Resources | 99 | 2012 | COMS, CSI, Siebel | TBD | Parking Deck |  |  |  |  | Operations, Client Services, Settlements |  | ERCOT Staff | 2010-09-16 |  |  | Provides language for effective participation of Quick Start Generation Resources (QSGRs) in SCED
2 - High | 5 | Board Approved | NPRR131 | Ancillary Service Trades with ERCOT | 9 | 2012 | MMS, COMS, CSI | Release 2.0 | Parking Deck | [6 empty] | NRG Texas | 2008-05-15 |  |  | Allows QSEs representing resources to procure A/S in the DAM
2 - High | 5 | Board Approved | NPRR146 | ICCP Telemetry Information Submittals | 9 | 2012 | Business Process, NMMS | Release 2.0 | Parking Deck | [6 empty] | AEP | 2008-07-31 |  |  | Allows NOMCRs that modify only ICCP data object names to be submitted within 15 days of the network model load date Possible resolution with business process changes
2 - High | 5 | Board Approved | NPRR207 | Unit Deselection | 9 | 2012 | COMS, MMS | Release 2.0 | Parking Deck | [6 empty] | QSTF | 2010-01-22 |  |  | Defers two changes: 1 – hourly RUC notification of recommended but deselected resources in RUC 2 – prevent QSEs from increasing Energy Offer Curves after a RUC Notification
2 - High | 5 | Board Approved | NPRR222 | Half-Hour Start Unit RUC Clawback | 9 | 2012 | COMS | Release 2.0 | Parking Deck | [6 empty] | WMS | 2010-04-09 |  |  | Removed from original NPRR207 language. Removes RUC clawback on Half-Hour Start Units in certain circumstances. Also changes the RUC Clawback on Half-Hour Start Units that did not participate in the DAM to 50%.
3 - High / Medium |  | Board Approved | NPRR244 | Clarification of Other Binding Documents | 8 | Various | None | Standalone Project | Parking Deck | [6 empty] | ERCOT Staff | 2010-06-03 |  |  | Internal review project needed to avoid posting confidential or vendor proprietary information
3 - High / Medium |  | Board Approved | NPRR240 | Proxy Energy Offer Curve | 9 | 2012 |  | Release 2.0 | Parking Deck | [6 empty] | IMM | 2010-05-26 |  |  | One grey-box section: “Energy Offer Curves that were constructed in whole or in part with proxy Energy Offer Curves shall be so marked in all ERCOT postings or references to the energy offer.”
3 - High / Medium |  | Board Approved | NPRR257 | Synchronization with Nodal Operating Guide Section 9, Monitoring Programs | 99 | Various |  | TBD | Parking Deck | [6 empty] | ERCOT Staff | 2010-07-23 |  |  | Greyboxes multiple sections to align with Nodal Operating Guide Section 9, Monitoring Programs
3 - High / Medium |  | Board Approved | NPRR258 | Sync with PRR824 and PRR833 and Additional Clarifications | 99 | 2012 | EMS, EIS | TBD | Parking Deck | [6 empty] | PDCWG | 2010-07-23 |  |  | Grey-boxes language to change the calculation of GREDP PDCWG suggests priority of “critical”
4 - Medium |  | Board Approved | NPRR164 | Resubmitting Ancillary Service offers in SASM | 9 | 2012 | MMS, EIP, EDW, CDR | Release 2.0 | Parking Deck | [6 empty] | TPTF | 2008-11-11 |  |  | Allows QSEs to take full advantage of A/S and energy co-optimization in the DAM and participate in the Supplemental Ancillary Service Market (SASM) by being able to resubmit A/S Offers at the higher of DAM MCPC or its offer price in the DAM.
4 - Medium |  | Board Approved | SCR755 | ERCOT.com Website Enhancements | 9 | 2012 |  | Release 2.0 | Parking Deck | [6 empty] | CCWG | 2009-02-25 |  |  | Implementation of 10 improvements to ERCOT.com received in the 2008 Market Participant Survey. Includes document archiving, search improvements, training, meeting calendar enhancements, and RSS feeds.
4 - Medium |  | Board Approved | NPRR153 | Generation Resource Fixed Quantity Block Offer | 10 | TBD | MMS, EIP, EDW, CDR | Future Release | Parking Deck | [6 empty] | TPTF | 2008-09-12 |  |  | Allows a fixed quantity and time block bid for Offline Non-Spin with the contingency that all hours be purchased in the block
4 - Medium |  | Board Approved | NOGRR034 | Rescind Telemetry Performance Calculation Exclusions | 99 | TBD |  | TBD | Parking Deck | [6 empty] | ERCOT Staff | 2010-01-22 |  |  | Grey-boxes language that allows QSE and TSPs to request removal of telemetry from Telemetry Standard performance metrics when certain situations exist.
4 - Medium |  | Board Approved | NPRR241 | Aggregate Incremental Liability (AIL) Calculation and Credit Reports Publish Corrections | 99 | TBD |  | TBD | Parking Deck | [6 empty] | ERCOT Staff | 2010-05-27 |  |  | One grey-box section: Changes the alternate posting format for 3 reports from XLS to XML (in addition to PDF).
4 - Medium |  | Board Approved | NPRR256 | Sync Nodal Protocols with PRR787, Add Non-Compliance Language to QSE Performance Standards | 99 | TBD | EMS, EDW | TBD | Parking Deck | [6 empty] | Luminant | 2010-07-15 |  |  | Seeks to exempt generation resources from GREDP calculation during testing and qualification periods. Not really a sync because additional exemptions to GREDP (Generation Resource Energy Deployment Performance) calculation are included
4 - Medium |  | Pending at Board | NPRR260 | Providing Access to MIS Secure Area to MIS Registered Users | 99 | TBD | Siebel, MPIM | TBD | Parking Deck | [6 empty] | Crescent Power | 2010-08-05 |  |  | Makes it possible for consultants, power marketers, aggregators, consumers and universities to get access to the MIS Secure area (without doing so by getting a digital certificate through a registered Market Participant)
TBD | 1 | Pending at Board | NPRR302 | Correct Fuel Type Language for Mitigated Offer Cap | 2 | 2011 | MMS | Deferred Defects - G2 - Mar 11 | Post-Go-Live | 1 | <$5k | 40 hours | 2 weeks |  | PPL | Morgan Stanley | 2010-12-07 |  |  | Revises the language for the Mitigated Offer Cap to eliminate use of the FOP in the calculation
TBD | 2 | Pending at PRS | NPRR303 | Requirement to Post PTP Options Cleared in DAM or Taken to Real-Time | 99 | TBD |  | TBD | Post-Go-Live | 1 | $12k-$15k |  | 3-4 weeks |  |  | Luminant | 2010-12-16 |  |  | Adds language to specify the need for ERCOT to post quantities of Point-to-Point (PTP) Options and PTP Options with Refund that were not cleared in the Day-Ahead Market (DAM) and taken to Real-Time for Settlement
TBD | 3 | Pending at PRS | NPRR290 | ERCOT Publication of DAM PSS/E Files | 99 | TBD | DAM | TBD | Parking Deck | 1 | [5 empty] | Luminant | 2010-10-28 |  |  | Requires ERCOT to publish certain data files (in Power System Simulator for Engineering (PSS/E format) for easy review by all Market Participants with standard power flow tools such as PTI PSS/E, Power World Simulator, etc.
TBD | 4 | Board Approved | NPRR221 | Automated Default Uplift Invoice | 99 | TBD | COMS | TBD | Parking Deck | 1 |  |  |  | If default occurs, manual process |  | ERCOT Staff | 2010-03-30 |  |  | Automation of manual process as a result of NPRR221
TBD | 5 |  |  | Ancillary Service Deliverability | 99 | TBD |  | TBD | Potomac Market Assessment | [6 empty] | Potomac Economics |  |  |  | Short term - Monitor and manage in the control room through HRUC and operator analysis and direct QSEs as necessary to other resources when issues occur. Medium term – Review procurement history and identify problems. Long term – Potential real time optimization with deliverability check. If needed.
TBD | 5 |  |  | CRR Derating | 99 | TBD |  | TBD | Potomac Market Assessment | [6 empty] | Potomac Economics |  |  |  | Monitor CRR deratings in DAM During Market Trials CRR market appeared to be undersubscribed
TBD | 5 |  |  | DAM Transmission Constraints Shadow Price Caps | 99 | TBD |  | TBD | Potomac Market Assessment | [6 empty] | Potomac Economics |  |  |  | Do not bind on constraints that do not have generation dispatch solutions (i.e. radial pockets). Do not bind on constraints with mitigation plans.
TBD | 5 |  |  | Intermittent Renewable Resource curtailment flag from SCED | 99 | TBD |  | TBD | Potomac Market Assessment | [6 empty] | Potomac Economics |  |  |  | Monitor the curtailments and performance and review the need for a curtailment flag post go live.
TBD | 5 |  |  | Load Zone Modeling/Pricing | 99 | TBD |  | TBD | Potomac Market Assessment | [6 empty] | Potomac Economics |  |  |  | Radial load pocket code and Static LDFs .
TBD | 5 |  |  | PTP Options in DAM (Computational) | 99 | TBD |  | TBD | Potomac Market Assessment | [6 empty] | Potomac Economics |  |  |  | Tested PTP options in Dam trials. Install new hardware.
TBD | 5 |  |  | RUC and RUC clawback | 99 | TBD |  | TBD | Potomac Market Assessment | [6 empty] | Potomac Economics |  |  |  | Monitor volumes (i.e. number of RUC units and determine whether units are participating in the DAM market and/or self scheduling
TBD | 5 |  |  | Scarcity Pricing | 99 | TBD |  | TBD | Potomac Market Assessment | [6 empty] | Potomac Economics |  |  |  | Monitor prices and behavior along with planning reserves, and new interconnect agreements . Continue to track the peaker net margin.
TBD | 5 |  |  | SCED and two step mitigation | 99 | TBD |  | TBD | Potomac Market Assessment | [6 empty] | Potomac Economics |  |  |  | This issue is somewhat linked to scarcity pricing and we will utilize some of the same monitoring that is planned for the scarcity concern.
TBD | 5 |  |  | Settlement at shadow Prices | 99 | TBD |  | TBD | Potomac Market Assessment | [6 empty] | Potomac Economics |  |  |  | Monitor during market cutover, create graphs and determine whether or not this is occurring with a frequency that justifies a make whole payment NPRR proposal.
TBD | 8 |  |  | Incremental Data Loading Capability | 99 | TBD |  | TBD | Post-Go-Live | [6 empty] | W. Rickerson | 2010-12-09 |  |  | Currently model data is loaded into the EMS/MMS as full model loads. The process of which is time consuming due to the volume of data carried with each model. 99% of the data is not changed with each model load, but additional time is spend in exporting, transferring, processing, and importing this data into receiving systems. The ability of EMS and MMS to accept CIM based incremental updates would greatly reduce the overhead of this processing time.
TBD | 8 |  |  | Resource Data Submission Application | 99 | TBD |  | TBD | Post-Go-Live | [6 empty] | W. Rickerson | 2010-12-09 |  |  | The goal of this project is to create a web-based application that will be used by Resource Entities to submit, view, and update model related to resource assets that they own and/or operate. This application will decouple the Resource Asset Registration Form process currently used and create a process that is focused only on model data. Essentially separating the financial information from the physical model information, allowing for a stream lined process.
TBD |  |  |  | CRR API | 9 | 2012 | CRR | Release 2.0 | Parking Deck | [6 empty] | TPTF |  |  |  | Functionality to be considered for post-go-live development
TBD |  |  |  | Large Wind Power Production Ramp Forecasting Phase 2 | 9 | 2012 |  | Release 2.0 | Parking Deck | [6 empty] | ERCOT Staff |  |  |  | Phase 2 of the project that built a display for ERCOT operators to indicate periods of time within the next 6 hours during which there is a high risk for a large wind power production ramp to occur
TBD |  | NPRR Required |  | MMS Multiple Network Models | 9 | 2012 | MMS | Release 2.0 | Parking Deck | [6 empty] | TPTF |  |  |  | Functionality to be considered for post-go-live development
TBD |  |  |  | Move Price Validation Tool (PVT) to a Server Application | 9 | 2012 | PVT | Release 2.0 | Parking Deck | [6 empty] | ERCOT Staff |  |  |  | Functionality to be considered for post-go-live development
TBD |  |  |  | NMMS API | 9 | 2012 | NMMS | Release 2.0 | Parking Deck | [6 empty] | TPTF |  |  |  | Functionality to be considered for post-go-live development
TBD |  |  |  | Update Credit PFE Model (Potential Future Exposure) | 9 | 2012 |  | Release 2.0 | Parking Deck | [6 empty] | ERCOT Staff |  |  |  | Enhance PFE model to include the following risk factors: • Price volatility analysis for the Day Ahead Market, • Bid and offer volume analysis in the Day Ahead Market, and • Value of Congestion Revenue Rights
TBD |  | Board Approved | NPRR286 | DAM Credit – Non-Business Day Processing | 99 | TBD |  | TBD | Parking Deck |  |  |  |  | ERCOT staff working on non-business days |  | ERCOT Staff | 2010-10-14 |  |  | Change the values of the reference to “95th percentile” to “90th percentile” in Section 4.4.10(6)(b)(i)(B) and Section 4.4.10(6)(b)(ii) consistent with the vote taken by the Credit Working Group (CWG) and the Market Credit Working Group (MCWG)
TBD |  |  |  | Add PSS Status to RARF | 99 | TBD | Siebel | TBD | Parking Deck |  |  |  |  | Manual posting in place |  | ERCOT Staff |  |  |  | Automation of manual process as a result of NPRR156
TBD |  |  |  | Automate Identification of PUNs for Reporting | 99 | TBD |  | TBD | Parking Deck |  |  |  |  | Delivered with table that is maintained manually |  | ERCOT Staff |  |  |  | NPRR202 required that Private Use Networks (PUNs) be excluded from State Estimator postings of transmission flows and voltages. This requirement is being met by adding a static table to the reporting infrastructure to store the list of known PUNs. This Parking Deck item would create a method to dynamically derive the population of PUNs for this reporting.
TBD |  |  |  | EILS Enhancements | 99 | TBD |  | TBD | Parking Deck | [6 empty] | ERCOT Staff |  |  |  | Automation of manual processes
TBD |  |  |  | EMS Upgrade | 99 | 2012 | EMS | TBD | Parking Deck | [6 empty] | ERCOT Staff |  |  |  | Upgrade EMS system from v2.3 to v2.5/v2.6
TBD |  | NPRR Required |  | Load Participation in SCED | 99 | TBD | MMS | TBD | Parking Deck | [6 empty] | DSWG |  |  |  | Functionality to be considered for post-go-live development Demand Side Working Group (DSWG) currently looking into the feasibility of demand response being economically dispatched by SCED
TBD |  |  |  | MOTE for Outage Scheduler | 99 | TBD |  | TBD | Parking Deck | [6 empty] | ERCOT Staff |  |  |  | The Nodal MOTE does not include providing an environment for Outage Scheduler. Without this environment, MPs will be unable to test their code when ERCOT makes changes to web services. Similarly, MPs who decide to use web services for the first time will not have a test environment to test their outage transactions with ERCOT.
TBD |  |  |  | RARF Automation | 99 | TBD |  | TBD | Parking Deck | [6 empty] | ERCOT Staff |  |  |  | Functionality to be considered for post-go-live development
TBD |  |  |  | TML Transition to MIS | 99 | TBD |  | TBD | Parking Deck | [6 empty] | ERCOT Staff |  |  |  | Upon go live, most applications that are currently available through TML will migrate to MIS and will only be accessible to MPs through the MIS portal. RMS has requested that Zonal Reports, Find ESI ID, Find Transactions, and Transaction submission be accessed through TML until MIS has had sufficient time to stabilize.
TBD |  |  |  | Additional resource status for resource startup/shutdown | 99 | TBD |  | TBD | QSE Issues List | [10 empty] | ERCOT published guidelines for telemetry and resource statuses during resource startup and shutdown. We would like additional resource statuses for conditions below LSL rather than using workarounds with existing resource statuses.
TBD |  |  |  | DAM Clearing Engine | 99 | TBD | MMS | TBD | QSE Issues List | [6 empty] | Luminant |  |  |  | Is there a need for a protocol revision to create shadow price limits in DAM equal to Real Time?
TBD |  | Dupe with NPRR282 |  | Proposal to use telemetered Ramp Rates instead of Ramps Rates provided through MMS UI/EWS | 99 | TBD |  | TBD | QSE Issues List | [6 empty] | Calpine |  |  |  | Proposal to use telemetered Ramp Rates instead of Ramps Rates provided through MMS UI/EWS.
TBD |  | Captured in the current defect list? |  | Real Time Operations | 99 | TBD | EMS, MMS | TBD | QSE Issues List | [6 empty] | Luminant |  |  |  | QSE AS Capacity Compliance Monitoring Notification: ERCOT will supply a notification to QSEs when the comparison between the QSEs AS Supply Responsibility in the EMS system with the AS Supply Responsibility in the MMS system indicates that the QSE is not providing sufficient capacity Question: will the notification also be available through XML form, similar to EIP 1.19, section 5.3.1.2? Outstanding question.
TBD |  |  |  | Trade Confirmation Timestamp | 99 | TBD |  | TBD | QSE Issues List | [10 empty] | ERCOT has not implemented a trade confirmation timestamp in the Trades area on the MMS. Although notifications provides a timestamp of when each QSE submits or confirms this can provide conflicting timestamps particularly when confirmation is done around 1430. A single timestamp record is needed on the Trades tab to confirm which RUC capacity will be treated in. This leaves a hole for shadow settlements to determine whether a trade was confirmed pre or post 1430.
TBD |  |  |  | Custom Filter – “Requesting Company” defaults to TCNPE, the “Operating Company” should, also. If someone needs to change that option, so be it. | 99 | TBD |  | TBD | TSP Issues List | [10 empty] | Items not addressed prior to Nodal go-live
TBD |  |  |  | ERCOT introduced NOMCRs (associated with TSP owned equipment) should remain ERCOT responsibility from a compliance perspective. | 99 | TBD | NMMS | TBD | TSP Issues List | [10 empty] | Items not addressed prior to Nodal go-live
TBD |  |  |  | Grey Box items and additional upgrades need some kind of guarantee that they will be completed in a timely manner. | 99 | TBD |  | TBD | TSP Issues List | [10 empty] | Items not addressed prior to Nodal go-live
TBD |  |  |  | Inconsistencies in RARF data versus current planning models. | 99 | TBD |  | TBD | TSP Issues List | [10 empty] | Items not addressed prior to Nodal go-live
TBD |  |  |  | Line segments are not selectable from both terminating substations, moreover, the search pattern is not obvious to users (IE., segment NEWTGF04 between NEW and TGF substations is only available from the (NEW) substation, and missing from the TGF substation). This issue applies to both Human Interface and web services interface. | 99 | TBD |  | TBD | TSP Issues List | [10 empty] | Items not addressed prior to Nodal go-live
TBD |  |  |  | Processes for operational status changes need to be addressed before go-live. | 99 | TBD |  | TBD | TSP Issues List | [10 empty] | Items not addressed prior to Nodal go-live
TBD |  |  |  | Selecting “Time” when entering outages is a click and drag, not a drop down box that worked quite well on the previous version | 99 | TBD |  | TBD | TSP Issues List | [10 empty] | Items not addressed prior to Nodal go-live
TBD |  |  |  | The information submitted into NMMS may be duplicative causing inaccurate models. | 99 | TBD |  | TBD | TSP Issues List | [10 empty] | Items not addressed prior to Nodal go-live
TBD |  |  |  | There has always been an issue in managing the Network model and outages. Does this problem still exist with Nodal tools? | 99 | TBD |  | TBD | TSP Issues List | [10 empty] | Items not addressed prior to Nodal go-live
TBD |  |  |  | There is not a “Historical Tracking” of outages. The previous version had {View Update Log}. | 99 | TBD |  | TBD | TSP Issues List | [10 empty] | Items not addressed prior to Nodal go-live
TBD |  |  |  | To verify outages have been entered correctly for all segments of a line, each tap station has to be entered in the search criteria. | 99 | TBD |  | TBD | TSP Issues List | [10 empty] | Items not addressed prior to Nodal go-live
TBD |  | Dupe with NPRR146 (ask Woody) |  | What is the definition of an Interim Update? The protocols give ERCOT 15 days to review the NOMCR for completeness. Responding to ERCOT’s request during this review period does not cause the NOMCR to convert to an Interim Update. Design of the Interim Update approval process and how interim updates have not yet been vetted in the NDSWG | 99 | TBD |  | TBD | TSP Issues List | [10 empty] | Items not addressed prior to Nodal go-live
TBD |  |  |  | What is the ERCOT business for managing and approving SPSs? | 99 | TBD |  | TBD | TSP Issues List | [10 empty] | Items not addressed prior to Nodal go-live
TBD |  |  |  | Where are the published EMS cases for MP review? | 99 | TBD |  | TBD | TSP Issues List | [10 empty] | Items not addressed prior to Nodal go-live

## Lookup Tables
Delivery Groups | Target Delivery Timeframe | Focus Area | Comments | Sort Char | Release Year | IA Phase
Deferred Defects - G1 - Jan 11 | January 2011 | DST, Planning Go-Live | Targeted for January 2011 | 1 | 2011 | 1
Deferred Defects - G2 - Mar 11 | March 2011 | TBD | Targeted for March 2011 | 2 | 2012 | 2
Deferred Defects - G3 - May 11 | May 2011 | TBD | Targeted for May 2011 | 3 | 2013+ | 3
Deferred Defects - G4 - Jun 11 | June 2011 | TBD | Targeted for June 2011 | 4 |  | 4
Deferred Defects - G5 - Jul 11 | July 2011 | TBD | Targeted for July 2011 | 5 | TBD | TBD
Deferred Defects - G6 - Aug 11 | August 2011 | EMS | Targeted for August 2011 | 6
Deferred Defects - G7 - Sept 11 | Sept 2011 | EMS | Targeted for September 2011 | 7
Release 2.0 | 2012 | TBD | First major enhancement release | 9
Future Release | TBD | TBD | Deferred to future release | 10
Standalone Project | Various | N/A | Projects not subject to the release schedule | 8
N/A | N/A | N/A | Prioritization not required | 11
TBD |  |  | Yet to be defined | 99