## Slide 1
2011 Prioritization Update to Market Subcommittees
Troy Anderson
ERCOT
Enterprise Project Portfolio Management
December 2010
Notes: <number>

## Slide 2: 2011 Project Prioritization – Prioritization of 2011 Nodal Work
Prioritization of 2011 Nodal work has begun
  Initial merged list from various sources has been drafted
  TAC and Board were briefed on the approach
  Three recommendations were received and are being adopted
    Add “Submission Date”, “Major System Impacted”, “Estimated Cost”
  Market subcommittees will be visited in December and January to discuss and review priorities
  Market subcommittee approval has been moved to February 2011
    TAC and Board consideration in March 2011
  Prioritization criteria is being updated for use in this process
    Allow us to better account for strategic alignment, resource availability, cost/benefit, and other factors
  New additions will be added as they arise in the stakeholder process

## Slide 3: Prioritization Timeline
Nodal Stabilization
December 2010
  Begin review of prioritized list with stakeholder groups
February 2011
  Seek approval from market subcommittees
March 2011
  Seek TAC and Board approval of initial prioritized list
Note: This is an aggressive timeline. If stabilization resource constraints arise that limit ERCOT’s ability to get an initial prioritization complete in December/January there will be a one month delay in the approval dates.
Dec 2010
Jan 2011
Feb 2011
Mar 2011
Initial Prioritization Process
TAC Consideration
Board Consideration
Apr 2011
Ongoing Prioritization Process
Impact Assessment of Parking Deck Items

## Slide 4: Project Approval & Prioritization Processes
ERCOT Assessment & Prioritization
60 days
Subcommittee
Review & Approval
PRS
TAC
Board of Directors
Parking Deck
Market Rules Processing
5 Business Days
Subcommittee
Language Consideration
PRS
Impact Analysis Review
TAC
Board of Directors
System Change Request
(SCR)
ERCOT Business Integration Processing
21 Day Comment Period
Impact Analysis
Analysis Period Varies Depending on subcommittee
Market Rules Processing
5 Business Days
PRS
Language Consideration
PRS
Impact Analysis Review
TAC
Board of Directors
Nodal Protocol Revision Request
(NPRR)
ERCOT Business Integration Processing
21 Day Comment Period
Impact Analysis
30 Day Analysis Period

## Slide 5: ERCOT Project Portfolio Delivery Timeline

## Slide 6: 2011 Project Prioritization – Prioritization of 2011 Nodal Work
See spreadsheet for draft prioritization list
  Important note:
    This is an initial draft to show format and set the stage for upcoming prioritization discussions
    The Ranks and Target Releases have not been reviewed by ERCOT management
  “2011_Merged_Nodal_Prioritization_v7.xlsx”

## Slide 7
  Appendix
Notes: <number>

## Slide 8: Nodal Stabilization Project
Scope
  Evaluate and remediate ERCOT Nodal Operational Issues including higher than normal: production outages, issue analysis, software defect remediation, stakeholder support, and request for information volumes
Objectives
  Maintain Nodal Operational Stability during the first months of System Operations
Duration
  7-month period, running 12/1/2010 – 6/30/2011
Current Status
  Hot patches continue to be migrated to production as issues are identified that cannot wait to be migrated in a scheduled release
  Issue triage process transitioning to Operations teams
Risks / Issues
  Issue volumes are higher than expected
  Complexity of issues is greater than expected
  System design changes are implemented before systems are fully stabilized
Technical Advisory Committee
6 December 2010

## Slide 9: Data Center Migration Project
Scope
  Replace data center hardware that is approaching end of life and migrate hardware to new Taylor and Bastrop data centers.
Objectives
  Reduce level of risk of hardware failure and resulting impact on critical business functions.
Current Status
  Procurement of hardware to begin December 6 for late 2010/early 2011 delivery.
  Migration schedule 90% complete for Q1 and Q2 2011.
  Resource plans 90% complete for Q1 and Q2 2011.
Duration
  27-month period, running October 2009 through December 2011.
Risks / Issues
  Resource availability and delivery timelines may be impacted by Stabilization efforts
Technical Advisory Committee
6 December 2010

## Slide 10: Planning Model Project
Scope
  Build Annual Planning Models from the NMMS Database also used to build Network Operations Model and models for the Market.
Objectives
  Attain much higher level of consistency between Operations and Planning models than experienced in the past.
Current Status
  Testing the Topology Processor and Model On Demand applications to retrieve data from NMMS Database to finished Planning model. Go-Live date set for April 1, 2011.
Duration
  5-month period, running 12/01/2010 – 4/01/2011
Risks / Issues
  TSP concerns about the amount of data that they need to add to Topology Processor output in Model On Demand to create satisfactory Planning model.
Technical Advisory Committee
6 December 2010

## Slide 11: Deferred Defects Project
Scope
  Evaluate and remediate the priority 3 defects that were deferred from the Nodal Project
Objectives
  Continue to improve the operational efficiency of the Nodal Applications and reduce the impact of workarounds for both ERCOT and Market Participants
Current Status
  Defect release bundles and estimates have been defined for delivery in 2011
  1st release mainly isolated to the individual application
Duration
  10-month period, running 12/1/2010 – 9/30/2011
Risks / Issues
  Resource availability and delivery timelines may be impacted by Stabilization efforts
Technical Advisory Committee
6 December 2010