## Slide 1
Business Integration Update to PRS
Troy Anderson
ERCOT
Enterprise Project Portfolio Management
January 20, 2011

## Slide 2: Business Integration Update – Agenda
  2010 Project Spending Update 3
    As of 1/10/2011
  Nodal Parking Deck (final) 4-7
    As of 1/1/2011
  Project Implementations 8-9
    December 2010
  2011 Prioritization of Nodal Work n/a
    To Be Discussed Later in PRS Meeting

## Slide 3: 2010 Project Spending Update – 1/10/2011
Program Area | Initial Budget | Current Budget | Forecast (November) | YTD Actual (Preliminary)
CO | $ 1,150,000 | $ 1,150,000 | $ 965,778 | $ 797,434
IO | $ 1,450,000 | $ 765,000 | $ 812,333 | $ 707,435
MO | $ 1,500,000 | $ 1,297,649 | $ 1,148,131 | $ 902,835
RO | $ 1,900,000 | $ 1,892,118 | $ 1,420,068 | $ 1,430,951
SO | $ 150,000 | $ 144,068 | $ 100,801 | $ 81,601
Minor Cap | $ 750,000 | $ 1,435,000 | $ 1,435,000 | $ 1,134,823
Released but Not Yet Reallocated | $ 0 | $ 5,932 | $ 0 | $ 0
Subtotals | $ 6,900,000 | $ 6,689,767 | $ 5,882,111 | $ 5,055,079
Met Center Replacement | $ 31,900,000 | $ 37,600,000 | $ 32,565,590 | $ 32,553,330
Data Center Hardware | $ 7,500,000 | $ 26,500,000 | $ 25,467,215 | $ 15,224,772
Grand Totals | $ 46,300,000 | $ 70,789,767 | $ 63,914,916 | $ 52,833,181
* $685k from IO to Minor Cap for software licenses ** $400k from Met Center to DC Hardware for telecom equip.
*** Includes Board-authorized carryover of $5.9M in unspent 2009 funds
***
**
**
*
*
****
**** Includes Board-authorized acceleration of $18.315M from projected 2011 funds

## Slide 4: Nodal Parking Deck – Approved
Source | Title | Priority | Approval Date
NPRR208 | Registration and Settlement of Distributed Generation (DG) Less Than One MW | Critical | BoD Approved 7/20/2010
NPRR219 | Resolution of Alignment Items A33,A92,A106,A150 - TSPs Must Submit Outages for Resource Owned Equipment & Clarification of Changes in Status of Transmission Element Postings | Critical | BoD Approved 10/19/2010
NPRR282 | Dynamic Ramp Rates Use in SCED | Critical | BoD Approved 1/18/2011
NPRR285 | Generation Resource Base Point Deviation Charge Corrections | Critical | BoD Approved 11/16/2010
NOGRR050 | Resolution of Reporting Issues Related to NPRR219 | Critical | BoD Approved 10/19/2010
SCR756 | Enhancements to the MarkeTrak Application | Critical | BoD Approved 7/20/2010
NPRR131 | Ancillary Service Trades with ERCOT | High | BoD Approved 1/19/2010
NPRR146 | ICCP Telemetry Information Submittals | High | BoD Approved 6/15/2010
NPRR181 | FIP Definition Revision | High | BoD Approved 1/19/2010
NPRR207 | Unit Deselection | High | BoD Approved 7/20/2010
NPRR210 | Wind Forecasting Change to P50, Synch PRR841 | High | BoD Approved 6/15/2010
Total Approved = 27
µ
µ
On Parking Deck due to resource impact only. Separately funded on 2011 PPL.
page 1 of 3

## Slide 5: Nodal Parking Deck – Approved
Source | Title | Priority | Approval Date
NPRR222 | Half-Hour Start Unit RUC Clawback | High | BoD Approved 7/20/2010
NPRR251 | Sync of PRR845, Definition for IDR Meters and Optional Removal of IDR Meters at a Premise Where an Advanced Meter Can be Provisioned | High | BoD Approved 9/21/2010
NPRR272 | Definition and Participation of Quick Start Generation Resources | High | BoD Approved 11/16/2010
NPRR293 | Requirement to Post CRR Option and Obligation Quantities Cleared in DAM or Taken to Real Time | High | BoD Approved 12/14/2010
SCR759 | acLineSegment Name Length Increase in Information Model Manager | High | BoD Approved 9/21/2010
NPRR240 | Proxy Energy Offer Curve | High / Medium | BoD Approved 9/21/2010
NPRR244 | Clarification of Other Binding Documents | High / Medium | BoD Approved 10/19/2010
NPRR257 | Synchronization with Nodal Operating Guide Section 9, Monitoring Programs | High / Medium | BoD Approved 11/16/2010
NPRR258 | Sync with PRR824 and PRR833 and Additional Clarifications | High / Medium | BoD Approved 11/16/2010
page 2 of 3

## Slide 6: Nodal Parking Deck – Approved
Source | Title | Priority | Approval Date
NPRR153 | Generation Resource Fixed Quantity Block Offer | Medium | BoD Approved 1/19/2010
NPRR164 | Resubmitting Ancillary Service offers in SASM | Medium | BoD Approved 1/19/2010
NPRR241 | Aggregate Incremental Liability (AIL) Calculation and Credit Reports Publish Corrections | Medium | BoD Approved 9/21/2010
NPRR256 | Sync Nodal Protocols with PRR787, Add Non-Compliance Language to QSE Performance Standards | Medium | BoD Approved 11/16/2010
NPRR260 | Providing Access to MIS Secure Area to MIS Registered Users | Medium | BoD Approved 1/18/2011
NOGRR034 | Rescind Telemetry Performance Calculation Exclusions | Medium | BoD Approved 9/21/2010
SCR755 | ERCOT.com Website Enhancements | Medium | BoD Approved 2/16/2010
page 3 of 3

## Slide 7: Nodal Parking Deck – Pending
Source | Title | Suggested Priority | Current Status
NPRR290 | ERCOT Publication of DAM PSS/E Files | TBD | Pending at PRS
SCR760 | Recommended Changes Needed for Information Model Manager and Topology Processor for Planning Models | Critical | Pending at TAC PRS Approved 11/22/2010
Total Pending = 2

## Slide 8: 2010 Project Implementations
January 2010 – None
February 2010
  CO PR-80047_02 DAM Control Center
  IO PR-90009_01 Infrastructure Monitoring Enhancement (Remedy Phase 3)
March 2010
  RO PR-90024_01 POLR Rule and Expedited Switch
      POLR Rule portion
      Expedited Switch delivered in August 2009
  SO PR-90002_01 Large Wind Power Production Ramp Forecasting
April 2010
  RO PR-90011_01 AMS Meter Flag
  RO PR-50088_01 Data Research and Reporting (Phase 1)
  SO PR-50029_01 Improvements to VSA/DSA Phase II
  CO PR-60029_01 Enterprise Records Management Framework
May 2010 – None
June 2010
  IO PR-90010_01 Monitoring & Reporting Tools
  MO PR-90006_01 Information Lifecycle Management (Phase 1)
Months represent project go-live dates, not project completion dates

## Slide 9: 2010 Project Implementations
July / August 2010
  None
September 2010
  IO PR-80001_01 Met Center Disposition
October 2010
  DC PR-10016_02 Network Gear (Phase 2)
  CO PR-10028_01 Physical Security project
November 2010
  None planned
December 2010
  DC PR-10015_01 Telcom Equipment (Phase 1)
  DC PR-10016_01 Network Gear (Phase 1)
  IO PR-10018_01 Annual Storage Growth (hardware purchased – some work remains to be done in 2011)
Months represent project go-live dates, not project completion dates