## Issues
MCT Issues Log TX SET V4.0
Issue # | Issue Type | Affected Txn | Change Control Affected | Issue Statement | Issue Status | Date added | Date of Status Change | Source
1 | Change Control | 814_04, 814_05, 814_14, 814_22 | 738 | New Change Control will be written by Kathy S. (CNP) and Kathryn T. (ERCOT) as CC738 is now outdated; new Change Control will be discussed at Feb. Texas SET meeting | Open | 2011-01-14
2 | Change Control | 814_04, 814_05, 814_27 | 740 | New Change Control will be written by Diana R. (TNMP) as CC740 is now outdated; new Change Control will be discussed at Feb. Texas SET meeting | Open | 2011-01-14
3 | General Discussion | 650_01, 650_02, 814_20M | 737 | If a TDSP receives a 650_01 for a SW Hold, the 650_02 back to the CR only confirms the receipt of the 650_01 and not that it was accepted; Acceptance of the SW hold will come from an 814_20M; if CR does not receive an 814_20M they will open a MarkeTrak issue | Closed | 2011-01-14