## Sheet1
# | Action Item | Assigned to | Deliverable | Target Date
1 | Evalution of Changes to Alert/Notification messages | QMWG | Recommendation to MISUG regarding elimination of some alerts, possible change to a subscription type service, change to notification triggers or message text. | End of 1st Quarter
2 | Changes to ERCOT Reports and website posting | QMWG | Recommendation to MISUG of reports and Real Time data needed on MIS and public website. Recommendation regarding ERCOT philosophy of reporting when no data available or report fails. | End of 1st Quarter
3 | SCED Execution Frequency | QMWG | ERCOT to report to group regarding use of the offset and amount of regulation remaining when SCED is run off-cycle. Review of ERCOT draft of NPRR detailing use of ONTEST during startup and shutdown of units and NPRR adding startup and shutdown resource status. | Ongoing
4 | GREDP Deep Dive | QMWG | ERCOT to report to the group regarding aggregate GREDP scores for resource types and details of GREDP calculations and exemptions. QMWG members present examples of questionable failure interval calculations. | Ongoing
5 | Wind to Follow Base Points Directive | QMWG | ERCOT will investigate Protocol compliance with Section 6.5.5.2 and publish a procedure. | End of 1st Quarter
6 | NSRS Deployment Instructions | QMWG | Need clarification from ERCOT regarding NSRS cancellation instructions as well as consideration of recommendation and possible NPRR to deploy NSRS via ICCP. | End of 1st Quarter
7 | Dispatch of units above HASL | QMWG | QMWG members should bring examples to illustrate the problem so that possible solutions can be discussed with ERCOT. | Ongoing
8 | Evaluation of Wind Forecast Accuracy | QMWG | Monthly review of wind forecast accuracy report prepared by ERCOT. | Ongoing
9 | TDSP Outages impacting LR ability to participate in the market | QMWG | Identify and develop solution to TDSP outage that removes a LR from the AS market when the LR can still perform and provide AS to ERCOT | TBD
10 | A/S deliverability | QMWG | Identify how ERCOT manages deliverability and recommend any potential changes | TBD
11 | Economic Planning Criteria | CMWG | Create a scope of work for Feb meeting, then deliver recommendation for proposed changes | End of Q2
12 | PTP Options in DAM | CMWG | Offer alternatives to how PTP Options are modeled in the DAM | ?
13 | CRR Auction Delays | CMWG | Identify technical and CRR Options | End of Q1
14 | SCED Load Participation | DSWG | Complete analysis of issues, Develop business requirements and a draft NPRR | End of Q3
15 | Review CAISO RDRP | DSWG | Review and report to DSWG | End of Q3
16 | NERC Issues | DSWG | Monitor and Report to DSWG | End of Q4
17 | Explore XML deployment of EILS | DSWG | Identify Issues, Costs, Timelines | End of Q3
18 | EILS Improvements | DSWG | EILS Subgroup report to DSWG | End of Q4
19 | Investigate Load participation issues (NOM, outages, etc) | DSWG | Identify Issues, Costs, Timelines | Ongoing
20 | Resolve issue of dependent loads in different deployment groups | DSWG | Create and communicate to all Market Participants and clear procedure to handle dependent resources | TBD
21 | Pre-DAM Credit Validation | MCWG | Review e-factors or replacement for e-factors | Q3
22 | Pre-DAM Credit Validation | MCWG | Determine if PTP Obligations can be offset with CRRs | Q2
23 | CRR Auction Credit Validation | MCWG | Examine Initial Margin (A&M) and Collateralization of purchase price | In time for balance of year or annual auction
24 | CMM Core Systems | MCWG | Examine FCE calculations | In time for balance of year or annual auction
25 | CMM Core Systems | MCWG | Tighten invoice timelines and collateral requirements | Q2
26 | CMM Core Systems | MCWG | Examine adequacy of collateral held for forward risk | Q2
27 | Netting/Mutuality | MCWG | Determine alternatives to First Priority Secured Interest agreements | In time for balance of year or annual auction
28 | ERCOT unsecured credit policies | MCWG | Review of the unsecured credit cap | Q1
29 | ERCOT unsecured credit policies | MCWG | Examine Form of LCs and guarantees | Q2
30 | ERCOT unsecured credit policies | MCWG | Comparison to best practices | Q3
31 | ERCOT unsecured credit policies | MCWG | Comprehensive review of unsecured credit assignment | Q4
32 | Review Investment Practices | MCWG | Recommend changes to current investment practices | Q3
33 | Advance Notice of Price & SCED Look-ahead | QSTF | Identify one or more ways SCED look-ahead can operate in ERCOT for generators and price responsive load resources | TBD
34 | Return from Mothball | GATF | Examine whether the return to service notification should be shortened | TBD
35 | WGR Definition | ETWG | Work on WGR Definition for sites with multiple turbine types | TBD
36 | Quarterly ETIP Report | ETWG | Develop report and determine future need for report | TBD
37 | Fuel Price Adjustments for Real-Time Mitigation | VCWG |  | TBD
38 | Short term fixes | VCWG | Long-term solution for PHR, VOX and emissions costs in VC | TBD
39 | Long term fixes | VCWG | Short-term solution for PHR, VOX, and emissions costs in VC | TBD