## Slide 1
Impact Assessment of Parking Deck and New NPRRs/SCRs
Phase 1
February 2011

## Slide 2: Parking Deck and New NPRR/SCR Prioritization – Agenda
  Phase 1 of Parking Deck Impact Analysis and Cost Benefit Analysis
    Reminder of Purpose p. 3
    Review of Revision Requests in this Phase p. 4
      PRS Suggested Changes p. 5
  IA/CBA Results and Target Implementations p. 6-8
  Endorsement Consideration p. 9
  Appendix
    Review of Parking Deck Origin and Recent Activities p. 11-12
    Guidelines for Assigning Items to the Impact Assessment Phases p. 13
    Remaining Impact Assessment Phases p. 14-16
    Reconciliation p. 17

## Slide 3: Parking Deck and New NPRR/SCR Prioritization – Reminder
  REMINDER: In February, we are reviewing the Impact Analysis and CBA documents for the first group of the Parking Deck items (named Phase 1)
  Delivery targets for each NPRR/SCR/NOGRR are based on the results of the IA/CBA, resource availability, complexity and other factors
  The IAs and CBAs are going through the stakeholder process for eventual consideration by TAC and the Board
  Remaining phases of the Parking Deck IAs and CBAs will be reviewed in the stakeholder process in the months ahead

## Slide 4: Parking Deck and New NPRR/SCR Prioritization
Phase 1 – First Phase of Impact Analysis & Cost Benefit Analysis
  NPRR208: Registration and Settlement of Distributed Generation (DG) Less Than One MW
  NPRR219: TSPs Must Submit Outages for Resource Owned Equipment and Clarification of Changes in Status of Transmission Element Postings
    Includes NOGRR050: Resolution of Reporting Issues Related to NPRR219
  NPRR221: Day-Ahead Market and Real-Time Market Default Allocation Changes
  NPRR251: Synchronization of PRR845, Definition for IDR Meters and Optional Removal of IDR Meters at a Premise Where an Advanced Meter Can be Provisioned
  NPRR282: Dynamic Ramp Rates Use in SCED
  * NPRR285: Generation Resource Base Point Deviation Charge Corrections
  NPRR290: ERCOT Publication of DAM PSS/E Files
  NPRR293: Requirement to Post PTP Obligation Quantities Awarded in DAM
  NPRR302: Correct Fuel Type Language for Mitigated Offer Cap
  NPRR303: Requirement to Post PTP Options Cleared in DAM or Taken to Real-Time
  SCR760: Recommended Changes Needed for Information Model Manager and Topology Processor for Planning Models
    Includes SCR759: acLineSegment Name Length Increase in Information Model Manager
Schedule
  December/January - IA/CBA development
  January - Market subcommittee review
  February - Market subcommittee endorsement
  March - TAC and Board consideration
* NPRR285 will go to TAC in February. If the Board approves, ERCOT will seek to expedite the implementation of the curtailment flag portion.

## Slide 5: Parking Deck and New NPRR/SCR Prioritization
Summary of Changes Recommended by PRS on January 27
  Accelerate to TAC and Board in February
    NPRR285: Generation Resource Base Point Deviation Charge Corrections
  Move from Phase 2 to Phase 1
    NPRR282: Dynamic Ramp Rates Use in SCED
  Move from Phase 3 to Phase 2
    NPRR241: Aggregate Incremental Liability (AIL) Calculation and Credit Reports Publish Corrections
  Move from Phase 2 to Phase 3
    NPRR257: Sync with Nodal Operating Guide Section 9, Monitoring Programs
  Move from TBD to Phase 2
    NPRR256: Sync Nodal Protocols with PRR787, Add Non-Compliance Language to QSE Performance Standards
  Move from TBD to Phase 3
    NPRR258: Sync with PRR824 and PRR833 and Additional Clarifications
All PRS Recommendations were incorporated into the impact assessment schedule (see appendix for details)

## Slide 6: Preliminary Impact Analysis Results – Phase 1 Items
2011 Implementation Recommended
  NPRR208 – Registration and Settlement of Distributed Generation (DG) Less Than One MW
    Target Delivery = September 2011 (150 day market notice required)
  NPRR285 – Generation Resource Base Point Deviation Charge Corrections
    Target Delivery = June 2011
    Possible decision to expedite the curtailment flag portion
  NPRR293 – Requirement to Post CRR Option and Obligation Quantities Cleared in DAM or Taken to Real Time
    Target Delivery = May 2011
  NPRR302 – Correct Fuel Type Language for Mitigated Offer Cap
    Target Delivery = March 2011
  NPRR251 – Sync PRR845, Definition for IDR Meters and Optional Removal of IDR Meters at a Premise Where an Advanced Meter Can be Provisioned
    Target Delivery = June 2011
  NPRR221 – Automated Default Uplift Invoice
    Target Delivery = September 2011

## Slide 7: Preliminary Impact Analysis Results – Phase 1 Items
Implementation Not Recommended at This Time
  NPRR219 – Resolution of Alignment Items A33,A92,A106,A150 - TSPs Must Submit Outages for Resource Owned Equipment & Clarification of Changes in Status of Transmission Element Postings
    Cost to implement greatly exceeds the offsetting labor savings achieved with this project
    Need to consider alternate approaches or combining with one or more related efforts
  NOGRR050 – Resolution of Reporting Issues Related to NPRR219
    Not recommended at this time due to its connection to NPRR219

## Slide 8: Preliminary Impact Analysis Results – Phase 1 Items
Recommendation TBD
  NPRR282 – Dynamic Ramp Rates Use in SCED
    ERCOT working to have IA/CBA for February PRS
  NPRR290 – ERCOT Publication of DAM PSS/E Files
    IA/CBA Pending at PRS
  NPRR303 – Requirement to Post PTP Options Cleared in DAM or Taken to Real-Time
    IA/CBA Pending at PRS
  SCR759 – acLineSegment Name Length Increase in Information Model Manager
    Likely being combined with SCR760
  SCR760 – Recommended Changes Needed for Information Model Manager and Topology Processor for Planning Models
    Tabled at TAC
These items will be considered in the stakeholder process as language is approved and IA/CBA documents are completed

## Slide 9: Parking Deck and New NPRR/SCR Prioritization – Endorsement
  Suggested subcommittee endorsement language:
    <Subcommittee name> endorses the Impact Analysis and Cost Benefit Analysis documents for Phase 1 of the Parking deck impact assessment:
      NPRR208 – NPRR219
      NPRR251 – NOGRR050
      NPRR293
    In addition, <Subcommittee name> endorses the delivery targets for the revision requests listed above. Items not targeted for delivery in 2011 will be considered in a future year as part of the release planning process.

## Slide 10
Appendix

## Slide 11: Parking Deck and New NPRR/SCR Prioritization – Origin
  PRR799 (approved 2/2009) allowed ERCOT to defer the impact assessment of revision requests requiring system changes that were deemed not needed for Nodal go-live by the ERCOT CEO
  The stakeholder approval process proceeded on these items with the understanding that impact assessment would be done at a later time
  These deferred items were housed in the Parking Deck and included a Board-approved Priority
    29 items were on the Parking Deck at Nodal go-live
      All are now Board-approved except SCR760 and NPRR290
      All have Priority assigned except NPRR290
    A number of other items were tracked from various sources to provide a place to house other ideas that might result in NPRRs, SCRs, etc.

## Slide 12: Parking Deck and New NPRR/SCR Prioritization – Recent Events
  In November 2010, ERCOT began planning for the impact assessment of the Parking Deck items
  A limited number of items were selected in the first phase of the Parking Deck impact assessment to avoid impacts to Nodal Stabilization resources
    The first phase of impact assessments is nearing completion
    Market subcommittee review will take place in February
  Further analysis by ERCOT suggests the need for 3 more impact assessment phases
  A special PRS meeting was held on January 27 to review ERCOT’s recommendation and the rationale behind it. Market input was provided and incorporated into the recommendation.

## Slide 13: Parking Deck and New NPRR/SCR Prioritization – Guidelines
  Guidelines for Determining Placement of a Parking Deck Item in the Impact Assessment Phases
    Priority
    Perceived impact on reliability and the market based on our experience since Nodal go-live
    Availability of Resources to Conduct Impact Assessments
    Complexity
      Likely Placement in Release 2.0
        Planning begins Q3 2011
        Implementation expected in 2012
      Dependencies with Other Changes
    Elimination of Manual Workarounds

## Slide 14: Parking Deck and New NPRR/SCR Prioritization
Phase 2 – Proposed Next Phase of IAs and CBAs
  NPRR210: Wind Forecasting Change to P50, Sync with PRR841
  NPRR240: Proxy Energy Offer Curve
  NPRR241: Aggregate Incremental Liability (AIL) Calculation and Credit Reports Publish Corrections
  NPRR244: Clarification of Other Binding Documents
  NPRR256: Sync Nodal Protocols with PRR787, Add Non-Compliance Language to QSE Performance Standards
  SCR755: ERCOT.com Website Enhancements
Proposed Schedule
  February/March - IA/CBA development
  March - Market subcommittee review
  April - Market subcommittee endorsement
  May - TAC and Board consideration

## Slide 15: Parking Deck and New NPRR/SCR Prioritization
Phase 3 – Proposed Next Phase of IAs and CBAs
  NPRR131: Ancillary Service Trades with ERCOT
    May move from Phase 3 to TBD based on outcome of a revision that is being drafted
  NPRR181: FIP Definition Revision
  NPRR207: Unit Deselection
  NPRR222: Half-Hour Start Unit RUC Clawback
  NPRR257: Synchronization with Nodal Operating Guide Section 9, Monitoring Programs
    Due to complexity, IA/CBA development might not finish until Phase 4
  NPRR258: Sync with PRR824 and PRR833 and Additional Clarifications
  NPRR260: Providing Access to MIS Secure Area to MIS Registered Users
  NPRR272: Definition and Participation of Quick Start Generation Resources
  NOGRR034: Rescind Telemetry Performance Calculation Exclusions
Proposed Schedule
  April/May - IA/CBA development
  May - Market subcommittee review
  June - Market subcommittee endorsement
  July - TAC and Board consideration

## Slide 16: Parking Deck and New NPRR/SCR Prioritization
Phase 4 – Proposed Final Phase of IAs and CBAs
  NPRR146: ICCP Telemetry Information Submittals
  NPRR153: Generation Resource Fixed Quantity Block Offer
Proposed Schedule
  June/July - IA/CBA development
  July - Market subcommittee review
  August - Market subcommittee endorsement
  September - TAC and Board consideration
TBD
  NPRR164: Resubmitting Ancillary Service Offers in SASM
    Pending resolution of NPRR307
This would conclude the Impact Analysis and CBA development of the Board-approved Parking Deck items

## Slide 17: Parking Deck and New NPRR/SCR Prioritization – Reconciliation
Why are we only being asked to approve 5 IAs/CBAs? There are 13 items in Phase 1 (see slide 4)
  Phase 1 contained both Parking Deck NPRRs as well has NPRRs submitted after go-live
  Also, some items were expedited and others are still undergoing language review or impact assessment
  Reconciliation
    Items seeking subcommittee approval in February 5
    Still TBD * (NPRR282, NPRR290, NPR303, SCR759, SCR760) 5
    Already Board-approved or being expedited (NPRR285, NPRR302) 2
    Internal item that doesn’t eliminate grey-box language (NPRR221) 1
    Total 13
  * Many of the TBD items will be ready for IA/CBA consideration by PRS in February