## Cover
ERCOT Portfolio Status Report (Week Ending 2/4/11)

## Portfolio
Delivery Area | Project | Task Description | Baseline Finish | Current Finish | This Weeks Status
| Stabilization | End Month 1 of Stabilization | Fri 12/31/10 | Fri 12/31/10 | Complete
| Stabilization | End Month 2 of Stabilization | Mon 1/31/11 | Mon 1/31/11 | Complete
| Stabilization | End Month 3 of Stabilization | Mon 2/28/11 | Mon 2/28/11 | Complete
| Stabilization | End Month 4 of Stabilization | Thu 3/31/11 | Thu 3/31/11 | Complete
| Stabilization | End Month 5 of Stabilization | Fri 4/29/11 | Fri 4/29/11 | Complete
| Stabilization | End Month 6 of Stabilization | Tue 5/31/11 | Tue 5/31/11 | Complete
| Stabilization | End Month 7 of Stabilization | Thu 6/30/11 | Thu 6/30/11 | Complete
| Data Center Migration |  |  |  | Complete
| Data Center Migration |  |  |  | Complete
| Data Center Migration |  |  |  | Complete
| Data Center Migration |  |  |  | Complete
| Data Center Migration |  |  |  | Complete
| Data Center Migration |  |  |  | Complete
| Data Center Migration |  |  |  | Complete
| Data Center Migration |  |  |  | Complete
| Data Center Migration |  |  |  | Complete
| Data Center Migration |  |  |  | Complete
| Network Gear Ph3 |  |  |  | Complete
| Network Gear Ph4 |  |  |  | Complete
| Network Gear Ph5 |  |  |  | Complete
| Network Gear Ph6 |  |  |  | Complete
| Network Gear Ph7 |  |  |  | Complete
| Network Gear Ph8 |  |  |  | Complete
| Network Gear Ph9 |  |  |  | Complete
| Network Gear Ph10 |  |  |  | Complete
| Network Gear Ph11 |  |  |  | Complete
| Network Gear Ph12 |  |  |  | Complete
| Network Gear Ph13 |  |  |  | Complete
| Network Gear Ph14 |  |  |  | Complete
| Telcom Equipment |  |  |  | Complete
| Telcom Equipment |  |  |  | Complete
| Telcom Equipment |  |  |  | Complete
| Telcom Equipment |  |  |  | Complete
| Telcom Equipment |  |  |  | Complete
| Telcom Equipment |  |  |  | Complete
| Telcom Equipment |  |  |  | Complete
| Planning Model Go-Live | iTest Testing | Mon 2/28/11 | Mon 2/28/11 | Complete
| Planning Model Go-Live | Migrate to nProd | Tue 3/1/11 | Tue 3/1/11 | Complete
| Planning Model Go-Live | Begin creating Planning Model (go-live) | Fri 4/1/11 | Fri 4/1/11 | Complete
| Planning Model Go-Live |  |  |  | Complete
| Planning Model Go-Live |  |  |  | Complete
| Planning Model Go-Live |  |  |  | Complete
| Deferred Defects | Group 1 Release complete | Mon 1/24/11 | Sun 1/23/11 | Complete
| Deferred Defects | Group 2 Release complete | Fri 3/25/11 | Thu 3/24/11 | Complete
| Deferred Defects | Group 3 Release complete | Fri 5/20/11 | Thu 5/19/11 | Complete
| Deferred Defects | Group 4 Release complete | Mon 6/20/11 | Fri 6/17/11 | Complete
| Deferred Defects | Group 5 Release complete | Mon 7/25/11 | Fri 7/22/11 | Complete
| Deferred Defects | Group 6 Release complete | Fri 8/19/11 | Thu 8/18/11 | Complete
| Deferred Defects | Group 7 Release complete | Thu 9/22/11 | Wed 9/21/11 | Complete
| Deferred Defects |  |  |  | Complete
| Deferred Defects |  |  |  | Complete
| Deferred Defects |  |  |  | Complete
| Deferred Defects |  |  |  | Complete
| Deferred Defects |  |  |  | Complete
| Deferred Defects |  |  |  | Complete
| Deferred Defects |  |  |  | Complete
| Deferred Defects |  |  |  | Green
| Deferred Defects |  |  |  | Green
| Deferred Defects |  |  |  | Complete
| ILM Ph2 | EXECUTION PHASE |  | Mon 12/31/12 | Complete
| ILM Ph2 |  |  |  | Complete
| ILM Ph2 |  |  |  | Complete
| ILM Ph2 |  |  |  | Complete
| ILM Ph2 |  |  |  | Complete
| ILM Ph2 |  |  |  | Complete
| ILM Ph2 |  |  |  | Complete
| ILM Ph2 |  |  |  | Complete
| ILM Ph2 |  |  |  | Complete
| ILM Ph2 |  |  |  | Complete
| ILM Ph2 |  |  |  | Complete
| ILM Ph2 |  |  |  | Complete
| ILM Ph2 |  |  |  | Complete
| ILM Ph2 |  |  |  | Complete
| ILM Ph2 |  |  |  | Green
| ILM Ph2 |  |  |  | Green
| ILM Ph2 |  |  |  | Complete
| Settlement System Upgrade | Requirements Complete | Fri 1/7/11 | Wed 2/2/11 | Complete
| Settlement System Upgrade | Conceptual Design Complete | Tue 5/31/11 | Mon 5/13/11 | Complete
| Settlement System Upgrade | Technical Architecture Complete | Thu 7/21/11 | Wed 7/5/11 | Complete
| Settlement System Upgrade | Test Plan Complete | Fri 2/4/11 | Wed 3/2/11 | Complete
| Settlement System Upgrade |  |  |  | Complete
| Settlement System Upgrade |  |  |  | Complete
| Settlement System Upgrade |  |  |  | Complete
| Settlement System Upgrade |  |  |  | Complete
| Settlement System Upgrade |  |  |  | Complete
| Settlement System Upgrade |  |  |  | Complete
| Settlement System Upgrade |  |  |  | Complete
| Settlement System Upgrade |  |  |  | Complete
| Settlement System Upgrade |  |  |  | Complete
| Settlement System Upgrade |  |  |  | Complete
| Settlement System Upgrade |  |  |  | Green
| Settlement System Upgrade |  |  |  | Green
| Settlement System Upgrade |  |  |  | Complete
| Data Research & Reporting | Migration to I-TEST | Fri 4/1/11 | Fri 4/1/11 | Complete
| Data Research & Reporting | I-TEST Sign-off | Fri 7/29/11 | Fri 7/29/11 | Complete
| Data Research & Reporting | PRODUCTION - GO LIVE | Mon 9/26/11 | Mon 9/26/11 | Complete
| Data Research & Reporting | Stabilization Complete | Fri 10/14/11 | Fri 10/14/11 | Complete
| Data Research & Reporting |  |  |  | Complete
| Data Research & Reporting |  |  |  | Complete
| Data Research & Reporting |  |  |  | Complete
| Data Research & Reporting |  |  |  | Complete
| Data Research & Reporting |  |  |  | Complete
| Data Research & Reporting |  |  |  | Complete
| Data Research & Reporting |  |  |  | Complete
| Data Research & Reporting |  |  |  | Complete
| Data Research & Reporting |  |  |  | Complete
| Data Research & Reporting |  |  |  | Complete
| Data Research & Reporting |  |  |  | Green
| Data Research & Reporting |  |  |  | Green
| Data Research & Reporting |  |  |  | Complete
| Data Agg Perf. Improvements | Perform Migration to ITEST |  | Thr 5/5/11 | Complete
| Data Agg Perf. Improvements | Go Live PMO EXEC |  | Mon 6/6/11 | Complete
| Data Agg Perf. Improvements |  |  |  | Complete
| Data Agg Perf. Improvements |  |  |  | Complete
| Data Agg Perf. Improvements |  |  |  | Complete
| Data Agg Perf. Improvements |  |  |  | Complete
| Data Agg Perf. Improvements |  |  |  | Complete
| Data Agg Perf. Improvements |  |  |  | Complete
| Data Agg Perf. Improvements |  |  |  | Complete
| Data Agg Perf. Improvements |  |  |  | Complete
| Data Agg Perf. Improvements |  |  |  | Complete
| Data Agg Perf. Improvements |  |  |  | Complete
| Data Agg Perf. Improvements |  |  |  | Complete
| Data Agg Perf. Improvements |  |  |  | Complete
| Data Agg Perf. Improvements |  |  |  | Green
| Data Agg Perf. Improvements |  |  |  | Green
| Data Agg Perf. Improvements |  |  |  | Complete
| ERMA | Go Live | Mon 2/28/11 | Mon 2/28/11 | Complete
| ERMA |  |  |  | Complete
| ERMA |  |  |  | Complete
| ERMA |  |  |  | Complete
| ERMA |  |  |  | Complete
| ERMA |  |  |  | Complete
| ERMA |  |  |  | Complete
| ERMA |  |  |  | Complete
| ERMA |  |  |  | Complete
| ERMA |  |  |  | Complete
| ERMA |  |  |  | Complete
| ERMA |  |  |  | Complete
| ERMA |  |  |  | Complete
| ERMA |  |  |  | Complete
| ERMA |  |  |  | Green
| ERMA |  |  |  | Green
| ERMA |  |  |  | Complete
LEGEND: BLUE - Complete, GREEN - No Delay, YELLOW - Delay w/o Impact, RED - Impacted Milestone
Project Name:
Project Contacts:
ERCOT Portfolio
Cagle Lowe, Troy Anderson
Overall Status:
Green
This Week's Activities and Accomplishments; Upcoming Activities

## Stabilization
LEGEND: BLUE - Complete, GREEN - No Delay, YELLOW - Delay w/o Impact, RED - Impacted Milestone
Upcoming Milestones
| Description | Baseline Start | Current Start | Baseline Finish | Current Finish | 1/21 % Complete | 1/28% Complete | 2/4% Complete | This Weeks Status | Variance Description | Mitigation
S-NS1 | Nodal Stabilization Project | 2010-12-01 | 2010-12-01 | 2011-06-30 | 2011-06-30 | 22% | 25% | 40% | Green
D-NS2 | Month 1 of Stabilization | 2010-12-01 | 2010-12-01 | 2010-12-31 | 2010-12-31 | 100% | 100% | 100% | Complete
S-NS3 | End Month 1 of Stabilization | 2010-12-31 | 2010-12-31 | 2010-12-31 | 2010-12-31 | 100% | 100% | 100% | Complete
D-NS4 | Month 2 of Stabilization | 2011-01-03 | 2011-01-03 | 2011-01-31 | 2011-01-31 | 52% | 53% | 100% | Complete
D-NS5 | iTest Refesh | 2011-01-10 | 2011-01-10 | 2011-02-08 | 2011-02-02 | 15% | 38% | 100% | Complete
S-NS6 | End Month 2 of Stabilization | 2011-01-31 | 2011-01-31 | 2011-01-31 | 2011-01-31 | 0% | 0% | 100% | Complete
D-NS7 | Month 3 of Stabilization | 2011-02-01 | 2011-02-01 | 2011-02-28 | 2011-02-28 | 0% | 0% | 1% | Green
S-NS8 | End Month 3 of Stabilization | 2011-02-28 | 2011-02-28 | 2011-02-28 | 2011-02-28 | 0% | 0% | 0%
D-NS9 | Month 4 of Stabilization | 2011-03-01 | 2011-03-01 | 2011-03-31 | 2011-03-31 | 0% | 0% | 0%
S-NS10 | End Month 4 of Stabilization | 2011-03-31 | 2011-03-31 | 2011-03-31 | 2011-03-31 | 0% | 0% | 0%
D-NS11 | Month 5 of Stabilization | 2011-04-01 | 2011-04-01 | 2011-04-29 | 2011-04-29 | 0% | 0% | 0%
S-NS12 | End Month 5 of Stabilization | 2011-04-29 | 2011-04-29 | 2011-04-29 | 2011-04-29 | 0% | 0% | 0%
D-NS13 | Month 6 of Stabilization | 2011-05-02 | 2011-05-02 | 2011-05-31 | 2011-05-31 | 0% | 0% | 0%
S-NS14 | End Month 6 of Stabilization | 2011-05-31 | 2011-05-31 | 2011-05-31 | 2011-05-31 | 0% | 0% | 0%
D-NS15 | Month 7 of Stabilization | 2011-06-01 | 2011-06-01 | 2011-06-30 | 2011-06-30 | 0% | 0% | 0%
S-NS16 | End Month 7 of Stabilization | 2011-06-30 | 2011-06-30 | 2011-06-30 | 2011-06-30 | 0% | 0% | 0%
- Continue development efforts for Deferred Defects Group 2 release
- Complete testing setup for DST testing
- Start DST testing cycles
This Week's Activities and Accomplishments
Planned Activities for Next Week
Project Name:
Project Contacts:
Stabilization
Adam Martinez
Risks & Issues
Schedule Status:
Green
Week Ending:
2/4/11
- Completed iTest Refresh and clone creation
- Completed reforecast efforts for Stabilization and Deferred Defects EACs
- Finalized test plans and scope for DST testing
- Started test data prep

## Data Center Migration-11000
LEGEND: BLUE - Complete, GREEN - No Delay, YELLOW - Delay w/o Impact, RED - Impacted Milestone
| Description | Baseline Start | Current Start | Baseline Finish | Current Finish | 1/21 % Complete | 1/28% Complete | 2/4% Complete | This Weeks Status | Variance Description | Mitigation
S-DCM1 | PR11000_01 Data Center Migration Consolidation | 2011-01-03 | 2011-01-03 | 2012-03-30 | 2012-04-12 | 0% | 0% | 2% | Yellow
S-DCM2 | EXECUTION | 2011-01-03 | 2011-01-03 | 2012-03-30 | 2012-04-12 | 0% | 0% | 2% | Yellow
D-DCM3 | PROCURE HARDWARE AND SOFTWARE | 2011-01-03 | 2011-01-03 | 2011-01-31 | 2011-02-14 | 0% | 0% | 50% | Yellow
D-DCM4 | SYSTEMS INSTALLATION | 2011-01-03 | 2011-01-03 | 2011-05-24 | 2011-05-02 | 0% | 0% | 0% | Yellow
D-DCM5 | Install Unix Power770 Frames (PROD) | 2011-01-17 | 2011-01-10 | 2011-03-10 | 2011-03-03 | 0% | 0% | 0% | Yellow
D-DCM6 | VTL Installs (PROD / TCC3) | 2011-02-07 | 2011-02-18 | 2011-02-10 | 2011-02-23 | 0% | 0% | 0%
D-DCM7 | Storage Install (PROD / TCC3) | 2011-01-31 | 2011-02-15 | 2011-02-18 | 2011-03-03 | 0% | 0% | 0% | Yellow
D-DCM8 | Install Unix Power770 Frames (DEV-TEST) | 2011-03-02 | 2011-02-07 | 2011-04-15 | 2011-03-24 | 0% | 0% | 0%
D-DCM9 | Install VTL Hardware (DEV-TEST / TDC1) | 2011-01-31 | 2011-02-15 | 2011-02-03 | 2011-02-18 | 0% | 0% | 0% | Yellow
D-DCM10 | Storage Install (DEV-TEST / TDC1) | 2011-01-31 | 2011-02-15 | 2011-02-11 | 2011-02-28 | 0% | 0% | 0% | Yellow
D-DCM11 | Install VTL Hardware (TDC2) | 2011-01-31 | 2011-02-15 | 2011-02-03 | 2011-02-18 | 0% | 0% | 0% | Yellow
D-DCM12 | Storage Install (TDC2) | 2011-01-31 | 2011-02-15 | 2011-02-11 | 2011-02-28 | 0% | 0% | 0% | Yellow
D-DCM13 | Install Unix Power770 Frames (PROD) | 2011-01-03 | 2011-01-03 | 2011-05-13 | 2011-04-21 | 0% | 0% | 0% | Yellow
D-DCM14 | Install VTL Hardware (PROD / BCC1) | 2011-05-19 | 2011-04-26 | 2011-05-24 | 2011-05-02 | 0% | 0% | 0%
D-DCM15 | Storage Install (PROD / BCC1) | 2011-04-06 | 2011-03-15 | 2011-04-20 | 2011-03-29 | 0% | 0% | 0%
D-DCM16 | SERVER BUILD | 2011-01-03 | 2011-01-03 | 2012-03-30 | 2012-04-12 | 0% | 0% | 0% | Yellow
D-DCM17 | INFRASTRUCTURE CHANGE REQUESTS | 2011-01-03 | 2011-01-03 | 2011-01-03 | 2011-01-03 | 0% | 0% | 0% | Yellow
D-DCM18 | SERVER INSTALLATION AND BUILD (Wave 1) | 2011-02-07 | 2011-02-18 | 2011-09-02 | 2011-09-15 | 0% | 0% | 0%
D-DCM19 | SERVER INSTALLATION AND BUILD (wave 2) | 2011-01-03 | 2011-01-03 | 2012-03-30 | 2012-04-12 | 0% | 0% | 0% | Yellow
D-DCM20 | SERVER INSTALLATION AND BUILD (wave 3) | 2011-01-03 | 2011-01-03 | 2011-02-11 | 2011-02-11 | 0% | 0% | 0% | Yellow
D-DCM21 | SERVER INSTALLATION AND BUILD (wave 4) | 2011-01-03 | 2011-01-03 | 2011-02-11 | 2011-02-11 | 0% | 0% | 0% | Yellow
D-DCM22 | SERVER INSTALLATION AND BUILD (wave 5) | 2011-01-03 | 2011-01-03 | 2011-02-11 | 2011-02-11 | 0% | 0% | 0% | Yellow
D-DCM23 | AS BUILT DOCUMENTATION | 2011-01-03 | 2011-01-03 | 2011-01-11 | 2011-01-11 | 0% | 0% | 0% | Yellow
D-DCM24 | PROJECT SIGN OFF | 2011-01-03 | 2011-01-03 | 2011-01-17 | 2011-01-17 | 0% | 0% | 0% | Yellow
D-DCM25 | TOLLGATE EXECUTION TO CLOSING | 2011-01-18 | 2011-01-18 | 2011-01-21 | 2011-01-21 | 0% | 0% | 0% | Yellow
D-DCM26 | CLOSING | 2011-01-03 | 2011-01-03 | 2011-02-23 | 2011-02-23 | 0% | 0% | 0% | Yellow
D-DCM27 | LESSONS LEARNED EXECUTION AND CLOSING PHASES | 2011-01-03 | 2011-01-03 | 2011-02-10 | 2011-02-10 | 0% | 0% | 0% | Yellow
D-DCM28 | INVOICE RECONCILIATION | 2011-01-03 | 2011-01-03 | 2011-02-21 | 2011-02-21 | 0% | 0% | 0% | Yellow
This Week's Activities and Accomplishments
Planned Activities for Next Week
Project Name:
Project Contacts:
Data Center Migration
Ken Meinen
Risks & Issues
Schedule Status:
Week Ending:
2/4/11
GREEN

## Data Center Migration-Network
LEGEND: BLUE - Complete, GREEN - No Delay, YELLOW - Delay w/o Impact, RED - Impacted Milestone
| Description | Baseline Start | Current Start | Baseline Finish | Current Finish | 1/21 % Complete | 1/28% Complete | 2/4% Complete | This Weeks Status | Variance Description | Mitigation
D-NG1 | PR10016_03 Network Gear Phase 3 | 2010-06-07 | 2010-05-10 | 2012-02-13 | 2012-02-09 | 31% | 32% | 33% | Green
S-NG2 | INITIATION | 2010-05-10 | 2010-05-10 | 2010-06-07 | 2010-06-07 | 100% | 100% | 100% | Complete
D-NG3 | INITIATION PHASE | 2010-05-10 | 2010-05-10 | 2010-06-07 | 2010-06-07 | 100% | 100% | 100% | Complete
D-NG4 | Review of Historical Information | 2010-05-11 | 2010-05-11 | 2010-05-14 | 2010-05-14 | 100% | 100% | 100% | Complete
D-NG5 | SCHEDULING REVIEW TO DEFINE PLANNING PHASE | 2010-05-17 | 2010-05-17 | 2010-05-25 | 2010-05-25 | 100% | 100% | 100% | Complete
D-NG6 | PROJECT PLAN | 2010-05-26 | 2010-05-26 | 2010-05-28 | 2010-05-28 | 100% | 100% | 100% | Complete
S-NG7 | PLANNING | 2010-06-07 | 2010-06-07 | 2010-06-28 | 2010-06-28 | 100% | 100% | 100% | Complete
D-NG8 | PLANNING PHASE | 2010-06-07 | 2010-06-07 | 2010-06-28 | 2010-06-28 | 100% | 100% | 100% | Complete
D-NG9 | BUSINESS REQUIREMENTS | 2010-06-07 | 2010-06-07 | 2010-06-11 | 2010-06-11 | 100% | 100% | 100% | Complete
S-NG10 | Business Requirements Complete | 2010-06-11 | 2010-06-11 | 2010-06-11 | 2010-06-11 | 100% | 100% | 100% | Complete
D-NG11 | SECURITY REQUIREMENTS | 2010-06-07 | 2010-06-07 | 2010-06-18 | 2010-06-18 | 100% | 100% | 100% | Complete
D-NG12 | SCHEDULING REVIEW TO DEFINE EXECUTION PHASE | 2010-06-14 | 2010-06-14 | 2010-06-17 | 2010-06-17 | 100% | 100% | 100% | Complete
D-NG13 | RESOURCE PLAN DOCUMENT FOR EXECUTION | 2010-06-18 | 2010-06-18 | 2010-06-21 | 2010-06-21 | 100% | 100% | 100% | Complete
D-NG14 | CASH FLOW DOCUMENT AT 90 Percent ACCURACY | 2010-06-22 | 2010-06-22 | 2010-06-25 | 2010-06-25 | 100% | 100% | 100% | Complete
D-NG15 | LESSONS LEARNED INITIATION AND PLANNING PHASE | 2010-06-21 | 2010-06-21 | 2010-06-25 | 2010-06-25 | 100% | 100% | 100% | Complete
D-NG16 | PLANNING TO EXECUTION PHASE DIVISIONAL TOLLGATE | 2010-06-21 | 2010-06-21 | 2010-06-28 | 2010-06-28 | 100% | 100% | 100% | Complete
S-NG17 | EXECUTION | 2010-06-28 | 2010-06-28 | 2011-12-30 | 2012-01-03 | 30% | 30% | 31% | Yellow
D-NG18 | EXECUTION PHASE | 2010-06-28 | 2010-06-28 | 2011-12-30 | 2012-01-03 | 30% | 30% | 31% | Yellow
D-NG19 | PROCURE HARDWARE AND SOFTWARE | 2011-01-10 | 2011-01-31 | 2011-02-24 | 2011-03-17 | 0% | 0% | 0% | Yellow
D-NG20 | Hardware and Software Orders Complete | 2011-02-24 | 2011-03-17 | 2011-02-24 | 2011-03-17 | 0% | 0% | 0%
D-NG21 | NETWORK GEAR PHASE TWO 10016 | 2010-06-28 | 2010-06-28 | 2011-03-21 | 2010-10-29 | 100% | 100% | 100% | Complete
D-NG22 | TCC3 | 2010-06-28 | 2010-06-28 | 2011-03-21 | 2010-10-29 | 100% | 100% | 100% | Complete
D-NG23 | NETWORK GEAR PHASE THREE 10016 | 2010-06-28 | 2010-06-28 | 2011-11-02 | 2011-12-21 | 27% | 28% | 31% | Yellow
D-NG24 | BASTROP MGMT | 2010-08-19 | 2010-11-01 | 2010-08-30 | 2010-12-06 | 100% | 100% | 100% | Complete
D-NG25 | BASTROP AGGREGATION SWITCHES | 2010-08-31 | 2010-11-01 | 2010-10-08 | 2010-12-28 | 100% | 100% | 100% | Complete
D-NG26 | BUILDING IDFs AND CORP CORE | 2010-10-11 | 2010-11-01 | 2010-10-20 | 2010-11-30 | 100% | 100% | 100% | Complete
D-NG27 | BASTROP SERVICES NETWORK | 2010-10-21 | 2010-11-01 | 2010-11-01 | 2010-11-30 | 100% | 100% | 100% | Complete
D-NG28 | BASTROP ITEST AND DEV | 2010-11-02 | 2011-02-28 | 2010-11-11 | 2011-03-25 | 0% | 0% | 0% | Yellow
D-NG29 | BASTROP PRODUCTION NETWORK SWITCHES | 2010-11-12 | 2010-11-01 | 2010-11-23 | 2010-12-14 | 100% | 100% | 100% | Complete
D-NG30 | BASTROP PROXY SERVER | 2010-11-24 | 2010-12-15 | 2010-12-07 | 2011-01-28 | 34% | 48% | 59% | Yellow
D-NG31 | BASTROP INTERNET | 2010-12-08 | 2010-12-15 | 2010-12-17 | 2011-01-27 | 38% | 53% | 63% | Yellow
D-NG32 | LINK BASTROP SWITCHES TO AUSTIN SWITCHES | 2011-02-14 | 2010-11-16 | 2011-05-04 | 2011-05-02 | 16% | 16% | 23%
D-NG33 | BASTROP SYSLOG | 2010-08-09 | 2011-01-03 | 2010-08-18 | 2011-03-10 | 25% | 25% | 50% | Yellow
D-NG34 | LINK BASTROP SWITCHES TO AUSTIN SWITCHES SECONDARY PATH | 2011-05-03 | 2011-05-03 | 2011-06-20 | 2011-06-20 | 0% | 0% | 0%
D-NG35 | LOAD BALANCER MIGRATIONS TO BASTROP | 2011-02-14 | 2011-06-21 | 2011-05-16 | 2011-08-18 | 0% | 0% | 0%
D-NG36 | DEV ITEST FIREWALL MIGRATIONs TO BASTROP | 2011-03-07 | 2011-09-01 | 2011-06-02 | 2011-10-24 | 0% | 0% | 0%
D-NG37 | INTERNET FIREWALL MIGRATIONs TO BASTROP | 2011-03-21 | 2011-09-01 | 2011-06-21 | 2011-10-31 | 0% | 0% | 0%
D-NG38 | WAN FIREWALL MIGRATIONs TO BASTROP | 2011-04-04 | 2011-09-01 | 2011-07-08 | 2011-10-31 | 0% | 0% | 0%
D-NG39 | DMZ FIREWALL MIGRATIONs TO BASTROP | 2011-04-18 | 2011-09-01 | 2011-07-22 | 2011-10-31 | 0% | 0% | 0%
D-NG40 | PROD FIREWALL MIGRATIONs TO BASTROP | 2011-05-02 | 2011-10-24 | 2011-07-22 | 2011-12-21 | 0% | 0% | 0%
D-NG41 | WAN MIGRATION TO BASTROP | 2011-05-16 | 2011-09-01 | 2011-08-10 | 2011-10-31 | 0% | 0% | 0%
D-NG42 | EMMS FIREWALL MIGRATIONs TO BASTROP | 2011-05-30 | 2011-08-08 | 2011-08-24 | 2011-10-05 | 0% | 0% | 0%
D-NG43 | CONTROL ROOM TURN UP AND MIGRATION | 2011-08-22 | 2011-08-08 | 2011-09-28 | 2011-09-14 | 0% | 0% | 0%
S-NG44 | Moves from MET to Bastrop Complete | 2011-12-21 | 2011-12-21 | 2011-12-21 | 2011-12-21 | 0% | 0% | 0%
D-NG45 | NETWORK GEAR 2011 NETWORK MON ITORING IMPLEMENTATION | 2011-01-17 | 2011-01-14 | 2011-12-16 | 2011-12-20 | 0% | 0% | 0% | Yellow
D-NG46 | Taylor | 2011-01-28 | 2011-01-28 | 2011-03-14 | 2011-03-14 | 0% | 0% | 0% | Yellow
D-NG47 | Bastrop | 2011-01-28 | 2011-01-28 | 2011-12-20 | 2011-12-20 | 0% | 0% | 0% | Yellow
D-NG48 | PROJECT GO LIVE AND SIGN OFF | 2011-12-19 | 2011-12-22 | 2011-12-28 | 2012-01-03 | 0% | 0% | 0%
S-NG49 | CLOSING | 2012-01-09 | 2012-01-04 | 2012-02-13 | 2012-02-09 | 0% | 0% | 0%
D-NG50 | CLOSING PHASE | 2012-01-09 | 2012-01-04 | 2012-02-13 | 2012-02-09 | 0% | 0% | 0%
D-NG51 | LESSONS LEARNED EXECUTION AND CLOSING PHASES | 2012-01-09 | 2012-01-04 | 2012-01-12 | 2012-01-10 | 0% | 0% | 0%
D-NG52 | INVOICE RECONCILIATION | 2012-01-13 | 2012-01-11 | 2012-02-08 | 2012-02-09 | 0% | 0% | 0%
D-NG53 | PROJECT MANAGEMENT AND ADMINISTRATION CLOSING PHASE | 2012-01-09 | 2012-01-04 | 2012-02-13 | 2012-02-09 | 0% | 0% | 0%
- RSA onsite turning up Bastrop enVision syslog server
- Finishing up work on enVision syslog server
This Week's Activities and Accomplishments
Planned Activities for Next Week
Project Name:
Project Contacts:
Data Center Migration - Network
Dawn Moldenhour
Risks & Issues
Schedule Status:
Week Ending:
(Risk) Layer 2 extension may result in unacceptable application latency.
(Risk) Complexity of the Layer 2 extension will likely result in frequent application and/or network issues.
(Risk) Spanning-Tree loop (network meltdown) as a result of the Layer 2 extension between MET and Bastrop; could result in complete datacenter outage.
(Risk) A power outage in either Austin or Bastrop has the potential to impact both datacenters.
(Risk) Equipment damage during transport.
(Risk) There could be a complete loss of communications to the Market due to single-homed network connections to WAN and internet if those services became unavailable in Taylor during migration.
GREEN
2/4/11

## Data Center Migration-Telecom
LEGEND: BLUE - Complete, GREEN - No Delay, YELLOW - Delay w/o Impact, RED - Impacted Milestone
| Description | Baseline Start | Current Start | Baseline Finish | Current Finish | 1/21 % Complete | 1/28% Complete | 2/4% Complete | This Weeks Status | Variance Description | Mitigation
D-TE1 | PR10015_02 Telcom Equipment | 2010-06-07 | 2009-11-09 | 2012-02-13 | 2011-12-30 | 50% | 51% | 53% | Green
S-TE2 | INITIATION | 2010-05-10 | 2010-05-10 | 2010-06-07 | 2010-06-07 | 100% | 100% | 100% | Complete
D-TE3 | INITIATION PHASE | 2010-05-10 | 2010-05-10 | 2010-06-07 | 2010-06-07 | 100% | 100% | 100% | Complete
D-TE4 | Review of Historical Information | 2010-05-11 | 2010-05-11 | 2010-05-14 | 2010-05-14 | 100% | 100% | 100% | Complete
D-TE5 | SCHEDULING REVIEW TO DEFINE PLANNING PHASE | 2010-05-17 | 2010-05-17 | 2010-05-25 | 2010-05-25 | 100% | 100% | 100% | Complete
D-TE6 | PROJECT PLAN | 2010-05-26 | 2010-05-26 | 2010-05-28 | 2010-05-28 | 100% | 100% | 100% | Complete
D-TE7 | INITIATION TO PLANNING PHASE DIVISIONAL TOLLGATE | 2010-06-01 | 2010-06-01 | 2010-06-07 | 2010-06-07 | 100% | 100% | 100% | Complete
S-TE8 | PLANNING | 2010-06-07 | 2010-06-07 | 2010-06-28 | 2010-06-28 | 100% | 100% | 100% | Complete
D-TE9 | PLANNING PHASE | 2010-06-07 | 2010-06-07 | 2010-06-28 | 2010-06-28 | 100% | 100% | 100% | Complete
D-TE10 | BUSINESS REQUIREMENTS | 2010-06-07 | 2010-06-07 | 2010-06-11 | 2010-06-11 | 100% | 100% | 100% | Complete
S-TE11 | Business Requirements Complete | 2010-06-11 | 2010-06-11 | 2010-06-11 | 2010-06-11 | 100% | 100% | 100% | Complete
D-TE12 | SECURITY REQUIREMENTS | 2010-06-07 | 2010-06-07 | 2010-06-18 | 2010-06-18 | 100% | 100% | 100% | Complete
D-TE13 | SCHEDULING REVIEW TO DEFINE EXECUTION PHASE | 2010-06-14 | 2010-06-14 | 2010-06-17 | 2010-06-17 | 100% | 100% | 100% | Complete
D-TE14 | RESOURCE PLAN DOCUMENT FOR EXECUTION | 2010-06-18 | 2010-06-18 | 2010-06-21 | 2010-06-21 | 100% | 100% | 100% | Complete
D-TE15 | CASH FLOW DOCUMENT AT 90 Percent ACCURACY | 2010-06-22 | 2010-06-22 | 2010-06-25 | 2010-06-25 | 100% | 100% | 100% | Complete
D-TE16 | LESSONS LEARNED INITIATION AND PLANNING PHASE | 2010-06-21 | 2010-06-21 | 2010-06-25 | 2010-06-25 | 100% | 100% | 100% | Complete
D-TE17 | PLANNING TO EXECUTION PHASE DIVISIONAL TOLLGATE | 2010-06-21 | 2010-06-21 | 2010-06-28 | 2010-06-28 | 100% | 100% | 100% | Complete
D-TE18 | PROJECT MANAGEMENT AND ADMINISTRATION PLANNING PHASE | 2010-06-07 | 2010-06-07 | 2010-06-28 | 2010-06-25 | 100% | 100% | 100% | Complete
S-TE19 | EXECUTION | 2010-06-28 | 2009-11-09 | 2011-12-30 | 2011-12-30 | 49% | 50% | 53% | Green
D-TE20 | EXECUTION AND CONTROL PHASE | 2010-06-28 | 2009-11-09 | 2011-12-09 | 2011-05-20 | 58% | 58% | 63% | Green
D-TE21 | TAYLOR Nice | 2011-01-17 | 2011-01-17 | 2011-01-28 | 2011-01-28 | 0% | 68% | 77% | Green
D-TE22 | Taylor PBX Upgrade | 2011-02-25 | 2011-02-25 | 2011-03-02 | 2011-03-02 | 0% | 0% | 0%
D-TE23 | TELECOM EQUPMENT PHASE TWO TCC3 BUILDOUT 10015 | 2010-06-28 | 2010-06-28 | 2010-11-12 | 2011-03-04 | 56% | 56% | 56% | Yellow
D-TE24 | PBX INSTALLATION | 2010-06-28 | 2010-06-28 | 2010-08-26 | 2011-03-04 | 86% | 86% | 86% | Yellow
D-TE25 | HOMACO FRAME | 2010-08-02 | 2010-08-02 | 2010-08-27 | 2010-08-27 | 100% | 100% | 100% | Complete
D-TE26 | DAS INSTALLATION | 2011-01-31 | 2011-02-04 | 2011-02-28 | 2011-03-04 | 0% | 0% | 0% | Yellow
D-TE27 | TERMINAL SERVERS FOR TCC3 | 2010-09-27 | 2011-01-03 | 2010-11-12 | 2011-01-27 | 8% | 8% | 8% | Yellow
D-TE28 | TELECOM EQUIPMENT PHASE TWO BCC1 BUILDOUT | 2010-06-28 | 2009-11-09 | 2010-12-03 | 2011-05-20 | 59% | 59% | 63% | Yellow
D-TE29 | PRE SUBSTANTIAL COMPLETION CHECKLIST | 2010-08-02 | 2010-06-28 | 2010-09-14 | 2010-09-10 | 100% | 100% | 100% | Complete
D-TE30 | Confirm Cable Ladder and Fiber Runner Are In Place | 2010-08-02 | 2010-06-28 | 2010-09-08 | 2010-07-15 | 100% | 100% | 100% | Complete
D-TE31 | Validate Control Room Cable Counts | 2010-09-09 | 2010-07-16 | 2010-09-14 | 2010-09-10 | 100% | 100% | 100% | Complete
D-TE32 | Substantial Completion of Bastrop | 2010-06-28 | 2009-11-09 | 2010-12-03 | 2011-05-13 | 67% | 67% | 70% | Yellow
D-TE33 | DSX and HOMACO IMPLEMENTATION | 2010-07-12 | 2010-07-12 | 2010-09-27 | 2010-10-13 | 100% | 100% | 100% | Complete
D-TE34 | SECURITY ESCORT REQUEST | 2010-09-07 | 2010-09-07 | 2010-09-07 | 2010-09-07 | 100% | 100% | 100% | Complete
D-TE35 | FACILITIES REQUEST | 2010-08-02 | 2010-08-02 | 2010-08-27 | 2010-08-27 | 100% | 100% | 100% | Complete
D-TE36 | Work with Facilities to Identify All Rack locations and Schedule Installation | 2010-08-02 | 2010-08-02 | 2010-08-27 | 2010-08-27 | 100% | 100% | 100% | Complete
D-TE37 | IMPLEMENT PBX | 2010-07-01 | 2010-05-03 | 2010-11-17 | 2011-05-13 | 43% | 43% | 46% | Yellow
D-TE38 | CSU IMPLEMENTATION | 2010-09-01 | 2010-08-31 | 2010-10-29 | 2010-10-29 | 100% | 100% | 100% | Complete
D-TE39 | VOICEMAIL | 2010-08-25 | 2011-01-03 | 2010-09-15 | 2011-05-13 | 2% | 2% | 8% | Yellow
D-TE40 | CALL DISTRIBUTION SYSTEM | 2010-09-16 | 2011-01-03 | 2010-10-06 | 2011-05-13 | 2% | 2% | 8% | Yellow
D-TE41 | DESKTOP PHONES | 2010-10-07 | 2010-11-15 | 2010-10-27 | 2010-12-21 | 40% | 40% | 40% | Yellow
D-TE42 | CONFERENCE BRIDGE | 2010-10-28 | 2011-01-03 | 2010-11-17 | 2011-05-13 | 2% | 2% | 8% | Yellow
D-TE43 | DC POWER IMPLEMENTATION | 2010-08-16 | 2010-08-16 | 2010-08-24 | 2010-08-24 | 100% | 100% | 100% | Complete
D-TE44 | Stratum 1 clock implementation | 2009-11-09 | 2009-11-09 | 2011-03-07 | 2011-03-07 | 89% | 90% | 89% | Yellow
D-TE45 | NTP GPS Implementation | 2010-11-01 | 2010-11-01 | 2011-01-28 | 2011-01-28 | 75% | 76% | 77% | Green
D-TE46 | Terminal Servers for Bastrop | 2010-08-30 | 2010-08-30 | 2011-02-25 | 2011-02-25 | 28% | 29% | 32% | Green
D-TE47 | TELLABS IMPLEMENTATION | 2010-06-28 | 2010-03-08 | 2010-11-10 | 2010-12-07 | 100% | 100% | 100% | Complete
D-TE48 | PRIMARY FIBER TAYLOR TO BASTROP ATT Project | 2010-06-28 | 2010-04-30 | 2010-11-22 | 2011-04-25 | 88% | 88% | 96% | Yellow
D-TE49 | Alpheus | 2010-06-28 | 2010-06-28 | 2010-08-17 | 2010-09-09 | 100% | 100% | 100% | Complete
D-TE50 | Extend Alpheus Fiber in to Bastrop MDF | 2010-07-28 | 2010-07-26 | 2010-08-17 | 2010-09-09 | 100% | 100% | 100% | Complete
D-TE51 | ATT SITE SURVEY and CONSTRUCTION | 2010-06-30 | 2010-06-30 | 2010-07-07 | 2010-07-06 | 100% | 100% | 100% | Complete
D-TE52 | TELECOM CARRIER EFFORT | 2010-06-28 | 2010-06-28 | 2010-09-13 | 2010-09-10 | 100% | 100% | 100% | Complete
D-TE53 | Bastrop Early Delivery | 2010-06-28 | 2010-06-28 | 2010-09-13 | 2010-09-10 | 100% | 100% | 100% | Complete
D-TE54 | Connectivity to Taylor | 2010-06-28 | 2010-06-28 | 2010-09-13 | 2010-09-10 | 100% | 100% | 100% | Complete
D-TE55 | Voice Service | 2010-08-16 | 2010-08-16 | 2010-09-13 | 2010-09-10 | 100% | 100% | 100% | Complete
D-TE56 | ATT FIBER SERVICES | 2010-06-29 | 2010-04-30 | 2010-11-22 | 2011-02-07 | 81% | 81% | 93% | Yellow
D-TE57 | Negotiate main contract with ATT | 2010-06-29 | 2010-04-30 | 2010-10-18 | 2011-02-04 | 84% | 84% | 97% | Yellow
D-TE58 | PHASE 2 SERVICES AUSTIN TO BASTROP | 2010-11-03 | 2010-09-22 | 2010-11-22 | 2010-10-29 | 100% | 100% | 100% | Complete
D-TE59 | PHASE 1 SERVICES TAYLOR TO BASTROP | 2010-10-19 | 2010-11-01 | 2010-11-02 | 2011-02-07 | 38% | 38% | 47% | Yellow
D-TE60 | Telecom Eqipment for 2010 and 2011 | 2010-07-06 | 2010-09-20 | 2010-12-03 | 2011-05-20 | 42% | 42% | 49% | Yellow
D-TE61 | Bastrop ETM and Voice Firewall | 2010-07-06 | 2010-11-01 | 2010-11-22 | 2011-03-04 | 44% | 44% | 44% | Yellow
D-TE62 | IPC NICE Bastrop | 2010-12-27 | 2010-12-27 | 2011-05-03 | 2011-05-03 | 6% | 7% | 20% | Green
D-TE63 | BASTROP CELLULAR | 2011-01-04 | 2011-02-07 | 2011-11-04 | 2011-03-16 | 0% | 0% | 0% | Yellow
D-TE64 | DEVELOP CONTRACT WITH CELLULAR SERVICE PROVIDER | 2011-01-04 | 2011-02-07 | 2011-03-14 | 2011-03-16 | 0% | 0% | 0% | Yellow
D-TE65 | BASTROP SATELLITE | 2011-01-04 | 2011-02-15 | 2011-12-09 | 2011-03-28 | 0% | 0% | 0% | Yellow
D-TE66 | DEVELOP CONTRACT WITH SATELLITE SERVICE PROVIDER | 2011-01-04 | 2011-02-15 | 2011-03-14 | 2011-03-28 | 0% | 0% | 0% | Yellow
D-TE67 | WAN and Secondary Fiber Taylor to Bastrop | 2010-09-20 | 2010-09-20 | 2011-05-17 | 2011-05-20 | 54% | 55% | 60% | Yellow
D-TE68 | DETERMINE THE CARRIER | 2010-09-13 | 2010-10-25 | 2010-11-12 | 2010-11-04 | 100% | 100% | 100% | Complete
D-TE69 | PRI IMPLEMENTATION | 2011-01-24 | 2010-10-28 | 2011-04-08 | 2011-03-03 | 73% | 73% | 73% | Yellow
D-TE70 | Construction | 2011-01-24 | 2010-12-06 | 2011-03-25 | 2010-12-15 | 100% | 100% | 100% | Complete
D-TE71 | INTERNET IMPLEMENTATION | 2011-01-17 | 2010-09-20 | 2011-04-08 | 2011-05-16 | 63% | 63% | 63% | Yellow
D-TE72 | Construction | 2011-01-17 | 2010-12-01 | 2011-03-25 | 2011-03-25 | 44% | 45% | 44% | Yellow
D-TE73 | OC48 IMPLEMENTATION | 2011-01-17 | 2010-10-25 | 2011-04-08 | 2011-04-27 | 23% | 23% | 23% | Yellow
D-TE74 | Construction | 2011-01-17 | 2010-11-24 | 2011-03-25 | 2011-04-21 | 15% | 15% | 15% | Yellow
D-TE75 | MISC WAN Implementation | 2010-10-04 | 2010-10-04 | 2011-03-28 | 2011-03-29 | 33% | 34% | 33% | Yellow
D-TE76 | ATT WAN Implementation | 2010-10-04 | 2010-10-04 | 2010-11-12 | 2011-05-20 | 73% | 73% | 92% | Yellow
D-TE77 | Construction | 2010-11-22 | 2010-11-22 | 2011-01-26 | 2011-01-31 | 67% | 68% | 100% | Complete
D-TE78 | Sprint WAN Implementation | 2010-10-11 | 2010-11-22 | 2010-11-19 | 2011-05-20 | 64% | 64% | 86% | Yellow
D-TE79 | Construction | 2010-11-22 | 2010-11-22 | 2011-01-26 | 2011-01-31 | 67% | 68% | 100% | Complete
D-TE80 | BASTROP FORUM | 2011-07-04 | 2011-04-29 | 2011-08-05 | 2011-05-02 | 0% | 0% | 0%
D-TE81 | Bastrop Emergency Notification System | 2011-04-29 | 2011-04-29 | 2011-05-02 | 2011-05-02 | 0% | 0% | 0%
S-TE82 | Ready to Cutover Production from Austin to Bastrop | 2011-05-03 | 2011-05-03 | 2011-05-03 | 2011-05-03 | 0% | 0% | 0%
D-TE83 | PROJECT GO LIVE AND SIGN OFF | 2011-12-12 | 2011-05-03 | 2011-12-22 | 2011-05-13 | 0% | 0% | 0%
D-TE84 | EXECUTION TO CLOSING PHASE TOLLGATE | 2011-12-26 | 2011-05-16 | 2011-12-30 | 2011-05-20 | 0% | 0% | 0%
S-TE85 | CLOSING | 2012-01-09 | 2011-05-23 | 2012-02-13 | 2011-06-22 | 0% | 0% | 0%
D-TE86 | CLOSING PHASE | 2012-01-09 | 2011-05-23 | 2012-02-13 | 2011-06-22 | 0% | 0% | 0%
D-TE87 | LESSONS LEARNED EXECUTION AND CLOSING PHASES | 2012-01-09 | 2011-05-23 | 2012-01-12 | 2011-05-26 | 0% | 0% | 0%
D-TE88 | INVOICE RECONCILIATION | 2012-01-13 | 2011-05-27 | 2012-02-08 | 2011-06-22 | 0% | 0% | 0%
- AT&T onsite installing ONS optical equipment to connect Taylor to Bastrop
- Alpheus internet equipment installation underway
- Evaluating DAS quotes
- Feb 8-9: Testing new Taylor PBX with new IPC
- Feb 18-20: Cutover new Taylor PBX system
- Alpheus service delivery expected April 4th
This Week's Activities and Accomplishments
Planned Activities for Next Week
Project Name:
Project Contacts:
Data Center Migration - Telecom
Dawn Moldenhour
Risks & Issues
Schedule Status:
Week Ending:
2/4/11
(Risk) Delays with carriers and/or vendor services could impact the project schedule.
GREEN

## Planning Model
LEGEND: BLUE - Complete, GREEN - No Delay, YELLOW - Delay w/o Impact, RED - Impacted Milestone
Upcoming Milestones
| Description | Baseline Start | Current Start | Baseline Finish | Current Finish | 1/21 % Complete | 1/28% Complete | 2/4% Complete | This Weeks Status | Variance Description | Mitigation
D-PGL1 | Planning Model Go-Live | 2010-12-01 | 2010-12-01 | 2011-04-01 | 2011-04-01 | 15% | 27% | 41% | Green
S-PGL2 | Planning Case Testing with TSPs | 2010-12-01 | 2010-12-01 | 2011-03-16 | 2011-03-15 | 22% | 45% | 66% | Green
D-PGL3 | TPIT Updates due to ERCOT | 2010-12-01 | 2010-12-01 | 2010-12-01 | 2010-12-01 | 100% | 100% | 100% | Complete
D-PGL4 | TSP TPIT Updates due to ERCOT | 2011-01-13 | 2011-01-13 | 2011-01-13 | 2011-01-13 | 0% | 100% | 100% | Complete
D-PGL5 | TPIT Interim due to TSPs from ERCOT | 2011-01-21 | 2011-01-21 | 2011-01-21 | 2011-01-21 | 0% | 100% | 100% | Complete
D-PGL6 | TPIT Interim Tuning | 2011-01-21 | 2011-01-21 | 2011-01-28 | 2011-01-28 | 0% | 0% | 100% | Complete
D-PGL7 | Create Final TPIT and Post | 2011-01-31 | 2011-01-31 | 2011-02-02 | 2011-02-04 | 0% | 0% | 100% | Complete
D-PGL8 | TPIT Update Complete | 2011-02-02 | 2011-02-04 | 2011-02-02 | 2011-02-04 | 0% | 0% | 100% | Complete
D-PGL9 | Pass 0 | 2010-12-08 | 2010-12-08 | 2011-01-07 | 2011-01-07 | 100% | 100% | 100% | Complete
D-PGL10 | Pass 1 | 2011-01-10 | 2011-01-10 | 2011-01-19 | 2011-01-19 | 63% | 100% | 100% | Complete
S-PGL11 | Pass 2 | 2011-01-20 | 2011-01-19 | 2011-02-02 | 2011-01-26 | 0% | 67% | 100% | Complete
D-PGL12 | Pass 3 | 2011-02-03 | 2011-01-27 | 2011-02-16 | 2011-02-15 | 0% | 0% | 47%
D-PGL13 | Pass 4 | 2011-02-17 | 2011-02-16 | 2011-03-02 | 2011-03-01 | 0% | 0% | 0%
D-PGL14 | Pass 5 | 2011-03-03 | 2011-03-02 | 2011-03-16 | 2011-03-15 | 0% | 0% | 0%
D-PGL15 | Defect Resolution | 2011-01-21 | 2011-01-21 | 2011-03-01 | 2011-03-01 | 0% | 0% | 1% | Green
S-PGL16 | Receive Release xxx from Siemens | 2011-01-21 | 2011-01-21 | 2011-01-21 | 2011-01-21 | 0% | 0% | 1% | Green
S-PGL17 | Install at ERCOT | 2011-01-21 | 2011-01-21 | 2011-01-24 | 2011-01-24 | 0% | 0% | 1% | Green
D-PGL18 | Dev Testing | 2011-01-25 | 2011-01-25 | 2011-02-14 | 2011-02-14 | 0% | 0% | 1% | Green
D-PGL19 | FAT Testing | 2011-02-15 | 2011-02-15 | 2011-02-23 | 2011-02-23 | 0% | 0% | 0%
S-PGL20 | iTest Testing | 2011-02-24 | 2011-02-24 | 2011-02-28 | 2011-02-28 | 0% | 0% | 0%
| Migrate to nProd | 2011-03-01 | 2011-03-01 | 2011-03-01 | 2011-03-01 | 0% | 0% | 0%
| Planning Model Go-Live Sequence | 2011-03-01 | 2011-03-01 | 2011-04-01 | 2011-04-01 | 0% | 0% | 0%
| Review Profiles and load standard PMCRs for Planning Model go-live | 2011-03-01 | 2011-03-01 | 2011-03-17 | 2011-03-17 | 0% | 0% | 0%
| Apply updates needed for Planning Model go-live | 2011-03-18 | 2011-03-18 | 2011-03-31 | 2011-03-31 | 0% | 0% | 0%
| Begin creating Planning Model (go-live) | 2011-04-01 | 2011-04-01 | 2011-04-01 | 2011-04-01 | 0% | 0% | 0%
- Completed TPIT update
- Completed Pass 3 TSP Profile and TSP PMCR submission
- Create Pass 3 case
This Week's Activities and Accomplishments
Planned Activities for Next Week
Project Name:
Project Contacts:
Planning Model
Janice Ayson
- The decision on how to move forward with Planning go-live was remanded back to ROS by TAC. We are moving forward with testing but have no definitive path to go-live at this time.
- Siemens is not responsive to our schedule. We are working multiple routes but our expected software delivery did not occur as scheduled and we have no expected delivery date at this time.
Risks & Issues
Schedule Status:
GREEN
Week Ending:
2/4/11

## Deferred Defects
LEGEND: BLUE - Complete, GREEN - No Delay, YELLOW - Delay w/o Impact, RED - Impacted Milestone
Upcoming Milestones
| Description | Baseline Start | Current Start | Baseline Finish | Current Finish | 1/21 % Complete | 1/28% Complete | 2/4% Complete | This Weeks Status | Variance Description | Mitigation
D-DD1 | Nodal Deferred Defects Project | 2010-12-01 | 2010-12-01 | 2011-09-22 | 2011-09-21 | 13% | 15% | 16% | Green
D-DD2 | Group 1 Release - January | 2010-12-01 | 2010-12-01 | 2011-01-24 | 2011-01-23 | 89% | 100% | 100% | Complete
S-DD3 | Group 1 Release complete | 2011-01-24 | 2011-01-23 | 2011-01-24 | 2011-01-23 | 0% | 100% | 100% | Complete
D-DD4 | Group 2 Release - March | 2011-01-03 | 2011-01-03 | 2011-03-25 | 2011-03-24 | 17% | 18% | 19% | Green
S-DD5 | Group 2 Release complete | 2011-03-25 | 2011-03-24 | 2011-03-25 | 2011-03-24 | 0% | 0% | 0%
D-DD6 | Group 3 Release - May | 2011-03-01 | 2011-03-01 | 2011-05-20 | 2011-05-19 | 0% | 0% | 0%
S-DD7 | Group 3 Release complete | 2011-05-20 | 2011-05-19 | 2011-05-20 | 2011-05-19 | 0% | 0% | 0%
D-DD8 | Group 4 Release - June | 2011-04-26 | 2011-04-26 | 2011-06-20 | 2011-06-17 | 0% | 0% | 0%
S-DD9 | Group 4 Release complete | 2011-06-20 | 2011-06-17 | 2011-06-20 | 2011-06-17 | 0% | 0% | 0%
D-DD10 | Group 5 Release - July | 2011-05-24 | 2011-05-24 | 2011-07-25 | 2011-07-22 | 0% | 0% | 0%
S-DD11 | Group 5 Release complete | 2011-07-25 | 2011-07-22 | 2011-07-25 | 2011-07-22 | 0% | 0% | 0%
D-DD12 | Group 6 Release - August | 2011-06-22 | 2011-06-22 | 2011-08-19 | 2011-08-18 | 0% | 0% | 0%
S-DD13 | Group 6 Release complete | 2011-08-19 | 2011-08-18 | 2011-08-19 | 2011-08-18 | 0% | 0% | 0%
D-DD14 | Group 7 Release - September | 2011-07-27 | 2011-07-27 | 2011-09-22 | 2011-09-21 | 0% | 0% | 0%
S-DD15 | Group 7 Release complete | 2011-09-22 | 2011-09-21 | 2011-09-22 | 2011-09-21 | 0% | 0% | 0%
- Continue development efforts for Deferred Defects Group 2 release
- Complete testing setup for DST testing
- Start DST testing cycles
EMS & OTS Stabilization /Deferred Defect projects:
- Continue evelopment of Group 2 defects
- Development of NPRR 285 (Curtailment Flag)
- Prepare for Off-cycle OTS release for Cycle 2 Training scenario
This Week's Activities and Accomplishments
Planned Activities for Next Week
Project Name:
Project Contacts:
Deferred Defects: Releases 1-7
Adam Martinez
Risks & Issues
Schedule Status:
Green
Week Ending:
2/4/11
- Completed iTest Refresh and clone creation
- Completed reforecast efforts for Stabilization and Deferred Defects EACs
- Finalized test plans and scope for DST testing
- Started test data prep
EMS & OTS Stabilization /Deferred Defect projects:
-Migrated EMS 6.17.1.4 (emergency release to fix RLC for non-spin resource schedule issue ) to nProd
- Development of Group 2 defects
- Development of NPRR 285 (Curtailment Flag)

## Zonal Decommissioning
LEGEND: BLUE - Complete, GREEN - No Delay, YELLOW - Delay w/o Impact, RED - Impacted Milestone
Upcoming Milestones
| Description | Baseline Start | Current Start | Baseline Finish | Current Finish | 1/21 % Complete | 1/28% Complete | 2/4% Complete | This Weeks Status | Variance Description | Mitigation
PR10015_01 Telcom-02 | [8 empty] | Yellow
PR10015_01 Telcom-03 | [8 empty] | Yellow
PR10015_01 Telcom-04 | [8 empty] | Yellow
PR10015_01 Telcom-05 | [8 empty] | Yellow
PR10015_01 Telcom-06 | [8 empty] | Yellow
PR10015_01 Telcom-07 | [8 empty] | Yellow
PR10015_01 Telcom-08 | [8 empty] | Yellow
PR10015_01 Telcom-09 | [8 empty] | Yellow
PR10015_01 Telcom-10 | [8 empty] | Yellow
PR10015_01 Telcom-11 | [8 empty] | Yellow
PR10015_01 Telcom-12 | [8 empty] | Yellow
PR10015_01 Telcom-13 | [8 empty] | Yellow
PR10015_01 Telcom-14 | [8 empty] | Yellow
PR10015_01 Telcom-15 | [8 empty] | Yellow
PR10015_01 Telcom-16 | [8 empty] | Yellow
PR10015_01 Telcom-17 | [8 empty] | Yellow
PR10015_01 Telcom-18 | [8 empty] | Yellow
PR10015_01 Telcom-19 | [8 empty] | Yellow
PR10015_01 Telcom-20 | [8 empty] | Yellow
PR10015_01 Telcom-21 | [8 empty] | Yellow
PR10015_01 Telcom-22 | [8 empty] | Yellow
PR10015_01 Telcom-23 | [8 empty] | Yellow
PR10015_01 Telcom-24 | [8 empty] | Yellow
PR10015_01 Telcom-25 | [8 empty] | Yellow
PR10015_01 Telcom-26 | [8 empty] | Yellow
PR10015_01 Telcom-27 | [8 empty] | Yellow
PR10015_01 Telcom-28 | [8 empty] | Yellow
PR10015_01 Telcom-29 | [8 empty] | Yellow
PR10015_01 Telcom-30 | [8 empty] | Yellow
PR10015_01 Telcom-31 | [8 empty] | Yellow
PR10015_01 Telcom-32 | [8 empty] | Yellow
PR10015_01 Telcom-33 | [8 empty] | Yellow
PR10015_01 Telcom-34 | [8 empty] | Yellow
PR10015_01 Telcom-35 | [8 empty] | Yellow
PR10015_01 Telcom-36 | [8 empty] | Yellow
PR10015_01 Telcom-37 | [8 empty] | Yellow
PR10015_01 Telcom-38 | [8 empty] | Yellow
PR10015_01 Telcom-39 | [8 empty] | Yellow
PR10015_01 Telcom-40 | [8 empty] | Yellow
PR10015_01 Telcom-41 | [8 empty] | Yellow
PR10015_01 Telcom-42 | [8 empty] | Yellow
PR10015_01 Telcom-43 | [8 empty] | Yellow
PR10015_01 Telcom-44 | [8 empty] | Yellow
PR10015_01 Telcom-45 | [8 empty] | Yellow
PR10015_01 Telcom-46 | [8 empty] | Yellow
PR10015_01 Telcom-47 | [8 empty] | Yellow
PR10015_01 Telcom-48 | [8 empty] | Yellow
PR10015_01 Telcom-49 | [8 empty] | Yellow
PR10015_01 Telcom-50 | [8 empty] | Yellow
PR10015_01 Telcom-51 | [8 empty] | Yellow
PR10015_01 Telcom-52 | [8 empty] | Yellow
PR10015_01 Telcom-53 | [8 empty] | Yellow
PR10015_01 Telcom-54 | [8 empty] | Yellow
PR10015_01 Telcom-55 | [8 empty] | Yellow
PR10015_01 Telcom-56 | [8 empty] | Yellow
PR10015_01 Telcom-57 | [8 empty] | Yellow
PR10015_01 Telcom-58 | [8 empty] | Yellow
PR10015_01 Telcom-59 | [8 empty] | Yellow
PR10015_01 Telcom-60 | [8 empty] | Yellow
PR10015_01 Telcom-61 | [8 empty] | Yellow
PR10015_01 Telcom-62 | [8 empty] | Yellow
PR10015_01 Telcom-63 | [8 empty] | Yellow
PR10015_01 Telcom-64 | [8 empty] | Yellow
PR10015_01 Telcom-65 | [8 empty] | Yellow
PR10015_01 Telcom-66 | [8 empty] | Yellow
PR10015_01 Telcom-67 | [8 empty] | Yellow
PR10015_01 Telcom-68 | [8 empty] | Yellow
PR10015_01 Telcom-69 | [8 empty] | Yellow
PR10015_01 Telcom-70 | [8 empty] | Yellow
PR10015_01 Telcom-71 | [8 empty] | Yellow
PR10015_01 Telcom-72 | [8 empty] | Yellow
PR10015_01 Telcom-73 | [8 empty] | Yellow
PR10015_01 Telcom-74 | [8 empty] | Yellow
PR10015_01 Telcom-75 | [8 empty] | Yellow
PR10015_01 Telcom-76 | [8 empty] | Yellow
PR10015_01 Telcom-77 | [8 empty] | Yellow
PR10015_01 Telcom-78 | [8 empty] | Yellow
PR10015_01 Telcom-79 | [8 empty] | Yellow
This Week's Activities and Accomplishments
Planned Activities for Next Week
Project Name:
Project Contacts:
Zonal Decommisioning
Jeff Robinson
Risks & Issues
Schedule Status:
GREEN
Week Ending:
2/4/11

## Texas SET 4.0
LEGEND: BLUE - Complete, GREEN - No Delay, YELLOW - Delay w/o Impact, RED - Impacted Milestone
Upcoming Milestones
| Description | Baseline Start | Current Start | Baseline Finish | Current Finish | 1/21 % Complete | 1/28% Complete | 2/4% Complete | This Weeks Status | Variance Description | Mitigation
PR10015_02 Telcom-01 | [8 empty] | Yellow
PR10015_02 Telcom-02 | [8 empty] | Yellow
PR10015_02 Telcom-03 | [8 empty] | Yellow
PR10015_02 Telcom-04 | [8 empty] | Yellow
PR10015_02 Telcom-05 | [8 empty] | Yellow
PR10015_02 Telcom-06 | [8 empty] | Yellow
PR10015_02 Telcom-07 | [8 empty] | Yellow
PR10015_02 Telcom-08 | [8 empty] | Yellow
PR10015_02 Telcom-09 | [8 empty] | Yellow
PR10015_02 Telcom-10 | [8 empty] | Yellow
PR10015_02 Telcom-11 | [8 empty] | Yellow
PR10015_02 Telcom-12 | [8 empty] | Yellow
PR10015_02 Telcom-13 | [8 empty] | Yellow
PR10015_02 Telcom-14 | [8 empty] | Yellow
PR10015_02 Telcom-15 | [8 empty] | Yellow
PR10015_02 Telcom-16 | [8 empty] | Yellow
PR10015_02 Telcom-17 | [8 empty] | Yellow
PR10015_02 Telcom-18 | [8 empty] | Yellow
PR10015_02 Telcom-19 | [8 empty] | Yellow
PR10015_02 Telcom-20 | [8 empty] | Yellow
PR10015_02 Telcom-21 | [8 empty] | Yellow
PR10015_02 Telcom-22 | [8 empty] | Yellow
PR10015_02 Telcom-23 | [8 empty] | Yellow
PR10015_02 Telcom-24 | [8 empty] | Yellow
PR10015_02 Telcom-25 | [8 empty] | Yellow
PR10015_02 Telcom-26 | [8 empty] | Yellow
PR10015_02 Telcom-27 | [8 empty] | Yellow
PR10015_02 Telcom-28 | [8 empty] | Yellow
PR10015_02 Telcom-29 | [8 empty] | Yellow
PR10015_02 Telcom-30 | [8 empty] | Yellow
PR10015_02 Telcom-31 | [8 empty] | Yellow
PR10015_02 Telcom-32 | [8 empty] | Yellow
PR10015_02 Telcom-33 | [8 empty] | Yellow
PR10015_02 Telcom-34 | [8 empty] | Yellow
PR10015_02 Telcom-35 | [8 empty] | Yellow
PR10015_02 Telcom-36 | [8 empty] | Yellow
PR10015_02 Telcom-37 | [8 empty] | Yellow
PR10015_02 Telcom-38 | [8 empty] | Yellow
PR10015_02 Telcom-39 | [8 empty] | Yellow
PR10015_02 Telcom-40 | [8 empty] | Yellow
PR10015_02 Telcom-41 | [8 empty] | Yellow
PR10015_02 Telcom-42 | [8 empty] | Yellow
PR10015_02 Telcom-43 | [8 empty] | Yellow
PR10015_02 Telcom-44 | [8 empty] | Yellow
PR10015_02 Telcom-45 | [8 empty] | Yellow
PR10015_02 Telcom-46 | [8 empty] | Yellow
PR10015_02 Telcom-47 | [8 empty] | Yellow
PR10015_02 Telcom-48 | [8 empty] | Yellow
PR10015_02 Telcom-49 | [8 empty] | Yellow
PR10015_02 Telcom-50 | [8 empty] | Yellow
PR10015_02 Telcom-51 | [8 empty] | Yellow
PR10015_02 Telcom-52 | [8 empty] | Yellow
PR10015_02 Telcom-53 | [8 empty] | Yellow
PR10015_02 Telcom-54 | [8 empty] | Yellow
PR10015_02 Telcom-55 | [8 empty] | Yellow
PR10015_02 Telcom-56 | [8 empty] | Yellow
PR10015_02 Telcom-57 | [8 empty] | Yellow
PR10015_02 Telcom-58 | [8 empty] | Yellow
PR10015_02 Telcom-59 | [8 empty] | Yellow
PR10015_02 Telcom-60 | [8 empty] | Yellow
PR10015_02 Telcom-61 | [8 empty] | Yellow
PR10015_02 Telcom-62 | [8 empty] | Yellow
PR10015_02 Telcom-63 | [8 empty] | Yellow
PR10015_02 Telcom-64 | [8 empty] | Yellow
PR10015_02 Telcom-65 | [8 empty] | Yellow
PR10015_02 Telcom-66 | [8 empty] | Yellow
PR10015_02 Telcom-67 | [8 empty] | Yellow
PR10015_02 Telcom-68 | [8 empty] | Yellow
PR10015_02 Telcom-69 | [8 empty] | Yellow
PR10015_02 Telcom-70 | [8 empty] | Yellow
PR10015_02 Telcom-71 | [8 empty] | Yellow
PR10015_02 Telcom-72 | [8 empty] | Yellow
PR10015_02 Telcom-73 | [8 empty] | Yellow
PR10015_02 Telcom-74 | [8 empty] | Yellow
PR10015_02 Telcom-75 | [8 empty] | Yellow
PR10015_02 Telcom-76 | [8 empty] | Yellow
PR10015_02 Telcom-77 | [8 empty] | Yellow
PR10015_02 Telcom-78 | [8 empty] | Yellow
PR10015_02 Telcom-79 | [8 empty] | Yellow
PR10015_02 Telcom-80 | [8 empty] | Yellow
PR10015_02 Telcom-81 | [8 empty] | Yellow
PR10015_02 Telcom-82 | [8 empty] | Yellow
PR10015_02 Telcom-83 | [8 empty] | Yellow
PR10015_02 Telcom-84 | [8 empty] | Yellow
PR10015_02 Telcom-85 | [8 empty] | Yellow
PR10015_02 Telcom-86 | [8 empty] | Yellow
PR10015_02 Telcom-87 | [8 empty] | Yellow
PR10015_02 Telcom-88 | [8 empty] | Yellow
PR10015_02 Telcom-89 | [8 empty] | Yellow
PR10015_02 Telcom-90 | [8 empty] | Yellow
PR10015_02 Telcom-91 | [8 empty] | Yellow
PR10015_02 Telcom-92 | [8 empty] | Yellow
PR10015_02 Telcom-93 | [8 empty] | Yellow
PR10015_02 Telcom-94 | [8 empty] | Yellow
PR10015_02 Telcom-95 | [8 empty] | Yellow
PR10015_02 Telcom-96 | [8 empty] | Yellow
PR10015_02 Telcom-97 | [8 empty] | Yellow
PR10015_02 Telcom-98 | [8 empty] | Yellow
PR10015_02 Telcom-99 | [8 empty] | Yellow
PR10015_02 Telcom-100 | [8 empty] | Yellow
PR10015_02 Telcom-101 | [8 empty] | Yellow
PR10015_02 Telcom-102 | [8 empty] | Yellow
PR10015_02 Telcom-103 | [8 empty] | Yellow
PR10015_02 Telcom-104 | [8 empty] | Yellow
PR10015_02 Telcom-105 | [8 empty] | Yellow
PR10015_02 Telcom-106 | [8 empty] | Yellow
PR10015_02 Telcom-107 | [8 empty] | Yellow
PR10015_02 Telcom-108 | [8 empty] | Yellow
PR10015_02 Telcom-109 | [8 empty] | Yellow
PR10015_02 Telcom-110 | [8 empty] | Yellow
PR10015_02 Telcom-111 | [8 empty] | Yellow
PR10015_02 Telcom-112 | [8 empty] | Yellow
PR10015_02 Telcom-113 | [8 empty] | Yellow
This Week's Activities and Accomplishments
Planned Activities for Next Week
Project Name:
Project Contacts:
Texas SET 4.0
Risks & Issues
Schedule Status:
Week Ending:
2/4/11
Green

## Information Lifecycle Mgmt Ph2
LEGEND: BLUE - Complete, GREEN - No Delay, YELLOW - Delay w/o Impact, RED - Impacted Milestone
UpcomingMilestones
| Description | Baseline Start | Current Start | Baseline Finish | Current Finish | 1/21 % Complete | 1/28% Complete | 2/4% Complete | This Weeks Status | VarianceDescription | Mitigation
d-ILM1 | PR90006_02 – ILM Commercial Systems Ph2 | 2010-04-30 | 2010-04-30 | 2013-02-28 | 2013-02-28 | 0% | 34% | 35% | Green
s-ILM2 | PLANNING PHASE | 2010-05-24 | 2010-05-24 | 2011-03-04 | 2011-03-31 | 0% | 44% | 51% | Yellow
d-ILM3 | Planning Detail - Lodestar and Siebel | 2010-05-24 | 2010-05-24 | 2011-01-21 | 2011-02-28 | 0% | 67% | 88% | Yellow
d-ILM4 | ILM Lodestar | 2010-05-24 | 2010-05-24 | 2011-01-21 | 2011-02-28 | 0% | 25% | 76% | Yellow
d-ILM5 | Lodestar Business Requirements | 2010-05-24 | 2010-05-24 | 2010-08-09 | 2010-08-02 | 0% | 100% | 100% | Complete
d-ILM6 | Lodestar Test Plan | 2010-08-02 | 2010-08-02 | 2011-01-14 | 2011-01-21 | 0% | 0% | 100% | Complete
d-ILM7 | Review and approve Lodestar test plan | 2010-12-15 | 2011-01-14 | 2011-01-14 | 2011-01-21 | 0% | 0% | 100% | Complete
d-ILM8 | Lodestar Evaluation for ILM | 2010-08-02 | 2010-12-17 | 2010-10-08 | 2011-02-28 | 0% | 0% | 0% | Yellow
d-ILM9 | Lodestar Conceptual Solution Design | 2010-10-20 | 2010-10-20 | 2010-10-25 | 2010-10-26 | 0% | 100% | 100% | Complete
s-ILM10 | Review and approve Lodestar CSD | 2010-10-26 | 2010-10-26 | 2010-10-26 | 2010-10-26 | 0% | 100% | 100% | Complete
d-ILM11 | Lodestar Detailed Design | 2010-11-16 | 2010-11-16 | 2010-12-15 | 2010-12-16 | 0% | 100% | 100% | Complete
d-ILM12 | Review and approve Lodestar Detailed Design document | 2010-12-08 | 2010-12-08 | 2010-12-16 | 2010-12-16 | 0% | 100% | 100% | Complete
s-ILM13 | ILM Siebel | 2010-06-07 | 2010-06-07 | 2011-01-14 | 2011-01-14 | 0% | 97% | 100% | Complete
d-ILM14 | Siebel Business Requirements | 2010-06-07 | 2010-06-07 | 2010-08-02 | 2010-08-02 | 0% | 100% | 100% | Complete
s-ILM15 | Business Operations Review | 2010-06-07 | 2010-06-07 | 2010-06-07 | 2010-06-07 | 0% | 100% | 100% | Complete
d-ILM16 | Operation & Infrastructure review | 2010-06-07 | 2010-06-07 | 2010-06-07 | 2010-06-07 | 0% | 100% | 100% | Complete
s-ILM17 | Perform Data classification | 2010-06-07 | 2010-06-07 | 2010-06-07 | 2010-06-07 | 0% | 100% | 100% | Complete
d-ILM18 | Review and approve Siebel requirements document | 2010-08-02 | 2010-08-02 | 2010-08-02 | 2010-08-02 | 0% | 100% | 100% | Complete
d-ILM19 | Siebel Test Plan | 2010-08-03 | 2010-08-03 | 2011-01-14 | 2011-01-14 | 0% | 0% | 100% | Complete
d-ILM20 | Review and Approve Siebel Test Plan | 2011-01-14 | 2011-01-14 | 2011-01-14 | 2011-01-14 | 0% | 0% | 100% | Complete
d-ILM21 | Siebel Conceptual Solution Design | 2010-08-02 | 2010-08-02 | 2010-09-28 | 2010-09-28 | 0% | 100% | 100% | Complete
d-ILM22 | Review and approve Siebel CSD | 2010-08-27 | 2010-08-27 | 2010-08-27 | 2010-08-27 | 0% | 100% | 100% | Complete
s-ILM23 | Siebel Detailed Design | 2010-09-28 | 2010-09-28 | 2010-11-15 | 2010-11-16 | 0% | 100% | 100% | Complete
d-ILM24 | Review and approve Siebel Detailed Design | 2010-10-25 | 2010-10-25 | 2010-11-16 | 2010-11-16 | 0% | 100% | 100% | Complete
s-ILM25 | Planning Detail - ISM, MIR, RCD | 2010-05-24 | 2011-01-03 | 2011-04-04 | 2011-03-31 | 0% | 0% | 7% | Green
d-ILM26 | ILM MIR | 2011-03-01 | 2011-03-01 | 2011-03-14 | 2011-03-14 | 0% | 0% | 0%
s-ILM27 | ILM RCD | 2011-03-01 | 2011-03-01 | 2011-03-14 | 2011-03-14 | 0% | 0% | 0%
d-ILM28 | ILM MV90 | 2011-03-01 | 2011-03-01 | 2011-04-04 | 2011-03-28 | 0% | 0% | 0%
s-ILM29 | ILM ISM | 2010-05-24 | 2011-01-03 | 2011-03-25 | 2011-03-31 | 0% | 0% | 9% | Yellow
d-ILM30 | ISM Business Requirements | 2010-12-09 | 2011-01-03 | 2010-12-07 | 2011-03-31 | 0% | 0% | 18% | Yellow
s-ILM31 | ISM Analysis | 2010-12-09 | 2011-01-03 | 2010-12-22 | 2011-01-14 | 0% | 0% | 0% | Yellow
d-ILM32 | Review and approve ISM business requirements | 2011-01-10 | 2011-03-21 | 2011-02-04 | 2011-03-31 | 0% | 0% | 0% | Yellow
d-ILM33 | ISM High Level Test Plan | 2011-02-07 | 2011-02-07 | 2011-01-14 | 2011-03-25 | 0% | 0% | 0%
d-ILM34 | EXECUTION PHASE | NA | 2011-03-31 | NA | 2012-12-31 | 0% | 0% | 0%
d-ILM35 | Execution Detail - Lodestar and Siebel | NA | 2011-04-01 | NA | 2012-03-08 | 0% | 0% | 0%
d-ILM36 | Execution Detail - ISM, MIR, RCD | NA | 2011-04-01 | NA | 2012-12-27 | 0% | 0% | 0%
d-ILM37 | CLOSING PHASE | NA | 2012-12-31 | NA | 2013-02-28 | 0% | 0% | 0%
d-ILM38 | LESSONS LEARNED EXECUTION AND CLOSING PHASES | NA | 2012-12-31 | NA | 2012-12-31 | 0% | 0% | 0%
s-ILM39 | MEETING TO CONDUCT LESSONS LEARNED Optional | NA | 2012-12-31 | NA | 2012-12-31 | 0% | 0% | 0%
d-ILM40 | INVOICE RECONCILIATION | NA | 2012-12-31 | NA | 2012-12-31 | 0% | 0% | 0%
s-ILM41 | PROJECT MANAGEMENT AND ADMINISTRATION CLOSING PHASE | NA | 2012-12-31 | NA | 2012-12-31 | 0% | 0% | 0%
s-ILM42 | PROJECT CLOSED | NA | 2013-02-28 | NA | 2013-02-28 | 0% | 0% | 0%
This Week's Activities and Accomplishments
Planned Activities for Next Week
Project Name:
Project Contacts:
Information Lifecycle Management Phase 2
PM - Heather Day
Business Owner - Jackie Ashbaugh
Risks & Issues
Schedule Status:
Week Ending:
2/4/11
Green
- Distributed WBS to project team to review gaps, prepare for estimates and finalize execution schedule.
- Continued analysis and design activities for Lodestar and Siebel replication.
- Completed team review of replication multiplexing CSD.
- Continued analysis and design of data purge utility for ISM.
- Continue analysis of impacts to downstream ISM products.
- Completed draft of ISM data purge utility CSD.
- Continue design activities for Lodestar and Siebel replication.
- Finalize ande distribute replication multiplexing CSD for approvals.
- Distribute ISM data purge utility CSD for team review.
- Continue POC for replication multiplexing.
- Continue design of data purge utility for ISM.
- Continue analysis of impacts to downstream ISM products.
- EIS resource constraints from 2010 have delayed all Planning Phase deliverables related to ISM. The schedule is being reworked and is currently in review with the team. A change control is anticipated to address the changes. Note -- no impact is anticipated to the overall project delivery. Activities are being reorganized to keep Lodestar and Siebel source system deliverables on track while continuing to move forward with ISM analysis and planning deliverables. Once execution activities for Lodestar and Siebel source systems are complete the planning for ISM will also be complete and execution activities for ISM can begin.

## Settlement System Upgrade
LEGEND: BLUE - Complete, GREEN - No Delay, YELLOW - Delay w/o Impact, RED - Impacted Milestone
UpcomingMilestones
| Description | Baseline Start | Current Start | Baseline Finish | Current Finish | 1/21 % Complete | 1/28% Complete | 2/4% Complete | This Weeks Status | VarianceDescription | Mitigation
D-SSU1 | PR10052_01 Settlement System Upgrade | 2010-03-22 | 2010-03-22 | 2011-09-08 | 2012-01-11 | 40% | 40% | 40% | Yellow
S-SSU2 | INITIATION | 2010-03-22 | 2010-03-22 | 2010-05-07 | 2010-09-20 | 100% | 100% | 100% | Complete
S-SSU3 | PLANNING PHASE | 2010-09-20 | 2010-09-20 | 2011-09-08 | 2011-08-24 | 35% | 34% | 36% | Green
D-SSU4 | Project Requirements | 2010-10-12 | 2010-09-23 | 2010-11-15 | 2011-02-02 | 70% | 70% | 100% | Complete
D-SSU5 | Business Requirement Validation | 2010-10-12 | 2010-10-14 | 2011-01-07 | 2011-02-02 | 64% | 67% | 67% | Yellow
S-SSU6 | Requirements Complete | 2011-01-07 | 2011-02-02 | 2011-01-07 | 2011-02-02 | 0% | 0% | 0% | Yellow
D-SSU7 | Conceptual Design | 2011-03-31 | 2011-01-21 | 2011-05-31 | 2011-05-13 | 17% | 17% | 10%
S-SSU8 | Conceptual Design Complete | 2011-05-31 | 2011-05-13 | 2011-05-31 | 2011-05-13 | 0% | 0% | 0%
D-SSU9 | Technical Architecture | 2011-06-17 | 2011-05-31 | 2011-07-21 | 2011-07-05 | 0% | 0% | 0%
S-SSU10 | Technical Architecture Complete | 2011-07-21 | 2011-07-05 | 2011-07-21 | 2011-07-05 | 0% | 0% | 0%
D-SSU11 | Security Risk Assessment | 2011-07-22 | 2011-07-05 | 2011-08-04 | 2011-07-19 | 0% | 0% | 0%
D-SSU12 | Test Plan | 2011-01-10 | 2011-01-26 | 2011-02-04 | 2011-03-02 | 2% | 1% | 1% | Yellow
S-SSU13 | Test Plan Complete | 2011-02-04 | 2011-03-02 | 2011-02-04 | 2011-03-02 | 0% | 0% | 0%
D-SSU14 | Planning Phase Administrative | 2010-09-20 | 2010-09-20 | 2011-09-08 | 2011-08-24 | 18% | 19% | 16% | Yellow
S-SSU15 | EXECUTION | NA | 2011-08-09 | NA | 2011-12-26 | 0% | 0% | 0%
D-SSU16 | PROJECT EXECUTION KICKOFF | NA | 2011-08-09 | NA | 2011-08-11 | 0% | 0% | 0%
D-SSU17 | PROCURE HARDWARE AND SOFTWARE | NA | 2011-08-09 | NA | 2011-09-12 | 0% | 0% | 0%
D-SSU18 | ARCHITECTURE AND SYSTEMS INSTALLATION | NA | 2011-08-09 | NA | 2011-09-29 | 0% | 0% | 0%
D-SSU19 | SERVER BUILD | NA | 2011-08-09 | NA | 2011-09-26 | 0% | 0% | 0%
D-SSU20 | SERVER INSTALLATION AND CABLING | NA | 2011-09-12 | NA | 2011-09-14 | 0% | 0% | 0%
D-SSU21 | SERVER CONFIGURATION AND SECURITY CHECK | NA | 2011-08-09 | NA | 2011-09-23 | 0% | 0% | 0%
D-SSU22 | SERVER NODE ACCESS REQUEST | NA | 2011-09-22 | NA | 2011-09-26 | 0% | 0% | 0%
D-SSU23 | APPLICATION INSTALLATION | NA | 2011-09-26 | NA | 2011-09-29 | 0% | 0% | 0%
D-SSU24 | DEVELOPMENT | NA | 2011-08-09 | NA | 2011-10-04 | 0% | 0% | 0%
D-SSU25 | TEST CASE DEVELOPMENT | NA | 2011-10-04 | NA | 2011-10-27 | 0% | 0% | 0%
D-SSU26 | Development | NA | 2011-10-06 | NA | 2011-10-07 | 0% | 0% | 0%
D-SSU27 | PRODUCT | NA | 2011-10-07 | NA | 2011-10-11 | 0% | 0% | 0%
D-SSU28 | INTEGRATION | NA | 2011-10-11 | NA | 2011-10-14 | 0% | 0% | 0%
D-SSU29 | UAT | NA | 2011-10-14 | NA | 2011-10-19 | 0% | 0% | 0%
D-SSU30 | MARKET | NA | 2011-10-19 | NA | 2011-10-24 | 0% | 0% | 0%
D-SSU31 | REGRESSION | NA | 2011-10-24 | NA | 2011-10-27 | 0% | 0% | 0%
D-SSU32 | PRODUCTION SUPPORT IMPLEMENTATION PLAN | NA | 2011-08-09 | NA | 2011-11-01 | 0% | 0% | 0%
D-SSU33 | TRAINING PLAN | NA | 2011-08-09 | NA | 2011-10-28 | 0% | 0% | 0%
D-SSU34 | TESTING | NA | 2011-08-09 | NA | 2011-10-25 | 0% | 0% | 0%
D-SSU35 | DEV TEST | NA | 2011-09-12 | NA | 2011-09-15 | 0% | 0% | 0%
D-SSU36 | PTEST | NA | 2011-09-12 | NA | 2011-10-13 | 0% | 0% | 0%
D-SSU37 | MIGRATION TO PTEST | NA | 2011-09-12 | NA | 2011-09-14 | 0% | 0% | 0%
D-SSU38 | PERFORM PRODUCT TEST | NA | 2011-10-06 | NA | 2011-10-13 | 0% | 0% | 0%
D-SSU39 | ITEST | NA | 2011-09-12 | NA | 2011-10-14 | 0% | 0% | 0%
D-SSU40 | INTEGRATION TEST QA | NA | 2011-10-07 | NA | 2011-10-13 | 0% | 0% | 0%
D-SSU41 | USER ACCEPTANCE TEST UAT | NA | 2011-10-13 | NA | 2011-10-19 | 0% | 0% | 0%
D-SSU42 | PERFORM UAT TEST | NA | 2011-10-14 | NA | 2011-10-19 | 0% | 0% | 0%
D-SSU43 | MARKET TEST CERT MOTE | NA | 2011-10-19 | NA | 2011-10-25 | 0% | 0% | 0%
D-SSU44 | MIGRATION TO CERT MOTE | NA | 2011-10-20 | NA | 2011-10-21 | 0% | 0% | 0%
D-SSU45 | PERFORM MARKET TESTING | NA | 2011-10-21 | NA | 2011-10-25 | 0% | 0% | 0%
D-SSU46 | TRAINING | NA | 2011-08-09 | NA | 2011-11-02 | 0% | 0% | 0%
D-SSU47 | MIGRATION PLAN | NA | 2011-11-02 | NA | 2011-11-04 | 0% | 0% | 0%
D-SSU48 | IMPLEMENTATION TO PRODUCTION | NA | 2011-08-09 | NA | 2011-11-24 | 0% | 0% | 0%
D-SSU49 | PRODUCTION RELEASE COORDINATION | NA | 2011-11-04 | NA | 2011-11-10 | 0% | 0% | 0%
D-SSU50 | MIGRATION | NA | 2011-11-10 | NA | 2011-11-22 | 0% | 0% | 0%
D-SSU51 | PROJECT SIGN OFF | NA | 2011-11-24 | NA | 2011-11-30 | 0% | 0% | 0%
D-SSU52 | AS BUILT DOCUMENTATION | NA | 2011-11-30 | NA | 2011-12-05 | 0% | 0% | 0%
D-SSU53 | TOLLGATE EXECUTION TO CLOSING | NA | 2011-12-05 | NA | 2011-12-09 | 0% | 0% | 0%
D-SSU54 | CLOSING | NA | 2011-12-09 | NA | 2012-01-11 | 0% | 0% | 0%
D-SSU55 | LESSONS LEARNED EXECUTION AND CLOSING PHASES | NA | 2011-12-09 | NA | 2011-12-29 | 0% | 0% | 0%
D-SSU56 | INVOICE RECONCILIATION | NA | 2011-12-09 | NA | 2012-01-09 | 0% | 0% | 0%
- Business owners approved requirements
- Work on test plan
- Start drafting TA for the DEV environment
- Meet with Cleary over contractors on project
This Week's Activities and Accomplishments
Planned Activities for Next Week
Project Name:
Project Contacts:
Settlement System Upgrade
Dawn Moldenhour
(Risk) Project is at risk of slipping schedule due to not having contractors extended, this is because higher priority projects will take precedence.
Risks & Issues
Schedule Status:
Week Ending:
2/4/11
Green

## Likewise Upgrade
LEGEND: BLUE - Complete, GREEN - No Delay, YELLOW - Delay w/o Impact, RED - Impacted Milestone
UpcomingMilestones
| Description | Baseline Start | Current Start | Baseline Finish | Current Finish | 1/21 % Complete | 1/28% Complete | 2/4% Complete | This Weeks Status | VarianceDescription | Mitigation
PR10016_03 Network-01 | [8 empty] | Yellow
PR10016_03 Network-02 | [8 empty] | Yellow
PR10016_03 Network-03 | [8 empty] | Yellow
PR10016_03 Network-04 | [8 empty] | Yellow
PR10016_03 Network-05 | [8 empty] | Yellow
PR10016_03 Network-06 | [8 empty] | Yellow
PR10016_03 Network-07 | [8 empty] | Yellow
PR10016_03 Network-08 | [8 empty] | Yellow
PR10016_03 Network-09 | [8 empty] | Yellow
PR10016_03 Network-10 | [8 empty] | Yellow
PR10016_03 Network-11 | [8 empty] | Yellow
PR10016_03 Network-12 | [8 empty] | Yellow
PR10016_03 Network-13 | [8 empty] | Yellow
PR10016_03 Network-14 | [8 empty] | Yellow
PR10016_03 Network-15 | [8 empty] | Yellow
PR10016_03 Network-16 | [8 empty] | Yellow
PR10016_03 Network-17 | [8 empty] | Yellow
PR10016_03 Network-18 | [8 empty] | Yellow
PR10016_03 Network-19 | [8 empty] | Yellow
PR10016_03 Network-20 | [8 empty] | Yellow
PR10016_03 Network-21 | [8 empty] | Yellow
PR10016_03 Network-22 | [8 empty] | Yellow
PR10016_03 Network-23 | [8 empty] | Yellow
PR10016_03 Network-24 | [8 empty] | Yellow
PR10016_03 Network-25 | [8 empty] | Yellow
PR10016_03 Network-26 | [8 empty] | Yellow
PR10016_03 Network-27 | [8 empty] | Yellow
PR10016_03 Network-28 | [8 empty] | Yellow
PR10016_03 Network-29 | [8 empty] | Yellow
PR10016_03 Network-30 | [8 empty] | Yellow
PR10016_03 Network-31 | [8 empty] | Yellow
PR10016_03 Network-32 | [8 empty] | Yellow
PR10016_03 Network-33 | [8 empty] | Yellow
PR10016_03 Network-34 | [8 empty] | Yellow
PR10016_03 Network-35 | [8 empty] | Yellow
PR10016_03 Network-36 | [8 empty] | Yellow
PR10016_03 Network-37 | [8 empty] | Yellow
PR10016_03 Network-38 | [8 empty] | Yellow
PR10016_03 Network-39 | [8 empty] | Yellow
PR10016_03 Network-40 | [8 empty] | Yellow
PR10016_03 Network-41 | [8 empty] | Yellow
PR10016_03 Network-42 | [8 empty] | Yellow
PR10016_03 Network-43 | [8 empty] | Yellow
PR10016_03 Network-44 | [8 empty] | Yellow
PR10016_03 Network-45 | [8 empty] | Yellow
PR10016_03 Network-46 | [8 empty] | Yellow
PR10016_03 Network-47 | [8 empty] | Yellow
PR10016_03 Network-48 | [8 empty] | Yellow
PR10016_03 Network-49 | [8 empty] | Yellow
PR10016_03 Network-50 | [8 empty] | Yellow
PR10016_03 Network-51 | [8 empty] | Yellow
PR10016_03 Network-52 | [8 empty] | Yellow
PR10016_03 Network-53 | [8 empty] | Yellow
PR10016_03 Network-54 | [8 empty] | Yellow
PR10016_03 Network-55 | [8 empty] | Yellow
PR10016_03 Network-56 | [8 empty] | Yellow
PR10016_03 Network-57 | [8 empty] | Yellow
PR10016_03 Network-58 | [8 empty] | Yellow
PR10016_03 Network-59 | [8 empty] | Yellow
PR10016_03 Network-60 | [8 empty] | Yellow
PR10016_03 Network-61 | [8 empty] | Yellow
PR10016_03 Network-62 | [8 empty] | Yellow
PR10016_03 Network-63 | [8 empty] | Yellow
PR10016_03 Network-64 | [8 empty] | Yellow
PR10016_03 Network-65 | [8 empty] | Yellow
PR10016_03 Network-66 | [8 empty] | Yellow
PR10016_03 Network-67 | [8 empty] | Yellow
PR10016_03 Network-68 | [8 empty] | Yellow
PR10016_03 Network-69 | [8 empty] | Yellow
PR10016_03 Network-70 | [8 empty] | Yellow
PR10016_03 Network-71 | [8 empty] | Yellow
This Week's Activities and Accomplishments
Planned Activities for Next Week
Project Name:
Project Contacts:
Likewise Upgrade
Risks & Issues
Schedule Status:
Week Ending:
2/4/11
Green

## MarkeTrak Upgrade & Enh
LEGEND: BLUE - Complete, GREEN - No Delay, YELLOW - Delay w/o Impact, RED - Impacted Milestone
UpcomingMilestones
| Description | Baseline Start | Current Start | Baseline Finish | Current Finish | 1/21 % Complete | 1/28% Complete | 2/4% Complete | This Weeks Status | VarianceDescription | Mitigation
PR10016_03 Network-01 | [8 empty] | Yellow
PR10016_03 Network-02 | [8 empty] | Yellow
PR10016_03 Network-03 | [8 empty] | Yellow
PR10016_03 Network-04 | [8 empty] | Yellow
PR10016_03 Network-05 | [8 empty] | Yellow
PR10016_03 Network-06 | [8 empty] | Yellow
PR10016_03 Network-07 | [8 empty] | Yellow
PR10016_03 Network-08 | [8 empty] | Yellow
PR10016_03 Network-09 | [8 empty] | Yellow
PR10016_03 Network-10 | [8 empty] | Yellow
PR10016_03 Network-11 | [8 empty] | Yellow
PR10016_03 Network-12 | [8 empty] | Yellow
PR10016_03 Network-13 | [8 empty] | Yellow
PR10016_03 Network-14 | [8 empty] | Yellow
PR10016_03 Network-15 | [8 empty] | Yellow
PR10016_03 Network-16 | [8 empty] | Yellow
PR10016_03 Network-17 | [8 empty] | Yellow
PR10016_03 Network-18 | [8 empty] | Yellow
PR10016_03 Network-19 | [8 empty] | Yellow
PR10016_03 Network-20 | [8 empty] | Yellow
PR10016_03 Network-21 | [8 empty] | Yellow
PR10016_03 Network-22 | [8 empty] | Yellow
PR10016_03 Network-23 | [8 empty] | Yellow
PR10016_03 Network-24 | [8 empty] | Yellow
PR10016_03 Network-25 | [8 empty] | Yellow
PR10016_03 Network-26 | [8 empty] | Yellow
PR10016_03 Network-27 | [8 empty] | Yellow
PR10016_03 Network-28 | [8 empty] | Yellow
PR10016_03 Network-29 | [8 empty] | Yellow
PR10016_03 Network-30 | [8 empty] | Yellow
PR10016_03 Network-31 | [8 empty] | Yellow
PR10016_03 Network-32 | [8 empty] | Yellow
PR10016_03 Network-33 | [8 empty] | Yellow
PR10016_03 Network-34 | [8 empty] | Yellow
PR10016_03 Network-35 | [8 empty] | Yellow
PR10016_03 Network-36 | [8 empty] | Yellow
PR10016_03 Network-37 | [8 empty] | Yellow
PR10016_03 Network-38 | [8 empty] | Yellow
PR10016_03 Network-39 | [8 empty] | Yellow
PR10016_03 Network-40 | [8 empty] | Yellow
PR10016_03 Network-41 | [8 empty] | Yellow
PR10016_03 Network-42 | [8 empty] | Yellow
PR10016_03 Network-43 | [8 empty] | Yellow
PR10016_03 Network-44 | [8 empty] | Yellow
PR10016_03 Network-45 | [8 empty] | Yellow
PR10016_03 Network-46 | [8 empty] | Yellow
PR10016_03 Network-47 | [8 empty] | Yellow
PR10016_03 Network-48 | [8 empty] | Yellow
PR10016_03 Network-49 | [8 empty] | Yellow
PR10016_03 Network-50 | [8 empty] | Yellow
PR10016_03 Network-51 | [8 empty] | Yellow
PR10016_03 Network-52 | [8 empty] | Yellow
PR10016_03 Network-53 | [8 empty] | Yellow
PR10016_03 Network-54 | [8 empty] | Yellow
PR10016_03 Network-55 | [8 empty] | Yellow
PR10016_03 Network-56 | [8 empty] | Yellow
PR10016_03 Network-57 | [8 empty] | Yellow
PR10016_03 Network-58 | [8 empty] | Yellow
PR10016_03 Network-59 | [8 empty] | Yellow
PR10016_03 Network-60 | [8 empty] | Yellow
PR10016_03 Network-61 | [8 empty] | Yellow
PR10016_03 Network-62 | [8 empty] | Yellow
PR10016_03 Network-63 | [8 empty] | Yellow
PR10016_03 Network-64 | [8 empty] | Yellow
PR10016_03 Network-65 | [8 empty] | Yellow
PR10016_03 Network-66 | [8 empty] | Yellow
PR10016_03 Network-67 | [8 empty] | Yellow
PR10016_03 Network-68 | [8 empty] | Yellow
PR10016_03 Network-69 | [8 empty] | Yellow
PR10016_03 Network-70 | [8 empty] | Yellow
PR10016_03 Network-71 | [8 empty] | Yellow
This Week's Activities and Accomplishments
Planned Activities for Next Week
Project Name:
Project Contacts:
MarkeTrak Upgrade & Enhancements
Risks & Issues
Schedule Status:
Week Ending:
2/4/11
24
Green

## Data Research & Rptng
LEGEND: BLUE - Complete, GREEN - No Delay, YELLOW - Delay w/o Impact, RED - Impacted Milestone
UpcomingMilestones
| Description | Baseline Start | Current Start | Baseline Finish | Current Finish | 1/21 % Complete | 1/28% Complete | 2/4% Complete | This Weeks Status | VarianceDescription | Mitigation
D-DRR1 | PR 50088_01 Data Research and Reporting | 2008-09-25 | 2006-05-19 | 2009-04-30 | 2011-10-31 | 86% | 88% | 88% | Yellow
S-DRR2 | INITIATION | 2006-11-10 | 2006-11-10 | 2009-04-29 | 2009-04-29 | 100% | 100% | 100% | Complete
D-DRR3 | INITIATION PHASE | 2006-11-10 | 2006-11-10 | 2009-04-29 | 2009-04-29 | 100% | 100% | 100% | Complete
D-DRR4 | SCHEDULING REVIEW TO DEFINE PLANNING PHASE | 2006-11-13 | 2006-11-13 | 2009-04-29 | 2009-04-29 | 100% | 100% | 100% | Complete
D-DRR5 | PROJECT CHARTER | 2006-12-22 | 2006-12-22 | 2006-12-28 | 2006-12-28 | 100% | 100% | 100% | Complete
D-DRR6 | INITIATION TO PLANNING PHASE DIVISIONAL TOLLGATE | 2007-02-16 | 2007-02-16 | 2007-03-01 | 2007-03-01 | 100% | 100% | 100% | Complete
S-DRR7 | PLANNING | 2008-09-25 | 2006-05-19 | 2009-04-30 | 2009-08-14 | 100% | 100% | 100% | Complete
D-DRR8 | PLANNING PHASE | 2008-09-25 | 2006-05-19 | 2009-04-30 | 2009-08-14 | 100% | 100% | 100% | Complete
D-DRR9 | PROJECT REQUIREMENTS_Old | 2007-02-26 | 2007-02-26 | 2009-02-27 | 2009-02-27 | 100% | 100% | 100% | Complete
S-DRR10 | PROJECT REQUIREMENTS | 2007-12-17 | 2007-12-17 | 2009-05-10 | 2009-05-10 | 100% | 100% | 100% | Complete
S-DRR11 | CSD Completion Milestone (Development) | 2009-07-01 | 2009-07-01 | 2009-07-01 | 2009-07-01 | 100% | 100% | 100% | Complete
S-DRR12 | EXECUTION | 2009-08-17 | 2009-08-17 | 2011-10-31 | 2011-10-31 | 80% | 83% | 84% | Green
D-DRR13 | EXECUTION PHASE | 2009-08-17 | 2009-08-17 | 2011-10-31 | 2011-10-31 | 80% | 83% | 84% | Green
D-DRR14 | EXECUTION AND CONTROL PHASE | 2009-08-17 | 2009-08-17 | 2011-10-31 | 2011-10-31 | 80% | 83% | 84% | Green
D-DRR15 | RELEASE 1 | 2008-10-09 | 2009-08-17 | 2009-04-30 | 2010-04-30 | 100% | 100% | 100% | Complete
S-DRR16 | Release 1 Go Live PMO EXEC MILESTONE 9 | 2010-04-11 | 2010-04-11 | 2010-04-11 | 2010-04-11 | 100% | 100% | 100% | Complete
D-DRR17 | RELEASE 2 | 2010-04-12 | 2010-04-12 | 2011-10-31 | 2011-10-31 | 67% | 71% | 73% | Green
D-DRR18 | Release 2: 2010 - Detailed Design and Development | 2010-04-12 | 2010-04-12 | 2011-10-31 | 2011-10-31 | 97% | 100% | 100% | Complete
S-DRR19 | Release 2 - Start | 2010-04-30 | 2010-04-30 | 2010-04-30 | 2010-04-30 | 100% | 100% | 100% | Complete
D-DRR20 | Business Requirements - Review Existing Documentation | 2010-05-03 | 2010-05-03 | 2010-06-30 | 2010-06-30 | 100% | 100% | 100% | Complete
S-DRR21 | Release 2: Business Requirements - Sign-off | 2010-06-30 | 2010-06-30 | 2010-06-30 | 2010-06-30 | 100% | 100% | 100% | Complete
D-DRR22 | Detailed Design and Development | 2010-04-12 | 2010-04-12 | 2011-01-28 | 2011-01-28 | 100% | 100% | 100% | Complete
D-DRR23 | Business Review and Sign-off of Detailed Design | 2010-05-17 | 2010-05-17 | 2010-09-30 | 2010-09-30 | 100% | 100% | 100% | Complete
D-DRR24 | Conduct Review and Sign-off of DD Docs | 2010-05-17 | 2010-05-17 | 2010-09-30 | 2010-09-30 | 100% | 100% | 100% | Complete
S-DRR25 | Detailed Design - Formal Sign-off - Completion Milestone | 2010-09-30 | 2010-09-30 | 2010-09-30 | 2010-09-30 | 100% | 100% | 100% | Complete
D-DRR26 | Development Team - Detailed Design and Development | 2010-04-12 | 2010-04-12 | 2011-01-28 | 2011-01-28 | 100% | 100% | 100% | Complete
D-DRR27 | Development Deliverables and Effort Hours | 2010-04-12 | 2010-04-12 | 2011-01-28 | 2011-01-28 | 100% | 100% | 100% | Complete
D-DRR28 | CONTRACTOR DDD and Development Hours | 2010-04-12 | 2010-04-12 | 2010-12-30 | 2010-12-30 | 100% | 100% | 100% | Complete
D-DRR29 | Release 2 Reports | 2010-04-12 | 2010-04-12 | 2010-07-02 | 2010-07-02 | 100% | 100% | 100% | Complete
D-DRR30 | GWT 2.0 Upgrade to DEV Environment | 2010-05-03 | 2010-05-03 | 2010-05-28 | 2010-05-28 | 100% | 100% | 100% | Complete
D-DRR31 | GUI DDD Documents | 2010-06-01 | 2010-06-01 | 2010-09-30 | 2010-09-30 | 100% | 100% | 100% | Complete
D-DRR32 | Transflow Report GUI | 2010-06-01 | 2010-06-01 | 2010-09-30 | 2010-09-30 | 100% | 100% | 100% | Complete
D-DRR33 | Protocol GUI | 2010-06-01 | 2010-06-01 | 2010-09-30 | 2010-09-30 | 100% | 100% | 100% | Complete
D-DRR34 | GUI Development | 2010-05-25 | 2010-05-25 | 2010-12-30 | 2010-12-30 | 100% | 100% | 100% | Complete
D-DRR35 | High Level Test Plan | 2010-08-02 | 2010-08-02 | 2010-09-24 | 2010-09-24 | 100% | 100% | 100% | Complete
D-DRR36 | Test Script Design Analysis and Development | 2010-08-02 | 2010-08-02 | 2010-12-30 | 2010-12-30 | 83% | 100% | 100% | Complete
D-DRR37 | Release 2 Traceability Matrix | 2010-05-17 | 2010-05-17 | 2010-11-30 | 2010-11-30 | 41% | 100% | 100% | Complete
D-DRR38 | General Business Analysis and Support (BA, RCC and RMA Teams) | 2010-04-30 | 2010-04-30 | 2010-12-15 | 2010-12-14 | 100% | 100% | 100% | Complete
D-DRR39 | Support Team Activities (Comm OPS, EIS DBA, EIS Test Lead) | 2010-05-28 | 2010-05-28 | 2010-12-17 | 2010-12-17 | 100% | 100% | 100% | Complete
D-DRR40 | Release 2: 2010 Project Management and Administration | 2010-04-30 | 2010-04-30 | 2010-12-30 | 2010-12-30 | 98% | 100% | 100% | Complete
D-DRR41 | Project Management - Project Manager Hours | 2010-04-30 | 2010-04-30 | 2010-12-30 | 2010-12-30 | 95% | 100% | 100% | Complete
D-DRR42 | Project Documentation and Review and Meetings - Business Owners | 2010-06-01 | 2010-06-01 | 2010-12-17 | 2010-12-17 | 100% | 100% | 100% | Complete
D-DRR43 | Release 2 - 2010 Project Team Meetings | 2010-06-03 | 2010-06-03 | 2010-12-17 | 2010-12-17 | 100% | 100% | 100% | Complete
D-DRR44 | Release 2 - 2010 Cash Flow | 2010-04-30 | 2010-04-30 | 2010-12-30 | 2010-12-30 | 99% | 100% | 100% | Complete
D-DRR45 | Release 2: 2011 - I-TEST and Production Deployment | 2011-01-03 | 2011-01-03 | 2011-07-29 | 2011-07-29 | 2% | 3% | 5% | Green
D-DRR46 | Test Scripts and Test Plan Development | 2011-01-03 | 2011-01-03 | 2011-04-29 | 2011-04-29 | 16% | 12% | 25% | Green
D-DRR47 | Release 2 - Test Script Development | 2011-01-03 | 2011-01-03 | 2011-04-29 | 2011-04-29 | 13% | 19% | 31% | Green
D-DRR48 | Test Script Development - Duration (~4 months for remaining 4,183 scripts) | 2011-01-03 | 2011-01-03 | 2011-02-04 | 2011-03-31 | 15% | 25% | 35% | Yellow
D-DRR49 | EIS Test Script Development | 2011-04-20 | 2011-04-20 | 2011-04-29 | 2011-04-29 | 5% | 0% | 0%
D-DRR50 | Release 2 - Detailed Test Plan | 2011-02-15 | 2011-02-01 | 2011-03-31 | 2011-04-13 | 20% | 10% | 20%
D-DRR51 | P-Test Activities | 2011-01-31 | 2011-01-31 | 2011-03-31 | 2011-03-31 | 15% | 8% | 19% | Green
D-DRR52 | I-TEST | 2011-03-30 | 2011-03-30 | 2011-07-29 | 2011-07-29 | 0% | 0% | 0%
S-DRR53 | Migration to I-TEST | 2011-03-30 | 2011-03-30 | 2011-04-01 | 2011-04-01 | 0% | 0% | 0%
D-DRR54 | I-TEST Execution | 2011-04-04 | 2011-04-04 | 2011-07-29 | 2011-07-29 | 0% | 0% | 0%
D-DRR55 | I-TEST Execution: RCC and Test Team | 2011-04-04 | 2011-04-04 | 2011-07-29 | 2011-07-29 | 0% | 0% | 0%
D-DRR56 | I-TEST: EIS Team | 2011-04-18 | 2011-04-18 | 2011-07-29 | 2011-07-29 | 0% | 0% | 0%
D-DRR57 | RMA Team | 2011-04-04 | 2011-04-04 | 2011-07-28 | 2011-07-28 | 0% | 0% | 0%
S-DRR58 | I-TEST Sign-off | 2011-07-29 | 2011-07-29 | 2011-07-29 | 2011-07-29 | 0% | 0% | 0%
D-DRR59 | I-TEST Support | 2011-04-04 | 2011-04-04 | 2011-07-29 | 2011-07-29 | 0% | 0% | 0%
D-DRR60 | PRODUCTION MIGRATION | 2011-07-26 | 2011-07-26 | 2011-09-28 | 2011-09-28 | 0% | 0% | 0%
S-DRR61 | PRODUCTION - GO LIVE | 2011-09-26 | 2011-09-26 | 2011-09-26 | 2011-09-26 | 0% | 0% | 0%
D-DRR62 | Post Production Verification | 2011-09-27 | 2011-09-27 | 2011-09-28 | 2011-09-28 | 0% | 0% | 0%
D-DRR63 | STABILIZATION and Post Production Verification | 2011-08-26 | 2011-08-26 | 2011-10-31 | 2011-10-31 | 0% | 0% | 0%
S-DRR64 | Stabilization Complete | 2011-10-14 | 2011-10-14 | 2011-10-14 | 2011-10-14 | 0% | 0% | 0%
D-DRR65 | Pre-ITEST | 2011-01-03 | 2011-01-03 | 2011-04-04 | 2011-04-04 | 0% | 20% | 45% | Green
D-DRR66 | EIS Controlled Products - Exception Reports | 2011-01-03 | 2011-01-03 | 2011-07-29 | 2011-08-26 | 0% | 20% | 50% | Yellow
D-DRR67 | I-TEST and Stabilization | 2011-04-05 | 2011-04-05 | 2011-08-31 | 2011-08-31 | 0% | 0% | 0%
D-DRR68 | Support Team Activities | 2011-01-03 | 2011-01-03 | 2011-10-31 | 2011-10-31 | 0% | 5% | 7% | Green
D-DRR69 | EIS DBA | 2011-01-03 | 2011-01-03 | 2011-07-29 | 2011-07-29 | 0% | 17% | 24% | Green
D-DRR70 | COMM OPS | 2011-07-06 | 2011-07-06 | 2011-09-26 | 2011-09-26 | 0% | 0% | 0%
D-DRR71 | Release Management | 2011-04-04 | 2011-04-04 | 2011-10-31 | 2011-10-31 | 0% | 0% | 0%
D-DRR72 | PROJECT SIGN OFF and Lessons Learned | 2011-08-19 | 2011-08-19 | 2011-10-21 | 2011-10-21 | 0% | 0% | 0%
D-DRR73 | Conduct Lessons Learned | 2011-08-19 | 2011-08-19 | 2011-10-21 | 2011-10-21 | 0% | 0% | 0%
D-DRR74 | 2011- Project Management and Administration | 2011-01-03 | 2011-01-03 | 2011-10-31 | 2011-10-31 | 0% | 15% | 26% | Green
D-DRR75 | Release 2 - Project Manager Hours - Duration | 2011-01-03 | 2011-01-03 | 2011-09-16 | 2011-09-16 | 0% | 6% | 19% | Green
D-DRR76 | Management Document Reviews/Meetings/Approvals (Business Owners) | 2011-01-03 | 2011-01-03 | 2011-08-05 | 2011-09-02 | 0% | 20% | 35% | Yellow
D-DRR77 | 2011 Cash Flow | 2011-01-03 | 2011-01-03 | 2011-10-31 | 2011-10-31 | 0% | 17% | 23% | Green
D-DRR78 | TOLLGATE EXECUTION TO CLOSING | 2011-10-21 | 2011-10-21 | 2011-10-31 | 2011-10-31 | 0% | 0% | 0%
S-DRR79 | CLOSING | 2011-09-26 | 2011-09-26 | 2011-10-31 | 2011-10-31 | 0% | 0% | 0%
D-DRR80 | CLOSING PHASE | 2011-09-26 | 2011-09-26 | 2011-10-21 | 2011-10-21 | 0% | 0% | 0%
D-DRR81 | Project Management and Administration | 2011-09-26 | 2011-09-26 | 2011-10-31 | 2011-10-31 | 0% | 0% | 0%
D-DRR82 | LESSONS LEARNED | 2011-10-03 | 2011-10-03 | 2011-10-07 | 2011-10-07 | 0% | 0% | 0%
D-DRR83 | INVOICE RECONCILIATION | 2011-10-17 | 2011-10-17 | 2011-10-24 | 2011-10-24 | 0% | 0% | 0%
S-DRR84 | PROJECT C LOSED | 2011-10-31 | 2011-10-31 | 2011-10-31 | 2011-10-31 | 0% | 0% | 0%
- Continue testing release in pTest
- Continue developing testing scenarios and test scripts for iTest testing
- Continue automating regression testing scripts
- Continue benchmarking activities to determine potential CPU, memory and storage needs.
- Continue testing activities in pTest
- Continue developing testing scenarios and test scripts for iTest testing
- Continue automating regression testing scripts
- Continue monitoring potential benchmarking
This Week's Activities and Accomplishments
Planned Activities for Next Week
Project Name:
Project Contacts:
Data Research & Reporting
Leo Castillo
- Project requires a specific testing resource to build replication scripts.
Risks & Issues
Schedule Status:
Week Ending:
2/4/11
Green

## Data Agg Perf Improvements
LEGEND: BLUE - Complete, GREEN - No Delay, YELLOW - Delay w/o Impact, RED - Impacted Milestone
UpcomingMilestones
| Description | Baseline Start | Current Start | Baseline Finish | Current Finish | 1/21 % Complete | 1/28% Complete | 2/4% Complete | This Weeks Status | VarianceDescription | Mitigation
D-DAggP1 | PR10055_01 AMS Performance Improvements | 2010-09-05 | 2010-09-05 | 2011-05-24 | 2011-07-25 | 21% | 42% | 42% | Yellow
S-DAggP2 | INITIATION | 2010-09-05 | 2010-09-05 | 2010-10-06 | 2010-10-06 | 100% | 100% | 100% | Complete
S-DAggP3 | PLANNING | 2010-09-13 | 2010-09-13 | 2011-02-11 | 2011-04-06 | 41% | 51% | 48% | Yellow
D-DAggP4 | BUSINESS REQUIREMENTS | 2010-11-01 | 2010-11-01 | 2011-02-09 | 2011-03-08 | 19% | 23% | 30% | Yellow
D-DAggP5 | RUN BASELINE BATCH | 2010-09-26 | 2010-09-26 | 2011-01-24 | 2011-03-17 | 24% | 46% | 43% | Yellow
D-DAggP6 | PROJECT SCHEDULE | 2011-01-25 | 2011-03-17 | 2011-01-31 | 2011-03-24 | 0% | 0% | 0% | Yellow
D-DAggP7 | PROJECT MANAGEMENT PLAN | 2011-01-27 | 2011-03-21 | 2011-02-03 | 2011-03-29 | 0% | 0% | 0% | Yellow
D-DAggP8 | TOLLGATE PLANNING TO EXECUTION | 2011-02-04 | 2011-03-29 | 2011-02-11 | 2011-04-06 | 0% | 0% | 0%
S-DAggP9 | EXECUTION | NA | 2011-03-25 | NA | 2011-06-22 | 1% | 0% | 0%
D-DAggP10 | PROJECT EXECUTION KICKOFF | NA | 2011-04-11 | NA | 2011-04-13 | 0% | 0% | 0%
D-DAggP11 | DEVELOPMENT | NA | 2011-04-13 | NA | 2011-04-19 | 0% | 0% | 0%
D-DAggP12 | TEST CASE DEVELOPMENT | NA | 2011-04-19 | NA | 2011-05-12 | 0% | 0% | 0%
D-DAggP13 | Development | NA | 2011-04-21 | NA | 2011-04-22 | 0% | 0% | 0%
D-DAggP14 | PRODUCT | NA | 2011-04-22 | NA | 2011-04-26 | 0% | 0% | 0%
D-DAggP15 | INTEGRATION | NA | 2011-04-26 | NA | 2011-04-29 | 0% | 0% | 0%
D-DAggP16 | UAT | NA | 2011-04-29 | NA | 2011-05-04 | 0% | 0% | 0%
D-DAggP17 | MARKET | NA | 2011-05-04 | NA | 2011-05-09 | 0% | 0% | 0%
D-DAggP18 | REGRESSION | NA | 2011-05-09 | NA | 2011-05-12 | 0% | 0% | 0%
D-DAggP19 | PRODUCTION SUPPORT IMPLEMENTATION PLAN | NA | 2011-05-12 | NA | 2011-05-17 | 0% | 0% | 0%
D-DAggP20 | TESTING | NA | 2011-04-19 | NA | 2011-05-18 | 5% | 0% | 0%
D-DAggP21 | DEV TEST | NA | 2011-04-19 | NA | 2011-04-22 | 33% | 0% | 0%
S-DAggP22 | Configure hardware and software | NA | 2011-04-19 | NA | 2011-04-20 | 100% | 0% | 0%
D-DAggP23 | PTEST | NA | 2011-04-22 | NA | 2011-05-03 | 0% | 0% | 0%
D-DAggP24 | MIGRATION TO PTEST | NA | 2011-04-22 | NA | 2011-04-26 | 0% | 0% | 0%
D-DAggP25 | PERFORM PRODUCT TEST | NA | 2011-04-26 | NA | 2011-05-03 | 0% | 0% | 0%
D-DAggP26 | ITEST | NA | 2011-05-03 | NA | 2011-05-11 | 0% | 0% | 0%
S-DAggP27 | Perform Migration to ITEST | NA | 2011-05-04 | NA | 2011-05-05 | 0% | 0% | 0%
D-DAggP28 | INTEGRATION TEST QA | NA | 2011-05-05 | NA | 2011-05-11 | 0% | 0% | 0%
D-DAggP29 | USER ACCEPTANCE TEST UAT | NA | 2011-05-03 | NA | 2011-05-16 | 0% | 0% | 0%
D-DAggP30 | PERFORM UAT TEST | NA | 2011-05-11 | NA | 2011-05-16 | 0% | 0% | 0%
D-DAggP31 | MIGRATION PLAN | NA | 2011-05-16 | NA | 2011-05-18 | 0% | 0% | 0%
D-DAggP32 | IMPLEMENTATION TO PRODUCTION | NA | 2011-03-25 | NA | 2011-06-07 | 0% | 0% | 0%
D-DAggP33 | PRODUCTION RELEASE COORDINATION | NA | 2011-05-18 | NA | 2011-05-24 | 0% | 0% | 0%
D-DAggP34 | Create Market Notification | NA | 2011-05-23 | NA | 2011-05-24 | 0% | 0% | 0%
D-DAggP35 | MIGRATION | NA | 2011-05-24 | NA | 2011-06-03 | 0% | 0% | 0%
S-DAggP36 | Go Live PMO EXEC | NA | 2011-06-03 | NA | 2011-06-06 | 0% | 0% | 0%
D-DAggP37 | PROJECT SIGN OFF | NA | 2011-06-07 | NA | 2011-06-13 | 0% | 0% | 0%
D-DAggP38 | AS BUILT DOCUMENTATION | NA | 2011-06-13 | NA | 2011-06-16 | 0% | 0% | 0%
D-DAggP39 | TOLLGATE EXECUTION TO CLOSING | NA | 2011-06-16 | NA | 2011-06-22 | 0% | 0% | 0%
S-DAggP40 | CLOSING | NA | 2011-06-22 | NA | 2011-07-25 | 0% | 0% | 0%
D-DAggP41 | LESSONS LEARNED EXECUTION AND CLOSING PHASES | NA | 2011-06-23 | NA | 2011-07-14 | 0% | 0% | 0%
D-DAggP42 | INVOICE RECONCILIATION | NA | 2011-06-22 | NA | 2011-07-21 | 0% | 0% | 0%
- Continue analysis on two identified alternatives to improve performance.
- Continue developing prototypes and proof of concept on these options
- Perform performance testing - Preliminary tests
- Develop schedule and milestones for this iteration.
This Week's Activities and Accomplishments
Planned Activities for Next Week
Project Name:
Project Contacts:
Data Agg Perf Improvements
Leo Castillo
- Project requires a dedicated Data Agg. resource.
Risks & Issues
Schedule Status:
Week Ending:
2/4/11
Green

## Enterprise Records Mgmt
LEGEND: BLUE - Complete, GREEN - No Delay, YELLOW - Delay w/o Impact, RED - Impacted Milestone
UpcomingMilestones
| Description | Baseline Start | Current Start | Baseline Finish | Current Finish | 1/21 % Complete | 1/28% Complete | 2/4% Complete | This Weeks Status | VarianceDescription | Mitigation
D-ERMA1 | PR10031_01 Enterprise Records Management | 2010-02-10 | 2010-01-20 | 2010-07-14 | 2011-03-23 | 68% | 88% | 86% | Yellow
D-ERMA2 | INITIATION | 2010-01-20 | 2010-01-20 | 2010-02-10 | 2010-02-10 | 100% | 100% | 100% | Complete
D-ERMA3 | INITIATION PHASE | 2010-01-20 | 2010-01-20 | 2010-02-10 | 2010-02-10 | 100% | 100% | 100% | Complete
D-ERMA4 | SCHEDULING REVIEW TO DEFINE PLANNING PHASE | 2010-01-21 | 2010-01-21 | 2010-02-01 | 2010-02-01 | 100% | 100% | 100% | Complete
D-ERMA5 | PROJECT PLAN | 2010-01-20 | 2010-01-20 | 2010-02-10 | 2010-02-10 | 100% | 100% | 100% | Complete
D-ERMA6 | INITIATION TO PLANNING PHASE DIVISIONAL TOLLGATE | 2010-01-20 | 2010-01-20 | 2010-02-10 | 2010-02-10 | 100% | 100% | 100% | Complete
S-ERMA7 | PLANNING | 2010-02-10 | 2010-01-20 | 2010-07-14 | 2010-08-20 | 100% | 100% | 100% | Complete
D-ERMA8 | PLANNING PHASE | 2010-02-11 | 2010-02-11 | 2010-03-10 | 2010-03-10 | 100% | 100% | 100% | Complete
S-ERMA9 | Business Requirements Complete | 2010-03-10 | 2010-03-10 | 2010-03-10 | 2010-03-10 | 100% | 100% | 100% | Complete
D-ERMA10 | SECURITY REQUIREMENTS | 2010-02-11 | 2010-02-11 | 2010-02-18 | 2010-02-18 | 100% | 100% | 100% | Complete
D-ERMA11 | Technical Infrastructure Requirements | 2010-02-11 | 2010-02-11 | 2010-02-22 | 2010-02-22 | 100% | 100% | 100% | Complete
D-ERMA12 | Assessment of Email Records Management Solutions | 2010-02-11 | 2010-02-11 | 2010-06-04 | 2010-08-17 | 100% | 100% | 100% | Complete
D-ERMA13 | RFP Criteria | 2010-02-11 | 2010-02-11 | 2010-02-16 | 2010-02-16 | 100% | 100% | 100% | Complete
D-ERMA14 | RFP Solicitation Process | 2010-03-11 | 2010-03-11 | 2010-03-18 | 2010-03-18 | 100% | 100% | 100% | Complete
D-ERMA15 | RFP Creation | 2010-03-18 | 2010-03-18 | 2010-04-12 | 2010-04-19 | 100% | 100% | 100% | Complete
D-ERMA16 | RFP II | 2010-07-12 | 2010-07-12 | 2010-08-17 | 2010-08-17 | 100% | 100% | 100% | Complete
D-ERMA17 | Market research | 2010-04-13 | 2010-04-20 | 2010-04-21 | 2010-04-28 | 100% | 100% | 100% | Complete
D-ERMA18 | RFP Release to industry | 2010-04-22 | 2010-04-29 | 2010-04-29 | 2010-05-06 | 100% | 100% | 100% | Complete
D-ERMA19 | Post-Solicitation Process | 2010-04-30 | 2010-05-03 | 2010-05-11 | 2010-05-07 | 100% | 100% | 100% | Complete
D-ERMA20 | Business Prep | 2010-05-10 | 2010-05-10 | 2010-06-11 | 2010-06-11 | 100% | 100% | 100% | Complete
D-ERMA21 | User Outlook Survey | 2010-05-10 | 2010-05-10 | 2010-05-28 | 2010-05-28 | 100% | 100% | 100% | Complete
D-ERMA22 | Define Outlook Policy | 2010-05-18 | 2010-05-18 | 2010-06-11 | 2010-06-11 | 100% | 100% | 100% | Complete
D-ERMA23 | Review Proposals | 2010-05-12 | 2010-05-21 | 2010-05-20 | 2010-06-16 | 100% | 100% | 100% | Complete
D-ERMA24 | Face-to-Face Discussions/Negotiations | 2010-05-21 | 2010-06-17 | 2010-06-04 | 2010-06-30 | 100% | 100% | 100% | Complete
D-ERMA25 | Procure Solution | 2010-06-07 | 2010-06-30 | 2010-06-21 | 2010-07-13 | 100% | 100% | 100% | Complete
D-ERMA26 | Implementation Planning | 2010-05-28 | 2010-06-24 | 2010-06-07 | 2010-07-01 | 100% | 100% | 100% | Complete
D-ERMA27 | HIGH LEVEL TEST PLAN | 2010-05-28 | 2010-06-24 | 2010-06-08 | 2010-07-02 | 100% | 100% | 100% | Complete
S-ERMA28 | Test Plan Complete | 2010-06-08 | 2010-07-02 | 2010-06-08 | 2010-07-02 | 100% | 100% | 100% | Complete
D-ERMA29 | SCHEDULING REVIEW TO DEFINE EXECUTION PHASE | 2010-05-28 | 2010-06-24 | 2010-06-15 | 2010-07-12 | 100% | 100% | 100% | Complete
D-ERMA30 | RESOURCE PLAN DOCUMENT FOR EXECUTION | 2010-05-28 | 2010-06-24 | 2010-06-02 | 2010-06-28 | 100% | 100% | 100% | Complete
D-ERMA31 | CASH FLOW DOCUMENT AT 90 Percent ACCURACY | 2010-05-28 | 2010-06-24 | 2010-06-03 | 2010-06-29 | 100% | 100% | 100% | Complete
D-ERMA32 | LESSONS LEARNED INITIATION AND PLANNING PHASE | 2010-06-04 | 2010-06-30 | 2010-06-14 | 2010-07-09 | 100% | 100% | 100% | Complete
D-ERMA33 | MEETING TO CONDUCT LESSONS LEARNED Optional | 2010-06-11 | 2010-07-08 | 2010-06-11 | 2010-07-08 | 100% | 100% | 100% | Complete
D-ERMA34 | PLANNING TO EXECUTION PHASE DIVISIONAL TOLLGATE | 2010-05-28 | 2010-06-24 | 2010-06-17 | 2010-08-17 | 100% | 100% | 100% | Complete
D-ERMA35 | PROJECT MANAGEMENT AND ADMINISTRATION PLANNING PHASE | 2010-02-10 | 2010-03-29 | 2010-07-14 | 2010-08-18 | 100% | 100% | 100% | Complete
S-ERMA36 | EXECUTION PHASE | 2010-08-18 | 2010-08-18 | 2011-03-02 | 2011-03-02 | 36% | 77% | 74% | Complete
D-ERMA37 | EXECUTION AND CONTROL PHASE | 2011-01-28 | 2011-02-28 | 2011-03-02 | 2011-03-02 | 0% | 0% | 0% | Yellow
s-ERMA38 | Pilot Complete | 2011-01-28 | 2011-02-28 | 2011-01-28 | 2011-02-28 | 0% | 0% | 0% | Yellow
S-ERMA39 | Go Live | 2011-02-28 | 2011-02-28 | 2011-02-28 | 2011-02-28 | 0% | 0% | 0% | Yellow
S-ERMA40 | Execution Phase Complete PMO EXEC MILESTONE 4 | 2011-03-02 | 2011-03-02 | 2011-03-02 | 2011-03-02 | 0% | 0% | 0%
S-ERMA41 | CLOSING PHASE | 2011-03-02 | 2011-03-02 | 2011-03-23 | 2011-03-23 | 0% | 0% | 0%
D-ERMA42 | LESSONS LEARNED EXECUTION AND CLOSING PHASES | 2011-03-03 | 2011-03-03 | 2011-03-07 | 2011-03-07 | 0% | 0% | 0%
D-ERMA43 | MEETING TO CONDUCT LESSONS LEARNED Optional | 2011-03-07 | 2011-03-07 | 2011-03-07 | 2011-03-07 | 0% | 0% | 0%
D-ERMA44 | INVOICE RECONCILIATION | 2011-03-02 | 2011-03-02 | 2011-03-02 | 2011-03-02 | 0% | 0% | 0%
D-ERMA45 | PROJECT MANAGEMENT AND ADMINISTRATION CLOSING PHASE | 2011-03-02 | 2011-03-02 | 2011-03-02 | 2011-03-02 | 0% | 0% | 0%
S-ERMA46 | PROJECT CLOSED | 2011-03-23 | 2011-03-23 | 2011-03-23 | 2011-03-23 | 0% | 0% | 0%
- Continued preparations for pilot.
- Migrated custom SharePoint code to production.
- Pushed out Silverlight to ERCOT workstations.
- Continue pilot preparations.
This Week's Activities and Accomplishments
Planned Activities for Next Week
Project Name:
Project Contacts:
Enterprise Records Management
PM - Heather Day
Business Owner - Carol McDonald
Risks & Issues
Schedule Status:
Week Ending:
2/4/11
Green

## Parking Deck
LEGEND: BLUE - Complete, GREEN - No Delay, YELLOW - Delay w/o Impact, RED - Impacted Milestone
UpcomingMilestones
| Description | Baseline Start | Current Start | Baseline Finish | Current Finish | 1/21 % Complete | 1/28% Complete | 2/4% Complete | This Weeks Status | VarianceDescription | Mitigation
PR10016_03 Network-01 | [8 empty] | Yellow
PR10016_03 Network-02 | [8 empty] | Yellow
PR10016_03 Network-03 | [8 empty] | Yellow
PR10016_03 Network-04 | [8 empty] | Yellow
PR10016_03 Network-05 | [8 empty] | Yellow
PR10016_03 Network-06 | [8 empty] | Yellow
PR10016_03 Network-07 | [8 empty] | Yellow
PR10016_03 Network-08 | [8 empty] | Yellow
PR10016_03 Network-09 | [8 empty] | Yellow
PR10016_03 Network-10 | [8 empty] | Yellow
PR10016_03 Network-11 | [8 empty] | Yellow
PR10016_03 Network-12 | [8 empty] | Yellow
PR10016_03 Network-13 | [8 empty] | Yellow
PR10016_03 Network-14 | [8 empty] | Yellow
PR10016_03 Network-15 | [8 empty] | Yellow
PR10016_03 Network-16 | [8 empty] | Yellow
PR10016_03 Network-17 | [8 empty] | Yellow
PR10016_03 Network-18 | [8 empty] | Yellow
PR10016_03 Network-19 | [8 empty] | Yellow
PR10016_03 Network-20 | [8 empty] | Yellow
PR10016_03 Network-21 | [8 empty] | Yellow
PR10016_03 Network-22 | [8 empty] | Yellow
PR10016_03 Network-23 | [8 empty] | Yellow
PR10016_03 Network-24 | [8 empty] | Yellow
PR10016_03 Network-25 | [8 empty] | Yellow
PR10016_03 Network-26 | [8 empty] | Yellow
PR10016_03 Network-27 | [8 empty] | Yellow
PR10016_03 Network-28 | [8 empty] | Yellow
PR10016_03 Network-29 | [8 empty] | Yellow
PR10016_03 Network-30 | [8 empty] | Yellow
PR10016_03 Network-31 | [8 empty] | Yellow
PR10016_03 Network-32 | [8 empty] | Yellow
PR10016_03 Network-33 | [8 empty] | Yellow
PR10016_03 Network-34 | [8 empty] | Yellow
PR10016_03 Network-35 | [8 empty] | Yellow
PR10016_03 Network-36 | [8 empty] | Yellow
PR10016_03 Network-37 | [8 empty] | Yellow
PR10016_03 Network-38 | [8 empty] | Yellow
PR10016_03 Network-39 | [8 empty] | Yellow
PR10016_03 Network-40 | [8 empty] | Yellow
PR10016_03 Network-41 | [8 empty] | Yellow
PR10016_03 Network-42 | [8 empty] | Yellow
PR10016_03 Network-43 | [8 empty] | Yellow
PR10016_03 Network-44 | [8 empty] | Yellow
PR10016_03 Network-45 | [8 empty] | Yellow
PR10016_03 Network-46 | [8 empty] | Yellow
PR10016_03 Network-47 | [8 empty] | Yellow
PR10016_03 Network-48 | [8 empty] | Yellow
PR10016_03 Network-49 | [8 empty] | Yellow
PR10016_03 Network-50 | [8 empty] | Yellow
PR10016_03 Network-51 | [8 empty] | Yellow
PR10016_03 Network-52 | [8 empty] | Yellow
PR10016_03 Network-53 | [8 empty] | Yellow
PR10016_03 Network-54 | [8 empty] | Yellow
PR10016_03 Network-55 | [8 empty] | Yellow
PR10016_03 Network-56 | [8 empty] | Yellow
PR10016_03 Network-57 | [8 empty] | Yellow
PR10016_03 Network-58 | [8 empty] | Yellow
PR10016_03 Network-59 | [8 empty] | Yellow
PR10016_03 Network-60 | [8 empty] | Yellow
PR10016_03 Network-61 | [8 empty] | Yellow
PR10016_03 Network-62 | [8 empty] | Yellow
PR10016_03 Network-63 | [8 empty] | Yellow
PR10016_03 Network-64 | [8 empty] | Yellow
PR10016_03 Network-65 | [8 empty] | Yellow
PR10016_03 Network-66 | [8 empty] | Yellow
PR10016_03 Network-67 | [8 empty] | Yellow
PR10016_03 Network-68 | [8 empty] | Yellow
PR10016_03 Network-69 | [8 empty] | Yellow
PR10016_03 Network-70 | [8 empty] | Yellow
PR10016_03 Network-71 | [8 empty] | Yellow
This Week's Activities and Accomplishments
Planned Activities for Next Week
Project Name:
Project Contacts:
Parking Deck
Risks & Issues
Schedule Status:
Week Ending:
2/4/11
Green