## Prioritized List
Priority | Rank | Current Status | Source Document | Description | Sort Char | Release Year | Systems Impacted | Target Release | Source | IA Phase | Estimated Cost | Estimated Effort | Estimated Duration | Work-arounds | Funding Source | Submitter | Submission Date | Actual Implementation Date | Prioritization Source | Additional Information
1 - Critical | 1 | Board Approved | NPRR208 | Registration and Settlement of Distributed Generation (DG) Less Than One MW | 7 | 2011 | S&B / Data Agg | Deferred Defects - G7 - Sept 11 | Parking Deck | 1 | $5k-$10k | 80-160 hours | 6 months |  | Parking Deck | NOIE DRG TF | 2010-01-25 |  |  | Revises the formula for Settlement of electricity consumption and out-flow by Customers with renewable Distributed Generation (DG). The revised formula fulfills the provisions of PUC RULE 25.213 that requires ERCOT to develop DG Settlement processes that “reflect the time of generation.” In order to fully synchronize the Protocols with the intent of the Rule as soon as practicable, ERCOT supports implementation of the grey-boxed language in NPRR208 as a “Critical” priority.
1 - Critical | 2 | Board Approved | NPRR285 | Generation Resource Base Point Deviation Charge Corrections | 4 | 2011 | COMS, MMS, Integration, EMS, Reg, CSI | Deferred Defects - G4 - Jun 11 | Parking Deck | 1 | $30k-$40k | 4-8 weeks | 3 months |  | Parking Deck | WMS | 2010-10-13 |  |  | Various greyboxes relating to Generation Resource Base Point Deviation Charge
1 - Critical | 3 | Board Approved | NPRR219 | Resolution of Alignment Items A33,A92,A106,A150 - TSPs Must Submit Outages for Resource Owned Equipment & Clarification of Changes in Status of Transmission Element Postings | 99 | Future Year TBD | Outage Scheduler, NMMS, Integration, Siebel, EIS, EWS, RARF | TBD | Parking Deck | 1 | $565k-$750k | 3,850-5,010 hours | 12-15 months | ERCOT staff entering data on behalf of MPs |  | ERCOT Staff | 2010-03-24 |  |  | Implement system change to allow Resources to submit Outages for Resource-owned transmission equipment
1 - Critical | 4 | Board Approved | NOGRR050 | Resolution of Reporting Issues Related to NPRR219 | 99 | Future Year TBD | Outage Scheduler, MIS, NMMS | TBD | Parking Deck | 1 | [5 empty] | CenterPoint Energy | 2010-08-12 |  |  | Grey-boxes several transmission Outage scheduling data elements from ERCOT reports until such time ERCOT systems can be modified to include only Transmission Service Provider’s (TSP’s) Outages in the reports
1 - Critical | 5 | Board Approved | NPRR282 | Dynamic Ramp Rates Use in SCED | 4 | 2011 | EMS | Deferred Defects - G4 - Jun 11 | Parking Deck | 1 | $30k-$35k | 450-550 hours | 3 months |  | Parking Deck | Calpine | 2010-09-28 |  |  | Proposes revisions that are intended to result in more reasonable Dispatch of Generation Resources when a telemetered Base Point requires the Resource to employ technologies that in turn change the Resource’s ramp rate.
1 - Critical | 6 | Tabled at TAC | SCR760 | Recommended Changes Needed for Information Model Manager and Topology Processor for Planning Models | 99 | TBD | NMMS | TBD | Parking Deck | 1 | $2.1M-$2.7M |  | 24-30 months | TBD |  | SSWG | 2010-11-04 |  |  | Proposes 8 changes to the Information Model Manager and Topology Processor
2 - High | 1 | Board Approved | NPRR293 | Requirement to Post CRR Option and Obligation Quantities Cleared in DAM or Taken to Real Time | 3 | 2011 | MMS, CDR, MIS | Deferred Defects - G3 - May 11 | Parking Deck | 1 | $12k-$15k | 175-195 hours | 2 months | ERCOT posting daily report until automated | Parking Deck | Luminant | 2010-11-04 |  |  | Adds language to specify the need for ERCOT to post the hourly energy bought and sold in the DAM at each Settlement Point for each hour in the Operating Day
2 - High | 2 | Board Approved | NPRR251 | Sync of PRR845, Definition for IDR Meters and Optional Removal of IDR Meters at a Premise Where an Advanced Meter Can be Provisioned | 4 | 2011 | Lodestar, EIS | Deferred Defects - G4 - Jun 11 | Parking Deck | 1 | $30k-$50k | 500-600 hours | 2 months |  | PPL | RMWG | 2010-07-08 |  |  | Grey-boxes language requiring IDR meters if usage warrants. Current language exempts situations where Advanced Meters have been installed. Also gray-boxes related reporting requirements for ERCOT.
2 - High | 3 | Board Approved | SCR759 | acLineSegment Name Length Increase in Information Model Manager | 99 | TBD | NMMS, MMS, CRR, EMS, OS | TBD | Parking Deck | 1 | $1M |  | 8-10 months |  |  | SSWG | 2010-05-27 |  |  | Increases the character size of the acLineSegment type under the Line Equipment Container from 2 to 14 in the IMM. Allows modeling of multi-section line segments. Not a major impact to IMM but cascading impacts to CRR and MMS Desire expressed at ROS to have this implemented for Planning Go-Live (~March 2011)
2 - High | 4 | Board Approved | NPRR181 | FIP Definition Revision | 99 | 2013+ | MMS, COMS, Integration | TBD | Parking Deck | 3 | [5 empty] | Luminant | 2009-06-10 |  |  | Revises the definition of Fuel Index Price (FIP) to correctly account for the timing difference between ERCOT’s application of FIP in its systems (midnight to midnight) and the timing of natural gas prices reflected by the index (i.e., hour ending 1000 to 0900).
2 - High | 4 | Board Approved | NPRR210 | Wind Forecasting Change to P50, Synch PRR841 | 99 | 2012 | COMS | TBD | Parking Deck | 2 | [5 empty] | Morgan Stanley | 2010-02-09 |  |  | Changes the wind forecast from the 80% probability to 50%. This change is also effective in determining if a QSE is capacity short. The boxed language changes the capacity short calculation back to the 80% forecast.
2 - High | 4 | Board Approved | NPRR272 | Definition and Participation of Quick Start Generation Resources | 99 | 2012 | MMS, COMS, CSI, Siebel, CDR | TBD | Parking Deck | 3 |  |  |  | Operations, Client Services, Settlements |  | ERCOT Staff | 2010-09-16 |  |  | Provides language for effective participation of Quick Start Generation Resources (QSGRs) in SCED
2 - High | 5 | Board Approved | NPRR131 | Ancillary Service Trades with ERCOT | 9 | 2012 | MMS, COMS, CSI | Release 2.0 | Parking Deck | 3 | [5 empty] | NRG Texas | 2008-05-15 |  |  | Allows QSEs representing resources to procure A/S in the DAM
2 - High | 5 | Board Approved | NPRR146 | ICCP Telemetry Information Submittals | 9 | 2012 | Business Process, NMMS | Release 2.0 | Parking Deck | 4 | [5 empty] | AEP | 2008-07-31 |  |  | Allows NOMCRs that modify only ICCP data object names to be submitted within 15 days of the network model load date Possible resolution with business process changes
2 - High | 5 | Board Approved | NPRR207 | Unit Deselection | 9 | 2012 | COMS, MMS, CDR, EIF, EWS | Release 2.0 | Parking Deck | 3 | [5 empty] | QSTF | 2010-01-22 |  |  | Defers two changes: 1 – hourly RUC notification of recommended but deselected resources in RUC 2 – prevent QSEs from increasing Energy Offer Curves after a RUC Notification
2 - High | 5 | Board Approved | NPRR222 | Half-Hour Start Unit RUC Clawback | 9 | 2012 | COMS, EIS | Release 2.0 | Parking Deck | 3 | [5 empty] | WMS | 2010-04-09 |  |  | Removed from original NPRR207 language. Removes RUC clawback on Half-Hour Start Units in certain circumstances. Also changes the RUC Clawback on Half-Hour Start Units that did not participate in the DAM to 50%.
3 - High / Medium |  | Board Approved | NPRR244 | Clarification of Other Binding Documents | 8 | Various | MIR, MIS, ERCOT.com | Standalone Project | Parking Deck | 2 | [5 empty] | ERCOT Staff | 2010-06-03 |  |  | Internal review project needed to avoid posting confidential or vendor proprietary information
3 - High / Medium |  | Board Approved | NPRR240 | Proxy Energy Offer Curve | 99 | TBD | EIS | TBD | Parking Deck | 2 | [5 empty] | IMM | 2010-05-26 |  |  | One grey-box section: “Energy Offer Curves that were constructed in whole or in part with proxy Energy Offer Curves shall be so marked in all ERCOT postings or references to the energy offer.”
3 - High / Medium |  | Board Approved | NPRR257 | Synchronization with Nodal Operating Guide Section 9, Monitoring Programs | 99 | Various | EIS | TBD | Parking Deck | 3 | [5 empty] | ERCOT Staff | 2010-07-23 |  |  | Greyboxes multiple sections to align with Nodal Operating Guide Section 9, Monitoring Programs
3 - High / Medium |  | Board Approved | NPRR258 | Sync with PRR824 and PRR833 and Additional Clarifications | 99 | 2012 | EMS, EIS | TBD | Parking Deck | 3 | [5 empty] | PDCWG | 2010-07-23 |  |  | Grey-boxes language to change the calculation of GREDP PDCWG suggests priority of “critical”
4 - Medium |  | Board Approved | NPRR164 | Resubmitting Ancillary Service Offers in SASM | 9 | 2012 | MMS, EIF, EIS, CDR | Release 2.0 | Parking Deck | TBD | [5 empty] | TPTF | 2008-11-11 |  |  | Allows QSEs to take full advantage of A/S and energy co-optimization in the DAM and participate in the Supplemental Ancillary Service Market (SASM) by being able to resubmit A/S Offers at the higher of DAM MCPC or its offer price in the DAM.
4 - Medium |  | Board Approved | SCR755 | ERCOT.com Website Enhancements | 99 | TBD | ERCOT.com | TBD | Parking Deck | 2 | [5 empty] | CCWG | 2009-02-25 |  |  | Implementation of 10 improvements to ERCOT.com received in the 2008 Market Participant Survey. Includes document archiving, search improvements, training, meeting calendar enhancements, and RSS feeds.
4 - Medium |  | Board Approved | NPRR153 | Generation Resource Fixed Quantity Block Offer | 10 | TBD | MMS, EIF, EIS, CDR | Future Release | Parking Deck | 4 | [5 empty] | TPTF | 2008-09-12 |  |  | Allows a fixed quantity and time block bid for Offline Non-Spin with the contingency that all hours be purchased in the block
4 - Medium |  | Board Approved | NOGRR034 | Rescind Telemetry Performance Calculation Exclusions | 99 | TBD |  | TBD | Parking Deck | 3 | [5 empty] | ERCOT Staff | 2010-01-22 |  |  | Grey-boxes language that allows QSE and TSPs to request removal of telemetry from Telemetry Standard performance metrics when certain situations exist.
4 - Medium |  | Board Approved | NPRR241 | Aggregate Incremental Liability (AIL) Calculation and Credit Reports Publish Corrections | 99 | TBD | CMM | TBD | Parking Deck | 2 | [5 empty] | ERCOT Staff | 2010-05-27 |  |  | One grey-box section: Changes the alternate posting format for 3 reports from XLS to XML (in addition to PDF).
4 - Medium |  | Board Approved | NPRR256 | Sync Nodal Protocols with PRR787, Add Non-Compliance Language to QSE Performance Standards | 99 | TBD | EMS, EIS (group w/258) | TBD | Parking Deck | 2 | [5 empty] | Luminant | 2010-07-15 |  |  | Seeks to exempt generation resources from GREDP calculation during testing and qualification periods. Not really a sync because additional exemptions to GREDP (Generation Resource Energy Deployment Performance) calculation are included
4 - Medium |  | Board Approved | NPRR260 | Providing Access to MIS Secure Area to MIS Registered Users | 99 | TBD | Siebel, MPIM, MIS, MIR, EWS, EIF | TBD | Parking Deck | 3 | [5 empty] | Crescent Power | 2010-08-05 |  |  | Makes it possible for consultants, power marketers, aggregators, consumers and universities to get access to the MIS Secure area (without doing so by getting a digital certificate through a registered Market Participant)

## Additional Items
Priority | Rank | Current Status | Source Document | Description | Sort Char | Release Year | Systems Impacted | Target Release | Source | IA Phase | Estimated Cost | Estimated Effort | Estimated Duration | Work-arounds | Funding Source | Submitter | Submission Date | Actual Implementation Date | Prioritization Source | Additional Information
TBD | TBD | Board Approved | NPRR302 | Correct Fuel Type Language for Mitigated Offer Cap |  | 2011 | MMS | Deferred Defects - G2 - Mar 11 | Post-Go-Live | 1 | <$5k | 40 hours | 2 weeks |  | PPL | Morgan Stanley | 2010-12-07 |  |  | Revises the language for the Mitigated Offer Cap to eliminate use of the FOP in the calculation
TBD | TBD | Pending at PRS | NPRR303 | Requirement to Post PTP Options Cleared in DAM or Taken to Real-Time |  | 2011 |  | Deferred Defects - G5 - Jul 11 | Post-Go-Live | 1 | $10k-$15k | 150-200 hours | 3-4 weeks |  | PPL | Luminant | 2010-12-16 |  |  | Adds language to specify the need for ERCOT to post quantities of Point-to-Point (PTP) Options and PTP Options with Refund that were not cleared in the Day-Ahead Market (DAM) and taken to Real-Time for Settlement
TBD | TBD | Pending at PRS | NPRR290 | ERCOT Publication of DAM PSS/E Files |  | 2011 | MMS, MIS | Deferred Defects - G6 - Aug 11 | Parking Deck | 1 | $20k-$25k | 300-350 hours | 4-8 weeks |  | PPL | Luminant | 2010-10-28 |  |  | Requires ERCOT to publish certain data files (in Power System Simulator for Engineering (PSS/E format) for easy review by all Market Participants with standard power flow tools such as PTI PSS/E, Power World Simulator, etc.
TBD | TBD | Pending at PRS | NPRR307 | Change SASM Offer Procedures |  | TBD | MMS | TBD | Post-Go-Live | [6 empty] | Morgan Stanley | 2011-01-11 |  |  | Deletes the requirement of valid SASM offers to be at or below the value of the offers in the Day Ahead Market (DAM).
TBD | TBD | Board Approved | NPRR221 | Automated Default Uplift Invoice |  | 2011 | COMS | Deferred Defects - G7 - Sept 11 | Parking Deck | 1 | $45k-$65k | 800-900 hours | 6-9 weeks | If default occurs, manual process | PPL | ERCOT Staff | 2010-03-30 |  |  | Automation of manual process as a result of NPRR221
TBD | 5 |  |  | Ancillary Service Deliverability | 99 | TBD |  | TBD | Potomac Market Assessment | [6 empty] | Potomac Economics |  |  |  | Short term - Monitor and manage in the control room through HRUC and operator analysis and direct QSEs as necessary to other resources when issues occur. Medium term – Review procurement history and identify problems. Long term – Potential real time optimization with deliverability check. If needed.
TBD | 5 |  |  | CRR Derating | 99 | TBD |  | TBD | Potomac Market Assessment | [6 empty] | Potomac Economics |  |  |  | Monitor CRR deratings in DAM During Market Trials CRR market appeared to be undersubscribed
TBD | 5 |  |  | DAM Transmission Constraints Shadow Price Caps | 99 | TBD |  | TBD | Potomac Market Assessment | [6 empty] | Potomac Economics |  |  |  | Do not bind on constraints that do not have generation dispatch solutions (i.e. radial pockets). Do not bind on constraints with mitigation plans.
TBD | 5 |  |  | Load Zone Modeling/Pricing | 99 | TBD |  | TBD | Potomac Market Assessment | [6 empty] | Potomac Economics |  |  |  | Radial load pocket code and Static LDFs .
TBD | 5 |  |  | PTP Options in DAM (Computational) | 99 | TBD |  | TBD | Potomac Market Assessment | [6 empty] | Potomac Economics |  |  |  | Tested PTP options in Dam trials. Install new hardware.
TBD | 5 |  |  | RUC and RUC clawback | 99 | TBD |  | TBD | Potomac Market Assessment | [6 empty] | Potomac Economics |  |  |  | Monitor volumes (i.e. number of RUC units and determine whether units are participating in the DAM market and/or self scheduling
TBD | 5 |  |  | Scarcity Pricing | 99 | TBD |  | TBD | Potomac Market Assessment | [6 empty] | Potomac Economics |  |  |  | Monitor prices and behavior along with planning reserves, and new interconnect agreements . Continue to track the peaker net margin.
TBD | 5 |  |  | SCED and two step mitigation | 99 | TBD |  | TBD | Potomac Market Assessment | [6 empty] | Potomac Economics |  |  |  | This issue is somewhat linked to scarcity pricing and we will utilize some of the same monitoring that is planned for the scarcity concern.
TBD | 5 |  |  | Settlement at shadow Prices | 99 | TBD |  | TBD | Potomac Market Assessment | [6 empty] | Potomac Economics |  |  |  | Monitor during market cutover, create graphs and determine whether or not this is occurring with a frequency that justifies a make whole payment NPRR proposal.
TBD | 8 |  |  | Incremental Data Loading Capability | 99 | TBD |  | TBD | Post-Go-Live | [6 empty] | ERCOT Staff | 2010-12-09 |  |  | Currently model data is loaded into the EMS/MMS as full model loads. The process of which is time consuming due to the volume of data carried with each model. 99% of the data is not changed with each model load, but additional time is spend in exporting, transferring, processing, and importing this data into receiving systems. The ability of EMS and MMS to accept CIM based incremental updates would greatly reduce the overhead of this processing time.
TBD | 8 |  |  | Resource Data Submission Application | 99 | TBD |  | TBD | Post-Go-Live | [6 empty] | ERCOT Staff | 2010-12-09 |  |  | The goal of this project is to create a web-based application that will be used by Resource Entities to submit, view, and update model related to resource assets that they own and/or operate. This application will decouple the Resource Asset Registration Form process currently used and create a process that is focused only on model data. Essentially separating the financial information from the physical model information, allowing for a stream lined process.
TBD |  |  |  | CRR API | 9 | 2012 | CRR | Release 2.0 | Parking Deck | [6 empty] | TPTF |  |  |  | Functionality to be considered for post-go-live development
TBD |  |  |  | Large Wind Power Production Ramp Forecasting Phase 2 | 9 | 2012 |  | Release 2.0 | Parking Deck | [6 empty] | ERCOT Staff |  |  |  | Phase 2 of the project that built a display for ERCOT operators to indicate periods of time within the next 6 hours during which there is a high risk for a large wind power production ramp to occur
TBD |  | NPRR Required |  | MMS Multiple Network Models | 9 | 2012 | MMS | Release 2.0 | Parking Deck | [6 empty] | TPTF |  |  |  | Functionality to be considered for post-go-live development
TBD |  |  |  | Move Price Validation Tool (PVT) to a Server Application | 9 | 2012 | PVT | Release 2.0 | Parking Deck | [6 empty] | ERCOT Staff |  |  |  | Functionality to be considered for post-go-live development
TBD |  |  |  | NMMS API | 9 | 2012 | NMMS | Release 2.0 | Parking Deck | [6 empty] | TPTF |  |  |  | Functionality to be considered for post-go-live development
TBD |  |  |  | Update Credit PFE Model (Potential Future Exposure) | 9 | 2012 |  | Release 2.0 | Parking Deck | [6 empty] | ERCOT Staff |  |  |  | Enhance PFE model to include the following risk factors: • Price volatility analysis for the Day Ahead Market, • Bid and offer volume analysis in the Day Ahead Market, and • Value of Congestion Revenue Rights
TBD |  | Board Approved | NPRR286 | DAM Credit – Non-Business Day Processing | 99 | TBD |  | TBD | Parking Deck |  |  |  |  | ERCOT staff working on non-business days |  | ERCOT Staff | 2010-10-14 |  |  | Change the values of the reference to “95th percentile” to “90th percentile” in Section 4.4.10(6)(b)(i)(B) and Section 4.4.10(6)(b)(ii) consistent with the vote taken by the Credit Working Group (CWG) and the Market Credit Working Group (MCWG)
TBD |  |  |  | Add PSS Status to RARF | 99 | TBD | Siebel | TBD | Parking Deck |  |  |  |  | Manual posting in place |  | ERCOT Staff |  |  |  | Automation of manual process as a result of NPRR156
TBD |  |  |  | Automate Identification of PUNs for Reporting | 99 | TBD |  | TBD | Parking Deck |  |  |  |  | Delivered with table that is maintained manually |  | ERCOT Staff |  |  |  | NPRR202 required that Private Use Networks (PUNs) be excluded from State Estimator postings of transmission flows and voltages. This requirement is being met by adding a static table to the reporting infrastructure to store the list of known PUNs. This Parking Deck item would create a method to dynamically derive the population of PUNs for this reporting.
TBD |  |  |  | EILS Enhancements | 99 | TBD |  | TBD | Parking Deck | [6 empty] | ERCOT Staff |  |  |  | Automation of manual processes
TBD |  |  |  | EMS Upgrade | 99 | 2012 | EMS | TBD | Parking Deck | [6 empty] | ERCOT Staff |  |  |  | Upgrade EMS system from v2.3 to v2.5/v2.6
TBD |  | NPRR Required |  | Load Participation in SCED | 99 | TBD | MMS | TBD | Parking Deck | [6 empty] | DSWG |  |  |  | Functionality to be considered for post-go-live development Demand Side Working Group (DSWG) currently looking into the feasibility of demand response being economically dispatched by SCED
TBD |  |  |  | MOTE for Outage Scheduler | 99 | TBD |  | TBD | Parking Deck | [6 empty] | ERCOT Staff |  |  |  | The Nodal MOTE does not include providing an environment for Outage Scheduler. Without this environment, MPs will be unable to test their code when ERCOT makes changes to web services. Similarly, MPs who decide to use web services for the first time will not have a test environment to test their outage transactions with ERCOT.
TBD |  |  |  | RARF Automation | 99 | TBD |  | TBD | Parking Deck | [6 empty] | ERCOT Staff |  |  |  | Functionality to be considered for post-go-live development
TBD |  |  |  | TML Transition to MIS | 99 | TBD |  | TBD | Parking Deck | [6 empty] | ERCOT Staff |  |  |  | Upon go live, most applications that are currently available through TML will migrate to MIS and will only be accessible to MPs through the MIS portal. RMS has requested that Zonal Reports, Find ESI ID, Find Transactions, and Transaction submission be accessed through TML until MIS has had sufficient time to stabilize.
TBD |  |  |  | Additional resource status for resource startup/shutdown | 99 | TBD |  | TBD | QSE Issues List | [10 empty] | ERCOT published guidelines for telemetry and resource statuses during resource startup and shutdown. We would like additional resource statuses for conditions below LSL rather than using workarounds with existing resource statuses.
TBD |  |  |  | DAM Clearing Engine | 99 | TBD | MMS | TBD | QSE Issues List | [6 empty] | Luminant |  |  |  | Is there a need for a protocol revision to create shadow price limits in DAM equal to Real Time?
TBD |  | Dupe with NPRR282 |  | Proposal to use telemetered Ramp Rates instead of Ramps Rates provided through MMS UI/EWS | 99 | TBD |  | TBD | QSE Issues List | [6 empty] | Calpine |  |  |  | Proposal to use telemetered Ramp Rates instead of Ramps Rates provided through MMS UI/EWS.
TBD |  | Captured in the current defect list? |  | Real Time Operations | 99 | TBD | EMS, MMS | TBD | QSE Issues List | [6 empty] | Luminant |  |  |  | QSE AS Capacity Compliance Monitoring Notification: ERCOT will supply a notification to QSEs when the comparison between the QSEs AS Supply Responsibility in the EMS system with the AS Supply Responsibility in the MMS system indicates that the QSE is not providing sufficient capacity Question: will the notification also be available through XML form, similar to EIP 1.19, section 5.3.1.2? Outstanding question.
TBD |  |  |  | Trade Confirmation Timestamp | 99 | TBD |  | TBD | QSE Issues List | [10 empty] | ERCOT has not implemented a trade confirmation timestamp in the Trades area on the MMS. Although notifications provides a timestamp of when each QSE submits or confirms this can provide conflicting timestamps particularly when confirmation is done around 1430. A single timestamp record is needed on the Trades tab to confirm which RUC capacity will be treated in. This leaves a hole for shadow settlements to determine whether a trade was confirmed pre or post 1430.
TBD |  |  |  | Custom Filter – “Requesting Company” defaults to TCNPE, the “Operating Company” should, also. If someone needs to change that option, so be it. | 99 | TBD |  | TBD | TSP Issues List | [10 empty] | Items not addressed prior to Nodal go-live
TBD |  |  |  | ERCOT introduced NOMCRs (associated with TSP owned equipment) should remain ERCOT responsibility from a compliance perspective. | 99 | TBD | NMMS | TBD | TSP Issues List | [10 empty] | Items not addressed prior to Nodal go-live
TBD |  |  |  | Grey Box items and additional upgrades need some kind of guarantee that they will be completed in a timely manner. | 99 | TBD |  | TBD | TSP Issues List | [10 empty] | Items not addressed prior to Nodal go-live
TBD |  |  |  | Inconsistencies in RARF data versus current planning models. | 99 | TBD |  | TBD | TSP Issues List | [10 empty] | Items not addressed prior to Nodal go-live
TBD |  |  |  | Line segments are not selectable from both terminating substations, moreover, the search pattern is not obvious to users (IE., segment NEWTGF04 between NEW and TGF substations is only available from the (NEW) substation, and missing from the TGF substation). This issue applies to both Human Interface and web services interface. | 99 | TBD |  | TBD | TSP Issues List | [10 empty] | Items not addressed prior to Nodal go-live
TBD |  |  |  | Processes for operational status changes need to be addressed before go-live. | 99 | TBD |  | TBD | TSP Issues List | [10 empty] | Items not addressed prior to Nodal go-live
TBD |  |  |  | Selecting “Time” when entering outages is a click and drag, not a drop down box that worked quite well on the previous version | 99 | TBD |  | TBD | TSP Issues List | [10 empty] | Items not addressed prior to Nodal go-live
TBD |  |  |  | The information submitted into NMMS may be duplicative causing inaccurate models. | 99 | TBD |  | TBD | TSP Issues List | [10 empty] | Items not addressed prior to Nodal go-live
TBD |  |  |  | There has always been an issue in managing the Network model and outages. Does this problem still exist with Nodal tools? | 99 | TBD |  | TBD | TSP Issues List | [10 empty] | Items not addressed prior to Nodal go-live
TBD |  |  |  | There is not a “Historical Tracking” of outages. The previous version had {View Update Log}. | 99 | TBD |  | TBD | TSP Issues List | [10 empty] | Items not addressed prior to Nodal go-live
TBD |  |  |  | To verify outages have been entered correctly for all segments of a line, each tap station has to be entered in the search criteria. | 99 | TBD |  | TBD | TSP Issues List | [10 empty] | Items not addressed prior to Nodal go-live
TBD |  | Dupe with NPRR146 (ask Woody) |  | What is the definition of an Interim Update? The protocols give ERCOT 15 days to review the NOMCR for completeness. Responding to ERCOT’s request during this review period does not cause the NOMCR to convert to an Interim Update. Design of the Interim Update approval process and how interim updates have not yet been vetted in the NDSWG | 99 | TBD |  | TBD | TSP Issues List | [10 empty] | Items not addressed prior to Nodal go-live
TBD |  |  |  | What is the ERCOT business for managing and approving SPSs? | 99 | TBD |  | TBD | TSP Issues List | [10 empty] | Items not addressed prior to Nodal go-live
TBD |  |  |  | Where are the published EMS cases for MP review? | 99 | TBD |  | TBD | TSP Issues List | [10 empty] | Items not addressed prior to Nodal go-live

## 2011 PPL
2011 Priority | 2011 Rank | Program Area | Source | Project Number | Capital Projects | 2011 Budget Range | Cumulative Budget Range | Current Status | Exec Sponsor | Description
1- Critical | 1 | DC | ERCOT | Various | Data Center Buildout | $30M-$40M | $30M-$35M | Execution | Morgan | Data Center Buildout Project - 8 subprojects addressing storage, servers, tape backup, telecommunication, and network gear
1- Critical | 2 | CO | ERCOT | 99911 | Minor Cap - Critical | $500k-$1M | $30M-$35M | Execution | Cleary | Critical priority Minor Cap purchases
1- Critical | 3 | RO | Market | 11002_01 | Texas SET 4.0 | $1M-$2M | $35M-$40M | Not Started | Cleary | TX SET project to include reconnect / disconnect, AMS, Acquisitions, Meter Tampering
1- Critical | 4 | MO | ERCOT | 90006_02 | Information Lifecycle Mgmt – Mkt Systems, Archive, Reporting | $1M-$2M | $35M-$40M | Planning | Cleary | Subproject of 90006_01 - optimizing data storage requirements for our commercial systems
1- Critical | 5 | IO | ERCOT | 11003_01 | Cyber Security Project #1 | $500k-$1M | $35M-$40M | Not Started | Manning | Enhance a specific area of ERCOT's cyber security capability
1- Critical | 6 | MO | ERCOT | 10052_01 | Settlement System Upgrade | $1M-$2M | $35M-$40M | Planning | Cleary | Replace the current application code with an optimized, self-supported solution. Includes only the conversion of code -- no enhancements.
1- Critical | 7 | CO | ERCOT | 11004_01 | Cyber Security Project #2 | $250k-$500k | $35M-$40M | Not Started | Manning | Enhance a specific area of ERCOT's cyber security capability
1- Critical | 8 | IO | ERCOT | 11005_01 | IT Security Infrastructure Upgrade | $100k-$250k | $35M-$40M | Not Started | Morgan | Upgrade a specific component of the IT security infrastructure
1- Critical | 9 | RO | PUCT / Market | 11006_01 | MarkeTrak Upgrade and Enhancements (PLANNING) | $100k-$250k | $40M-$45M | Not Started | Cleary | Enhance MarkeTrak application for new PUCT requirements and other enhancements requested by market participants. Examples: new subtypes for Expedited Switch Rescission and Meter Tampering, improved data validation, and AMS usage parameters
2-High | 10 | RO | ERCOT | 50088_01 | Data Research and Reporting | $500k-$1M | $40M-$45M | Execution | Cleary | Transition of ETS reporting from Data Archive to Enterprise Data Warehouse - Final stage of project
2-High | 11 | MO | ERCOT | 10055_01 | Data Agg Performance Improvements | $250k-$500k | $40M-$45M | Planning | Cleary | New project to address data aggregation processing performance risk Expected to start in 2010 and conclude in 2011
2-High | 12 | CO | ERCOT | 10031_01 | Enterprise Records Management Automation (ERMA) | <$50k | $40M-$45M | Execution | Magness | Provide a centralized record management repository for ERCOT with email integration.
2-High | 13 |  |  | New |  |  |  | Not Started
2-High | 14 |  |  | New |  |  |  | Not Started
2-High | 15 |  |  | New |  |  |  | Not Started
Cutline
2-High | 50 | IO | ERCOT | New | IDM (databases only) | $500k-$1M | $40M-$45M | Not Started | Morgan | Eliminate maintenance of two systems to control access to ERCOT systems.
2-High | 51 | MC | ERCOT | New | Minor Cap - High | $250k-$500k | $40M-$45M | Not Started | Cleary | High priority Minor Cap purchases
2-High | 52 | CO | ERCOT | New | Cyber Security Project #3 | $250k-$500k | $40M-$45M | Not Started | Manning | Enhance a specific area of ERCOT's cyber security capability
2-High | 53 | IO | ERCOT | New | Oracle Access Management | $250k-$500k | $40M-$45M | Not Started | Morgan | Replace a manual effort carried out by the DBA’s.
2-High | 54 | IO | ERCOT | New | Cyber Security Project #4 | $100k-$250k | $40M-$45M | Not Started | Morgan | Enhance a specific area of ERCOT's cyber security capability
2-High | 55 | MO | Market/ ERCOT | 90015_01 | Web-enabled Registration | $100k-$250k | $40M-$45M | Not Started | Cleary | Create an interface that MPs (and potential MPs) can use to electronically submit and update registration data post nodal go-live.
2-High | 56 | IO | ERCOT | New | Tripwire | $100k-$250k | $40M-$45M | Not Started | Morgan | Tripwire has been deployed for approximately 3 years. To garner further benefit to our investment we would like to deploy a new utility Tripwire has available called Log Center.
2-High | 57 | IO | ERCOT | New | Storage Replication Strategies | $50k-$100k | $40M-$45M | Not Started | Morgan | Resize Ptest and Itest environments
2-High | 58 | MO | ERCOT | 90017_01 | ERCOT.com CMS Replacement | $250k-$500k | $45M-$50M | Not Started | Cleary | Replace the Serena Collage application and Market Information Repository (MIR)
2-High | 59 | MO | ERCOT | 10006_01 | EPS Meter DB Redesign | $500k-$1M | $45M-$50M | Not Started | Cleary | Move departmental EPS Meter database and web views due to unsupported compatibility.
2-High | 60 | IO | ERCOT | New | Secure Storage Bldg | $250k-$500k | $45M-$50M | Not Started | Morgan | Facilities secured storage and shop
2-High | 61 | IO | ERCOT | New | Blue Bldg Reconfig | $100k-$250k | $45M-$50M | Not Started | Morgan | Blue Building reconfiguration
2-High | 62 | CO | ERCOT | 10039_01 | Physical Security Project #1 | $250k-$500k | $45M-$50M | Not Started | Manning | Enhance a specific area of ERCOT's physical security
3-High/Med | 63 | MC | ERCOT | New | Minor Cap - Other | $250k-$500k | $45M-$50M | Not Started | Cleary | Lower priority Minor Cap items
3-High/Med | 64 | IO | ERCOT | New | OS Upgrades | $250k-$500k | $45M-$50M | Not Started | Morgan | Upgrade Windows, Linux, AIX and other supporting applications to the latest versions.
3-High/Med | 65 | MO | ERCOT | New | AppWorx Upgrade | TBD | $45M-$50M | Not Started | Morgan | Upgrade to newer version.
3-High/Med | 66 | RO | ERCOT | New | Rearchitecture of Zonal TIBCO Framework (to be consistent with Nodal) | TBD | $45M-$50M | Not Started | Morgan | Upgrade to Zonal TIBCO to be consistent with Nodal TIBCO
3-High/Med | 67 | RO | ERCOT | 10004_01 | Retail Testing Website Enhancement | $250k-$500k | $45M-$50M | Not Started | Cleary | ERCOT upgrade to transition to Enterprise Architecure approved infrastructure. No functional changes planned.
3-High/Med | 68 | RO | ERCOT | New | Siebel Table Split | TBD | $45M-$50M | Not Started | Cleary | The objective of this project is to make modifications to the Siebel data model to gain performance efficiencies and comply with Siebel technical data architecture guidelines.
3-High/Med | 69 | RO | ERCOT | New | Siebel Upgrade | TBD | $45M-$50M | Not Started | Morgan | The objective of this project is to upgrade Siebel to the latest Siebel release.
3-High/Med | 70 | RO | ERCOT | 10050_01 | TIBCO Upgrade | $100k-$250k | $45M-$50M | Not Started | Morgan | This project will upgrade ERCOT’s TIBCO infrastructure and underlying Linux Operating System (Zonal only).
3-High/Med | 71 | IO | ERCOT | New | TCC2 Delivery Room Reconfig | $250k-$500k | $45M-$50M | Not Started | Morgan | TCC2 Delivery Room reconfiguration
3-High/Med | 72 | IO | ERCOT | New | TCC2 Cube Reconfig | $500k-$1M | $50M-$55M | Not Started | Morgan | TCC2 Cube reconfiguration
3-High/Med | 73 | IO | ERCOT | New | TCC2 Hope Room Reconfig | $250k-$500k | $50M-$55M | Not Started | Morgan | TCC2 Hope Room reconfiguration
3-High/Med | 74 | IO | ERCOT | New | TCC1 Cube Reconfig | $500k-$1M | $50M-$55M | Not Started | Morgan | TCC1 1st floor cubicle reconfiguration
3-High/Med | 75 | IO | ERCOT | New | Windows 7 | $100k-$250k | $50M-$55M | Not Started | Morgan | Windows 7 upgrade
4-Medium | 76 | MO | Market | New | Default Uplift Process | TBD | $50M-$55M | Not Started | Cleary | Modify the existing Lodestar uplift functionality to support uplift of defaults on DAM Invoices and RTM Invoices through a Default Uplift Invoice, in an automated fashion.
4-Medium | 77 | MO | Market | 10008_01 | Enhancements to API for Disputes | TBD | $50M-$55M | Not Started | Cleary | Enhance the API Disputes functionality for updates, search and other functions post nodal go-live.
4-Medium | 78 | MO | ERCOT | 90006_03 | System Right-Sizing for ILM | TBD | $50M-$55M | Not Started | Morgan | All systems coming online with Nodal - need to establish ongoing maintenance activities. Replication from Nodal systems. CRR, CMM sources only.
4-Medium | 79 | CO | ERCOT | 70015_01 | Cyber Security Project #5 | $100k-$250k | $50M-$55M | Not Started | Manning | Enhance a specific area of ERCOT's cyber security capability
4-Medium | 80 | RO | ERCOT | New | Test Automation Tool Upgrade | TBD | $50M-$55M | Not Started | Morgan | Affects anything using WinRunner today
4-Medium | 81 | CO | ERCOT | 10030_01 | Vendor Contract Information Database Review | <$50k | $50M-$55M | Not Started | Cleary | Move the management of vendors and vendor contracts from the current, in-house developed application to a best-practice model application
4-Medium | 82 | CO | ERCOT | New | Cyber Security Project #6 | TBD | $50M-$55M | Not Started | Manning | Enhance a specific area of ERCOT's cyber security capability
4-Medium | 83 | CO | ERCOT | New | Cyber Security Project #7 | TBD | $50M-$55M | Not Started | Manning | Enhance a specific area of ERCOT's cyber security capability
4-Medium | 84 | CO | ERCOT | 10049_01 | Collateral Calculation Enhancement | $100k-$250k | $50M-$55M | Not Started | Cleary
9-Parking Lot |  | RO | PUCT | 90007_01 | Advanced Metering – Long-Term Settlement Solution | TBD | TBD | Not Started
9-Parking Lot |  | MO | Market | 10007_01 | Verifiable Cost Management System (VCMS) | TBD | TBD | Not Started
9-Parking Lot |  | CO | ERCOT | 10029_01 | Governance, Risk & Compliance (GRC) | TBD | TBD | Not Started
9-Parking Lot |  | CO | ERCOT | 10032_01 | App Log Centralization | TBD | TBD | Not Started
9-Parking Lot |  | CO | ERCOT | 10043_01 | BOD Material Preparation & BOD Resolution Tracking | TBD | TBD | Not Started
9-Parking Lot |  | CO | ERCOT | 10045_01 | Document Preparation Software - Legal | TBD | TBD | Not Started
9-Parking Lot |  | CO | ERCOT | 10046_01 | Lawson Pcard Module | TBD | TBD | Not Started
9-Parking Lot |  | CO | ERCOT | New | Open Enrollment | TBD | TBD | Not Started
9-Parking Lot |  | IO | ERCOT | New | Oracle Upgrade | TBD | TBD | Not Started
9-Parking Lot |  | MO | ERCOT | New | Rewrite REC Program | TBD | TBD | Not Started

## Market-Facing Defects
Defect ID | Summary | Market Description | Production Target Date | System | Counts
5963 | OS Core: for MP UI: The NewPlanned and New latest End dates should be extended one more time | Once an outage has been extended it can't be extended again. | 2011-01-19 | Outage Scheduler | Current Day Reports | 13
6879 | OS: Core: Transmission M1 - Withdrawn outages which are not active should not be ended | A withdrawn Outage does not require an Actual End even though the UI will display the field. | 2011-01-19 | Outage Scheduler | Congestion Revenue Rights | 6
7077 | OS Core: RUI-PL_GRP_Status-Study-poor error message when trying to add notes | When an outage has a status of Study and the user attempts to add a note, the error message needs to be more specific. | 2011-01-19 | Outage Scheduler | Enterprise Data Warehouse | 1
8755 | OS UI: Usability: Associated Equipment Table: Select All for the check boxes | When the user views associated equipment they must select each piece of the line in a check box. A "Select All" button is needed. | 2011-01-19 | Outage Scheduler | Enterprise Web Services | 16
10276 | OS UI Usability: When your right click from Print, Export.xml or Export.csv you get a blank page | When the user clicks on the "Print summary information", "Export.xml or Export.csv, they may receive a blank page. | 2011-01-19 | Outage Scheduler | Market Information System | 4
10512 | OS UI Print Summary Information link screen shares the same title as the Summary Screen | The "Print Summery Information" window has the same title in the title bar at the top of the screen as Summery screen. | 2011-01-19 | Outage Scheduler | Market Management System | 5
13039 | OS Core: When an outage is at PComp state, Actual End is not editable | Enter the required supporting notes then the Actual End becomes editable. | 2011-01-19 | Outage Scheduler | Market Manager | 3
13575 | OS Core: Outage past its end date cannot be extended gives an invalid error message | Once an outage has passed the Planned End Date/time the user can't extend the outage. If the MP attempts to extend the outage, the error message they receive is misleading. | 2011-01-19 | Outage Scheduler | Market Participant Identity Management | 3
13588 | OS UI TSP WRN column - arrows do not highlight asc or dec when clicked | The arrows on the summary columns do not indicate if the column is sorted ascending or descending | 2011-01-19 | Outage Scheduler | MIS Dashboard | 1
15186 | DST-NP6-235 - System-Wide Demand report output does not have enough data during CDT time. | .NP6-235 - System-Wide Demand report output does not have enough data during CDT time. | 2011-01-19 | Reports | Network Model Management System | 1
15267 | DST-NP3-217-Temperature Adjusted Dynamic Ratings - Report output has 2.00 hour on CDT day. | .NP3-217-Temperature Adjusted Dynamic Ratings - Report output has 2.00 hour on CDT day. Fixes putting '*' by extra hour during Fall DST transition. | 2011-01-19 | Reports | Outage Scheduler | 17
15269 | DST-NP4-159-Load Forecast Distribution Factors - Report output has 2.00 hour on CDT day. | .NP4-159-Load Forecast Distribution Factors - Report output has 2.00 hour on CDT day. Fixes putting '*' by extra hour during Fall DST transition. | 2011-01-19 | Reports | Outage Scheduler UI | 6
17781 | OS Core: The OS needs to auto populate the Actual Start/Actual End on an outage with the "Nature of Work" of "New Equipment Energization" | When a MP is putting a new piece of equipment in service they are suppose to enter an outage with a Planned Start date of a network model load prior to the date the equipment we be energized. Since the model load will be around MN they have asked that the system auto populate the Actual Start. When a MP is retiring a piece of equipment they are suppose to enter an outage with a Planned End date of a network model load after the equipment is removed from service. Since the model load will be around MN they have asked that the system auto populate the Actual End. | 2011-01-19 | Outage Scheduler | Registration | 2
17922 | OS Core: MP is unable to extend an outage a second time | The MPs are unable to extend an outage more than one time. | 2011-01-19 | Outage Scheduler | Reports | 3
18006 | Self Energy Trade Net Trade of Letter Other Than 'P' or 'S' Not Handled Properly | Characters outside of 'P' and 'S' for a self energy trade are not handled properly by the MMS Market Manager. | 2011-01-19 | Market Manager | Total | 81
18038 | Self energy trade submission formed incorrectly when value changes on Int End 30 or 45 | Self energy trades will fail from the MMS MM when the MW value or P/S value of one hour carries over into the next hour and changes on either the 30 or 45 minute interval | 2011-01-19 | Market Manager
18039 | Clicking to see details of partially confirmed trade from unconfirmed trade is read-only | Clicking to view the details of the unconfirmed portion of a partially confirmed trade entered by the user brings up a read-only screen. This screen should be editable | 2011-01-19 | Market Manager
18069 | MIS - Dashboard - LF vs Actual label change | On the Load Forecast vs Actual dashboard, the labels will be changed to more accurately reflect the data given. 'Online Generation - Actual' will become 'Current Day COP HSLs for Online Generation', and 'Online Generation - Planned' will become 'Day-Ahead COP HSLs for Online Generation'. | 2011-01-19 | MIS Dashboard
14113 | EWS Sync Response loses correlation with async for schema errors | When inbound submissions fail to validate to the schema, ensure that the mRIDs associated to that submission are returned in the Notification message. | 2011-01-21 | Enterprise Web Services
15195 | SHORT DST - Market Info: SystemLoad, the time of EWS response is incorrect when the TimeEnding of CDR report is 3:00 on short day (CST->CDT). | SystemLoad has incorrect time after Daylight Savings Time transition. | 2011-01-21 | Enterprise Web Services
15220 | SHORT DST - Market Info: SPPs_DAM, the ending of EWS response is incorrect when the HourEnding of CDR report is 2:00 on short day (CST->CDT). | For the day in which CST to CDT takes place, the second hour in many reports is being reported with a "time" element of 01:00:00-06:00 and an "ending" element of 02:00:00-06:00. The "ending" element should instead be 03:00:00-05:00. | 2011-01-21 | Enterprise Web Services
15235 | SHORT DST - Market Info: TotalEnergys, the ending of EWS response is incorrect when the HourEnding of CDR report is 2:00 on short day (CST->CDT). | For the day in which CST to CDT takes place, the second hour in many reports is being reported with a "time" element of 01:00:00-06:00 and an "ending" element of 02:00:00-06:00. The "ending" element should instead be 03:00:00-05:00. | 2011-01-21 | Enterprise Web Services
15276 | SHORT DST - Market Info: MarketTotals, the ending of EWS response is incorrect when the HourEnding of CDR report is 2:00 on short day (CST->CDT). | For the day in which CST to CDT takes place, the second hour in many reports is being reported with a "time" element of 01:00:00-06:00 and an "ending" element of 02:00:00-06:00. The "ending" element should instead be 03:00:00-05:00. | 2011-01-21 | Enterprise Web Services
15277 | SHORT DST - Market Info: BindingConstraints, the deliveryTime of EWS response is incorrect when the HourEnding of CDR report is 2:00 or RUCTimeStamp of CDR report is 14:xx:xx on short day (CST->CDT). | For the day in which CST to CDT takes place, the second hour in many reports is being reported with a "time" element of 01:00:00-06:00 and an "ending" element of 02:00:00-06:00. The "ending" element should instead be 03:00:00-05:00. | 2011-01-21 | Enterprise Web Services
15278 | SHORT DST - Market Info: AggregatedASOfferCurves, the endTime of EWS response is incorrect when the HourEnding of CDR report is 2:00 on short day (CST->CDT). | For the day in which CST to CDT takes place, the second hour in many reports is being reported with a "time" element of 01:00:00-06:00 and an "ending" element of 02:00:00-06:00. The "ending" element should instead be 03:00:00-05:00. | 2011-01-21 | Enterprise Web Services
15292 | SHORT DST - Market Info: ASServicePlan, the ending of EWS response is incorrect when the HourEnding of CDR report is 2:00 on short day (CST->CDT). | For the day in which CST to CDT takes place, the second hour in many reports is being reported with a "time" element of 01:00:00-06:00 and an "ending" element of 02:00:00-06:00. The "ending" element should instead be 03:00:00-05:00. | 2011-01-21 | Enterprise Web Services
15293 | SHORT DST - Market Info: TotalASOffers, the ending of EWS response is incorrect when the HourEnding of CDR report is 2:00 on short day (CST->CDT). | For the day in which CST to CDT takes place, the second hour in many reports is being reported with a "time" element of 01:00:00-06:00 and an "ending" element of 02:00:00-06:00. The "ending" element should instead be 03:00:00-05:00. | 2011-01-21 | Enterprise Web Services
15314 | SHORT DST - Market Info: SPPs_RTM, both time and ending of EWS response are incorrect when the DeliveryDate of CDR report is short day (CST->CDT). | For the day in which CST to CDT takes place, the SPP reports are reported with a -06:00 offset when it should be -05:00 after the CDT transition. | 2011-01-21 | Enterprise Web Services
15348 | SHORT DST - Market Info: DynamicRatings, the createTime of EWS response is incorrect when CreateTime of CDR report is short day (CST->CDT). | Market Info: DynamicRatings, the createTime of EWS response is incorrect when CreateTime of CDR report is short day 3/14/2010 (CST->CDT). | 2011-01-21 | Enterprise Web Services
15353 | SHORT DST - Market Info: LoadRatioShares, both time and ending of EWS response are incorrect when DeliveryDate of CDR report is short day (CST->CDT) and HourEnding of CDR report is 24:00. | Market Info: LoadRatioShares, both time and ending of EWS response are incorrect when DeliveryDate of CDR report is short day 3/14/2010 (CST->CDT) and HourEnding of CDR report is 24:00. | 2011-01-21 | Enterprise Web Services
15368 | SHORT DST - Market Info: LoadForecasts, both time and ending of EWS response are incorrect when the HourEnding of CDR report is 1:00 and 2:00 and DeliveryDate of CDR report is short day (CST->DST). | Market Info: LoadForecasts (LOAD, SYSTEM and WEATHER), both time and ending of EWS response are incorrect when the HourEnding of CDR report is 1:00 and 2:00 and DeliveryDate of CDR report is short day 3/14/2010 (CST->DST). | 2011-01-21 | Enterprise Web Services
15392 | SHORT DST - Market Info: TotalLoad, the time of EWS response is incorrect when the TimeEnding of CDR report is 03:XX and the DeliveryDate is short day (CST->DST). | For the TotalLoad report, the time in the response is incorrect when the TimeEnding of CDR report is 03:XX and the DeliveryDate is short day 3/14/2010 (CST->DST). | 2011-01-21 | Enterprise Web Services
17266 | MPIM - ITEST - Enhancement - Certificate Renewal Emails Do Not Contain the DUNS | The MP will not see a DUNs within the email they receive to renew their digital certificate. | 1/23/2011 - Covered under Retail MP notice | Market Participant Identity Management
17670 | Invalid time values for TotalLoad market info service. | Total Load report available via EWS is reporting at an incorrect time interval. | 2011-01-21 | Enterprise Web Services
17821 | Support disabling of individual adapters in EWS | Provide method to return accurate information on the availability of the EWS transaction. | 2011-01-21 | Enterprise Web Services
18467 | OS UI: Remove from the OS UI the 3 day rule for NPE as of OS core release 2.3.0 | The User can wait to extend the outage until 3 days before the PE date. The user may also extend the outage using the API without the limitation. | 2011-01-19 | Outage Scheduler
18472 | NPRR261: PTC: Summer: Remove restriction for interim update to make it simple 90 days for all cases | The user needs to be able to submit model information for each month in the summer and not the summer as a block model update. | 2011-01-19 | Network Model Management System
18307 | DC Ties incorrectly show up as a QSE in the Market Manager | DC Ties are incorrectly listed on the drop down list for QSEs (for example, when creating an energy trade, one of the options on the drop down for 'seller' is 'DC_E'). | 2011-01-20 | Market Management System
18357 | Wrong DELIVERY_HOUR in HRUC Message | The hour in the text of the HRUC alert that is available to all MPs is offset by one hour. Startup/Shutdown Instructions for individual QSE awards are correct. Example: HRUC-AWD-RPT Reports on HRUC Awards for operating date 12/06/2010 hr 21 are available. Should say hr 20. | 2011-01-20 | Market Management System
15269 | DST-NP4-159-Load Forecast Distribution Factors - Report output has 2.00 hour on CDT day. | .NP4-159-Load Forecast Distribution Factors - Report output has 2.00 hour on CDT day. Fixes putting '*' by extra hour during Fall DST transition. | 2011-02-23 | Current Day Reports
18423 | CRR: MUI Downloads: Error message "System is experiencing difficulties" during market results posting | Market Participants are unable to download Private Results after market posting due to a resource conflict in the application. | 2011-02-23 | Congestion Revenue Rights
18424 | CRR: MUI Downloads: Time Stamp of the Network and Market download files is earlier than when the market is first posted | Download files are using GMT time in the MUI rather than CPT; in some instances, the files appear to have been written prior to when the market results were posted. | 2011-02-23 | Congestion Revenue Rights
18425 | CRR: MUI Downloads: Market Results download files were not generated after an auction was posted | Download files were not created as a result of resource conflict while market participants were attempting to download files as the system was trying to write them. A separate process is now dedicated to the writing of the files; this is related to defect 18423. | 2011-02-23 | Congestion Revenue Rights
18619 | CRR: MUI Portfolio Editor: Auction Portfolio allows users to enter a 0 price for Options and save the Portfolio | CRR portfolio editor allows a zero priced OPTION to be saved and submitted to an auction. Minimum price for an Option should be $0.01. | 2011-02-23 | Congestion Revenue Rights
18622 | CRR: MUI Downloads: Monitored lines and transformer download file was not checking the last modified date to know when to display new data | When updates to the limits were made in the Market Operator interface, the timestamp on the datacase was not updated to reflect the changes, and hence, the monitored lines and transformers file was not updated for the Market Participant. | 2011-02-23 | Congestion Revenue Rights
18664 | CRR: MUI Credit Limit Editor: Unable to open credit limit editor page due to missing parameter (for both Market Participant and Counterparty) | System not available message was displayed for the credit limit editor due to a missing parameter in the system. | 2011-02-23 | Congestion Revenue Rights
18654 | Two State Estimator - ER reports not available on MIS SE Reports portlet | These EDW reports are available via the MIS Reports and Extracts page, but not on the SE Reports and Index portlet. | 2011-02-23 | Market Information System
18665 | Add new link to Data Aggregation page: NP9-288-SG, IDR Protocol Compliance Verification for Disputes | Missed requirement | 2011-02-23 | Market Information System
18555 | NP7-464 Updates to Run Time and Query Logic | When DAM is delayed and results are not published by 1500, then the previous day's data is published. Changing the posting to be published at 1800 should account for most days when DAM is delayed. Also, adding logic to the query for the posting to look for sysdate+1 will ensure that the previous day's DAM data is not posted for this report. | 2011-02-28 | Current Day Reports
18593 | NP6787 - LMPs by Electrical Buses: Fix Spring DST date logic | NP6787 - LMPs by Electrical Buses | 2011-02-28 | Current Day Reports
18594 | NP6788 - LMPs by Resource Nodes, Load Zones: Fix Spring DST date logic | NP6788 - LMPs by Resource Nodes, Load Zones | 2011-02-28 | Current Day Reports
18595 | NP7807 - SPP Real Time Point to Point Option Price Report: Fix Spring DST date logic | NP7807 SPP Real Time Point to Point Option Price Report | 2011-02-28 | Current Day Reports
18596 | NP5200 - Contingencies Deselected in RUC: Fix Spring DST date logic | NP5200 Contingencies Deselected in RUC | 2011-02-28 | Current Day Reports
18597 | NP5649 - Temporarily Removed Contingencies: Fix Spring DST date logic | NP5649 - Temporarily Removed Contingencies | 2011-02-28 | Current Day Reports
18598 | NP5752 - Hourly RUC Committed or Decommitted Resources: Fix Spring DST date logic | NP5752 - Hourly RUC Committed or Decommitted Resources | 2011-02-28 | Current Day Reports
18599 | NP5755 - Hourly RUC Active and Binding Transmission Cons.: Fix Spring DST date logic | NP5755 - Hourly RUC Active and Binding Transmission Cons. | 2011-02-28 | Current Day Reports
18600 | NP686 - SCED Shadow Prices and Binding Transmission Constr.: Fix Spring DST date logic | NP686 - SCED Shadow Prices and Binding Transmission Constr. | 2011-02-28 | Current Day Reports
18601 | SYS608 - Shift Factors: Fix Spring DST date logic | SYS608 - Shift Factors: Fix Spring DST date logic | 2011-02-28 | Current Day Reports
18602 | NP6635CDB - Online Generation Actual (Load Forecast vs Actual): Fix Spring DST date logic | NP6635CDB - Online Generation Actual (Load Forecast vs Actual) | 2011-02-28 | Current Day Reports
18607 | NPR6635EDB - Actual Load (Load Forecast vs Actual): Fix Spring DST date logic | NPR6635EDB - Actual Load (Load Forecast vs Actual): | 2011-02-28 | Current Day Reports
18544 | PUCT Rule requires a new report posting: NP6-627-CD, State Estimator Bus Voltages | PUCT required new report, SE Bus Voltages; must be available by 3/1. | 2011-02-28 | Market Information System
17848 | NER63 MIS - ITEST - "Load Forecast vs. Actual" dashboard - Graph Truncates on Landing Page | Market will see graph as is | 2011-03-23 | Market Information System
12022 | All price within a CRR offer/PTP Bid Hour Block should be Same | The system accepts submissions of PTP Bids and CRR Offers that are blocked across time and have different MW and Price values within the time block. These are not valid offers and bids and should be rejected. The defect fix will remove the ability to specify different MW and price for time-blocked offers and bids. | 2011-03-23 | Market Management System
18554 | Self Energy Trade Net Trade of Letter Other Than 'P' or 'S' Not Handled Properly | If the letter for the Net Trade is entered as say a 'D' as opposed to a 'P' or an 'S' during the creation of a self energy trade, the UI gives an appropriate error message, but not all bad fields are highlighted. This fix will highlight all the fields in error. | 2011-03-23 | Market Management System
18644 | Notices tab cannot display special characters | This fix displays any special characters entered in the Notices Tab. | 2011-03-23 | Market Management System
18525 | OS: Extensions to 2.3.0 | For the Nature of work Retirement Old Equipment outages are auto ended on their end date For the Nature of work New Equipment Energization outages are auto started on their start date | 2011-03-23 | Outage Scheduler
18538 | OS: NPE can't move a NPE inward for both QSE and TSP all outage types | New Planned End cannot be moved inward. This should be allowed as long as none of the original date rules are broken. | 2011-03-23 | Outage Scheduler
18683 | OS: Do not auto populate the AE when the Nature of Work New Energization is selected | The AE is not auto-populated when the user selects New Equipment Energization | 2011-03-23 | Outage Scheduler
7922 | TSP Issues List: OS Core All: TSP: From Station is assigned to only one end of a line. | When the user is entering an outage on a Line, the From Station is only assigned to one end of the line. Both "to" and "from" station will now be available to select from in the Outage | 2011-03-23 | Outage Scheduler
18214 | Once an outage is submitted the TSP should be able to shorten an outage to less than the outages restoration time. | TSP is not able to shorten an outage to be less than the outage restoration time. | 2011-03-23 | Outage Scheduler
9761 | OS UI: Copying an outage from the Success screen does not copy Notes | When the MP copies an existing outage that has Requestor Notes, the original notes are being copied. | 2011-03-23 | Outage Scheduler UI
10343 | OS UI Usability: When the Custom Filter is open sort of a column in the table should not close the filter | When the MP sorts a column the filter closes the MP must reopen the filter to see their current choices for the filter. | 2011-03-23 | Outage Scheduler UI
10610 | OS UI All: Group: Sections reopen when I click though the linked Outage ID in a group table | In the details of a group outage, if the user collapses one of the areas of the outage information then clicks on another outage in the "Equipment in Group" section, the collapsed area reopens. | 2011-03-23 | Outage Scheduler UI
12337 | OS Core:: TSP: Forced Submit -missing fields from screen | The forced outage submit does not display the primary and secondary phone numbers | 2011-03-23 | Outage Scheduler UI
17943 | OS UI Copy when going from a PL to a FR you should not include a ES on the create | When an MP copies a Planned Outage and then changes the copied outage to a Forced outage when submitted they receive an error message then the Earliest Start should be equal to or less than the Planned Start. | 2011-03-23 | Outage Scheduler UI
18203 | OS UI - QSE equipment cannot be deleted without causing an application error. | The user may refresh the page, after deleting any equipment, and then re-enter the equipment row. | 2011-03-23 | Outage Scheduler UI
18518 | Siebel - New Sub types for Service Request under type Registration | the MP's whom have a valid DC and can access SR/SD will be able to view and access the additional SR types via MIS/TML | 2011-03-27 | Registration
18534 | Siebel - eService Screen is not refreshing the Charge Type Values when we Select other Dispute sub-Type value | eService is viewable to the MP's that have a valid DC and has the correct role to access nodal settlement disputes via MIS and/or TML | 2011-03-27 | Registration
18559 | MPIM - MPIM screen displays Some Frame Page | The USA's can access MPIM and see the tab labeled Some Frame Page. | 2011-03-27 | Market Participant Identity Management
18287 | Itest MPIM - Tracking defect for updating the MP email correspondence | The MP is receiving an email that is prompting them to contact their DC USAs. This is a miscommunication delivered in the automatic generated email notification from MPIM. | 2011-03-27 | Market Participant Identity Management
18124 | NP3-987 7-Day Event Trigger Posting when LMP exceeds 50xFIP - Fix Fall DST time issue | NP3-987 7-Day Event Trigger Posting when LMP exceeds 50xFIP - Fix is on Fall DST | 2011-03-31 | Enterprise Data Warehouse

## Lookup Tables
Delivery Groups | Target Delivery Timeframe | Focus Area | Comments | Sort Char | Release Year | IA Phase
Deferred Defects - G1 - Jan 11 | January 2011 | DST, Planning Go-Live | Targeted for January 2011 | 1 | 2011 | 1
Deferred Defects - G2 - Mar 11 | March 2011 | Various | Targeted for March 2011 | 2 | 2012 | 2
Deferred Defects - G3 - May 11 | May 2011 | Various | Targeted for May 2011 | 3 | 2013+ | 3
Deferred Defects - G4 - Jun 11 | June 2011 | Various | Targeted for June 2011 | 4 | TBD | 4
Deferred Defects - G5 - Jul 11 | July 2011 | Various | Targeted for July 2011 | 5 | Future Year TBD | TBD
Deferred Defects - G6 - Aug 11 | August 2011 | EMS | Targeted for August 2011 | 6
Deferred Defects - G7 - Sept 11 | Sept 2011 | EMS | Targeted for September 2011 | 7
Release 2.0 | 2012 | TBD | First major enhancement release | 9
Future Release | TBD | TBD | Deferred to future release | 10
Standalone Project | Various | N/A | Projects not subject to the release schedule | 8
N/A | N/A | N/A | Prioritization not required | 11
TBD |  |  | Yet to be defined | 99