|  |  |  |  | System Planning Division |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report to Reliability and Operations Subcommittee for January 2011 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
| Item |  |  |  |  |  |  |  |  |
| 1. | - ERCOT is currently tracking 191 active generation interconnection requests totaling almost 64,000 MW. This includes almost 37,000 MW of wind generation. |  |  |  |  |  |  |  |
| 2. | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $51.1 Million - Transmission Projects endorsed in 2010 total $268.8 Million - All projects (in engineering, routing, licensing and construction) total approximately $9.3 Billion - Transmission Projects energized in 2010 total about $857.1 million |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	New Generation Registering for Commercial Operations	1

1.2	Publicly Disclosed Generation Interconnection Projects	4

1.3	Generation Projects Undergoing Full Interconnection Studies (not otherwise public)	6

1.4	Wind Generation	8

2.	Regional Planning Group Project Reviews	10

3.	Congestion Costs	11

4.	Wind Generation as a Percent of Load	13

5.	Planning Model Activities	14

6.	Other Notable Activities	15

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## New Generation Registering for Commercial Operations

The total installed wind capacity is reported as 9,400 MW by the resource owners through the registration process.

Summary of Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |  |  |  |  |
| --- | --- | --- | --- | --- |
| Currently tracking 191 active generation interconnection or change requests |  |  |  |  |
| As of January 31, 2011 | North | South | West | Total |
| Security Screening Study | 3 | 2 | 9 | 14 |
| SSS Completed | 1 | 2 | 14 | 17 |
| Full Interconnect Study | 18 | 14 | 88 | 120 |
| FIS Completed | 5 | 13 | 4 | 22 |
| Interconnect Agreement Completed | 7 | 6 | 5 | 18 |
| Capacity under Interconnection Agreements | 5,147 | 3,742 | 756 | 9,645 |
| Capacity for Grid, MW | 18,815 | 12,796 | 32,127 | 63,738 |
| Wind Capacity, MW | 3,507 | 4,093 | 29,226 | 36,826 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Projects w/ Interconnect Agreement/Public Letter (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- |
| Gas-CombinedCycle |  |  | 5,352 | 12,043 |
| Gas-All Other |  |  |  | 650 |
| Total Gas | 11 | 7,330 | 5,352 | 12,693 |
| Nuclear |  |  | 5,900 | 5,900 |
| Coal |  | 1,740 | 3,210 | 4,950 |
| Wind | 2,982 | 28,291 | 5,553 | 36,826 |
| Solar | 420 | 819 |  | 1,239 |
| Biomass |  | 50 | 100 | 150 |
| Other |  | 740 | 1,240 | 1,980 |
| Grand Total | 3,413 | 38,970 | 21,355 | 63,738 |

## Publicly Disclosed Generation Interconnection Projects

The table below summarizes the publicly disclosed generation projects for the ERCOT region.

(Status: IA=Interconnect Agreement, PL=Public Letter, XX= cancelled)

| Generation Interconnections as of January 31, 2011 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR | SiteName | Status | County | Region | COD | Fuel Type |  | MW For Grid | Change from Last Report |
| 08INR0065 | Buffalo Gap 4 and 5 | PL | Nolan | West | Mar-11 |  | Wind | 465 |  |
| 09INR0029 | CFB Power Plant Units 11&12 | IA | Calhoun | South | Mar-11 |  | Coal | 260 |  |
| 10INR0010 | Jack County 2 | IA | Jack | North | Jun-11 |  | Gas-CC | 620 |  |
| 08INR0038 | M Bar Wind | PL | Andrews | West | Dec-11 |  | Wind | 194 |  |
| 09INR0034 | Gatesville Wind Farm | PL | Coryell | North | Dec-11 |  | Wind | 200 |  |
| 12INR0003 | Throckmorton Wind Farm | PL | Throckmorton | West | Dec-11 |  | Wind | 400 |  |
| 08INR0025 | Pistol Hill Energy Center | PL | Ector | West | Dec-11 |  | Wind | 300 |  |
| 06INR0012b | Sherbino Mesa Wind Farm 2 | IA | Pecos | West | Jan-12 |  | Wind | 150 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Feb-12 |  | Coal | 925 |  |
| 08INR0062 | Archer-Young | IA | Young | West | Mar-12 |  | Wind | 250 |  |
| 11INR0084 | 2W Whatley Phase 1 | PL | Ector | West | Mar-12 |  | Wind | 45 |  |
| 09INR0007 | Nacogdoches Project | IA | Nacogdoches | North | Apr-12 |  | Biomass | 100 |  |
| 07INR0004 | Pampa Energy Center | PL | Gray | West | May-12 |  | Coal | 165 |  |
| 09INR0024 | B&B Panhandle Wind | PL | Carson | West | Jun-12 |  | Wind | 1001 |  |
| 09INR0037 | Scurry County Wind III | PL | Scurry | West | Jun-12 |  | Wind | 350 |  |
| 05INR0015b | Gulf Wind 2 | PL | Kenedy | South | Jul-12 |  | Wind | 400 | Date |
| 12INR0004 | Fort Concho Wind Farm | PL | Tom Green | West | Jul-12 |  | Wind | 400 |  |
| 12INR0043 | 2W Whatley Phase 2 | PL | Ector | West | Aug-12 |  | Wind | 290 |  |
| 08INR0011 | Senate Wind Project | IA | Jack | North | Sep-12 |  | Wind | 150 |  |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Dec-12 |  | Wind | 120 |  |
| 06INR0022c | Penascal Wind Farm 3 | IA | Kenedy | South | Dec-12 |  | Wind | 202 |  |
| 05INR0015c | Gulf Wind 3 | PL | Kenedy | South | Dec-13 |  | Wind | 400 | Date |
| 10INR0020a | Panda Temple Power | IA | Bell | North | Feb-14 |  | Gas-CC | 780 |  |
| 06INR0006 | Cobisa-Greenville | IA | Hunt | North | May-14 |  | Gas-CC | 1792 |  |
| 10INR0022 | Pondera King Power Project | IA | Harris | South | Jun-14 |  | Gas-CC | 1380 |  |
| 04INR0011b | Cedar Elm | IA | Shackelford | West | Jun-14 |  | Wind | 136 |  |
| 04INR0011c | Cottonwood Wind | IA | Shackelford | West | Jun-14 |  | Wind | 100 |  |
| 14INR0005 | White Stallion Energy Center | PL | Matagorda | South | Jul-14 |  | Coal | 1200 |  |
| 10INR0020b | Panda Temple Power | IA | Bell | North | May-15 |  | Gas-CC | 780 | Date |
| 12INR0016a | Las Brisas Energy Center | IA | Nueces | South | Jun-15 |  | Other | 620 |  |
| 14INR0002 | Coleto Creek Unit 2 | IA | Goliad | South | Jan-16 |  | Coal | 660 | Date |
| 12INR0016b | Las Brisas Energy Center | IA | Nueces | South | Jun-16 |  | Other | 620 |  |
| 15INR0008 | STP 3 and 4 | PL | Matagorda | South | Jun-16 |  | Nuclear | 2700 |  |
| 15INR0002 | Comanche Peak 3 and 4 | PL | Somervel | North | Dec-18 |  | Nuclear | 3200 |  |
|  |  |  |  |  |  |  | TOTAL | 21,355 |  |

County Location of Installed Generation and Interconnection Requests (all fuels)

## Generation Projects Undergoing Full Interconnection Studies (not otherwise public)

| INR | County | Capacity | COD | Fuel |  | INR | County | Capacity | COD | Fuel |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 09INR0054 | Stonewall | 149 | TBD | Wind |  | 10INR0048 | Hardeman | 1,000 | TBD | Wind |
| 10INR0016 | Childress | 150 | TBD | Wind |  | 10INR0054 | Palo Pinto | 36 | TBD | Wind |
| 10INR0079 | Nolan | 60 | TBD | Wind |  | 10INR0029 | Hood | 810 | TBD | Gas |
| 10INR0013 | Upton | 400 | TBD | Wind |  | 10INR0052a | Knox | 21 | TBD | Wind |
| 09INR0074 | Motley | 70 | TBD | Wind |  | 10INR0041 | Floyd | 135 | TBD | Wind |
| 11INR0029 | Throckmorton | 200 | TBD | Wind |  | 10INR0008 | Pecos | 500 | TBD | Wind |
| 07INR0013 | Coke | 200 | TBD | Wind |  | 10INR0019 | Deaf Smith | 609 | TBD | Wind |
| 10INR0032 | Navarro | 775 | TBD | Gas |  | 10INR0033 | Armstrong | 399 | TBD | Wind |
| 10INR0042 | Mason | 170 | TBD | Wind |  | 10INR0077 | Callahan | 101 | TBD | Wind |
| 10INR0051 | Brazoria | 200 | TBD | Wind |  | 11INR0076 | Archer | 94 | TBD | Wind |
| 11INR0050 | Crosby | 149 | Mar-11 | Wind |  | 11INR0081 | Live Oak | 72 | Mar-11 | Wind |
| 11INR0082A | Val Verde | 50 | Mar-11 | Wind |  | 11INR0083A | Crockett | 50 | Mar-11 | Wind |
| 11INR0085 | Nolan | 106 | Mar-11 | Wind |  | 11INR0088 | Brazos | 45 | Mar-11 | Gas |
| 11INR0071 | Harris | 7 | Apr-11 | Gas |  | 11INR0037 | Smith | 50 | May-11 | Biomass |
| 11INR0058 | Pecos | 135 | May-11 | Solar |  | 11INR0060 | Tom Green | 90 | May-11 | Solar |
| 11INR0061 | Presidio | 90 | May-11 | Solar |  | 11INR0062 | Nueces | 149 | May-11 | Wind |
| 08INR0020 | Eastland | 200 | Jun-11 | Wind |  | 09INR0050 | Fannin | 1,200 | Jun-11 | Gas |
| 10INR0023 | Haskell | 386 | Jun-11 | Wind |  | 11INR0054 | San Patricio | 161 | Jun-11 | Wind |
| 10INR0089 | Harris | 40 | Jun-11 | Other |  | 11INR0019 | Upton | 200 | Jun-11 | Wind |
| 11INR0091 | Webb | 92 | Jun-11 | Wind |  | 11INR0006 | Lamar | 579 | Jul-11 | Gas |
| 11INR0040 | freestone | 640 | Aug-11 | Gas |  | 11INR0047 | Deaf Smith | 600 | Sep-11 | Wind |
| 11INR0079a | Clay | 200 | Sep-11 | Wind |  | 10INR0062a | Pecos | 80 | Oct-11 | Wind |
| 10INR0081b | Clay | 19 | Oct-11 | Wind |  | 11INR0090 | Howard | 60 | Nov-11 | Solar |
| 11INR0094 | Kent | 100 | Nov-11 | Solar |  | 11INR0013 | Mills | 150 | Dec-11 | Wind |
| 11INR0025 | Crockett | 400 | Dec-11 | Wind |  | 11INR0043 | Coke | 300 | Dec-11 | Wind |
| 11INR0070 | Reeves | 50 | Dec-11 | Solar |  | 11INR0005 | Upton | 500 | Dec-11 | Wind |
| 11INR0089 | Hays | 20 | Dec-11 | Solar |  | 09INR0048 | Jack | 150 | Dec-11 | Wind |
| 12INR0033 | Motley | 150 | Jan-12 | Wind |  | 10INR0085 | Ector | 40 | Jan-12 | Solar |
| 10INR0018 | Madison | 550 | Mar-12 | Gas |  | 12INR0042 | Deaf Smith | 400 | Mar-12 | Wind |
| 09INR0031 | Ector | 275 | May-12 | Gas |  | 12INR0007 | Lamar | 296 | May-12 | Gas |
| 10INR0081a | Clay | 30 | May-12 | Wind |  | 08INR0031 | Childress | 100 | Jun-12 | Wind |
| 12INR0053 | Crockett | 615 | Jun-12 | Wind |  | 08INR0041 | Coke | 200 | Oct-12 | Wind |
| 12INR0026 | Randall | 400 | Oct-12 | Wind |  | 08INR0044 | Concho | 200 | Nov-12 | Wind |
| 08INR0042 | Coke | 200 | Dec-12 | Wind |  | 09INR0025 | Concho | 180 | Dec-12 | Wind |
| 12INR0005 | Floyd | 1,100 | Dec-12 | Wind |  | 12INR0029 | Swisher | 500 | Dec-12 | Wind |
| 10INR0024 | Briscoe | 2,940 | Jan-13 | Wind |  | 12INR0027 | Gray | 200 | Jan-13 | Wind |
| 09INR0058 | Howard | 250 | Mar-13 | Wind |  | 10INR0056 | Borden | 249 | Mar-13 | Wind |
| 12INR0034 | Borden | 342 | Mar-13 | Wind |  | 11INR0082B | Val Verde | 150 | Mar-13 | Wind |
| 11INR0083B | Crockett | 100 | Mar-13 | Wind |  | 12INR0018 | Gray | 500 | Apr-13 | Wind |
| 10INR0062b | Pecos | 220 | May-13 | Wind |  | 13INR0020a | Glasscock | 200 | May-13 | Wind |
| 09INR0051 | Borden | 249 | Jun-13 | Wind |  | 13INR0023 | Ector | 240 | Jul-13 | Gas |
| 13INR0016 | Deaf Smith | 251 | Aug-13 | Wind |  | 13INR0004 | Deaf Smith | 500 | Oct-13 | Wind |
| 13INR0005 | Carson | 600 | Oct-13 | Wind |  | 13INR0028 | Hale | 392 | Nov-13 | Gas |
| 12INR0002a | Briscoe | 200 | Dec-13 | Wind |  | 09INR0077 | Reagan | 500 | Dec-13 | Wind |
| 13INR0007 | Pecos | 200 | Dec-13 | Wind |  | 13INR0017 | Childress | 200 | Dec-13 | Wind |
| 10INR0009 | Castro | 300 | Dec-13 | Wind |  | 09INR0073 | Scurry | 200 | Dec-13 | Wind |
| 13INR0010 | Parmer | 1,200 | Dec-13 | Wind |  | 08INR0019a | Gray | 250 | Jan-14 | Wind |
| 08INR0019b | Gray | 250 | Jan-14 | Wind |  | 08INR0019c | Gray | 250 | Jan-14 | Wind |
| 13INR0006 | Gray | 750 | Jan-14 | Wind |  | 10INR0015 | Mitchell | 350 | May-14 | Wind |
| 13INR0020b | Glasscock | 150 | May-14 | Wind |  | 14INR0003 | Nolan | 850 | Jun-14 | Coal |
| 14INR0001 | Pecos | 500 | Dec-14 | Wind |  | 13INR0021 | Llano | 600 | Dec-14 | Gas |
| 12INR0002b | Briscoe | 200 | Dec-14 | Wind |  | 12INR0002c | Briscoe | 350 | Dec-15 | Wind |
| 16INR0002 | Brazoria | 700 | Jun-17 | Other |  |  |  |  |  |  |

## Wind Generation

Wind Capacity Installed by Year

County Location of Installed Capacity and Interconnection Requests (Wind only)

# Regional Planning Group Project Reviews

- Brazos Electric Cooperative has submitted a project to move some load that is currently being served by the Entergy Texas system into the ERCOT system.  The project would involve disconnecting the subject load from the Entergy Texas system, constructing a new 345/ 138 kV substation in ERCOT, upgrading an existing 69 kV line in the ERCOT system and constructing two new 138 kV lines to serve the load from the ERCOT system.  The estimated cost of this project is $51.1 M.  The project is currently undergoing ERCOT Independent Review.

# Congestion Costs

Dollars shown in graphs are settlement quality.

OOMC and RUC net Make Whole payment in million$

Monthly Average MCPE and LMP

Binding Constraints - December 2010

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Cost $ (Shadow Price*Limit) | Transmission Project | Clearance |
| --- | --- | --- | --- | --- | --- | --- |
| BASE CASE | West to North Stability Limit | 3865 | 0 - 612 | 11,923,923 | CREZ |  |
| W.A. Parish - Obrien 345kV | Garrott - Midtown 138kV | 1313 | 0 - 3500 | 3,200,445 | Upgrade 138 kV underground Ckt. 90 Garrott to Midtown to Polk [11TPIT0072] |  |
| Anctp - Ncwam 138kV | Odessa North 138/69KV autotransformer | 1362 | 0 - 2800 | 3,108,366 | 5YTP [2009-R4] | Outage on Moss Switch - Permian Basin SES 138kV |
| Cabaniss To Airline 138kV | Naval Base - North Padre 69kV | 173 | 0 - 2800 | 856,227 | Rebuild Airline to Naval Base 69 kV line [06TPIT0015] | Outage on Holly - Rodd Field 138 kV |
| BASE CASE, Cabaniss - Airline 138kV | Nelson Sharpe 138KV phase shifting transformer | 383 | 0 - 3500 | 757,303 | Barney Davis to Nelson Sharpe 138 kV line rebuild [12TPIT0069] | Outage on Holly - Rodd Field 138 kV |
| Austrop - Lost Pines 345kV | SALEM LCRA 345/138kV autotransformer | 95 | 0 - 4500 | 645,328 | Fayetteville Power Project [15TPIT0009] |  |
| Cagnon - Marbach 138kV | Five Points - Westside CPS 138kV | 320 | 0 - 940 | 439,002 | Westside substation equipment upgrade [12TPIT0054] | Outage on Cagnon 345/138kV autotransformer |
| Garfield-Hicross and Onion-Pilot 138kV | Garfield - Onion Creek 138kV | 193 | 0 - 3500 | 403,271 |  |  |
| Watermill - Tricorner -Tylergnd 345kV | Trinidad 345kV step-up transformer | 2 | 4500 - 4500 | 256,725 |  |  |
| Morgan Creek SES - China Grove 138kV | Morgan Creek SES - China Grove 138kV | 4 | 3500 - 3500 | 215,221 |  |  |

# Wind Generation as a Percent of Load

One-hour average Settlement quality data shown.

# Planning Model Activities

- ERCOT and SSWG continued work to create a 2012 case using PSSE version 32 format starting Dec. 3, 2010.  All standard PMCR’s will be applied to this case and the case will be completed using PMCR’s to model transmission projects expected to by complete by July 1, 2012.  This case will be compared to the current DSB 2012SUM1 case completed in Nov. 2010.

- ERCOT and the TSP are working to complete Cost Benefit Analysis for SCR760 based on the ROS approved comments from the January meeting.

# Other Notable Activities

- Work on the 2010 Five-Year Transmission Plan (5YTP) is wrapping up.  All studies have been completed to identify the projects needed to reliably serve load and reduce congestion for years 2011 through 2015.  The study is currently in the report writing phase.

- Transient Stability Study for 2011 Winter off-peak conditions: As part of the annual reliability assessment of the network, a transient stability study study is been performed on an ERCOT 2011 Winter off-peak case.