## Slide 1
Business Integration Update to PRS
Troy Anderson
ERCOT
Enterprise Project Portfolio Management
March 24, 2011

## Slide 2: Business Integration Update – Agenda
  2011 Project Portfolio Status 3-4
  2011 Project Financial Summary 5
  Nodal Parking Deck Prioritization Status 6-7
  2012 Project Prioritization Schedule 8
  Market Input into Cost Benefit Analysis 9

## Slide 3: 2011 Project Portfolio Status

## Slide 4: 2011 Project Portfolio Status

## Slide 5: 2011 Project Spending Update – 3/20/2011
Project Area | Initial Budget | Current Budget | Forecast | YTD Actual
Data Center Hardware | $ 33,715,000 | $ 33,715,000 | $ 29,374,300 | $ 19,855,100
Other Projects | $ 8,185,000 | $ 8,185,000 | $ 7,566,500 | $ 579,400
Grand Totals | $ 41,900,000 | $ 41,900,000 | $ 36,940,800 | $ 20,464,500

## Slide 6: Impact Analysis Results – Phase 1 Items
2011 Implementation Recommended
  NPRR208 – Registration & Settlement of Distributed Generation (DG) Less Than 1 MW
    Est. Cost = $5k-$10k Target Delivery = September 2011 Priority = Critical
    150 day notice required
  NPRR251 – Sync PRR845, Definition for IDR Meters and Optional Removal of IDR Meters at a Premise Where an Advanced Meter Can be Provisioned
    Est. Cost = $30k-$50k Target Delivery = June 2011 Priority = High
  NPRR282 – Dynamic Ramp Rates Use in SCED
    Est. Cost = $30k-$35k Target Delivery = June 2011 Priority = Critical
  NPRR285 – Generation Resource Base Point Deviation Charge Corrections
    Est. Cost = $30k-$40k Target Delivery = May 2011 Priority = Critical
  NPRR293 – Requirement to Post PTP Obligation Quantities Awarded in DAM
    Est. Cost = $12k-$15k Target Delivery = May 2011 Priority = High
All of these NPRRs will be funded from the Parking Deck portion of the post Go-Live funds authorized by the Board as part of the 2011 ERCOT budget

## Slide 7: Parking Deck NPRR/SCR Prioritization Schedule
Phase 1 of Parking Deck IAs and CBAs (March 2011 Board meeting)
  7 items considered at Tuesday’s Board meeting
Phase 2 of Parking Deck IAs and CBAs (target Board meeting = May 2011)
  NPRR210: Wind Forecasting Change to P50, Sync with PRR841
  NPRR240: Proxy Energy Offer Curve *
  NPRR241: Aggregate Incremental Liability (AIL) Calculation and Credit Reports Publish Corrections
  NPRR244: Clarification of Other Binding Documents
  NPRR256: Sync with PRR787, Add Non-Compliance Language to QSE Performance Standards
  SCR755: ERCOT.com Website Enhancements
Phase 3 of Parking Deck IAs and CBAs (target Board meeting = July 2011)
  NPRR131: Ancillary Service Trades with ERCOT
  NPRR181: FIP Definition Revision
  NPRR207: Unit Deselection
  NPRR222: Half-Hour Start Unit RUC Clawback
  NPRR257: Synchronization with Nodal Operating Guide Section 9, Monitoring Programs
  NPRR258: Sync with PRR824 and PRR833 and Additional Clarifications
  NPRR260: Providing Access to MIS Secure Area to MIS Registered Users
  NPRR272: Definition and Participation of Quick Start Generation Resources
  NOGRR034: Rescind Telemetry Performance Calculation Exclusions
Phase 4 of Parking Deck IAs and CBAs (target Board meeting = September 2011)
  NPRR146: ICCP Telemetry Information Submittals
  NPRR153: Generation Resource Fixed Quantity Block Offer
* ERCOT needs to move NPRR240 from Phase 2 to Phase 3

## Slide 8: 2012 Project Prioritization Schedule
March - April 2011
  ERCOT develops draft 2012 project list
    Requests and incorporates input from the market
May 2011
  Initial review at market subcommittee meetings
    COPS (May 10) WMS (May 11)
    RMS (May 18) ROS (May 12)
    PRS (May 19)
June 2011
  Approval/endorsement by market subcommittees
    COPS (June 14) WMS (June 15)
    RMS (June 22) ROS (June 16)
    PRS (June 23)
July 2011
  Approval/endorsement by TAC (July 7)
  Available for F&A and Board review (July 18)

## Slide 9: Business Integration Update – Market Input into CBAs
Recent revision requests have highlighted the need for an improved mechanism for gathering input from the market for inclusion in the CBA form
PRS input requested so we can maximize the value of this component of the approval process
Considerations:
  Input from revision request sponsor is critical
  Sponsoring market subcommittee would have interest in the message sent by the CBA
  Limited time when an item is voted “urgent”
  ERCOT has been arranging ad hoc sessions to develop market CBA content for higher cost revision requests