## NPRR343 Summary
Cost Benefit Analysis Summary
Request Information
PRR / SCR / PR / "New": | NPRR343 |  |  | Estimator's Name: |  | S. Reedy, K. Kasparian
Project Title: | CRR Bid and PTP Obligation Bid Criteria Change |  |  | Sponsor's Name: |  | S. Reedy
|  |  |  | Estimate Date: |  | 2011-04-04
Project Description: | Enhance the MMS System to limit the ability to purchase CRRs and DAM PTP Obligation bids within the same station.
Benefits and Impacts
1 - Reduces unecessary bids from the CRR Auction resulting in less load on the System and more available bid capacity for the market
2 - Reduces the risk of underfunding
Feasibility
Alternatives
Assumptions
1 - The Impact Analysis Cost Range is $400,000 - $450,000 so $425,000 was used for the cost benefit analysis
2 - Limiting the ability to purchase CRRs within the same station leaves more auction capacity for higher value CRR paths. More auction capacity for higher value CRR paths leads to higher CRR Auction revenues.
3 - Market Benefits have been quantified as follows: If 2000 station to station CRRs are available with an average value of $25 (price separation that is not due to congestion) this would lead to $50,000 per month taken out of the Market. $50k * 12 months per year = $600k savings per year.
Cost and Benefit Summary
Project Costs | ERCOT Implementation Cost | 430000 |  |  |  |  | All values in this section are rounded to 2 significant digits
| Market Implementation Cost | 0
| Total Implementation Cost |  | 430000
| ERCOT Ongoing Cost | 0
| Market Ongoing Cost | 0
| Total Ongoing Cost |  | 0
[5 empty] | 430000 |  | Total Cost
Project Benefit | ERCOT Benefit | 0
| Market Benefit | 2200000
[5 empty] | 2200000 |  | Total Benefit
|  | Net (Cost) - Benefit |  |  | 1770000
Calculation Parameters
Market Cost | Impacted Number of QSEs |  |  | 0
| Impacted Number of CRs |  |  | #REF!
| Impacted Number of TDSPs |  |  | #REF!
| Impacted Number of Resources |  |  | #REF!
Present Value Interest Rate: |  |  |  | 6%
Changing this parameter is not recommended
It is used to calculate present value of future cash flows

## NPRR343 Detail
Cost Benefit Analysis Data Entry Worksheet
PRR / SCR / Etc.: | NPRR343 | Project Title: | CRR Bid and PTP Obligation Bid Criteria Change
Sponsor: | S. Reedy | Estimate Date: | 2011-04-04 | Estimator: | S. Reedy, K. Kasparian
Project Description: (please be clear and concise) | Enhance the MMS System to limit the ability to purchase CRRs and DAM PTP Obligation bids within the same station.
Benefits and Impacts
Click here for ideas on benefit and impact areas… ---------------------------------------------------------------------------------->>>
1 | Reduces unecessary bids from the CRR Auction resulting in less load on the System and more available bid capacity for the market
2 | Reduces the risk of underfunding
3
4
5
6
7
8
Feasibility
Click here for ideas on feasibility… ---------------------------------------------------------------------------------->>>
Dependencies
Other 1
Other 3
Alternatives
Click here for ideas on alternatives… ---------------------------------------------------------------------------------->>>
1
2
Assumptions
Click here for ideas on assumptions… ---------------------------------------------------------------------------------->>>
1 | The Impact Analysis Cost Range is $400,000 - $450,000 so $425,000 was used for the cost benefit analysis
2 | Limiting the ability to purchase CRRs within the same station leaves more auction capacity for higher value CRR paths. More auction capacity for higher value CRR paths leads to higher CRR Auction revenues.
3 | Market Benefits have been quantified as follows: If 2000 station to station CRRs are available with an average value of $25 (price separation that is not due to congestion) this would lead to $50,000 per month taken out of the Market. $50k * 12 months per year = $600k savings per year.
4
5
6
7
ERCOT Cost and Benefit Detail
ERCOT Internal Cost | Type | Year 0 | Year 1 | Year 2 | Year 3
Implementation Cost | Project | 425000 | 0 | 0 | 0 | NPV = | 0
Ongoing Cost (O&M) | Staffing |  |  |  |  | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Present Value of Internal ERCOT Cost: | 430000
ERCOT Internal Benefit | Type | Year 0 | Year 1 | Year 2 | Year 3
Direct Cost Savings | Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
Productivity Increases | Select type… | 0 | 0 | 0 | 0 | NPV = | 0
Cost Avoidance | Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Present Value of Internal ERCOT Benefit: | 0
Market Cost and Benefit Detail
Market Cost | Type | Year 0 | Year 1 | Year 2 | Year 3
Implementation Cost | Select type… | 0 | 0 | 0 | 0 | NPV = | 0
Ongoing Cost | Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Present Value of Market Cost: | 0
Market Benefit | Type | Year 0 | Year 1 | Year 2 | Year 3
Benefits for Market | Select type… | 600000 | 600000 | 600000 | 600000 | NPV = | 1603807.1697
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Select type… | 0 | 0 | 0 | 0 | NPV = | 0
| Total Present Value of Market Benefit: | 2200000
Total Cost | 430000 |  | Net (Cost) - Benefit ($) |  | 1770000
Total Benefit | 2200000 |  | Cost Benefit Ratio |  | 5.1163
Summary values are rounded to 2 significant digits.
Additional Comments
Enter any additional comments here…
1
2
3
4
Benefit and Impact Prompts
GOVERNANCE: Is the project required to support a PUCT rulemaking or government requirement?
GOVERNANCE: Is the project required by a market or ERCOT committee?
GOVERNANCE: Will the project provide better information for management decision making?
RELIABILITY: Does the project improve the reliability of the grid?
RELIABILITY: Does the project improve the reliability of ERCOT's computing infrastructure?
RELIABILITY: Is there a significant operational need for the project?
SAFETY: Will the project enhance safety within ERCOT?
SECURITY: Is there a physical or cyber-security issue that is addressed by this effort?
SECURITY: Does the project address an audit finding?
SECURITY: Will the project decrease the chance of fraud or help protect sensitive data?
RISK REDUCTION: Does this reduce risk to ERCOT in some significant manner?
RESOURCES: Does the project reduce the number of resources needed to support current operations?
RESOURCES: Does the project deliver infrastructure components that are more efficient or more easily upgraded?
DATA MANAGEMENT: Does this improve the accuracy, timeliness and transparency of transactions or settlements?
DATA MANAGEMENT: Does this enhance or optimize our data storage capability?
DATA MANAGEMENT: Does this improve reporting capabilities (financial, operational, etc.)?
EFFICIENCY: Does the project improve the efficiency or effectiveness of ERCOT?
EFFICIENCY: Does the project automate, improve or streamline a necessary function?
INVESTMENT: Is the project an investment in new capability or does it support the current architecture?
OTHER: Are there other areas that will indirectly benefit from this project?
Feasibility Prompts
REQUIREMENTS: Are high level requirements clearly defined?
REQUIREMENTS: How complex are the potential solutions?
REQUIREMENTS: Does a required completion date make delivery more difficult?
DELIVERY: Can the project be broken down into smaller sections or delivered in stages to reduce risk?
DELIVERY: Will training be required as the project is rolled out?
DEPENDENCIES: Are there major dependencies on other projects that make this difficult to implement?
Alternative Prompts
DELIVERY: Is a manual workaround an option (short-term or long-term)?
DELIVERY: Does a partial implementation provide enough value to be worth considering?
DELIVERY: Should a phased implementation be considered to reduce risk or accelerate key benefits?
DELIVERY: If this is an automation project is it reasonable to consider using the current process?
Assumption Prompts
DEPENDENCIES: Is this request is dependent on another ERCOT project (either active or planned)?
DELIVERABLES: Are specific key deliverables required from this project?
DELIVERABLES: What is the useful life of the deliverables of this project?
RESOURCES: Are computing resources assumed that are not to be delivered by this project?
RESOURCES: Are specific key resources assumed to be available for this project?
RESOURCES: Are there facilities requirements necessary for this project?
REQUIREMENTS: Is completion required by a specific date?