## Slide 1
Business Integration Update
April 2011

## Slide 2: Business Integration Update – Agenda
  2011 Project Portfolio Update p. 3-7
    Project Portfolio Gantt Chart
    Recent Developments
  Remaining Phases of Parking Deck Impact Assessment p. 8
  2012 Project Prioritization Schedule p. 9-10
  Appendix
    Phase 1 Results p. 12
    Phase 2 / Phase 3 Items p. 13
    Phase 4 / TBD Items p. 14

## Slide 3: Project Portfolio – as of 4/8/2011

## Slide 4: Project Portfolio – as of 4/8/2011

## Slide 5: Project Portfolio – as of 4/8/2011

## Slide 6: Project Portfolio – Recent Developments
TAC and PRS Approval of Several Additions to the PPL
  NPRR310, NPRR316, NPRR320, NPRR329, NPRR339, NPRR341, NPRR343
Post-Nodal Items and PPL Items are now Merged on the PPL
  See PPL posted on ERCOT.com
  Using the PPL as a baseline, ERCOT merged in the Post-Nodal Items based on our general understanding of priorities
    To assist you in seeing where the additions were made, the Post-Nodal item ranks are temporarily highlighted in yellow
    Market input on the results of this merging effort is appreciated
    This update was in response to feedback from the Board in March
Changes to Previously Reporting Release Plans
  Going forward, ERCOT will stop including the estimated release target in the Impact Analysis
  This information will be captured in the PPL and on the project portfolio Gantt chart since it is subject to change
    Example: ERCOT is re-evaluating the delivery timeline for NPRR251
    Subsequent priorities are likely to shift delivery of this NPRR from June to September

## Slide 7: Project Portfolio – Recent Developments
Cost Benefit Analysis
  Recent revision requests have highlighted the need for an improved mechanism for gathering input from the market for inclusion in the CBA
  TAC and PRS are increasing their focus on CBA content
  How can market subcommittees contribute to this effort?
    Encourage revision request sponsors to provide input on the costs and benefits of new submissions
    Consider the message that the results of the CBA send on the merits of the change
  ERCOT will continue to assist in the process by arranging ad hoc sessions for complex CBAs

## Slide 8: Remaining Phases of Parking Deck Impact Assessments
In response to Board feedback in March, ERCOT is combining the 2nd and 3rd phases of the Parking Deck Impact Assessment
  See Appendix for details
  Expected date for market endorsement: June
  Phases 2 and 3 are now on the same schedule as the 2012 project prioritization review and approval

## Slide 9: 2012 Project Prioritization – Schedule
April 2011
  ERCOT prepares draft 2012 project list and reviews schedule with market
    Request input from the market on new additions
May 2011
  Initial review at market subcommittee meetings
    COPS (May 10)
    WMS (May 11)
    ROS (May 12)
    RMS (May 18)
June 2011
  Approval/endorsement by market subcommittees
    COPS (June 14)
    WMS (June 15)
    ROS (June 16)
    RMS (June 22)
    PRS (June 23)
July 2011
  Approval/endorsement by TAC (July 7)
  Available for F&A and Board review (July 18)

## Slide 10: 2012 Project Prioritization – Preview
Highlights of Likely Items to be Funded on the 2012 PPL
  Execution phase of Nodal 2.0
    Expected to include a number of currently approved and in-flight NPRRs
    Current target go-live date = March/April 2012 (dependent on size and complexity of release)
  Continuation of current PPL projects
    Texas SET 4.0
    SCR760 - Recommended Changes Needed for Information Model Mgr and Topology Processor for Planning Models
    MarkeTrak Upgrade and Enhancements
    Information Lifecycle Management (ILM)
    Settlement System Upgrade
  Web-enabled Registration
  REC Program Upgrade and Enhancements
  Recurring items
    Minor Cap
    IT infrastructure upgrades
      In most cases, these are upgrades that were put on hold during the course of Nodal
    Security projects

## Slide 11
Appendix

## Slide 12: Impact Analysis Results – Phase 1 Items – Board Approved
2011 Implementation Recommended
  NPRR208 – Registration & Settlement of Distributed Generation (DG) Less Than 1 MW
    Est. Cost = $5k-$10k Target Delivery = September 2011 (150 day notice required)
  NPRR251 – Sync PRR845, Definition for IDR Meters and Optional Removal of IDR Meters at a Premise Where an Advanced Meter Can be Provisioned
    Est. Cost = $30k-$50k Target Delivery = June 2011
  NPRR282 – Dynamic Ramp Rates Use in SCED
    Est. Cost = $30k-$35k Target Delivery = June 2011
  NPRR293 – Requirement to Post PTP Obligation Quantities Awarded in DAM
    Est. Cost = $12k-$15k Target Delivery = May 2011
2011 Implementation Not Recommended
  NPRR219 – Resolution of Alignment Items A33,A92,A106,A150 - TSPs Must Submit Outages for Resource Owned Equipment & Clarification of Changes in Status of Transmission Element Postings
    Cost to implement greatly exceeds the offsetting labor savings achieved with this project ($565k-$750k)
    Need to consider alternate approaches or combining with one or more related efforts
  NOGRR050 – Resolution of Reporting Issues Related to NPRR219
    Not recommended at this time due to its connection to NPRR219

## Slide 13: Parking Deck Prioritization – Remaining Impact Assessments
Phase 2 / Phase 3 of Parking Deck IAs and CBAs
  NPRR210: Wind Forecasting Change to P50, Sync with PRR841
  NPRR240: Proxy Energy Offer Curve
  NPRR241: Aggregate Incremental Liability (AIL) Calculation and Credit Reports Publish Corrections
  NPRR244: Clarification of Other Binding Documents
  NPRR256: Sync with PRR787, Add Non-Compliance Language to QSE Performance Standards
  SCR755: ERCOT.com Website Enhancements
  NPRR181: FIP Definition Revision
  NPRR207: Unit Deselection
  NPRR222: Half-Hour Start Unit RUC Clawback
  NPRR257: Synchronization with Nodal Operating Guide Section 9, Monitoring Programs
  NPRR258: Sync with PRR824 and PRR833 and Additional Clarifications
  NPRR260: Providing Access to MIS Secure Area to MIS Registered Users
  NPRR272: Definition and Participation of Quick Start Generation Resources
  NOGRR034: Rescind Telemetry Performance Calculation Exclusions
Schedule
  April/May - IA/CBA development
  May - Market subcommittee review
  June - Market subcommittee endorsement
  July - TAC and Board consideration

## Slide 14: Parking Deck Prioritization
Phase 4 – Final Phase of Parking Deck IAs and CBAs
  NPRR146: ICCP Telemetry Information Submittals
  NPRR153: Generation Resource Fixed Quantity Block Offer
Proposed Schedule
  June/July - IA/CBA development
  July - Market subcommittee review
  August - Market subcommittee endorsement
  September - TAC and Board consideration
TBD
  NPRR131: Ancillary Service Trades with ERCOT
    Pending resolution of NPRR316
  NPRR164: Resubmitting Ancillary Service Offers in SASM
    Pending resolution of NPRR307
This would conclude the Impact Analysis and CBA development of the Board-approved Parking Deck items