|  |  |  |  | System Planning Division |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Monthly Status Report to Reliability and Operations Subcommittee for March 2011 |  |  |
|  |  | Report Highlights |  |  |  |  |  |  |
| Item |  |  |  |  |  |  |  |  |
| 1. | - ERCOT is currently tracking 203 active generation interconnection requests totaling over 64,000 MW. This includes over 37,000 MW of wind generation. |  |  |  |  |  |  |  |
| 2. | - ERCOT is currently reviewing proposed transmission improvements with a total cost of $555.6 Million - Transmission Projects endorsed in 2011 total $23.6 Million - All projects (in engineering, routing, licensing and construction) total approximately $9.5 Billion - Transmission Projects energized in 2011 total about $174.0 million |  |  |  |  |  |  |  |

Table of Contents

1.	Generation Interconnection	1

1.1	New Generation Registering for Commercial Operations	1

1.2	Publicly Disclosed Generation Interconnection Projects	4

1.3	Generation Projects Undergoing Full Interconnection Studies (not otherwise public)	6

1.4	Wind Generation	8

2.	Regional Planning Group Project Reviews	10

3.	Congestion Costs	11

4.	Wind Generation as a Percent of Load	13

5.	Planning Model Activities	14

6.	Other Notable Activities	15

# 1.	Generation Interconnection

Additional information regarding detailed generation interconnection and impact studies is contained in the “Generation Project Interconnection Information” folder in the “Operations and System Planning” area on the ERCOT website:  http://planning.ercot.com/login/login.

## New Signed Generation Interconnection Agreements

## Los Vientos (11INR0033a/11INR0033b) 400 MW Wind in Cameron County

## Magic Valley (formerly Willacy Wind, 10INR0060) 200 MW Wind in Willacy County

## New Generation Registering for Commercial Operations

The total installed wind capacity is reported as 9,400 MW by the resource owners through the registration process. Installed capacity in North, South and West is 228 MW, 1216 MW, and 7956 MW respectively. 856 MW is able to switch between the West and South zones.

Summary of Active Generation Interconnection Requests

| GENERATION INTERCONNECTION REQUESTS CURRENTLY BEING PROCESSED |  |  |  |  |
| --- | --- | --- | --- | --- |
| Currently tracking 203 active generation interconnection or change requests |  |  |  |  |
| As of March 31, 2011 | North | South | West | Total |
| Security Screening Study | 2 | 7 | 8 | 17 |
| SSS Completed | 1 | 3 | 17 | 21 |
| Full Interconnect Study | 18 | 10 | 79 | 107 |
| FIS Completed | 5 | 9 | 6 | 20 |
| Interconnect Agreement Completed | 7 | 9 | 3 | 16 |
| Capacity under Interconnection Agreements | 5,092 | 4,344 | 520 | 9,956 |
| Capacity for Grid, MW | 18,690 | 12,779 | 33,109 | 64,578 |
| Wind Capacity, MW | 3,457 | 3,999 | 30,061 | 37,517 |

| Fuel Type | Confidential Projects (MW) | Projects Under Full Study (MW) | Projects w/ Interconnect Agreement/Public Letter (MW) | Grand Total (MW) |
| --- | --- | --- | --- | --- |
| Gas-CombinedCycle |  |  | 5,297 | 12,235 |
| Gas-All Other |  |  |  | 403 |
| Total Gas | 11 | 7,330 | 5,297 | 12,638 |
| Nuclear |  |  | 5,900 | 5,900 |
| Coal |  | 1,740 | 3,210 | 4,950 |
| Wind | 3,410 | 28,188 | 5,919 | 37,517 |
| Solar | 566 | 877 |  | 1,443 |
| Biomass |  | 50 | 100 | 150 |
| Other |  | 740 | 1,240 | 1,980 |
| Grand Total | 3,987 | 38,925 | 21,666 | 64,578 |

## Publicly Disclosed Generation Interconnection Projects

The table below summarizes the publicly disclosed generation projects for the ERCOT region.

(Status: IA=Interconnect Agreement, PL=Public Letter, XX= cancelled)

| Generation Interconnections as of March 31, 2011 |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| INR | SiteName | Status | County | Region | COD | Fuel Type |  | MW For Grid | Change from Last Report |
| 09INR0029 | CFB Power Plant Units 11&12 | IA | Calhoun | South | Apr-11 |  | Coal | 260 |  |
| 08INR0065 | Buffalo Gap 4 and 5 | PL | Nolan | West | Apr-11 |  | Wind | 465 |  |
| 10INR0010 | Jack County 2 | IA | Jack | North | Sep-11 |  | Gas-CC | 565 | Date |
| 09INR0034 | Gatesville Wind Farm | PL | Coryell | North | Dec-11 |  | Wind | 200 |  |
| 12INR0003 | Throckmorton Wind Farm | PL | Throckmorton | West | Dec-11 |  | Wind | 400 |  |
| 08INR0038 | M Bar Wind | PL | Andrews | West | Dec-11 |  | Wind | 194 |  |
| 08INR0025 | Pistol Hill Energy Center | PL | Ector | West | Dec-11 |  | Wind | 300 |  |
| 06INR0012b | Sherbino Mesa Wind Farm 2 | IA | Pecos | West | Jan-12 |  | Wind | 150 |  |
| 09INR0001 | Sandy Creek 1 | IA | McLennan | North | Feb-12 |  | Coal | 925 |  |
| 08INR0062 | Archer-Young | IA | Young | West | Mar-12 |  | Wind | 250 |  |
| 11INR0084 | 2W Whatley Phase 1 | PL | Ector | West | Mar-12 |  | Wind | 45 |  |
| 09INR0007 | Nacogdoches Project | IA | Nacogdoches | North | Apr-12 |  | Biomass | 100 |  |
| 07INR0004 | Pampa Energy Center | PL | Gray | West | May-12 |  | Coal | 165 |  |
| 09INR0037 | Scurry County Wind III | PL | Scurry | West | Jun-12 |  | Wind | 350 |  |
| 09INR0024 | B&B Panhandle Wind | PL | Carson | West | Jun-12 |  | Wind | 1001 |  |
| 10INR0060 | Willacy Wind Project | IA | Willacy | South | Jun-12 |  | Wind | 202 | New |
| 05INR0015b | Gulf Wind 2 | PL | Kenedy | South | Jul-12 |  | Wind | 400 |  |
| 12INR0004 | Fort Concho Wind Farm | PL | Tom Green | West | Jul-12 |  | Wind | 400 |  |
| 12INR0043 | 2W Whatley Phase 2 | PL | Ector | West | Aug-12 |  | Wind | 290 |  |
| 08INR0011 | Senate Wind Project | IA | Jack | North | Sep-12 |  | Wind | 150 |  |
| 08INR0018 | Gunsight Mountain | IA | Howard | West | Dec-12 |  | Wind | 120 |  |
| 11INR0033a | Los Vientos Phase 1 | IA | Cameron | South | Dec-12 |  | Wind | 200 | New |
| 11INR0033b | Los Vientos Phase 2 | IA | Cameron | South | Dec-12 |  | Wind | 200 | New |
| 06INR0022c | Penascal Wind Farm 3 | IA | Kenedy | South | Dec-12 |  | Wind | 202 |  |
| 05INR0015c | Gulf Wind 3 | PL | Kenedy | South | Dec-13 |  | Wind | 400 |  |
| 10INR0020a | Panda Temple Power | IA | Bell | North | Feb-14 |  | Gas-CC | 780 |  |
| 06INR0006 | Cobisa-Greenville | IA | Hunt | North | May-14 |  | Gas-CC | 1792 |  |
| 10INR0022 | Pondera King Power Project | IA | Harris | South | Jun-14 |  | Gas-CC | 1380 |  |
| 14INR0005 | White Stallion Energy Center | PL | Matagorda | South | Jul-14 |  | Coal | 1200 |  |
| 10INR0020b | Panda Temple Power | IA | Bell | North | May-15 |  | Gas-CC | 780 |  |
| 12INR0016a | Las Brisas Energy Center | IA | Nueces | South | Jul-15 |  | Other | 620 |  |
| 14INR0002 | Coleto Creek Unit 2 | IA | Goliad | South | Jan-16 |  | Coal | 660 |  |
| 15INR0008 | STP 3 and 4 | PL | Matagorda | South | Jun-16 |  | Nuclear | 2700 |  |
| 12INR0016b | Las Brisas Energy Center | IA | Nueces | South | Jul-16 |  | Other | 620 |  |
| 15INR0002 | Comanche Peak 3 and 4 | PL | Somervel | North | Dec-18 |  | Nuclear | 3200 |  |
|  |  |  |  |  |  |  | Total | 21,666 |  |

County Location of Installed Generation and Interconnection Requests (all fuels)

## Generation Projects Undergoing Full Interconnection Studies (not otherwise public)

| INR | County | Capacity | COD | Fuel |  | INR | County | Capacity | COD | Fuel |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 09INR0061 | Kent | 258 | TBD | Wind |  | 09INR0054 | Stonewall | 149 | TBD | Wind |
| 10INR0048 | Hardeman | 1,000 | TBD | Wind |  | 10INR0054 | Palo Pinto | 36 | TBD | Wind |
| 10INR0079 | Nolan | 60 | TBD | Wind |  | 10INR0016 | Childress | 150 | TBD | Wind |
| 10INR0029 | Hood | 810 | TBD | Gas |  | 10INR0052a | Knox | 21 | TBD | Wind |
| 10INR0013 | Upton | 400 | TBD | Wind |  | 10INR0041 | Floyd | 135 | TBD | Wind |
| 09INR0074 | Motley | 70 | TBD | Wind |  | 11INR0029 | Throckmorton | 200 | TBD | Wind |
| 10INR0042 | Mason | 170 | TBD | Wind |  | 10INR0032 | Navarro | 775 | TBD | Gas |
| 10INR0051 | Brazoria | 200 | TBD | Wind |  | 10INR0080 | Presidio | 144 | TBD | Solar |
| 10INR0077 | Callahan | 101 | TBD | Wind |  | 10INR0033 | Armstrong | 399 | TBD | Wind |
| 10INR0019 | Deaf Smith | 609 | TBD | Wind |  | 10INR0008 | Pecos | 500 | TBD | Wind |
| 07INR0013 | Coke | 200 | TBD | Wind |  | 11INR0076 | Archer | 94 | TBD | Wind |
| 11INR0088 | Brazos | 45 | TBD | Gas |  | 11INR0085 | Nolan | 106 | TBD | Wind |
| 11INR0050 | Crosby | 149 | TBD | Wind |  | 11INR0086 | Travis | 60 | TBD | Solar |
| 11INR0075 | Fort Bend | 15 | TBD | Coal |  | 11INR0037 | Smith | 50 | May-11 | Biomass |
| 11INR0062 | Nueces | 149 | May-11 | Wind |  | 11INR0061 | Presidio | 90 | May-11 | Solar |
| 11INR0060 | Tom Green | 90 | May-11 | Solar |  | 11INR0058 | Pecos | 135 | May-11 | Solar |
| 09INR0050 | Fannin | 1,200 | Jun-11 | Gas |  | 11INR0091 | Webb | 92 | Jun-11 | Wind |
| 11INR0065 | Nueces | 240 | Jun-11 | Wind |  | 11INR0057 | Cameron | 165 | Jun-11 | Wind |
| 11INR0054 | San Patricio | 161 | Jun-11 | Wind |  | 10INR0089 | Harris | 40 | Jun-11 | Other |
| 11INR0019 | Upton | 200 | Jun-11 | Wind |  | 10INR0023 | Haskell | 386 | Jun-11 | Wind |
| 08INR0020 | Eastland | 200 | Jun-11 | Wind |  | 11INR0006 | Lamar | 579 | Jul-11 | Gas |
| 11INR0040 | freestone | 640 | Aug-11 | Gas |  | 11INR0079a | Clay | 200 | Sep-11 | Wind |
| 11INR0039 | Starr | 201 | Sep-11 | Wind |  | 11INR0047 | Deaf Smith | 600 | Sep-11 | Wind |
| 10INR0081b | Clay | 19 | Oct-11 | Wind |  | 10INR0062a | Pecos | 80 | Oct-11 | Wind |
| 10INR0021 | Grayson | 646 | Nov-11 | Gas |  | 11INR0094 | Kent | 100 | Nov-11 | Solar |
| 11INR0090 | Howard | 60 | Nov-11 | Solar |  | 08INR0049 | Clay | 50 | Dec-11 | Wind |
| 11INR0071 | Harris | 7 | Dec-11 | Gas |  | 11INR0067 | Cameron | 78 | Dec-11 | Wind |
| 11INR0070 | Reeves | 50 | Dec-11 | Solar |  | 11INR0043 | Coke | 300 | Dec-11 | Wind |
| 11INR0025 | Crockett | 400 | Dec-11 | Wind |  | 11INR0005 | Upton | 500 | Dec-11 | Wind |
| 10INR0082 | Travis | 30 | Dec-11 | Solar |  | 09INR0048 | Jack | 100 | Dec-11 | Wind |
| 12INR0033 | Motley | 150 | Jan-12 | Wind |  | 12INR0021 | Edwards | 165 | Jan-12 | Wind |
| 10INR0085 | Ector | 40 | Jan-12 | Solar |  | 10INR0018 | Madison | 550 | Mar-12 | Gas |
| 12INR0042 | Deaf Smith | 400 | Mar-12 | Wind |  | 12INR0045 | Kleberg | 135 | Mar-12 | Wind |
| 12INR0075 | Wilbarger | 499 | Apr-12 | Wind |  | 12INR0007 | Lamar | 296 | May-12 | Gas |
| 11INR0049 | Wharton | 275 | May-12 | Gas |  | 10INR0081a | Clay | 30 | May-12 | Wind |
| 09INR0031 | Ector | 275 | May-12 | Gas |  | 12INR0006 | Limestone | 875 | Jun-12 | Coal |
| 12INR0053 | Crockett | 615 | Jun-12 | Wind |  | 08INR0031 | Childress | 100 | Jun-12 | Wind |
| 12INR0026 | Randall | 400 | Oct-12 | Wind |  | 08INR0041 | Coke | 200 | Oct-12 | Wind |
| 12INR0035 | Nueces | 249 | Nov-12 | Wind |  | 08INR0054 | Comanche | 401 | Dec-12 | Wind |
| 12INR0072 | Kinney | 100 | Dec-12 | Wind |  | 11INR0081 | Live Oak | 72 | Dec-12 | Wind |
| 12INR0057 | Ector | 40 | Dec-12 | Solar |  | 12INR0005 | Floyd | 1,100 | Dec-12 | Wind |
| 09INR0025 | Concho | 180 | Dec-12 | Wind |  | 08INR0042 | Coke | 200 | Dec-12 | Wind |
| 12INR0029 | Swisher | 500 | Dec-12 | Wind |  | 12INR0027 | Gray | 200 | Jan-13 | Wind |
| 10INR0024 | Briscoe | 2,940 | Jan-13 | Wind |  | 13INR0010a | Parmer | 200 | Jan-13 | Wind |
| 12INR0034 | Borden | 342 | Mar-13 | Wind |  | 11INR0083B | Crockett | 100 | Mar-13 | Wind |
| 11INR0082B | Val Verde | 150 | Mar-13 | Wind |  | 10INR0056 | Borden | 249 | Mar-13 | Wind |
| 09INR0058 | Howard | 250 | Mar-13 | Wind |  | 12INR0018 | Gray | 500 | Apr-13 | Wind |
| 13INR0020a | Glasscock | 200 | May-13 | Wind |  | 10INR0062b | Pecos | 220 | May-13 | Wind |
| 09INR0051 | Borden | 249 | Jun-13 | Wind |  | 09INR0041 | Mitchell | 300 | Jun-13 | Wind |
| 13INR0023 | Ector | 240 | Jul-13 | Gas |  | 13INR0016 | Deaf Smith | 251 | Aug-13 | Wind |
| 13INR0025 | Randall | 150 | Sep-13 | Wind |  | 11INR0083A | Crockett | 50 | Sep-13 | Wind |
| 11INR0082A | Val Verde | 50 | Sep-13 | Wind |  | 13INR0005 | Carson | 600 | Oct-13 | Wind |
| 13INR0004 | Deaf Smith | 500 | Oct-13 | Wind |  | 13INR0028 | Hale | 392 | Nov-13 | Gas |
| 11INR0013 | Mills | 150 | Dec-13 | Wind |  | 13INR0017 | Childress | 200 | Dec-13 | Wind |
| 13INR0007 | Pecos | 200 | Dec-13 | Wind |  | 12INR0002a | Briscoe | 200 | Dec-13 | Wind |
| 10INR0009 | Castro | 300 | Dec-13 | Wind |  | 09INR0077 | Reagan | 500 | Dec-13 | Wind |
| 09INR0073 | Scurry | 200 | Dec-13 | Wind |  | 13INR0006 | Gray | 750 | Jan-14 | Wind |
| 08INR0019c | Gray | 250 | Jan-14 | Wind |  | 08INR0019b | Gray | 250 | Jan-14 | Wind |
| 08INR0019a | Gray | 250 | Jan-14 | Wind |  | 13INR0010b | Parmer | 500 | Jan-14 | Wind |
| 13INR0020b | Glasscock | 150 | May-14 | Wind |  | 10INR0015 | Mitchell | 350 | May-14 | Wind |
| 14INR0003 | Nolan | 850 | Jun-14 | Coal |  | 14INR0006 | Floyd | 151 | Oct-14 | Wind |
| 13INR0021 | Llano | 600 | Dec-14 | Gas |  | 14INR0001 | Pecos | 500 | Dec-14 | Wind |
| 12INR0002b | Briscoe | 200 | Dec-14 | Wind |  | 13INR0010c | Parmer | 500 | Jan-15 | Wind |
| 15INR0011b | Borden | 38 | Dec-15 | Solar |  | 15INR0011a | Borden | 112 | Dec-15 | Wind |
| 12INR0002c | Briscoe | 350 | Dec-15 | Wind |  | 16INR0002 | Brazoria | 700 | Jun-17 | Other |

## Wind Generation

Wind Capacity Installed by Year

County Location of Installed Capacity and Interconnection Requests (Wind only)

# Regional Planning Group Project Reviews

- Brazos Electric Cooperative has submitted a project to move some load that is currently being served by the Entergy Texas system into the ERCOT system.  The project would involve disconnecting the subject load from the Entergy Texas system, constructing a new 345/ 138 kV substation in ERCOT, upgrading an existing 69 kV line in the ERCOT system and constructing two new 138 kV lines to serve the load from the ERCOT system.  The estimated cost of this project is $51.1 M.  This Tier 1 project is currently undergoing ERCOT Independent Review.

- CenterPoint Energy has submitted the 2014 Houston Area Dynamic Reactive Project to address the need for additional dynamic reactive compensation in the Houston area. This project calls for dynamic reactive devices at two locations (on the CenterPoint’s transmission system), with the compensation devices to be in service before summer peak 2014. The approximate cost for this project is $125 Million, depending on the selected dynamic reactive device technology. This Tier 1 project is currently undergoing ERCOT Independent Review.

- American Electric Power Service Corporation has submitted the Laredo to the lower Rio Grande Valley 345 kV Project to improve reliability of the lower Rio Grande Valley transmission system. This project proposes a new 345kV transmission line to be constructed from Laredo to the lower Rio Grande Valley to provide a third 345kV source to the area with an in-service date in the 2016/2017 timeframe. The estimated cost for this project is $379.5 Million. This Tier 1 project is currently in the comment phase.

- Oncor and WETT has submitted a project with proposed changes to the Lamesa Area Upgrade project. The original Lamesa Area Upgrade Project was reviewed and approved by RPG previously. As per the RPG Charter and Procedures changes to already-approved projects will be processed as Tier 3 project. This Tier 3 project is currently in the comment phase.

# Congestion Costs

Dollars shown in RUC Make Whole payment graph are settlement quality.

OOMC and RUC net Make Whole payment in million$

Monthly Average MCPE and LMP

Binding Constraints - February 2011

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Cost $ (Shadow Price*Limit) | Transmission Project | Clearance |
| --- | --- | --- | --- | --- | --- | --- |
| Nelson Sharpe - Ajo 345kV | Lon Hill - North Edinburg 345kV | 78 | 0 - 4500 | 31,689,757 |  |  |
| BASE CASE | Valley Import | 150 | 0 - 5000 | 30,105,744 |  |  |
| Denton - Argyle & West Denton 138kV | West Denton - Jim Cristal 138kV | 329 | 234 - 3500 | 20,313,041 | 5YTP [2009-R11] |  |
| BASE CASE | West to North Stability Limit | 1908 | 0 - 1162 | 9,767,701 | CREZ |  |
| West Levee Switch 345/138kV AT1 | West Levee Switch 345/138kV AT2 | 98 | 0 - 3500 | 9,073,730 | 5YTP [2009-R21] |  |
| Chamber - King & Cedar Bayou - Northbelt 345kV | Center - PH Robinson 345kV | 78 | 0 - 4500 | 6,386,600 |  |  |
| Kendall 345/138kV AT2 | Kendall 345/138kV AT1 | 225 | 0 - 4500 | 4,434,846 | Kendall Autotransformer Replacement [12TPIT0024] | Kendall 345/138kV AT2 |
| Twin Oak Switch - Gibbons Creek & Jack Creek 345kV | Twin Oak Switch - Jewet 345kV | 85 | 1 - 4500 | 4,215,057 |  |  |
| Braunig - Toyota & Valley 138kV, DCKT WB Tuttle - Austin Road 138kV, Fern Street - Ball Park 138kV, Nacogdoches Road - Skyline 138kV | Five Points - Westside CPS 138kV | 1444 | 0 - 3500 | 3,660,830 | Westside substation equipment upgrade [12TPIT0054] | Outage on Cagnon - Marbach 138kV |
| Kiowa Switch - Kiamichi 345kV | Kiowa Switch - Kiamichi 345kV | 6 | 4500 - 4500 | 2,736,638 |  |  |

Binding Constraints - January to February 2011

| Contingency | Binding Element | Number of 5-min intervals | Shadow Price Range $/MWh | Estimated Congestion Cost $ (Shadow Price*Limit) | Transmission Project | Clearance |
| --- | --- | --- | --- | --- | --- | --- |
| BASE CASE | Valley Import | 273 | 0 - 5000 | 41,457,339 |  |  |
| Nelson Sharpe - Ajo 345kV | Lon Hill - North Edinburg 345kV | 78 | 0 - 4500 | 31,689,757 |  |  |
| BASE CASE | West to North Stability Limit | 6595 | 0 - 2833 | 30,330,806 | CREZ |  |
| Denton - Argyle & West Denton 138kV, Fort Worth - W_Dent 138kV | West Denton - Jim Cristal 138kV | 383 | 40 - 3500 | 22,404,765 | 5YTP [2009-R11] |  |
| West Levee Switch 345/138kV AT1 | West Levee Switch 345/138kV AT2 | 98 | 0 - 3500 | 9,073,730 | 5YTP [2009-R21] |  |
| Chamber - King & Cedar Bayou - Northbelt 345kV | Center - PH Robinson 345kV | 78 | 0 - 4500 | 6,386,600 |  |  |
| Braunig - Toyota & Valley 138kV, DCKT WB Tuttle - Austin Road 138kV, Fern Street - Ball Park 138kV, Nacogdoches Road - Skyline 138kV, Streich - Braunig 138kV, Calavers -Streich 138kV | Five Points - Westside CPS 138kV | 2037 | 0 - 3500 | 5,108,772 | Westside substation equipment upgrade [12TPIT0054] | Outage on Cagnon - Marbach 138kV, Marbach - Valley 138kV |
| Kendall 345/138kV AT2 | Kendall 345/138kV AT1 | 225 | 0 - 4500 | 4,434,846 | Kendall Autotransformer Replacement [12TPIT0024] | Kendall 345/138kV AT2 |
| Twin Oak Switch - Gibbons Creek & Jack Creek 345kV | Twin Oak Switch - Jewet 345kV | 85 | 1 - 4500 | 4,215,057 |  |  |
| Lon Hill - North Edinburg 345KV | Rio Hondo 345kV Series Capacitor 1 | 15 | 460 - 4500 | 3,251,815 |  |  |

# Wind Generation as a Percent of Load

One-hour average of total wind power output as a percentage of ERCOT load.

# Planning Model Activities

- ERCOT and SSWG agreed on a timeline and strategy to complete Data Set A.  Per the SSWG Supplemental Procedures, ERCOT will provide the NMMS model for Generation and Private Utility Networks that it has received in RARFs and output using the Topology Processor.  ERCOT will be assigned and will use a new six digit bus number range above 100,000 and will use up to 12 characters for the bus name for generation buses.  The bus name will be a concatenation of the NMMS Unit Name preceded by an underscore and as much of the NMMS Station Name that will fit within the 12 character limitation.

- ERCOT has submitted the first two parts of SCR760 as enhancements to Siemens following ERCOT Board approval in March 2011.  The two parts submitted were items 7 and 8.  In the following table, the color red will be used to show status of Not Submitted, meaning that the SCR sub part has not been submitted to Siemens as a Service Request.  Yellow will indicate that the SCR sub part has been submitted.  The color will remain yellow and the status will change in order to Submitted, Planning (Siemens writing code and asking for information), Release (Siemens produces first code to test), and Testing (code has completed internal test and is moving through release management).  The color will change to green and the status will change to Production when the code has been tested and installed on the machines that ERCOT uses to produce Topology Processor output for Planning and CRR.

| SCR Sub Part | SCR Description | Status |
| --- | --- | --- |
| SCR760-1 | Upgrade to PSS/E v32 | Not Submitted |
| SCR760-2 | Distribution Capacitor banks | Not Submitted |
| SCR760-3 | Zero Impedance Line Ratings | Not Submitted |
| SCR760-4 | Associate Loads and Capacitor banks with the correct CNG | Not Submitted |
| SCR760-5 | Additional Transformer Data for Planning | Not Submitted |
| SCR760-6 | FACTS Devices | Not Submitted |
| SCR760-7 | Assign valid PSSE IDs to Breakers/ Switches/ Series Devices | Submitted |
| SCR760-8 | Phase shift of Autos for short circuit studies | Submitted |
| SCR760-9 | Multisection Line Grouping | Not Submitted |

# Other Notable Activities

- The 2010 Five-Year Transmission Plan (5YTP) studies final report was posted to the ERCOT Planning and Operations Information website on March 23, 2011.

- Transient Stability Study for 2011 winter off-peak conditions: As part of the annual reliability assessment of the network, a transient stability study is being performed on an ERCOT 2011 winter off-peak case.