## All_06.01
Item # | Short Description | Notes | Issue Group | New/Modification/Delete | Source | Date Added | Assigned to | Priority | Status
1 | Communication of Alerts | Discussed a Subscription type service NATF 1-4-11: James Jackson to receive input from the Market on which alerts are not needed and which should have a higher priority. To be addressed at the MIS Users Group. MISUG 1/13 - Telemetry alerts coming every 2 seconds. ERCOT looking into short cycle alerts, as well. ERCOT has msgs coming out with no importance - DAM postings are done. DRUC market is closed. - why sending msgs with no meaning? Need more definition around notices/alerts and define meaning. Focus from NATF - RLC alerts, many not be high priority, confusing and don't know what they mean. Subscription service - so you are receiving and performing what is necessary on what is critical. Non-spin specifically - do something different. MISUG sees this would be covered by another group View key notifications on dashboards. Although delivered to all MP types, QSEs are the primary users and those acting on the notifications/alerts received. Need to look into what the TSPs are using, as well. Alerts are big and hard to define. | EWS | Modification | qse_issues_list - 1 | 2011-01-13 | MISUG | HIGH | 2/22 - moved back to MISUG for discussion from QSEWG
2 | Reports and Extracts- Frequency of Queries | Discussed reasonable number of queries MISUG 1/13 - Addressing screen scraping | ext/rpt | Modification | qse_issues_list - 2 | 2011-01-13 | MISUG | CLOSED | CLOSED
3 | Report Requirements when “no data is available” | When RUC commits zero Resources, there is no report ----- but there is a message that says "see report". For this one report, can we create a report with a message like "this page intentionally left blank"? MISUG 1/13 - Looking for notification that HRUC ran successfully but no units were chosen. incidents on Dec 23rd - no data ahead market invoices or statements posted that day - caused scramble - no CRRs cleared in DAM, so no invoices - in lieu of calling ERCOT client services - get some notification - need some communication. Expecting something, but not receiving. <SEWG? MISUG?> Attempting to download an extract and never got data for a DUNS because there was no data for a couple of days per ERCOT confirmation. Looking for this for all instances where MPs would get something that says we ran the report and there was no data to provide. | ext/rpt | Modification | qse_issues_list - 5 | 2011-01-13 | MISUG | LOW
4 | HRUC after Approval (Reporting Issue) | In rare occasions, after RUC has been executed and the approval has been made there may be a Verbal RUC issued. We need to come up with a way to share with the entire Market the Verbal RUC instructions. MISUG 1/13 - Looking for a notification and report pair similar to what is provided for the RUC events. Data in same format specifically for the verbal RUCs. Cancelled RUCs to be modeled in the same way in the RUC Commit/Decommit Report MIS 06012011: QMWG Discussion follow up: do not want to provide cancel/deselected RUCs in a public report due to CEII information on a resources status. Information currently not provided. At operator discretion but info not made available to market. Information to specific resource is also not provided in a certified report or notification. Not sure that there is a need for this information at this time. | alerts/notifications/ext/rpt | New | qse_issues_list - 12 | 2011-01-13 | MISUG | HIGH | discuss 6/1
5 | Portal Time-outs | 1-4-11: NATF defined this item a little better and suggest it should be addressed by the MIS Users Group. MISUG 1/13 - When using dashboards and MMUI, timeouts are occurring where the dashboards are refreshed and MM UI go blank and then you have to close, relaunch. What version of IE is being used when you have this occur? - IE6 Maybe associated to timeouts on the app server, so resources don't get tied up. Why does this happen for some people and not others? ERCOT needs to perform analysis on best practices | MIS dashboards | Modification | qse_issues_list - 13 | 2011-01-13 | MISUG | LOW
6 | Reports only available on MIS secure, that may need to be more accessible: Load Forecast, Wind ….. There is no Non-Spin Deployment report | MISUG 1/13 - Kenan (NATF) working on a list of rpts/exts that are currently secure to be reclassified as public. | security classification | Modification | qse_issues_list - 14 | 2011-01-13 | MISUG | CLOSED | 2/22 - moved to MISUG for discussion from City Public Service/NATF; NPRR329; implemented 05/2011
7 | MIS existing Dashboards * DAM & RTM LMPs * LMP Contour Map * LMP Ticker * Load Forecast vs. Actual * Real-Time System Conditions * SCED Up Down * System Ancillary Service Capacity Monitor | Make MIS existing Dashboards public MISUG 1/13 - Most information on dashboards was public prior to go-live. No security classification issues. Benefit is in how you display the data. Information in zonal market were much more friendly. If the data is available in other formats, likely don't need to implement the dashboards. Consider NPRR that the public is looking to registered as a market participant and be in MIS SECURE. This is another solution. | security classification | Modification | Market feedback | 2011-01-13 | MISUG | LOW
8 | Active Binding Constraints | Make public MISUG 1/13 - Looking for current real time active binding constraints to be moved from SECURE MIS to PUBLIC MIS. List them for RTM. DAM runs - shadow price report will show binding constraints for DAM. | security classification | Modification | Reliant | 2011-01-13 | MISUG | See #6
9 | Load Zone/Hub monthly price spreadsheet | Would like to see a posting of the historical prices for both DAM & RTM similar to what used to be available for MCPE in zonal. http://www.ercot.com/mktinfo/prices/ MISUG 1/13 - Used by commercial industrial customers today to check their bills, prices, etc. Excel spreadsheet. Frequency - just looking for prices (HUB, zones) could be 2-3 days after the operating day. Daily and compiled by month. Public. Add a separate tab for price corrections. Would like to see original price and the corrected price. | ext/rpt | New | Reliant | 2011-01-13 | MISUG | LOW
10 | Settlement Statement Totals | Create a new public report for nodal providing what was provided in zonal at http://www.ercot.com/mktinfo/settlements/. MISUG 1/13 - Specific bill determinants (RUC, direct shortfall, LRS <uplift charges>, AS including SASMs, load related charges, DA congestion rent, CRR balancing account) Public. looking for at least daily like with zonal. MP feedback - Please provide for each DAM and Each RUC the following system billing determinates: DAMWAMTTOT; RMRDAMWREVTOT; DAETOT; RUCMWAMTRUCTOT; RUCCAPTOT; RUCSFTOT | ext/rpt | New | Reliant | 2011-01-13 | MISUG | LOW
11 | Short Term Load Forecast Wind Forecasts (STWPF, WGRPP) | Make public MISUG 1/13 - numbers like in zonal. Wind forecast report from SECURE to public - (see #6) Aggregated Wind Generation Resource Power Potential Forecast Short term Load Forecast - change from SECURE to public (see#6) 7 day and 36 month load forecast | security classification | Modification | Public Requests | 2011-01-13 | MISUG | See #6
12 | Daily Grid Operations Report | Create report for Nodal and make public. MISUG 1/13 - Non-spin deployments happen. Transmission alerts. Unit trips (redacted). Reserves. OCNs. Report was perfect the way it was in zonal. Units that were RUCd with the beginning interval. Transparency to things that weren't like OOMC and OOME. Anything not already available somewhere: SCED offsets VDIs Other instructions Follow base point instructions for wind units Responsive deployments Available capacity - how much is dispatchable in a SCED interval - is this a real time piece of information that would be displayed somewhere else? may be a dashboard requirements Any changes to the K factors used in the SCED equation (generation to be dispatched calculation) Quick synopsis for people that are using information on the front. Look into a monthly report | ext/rpt | New | Public Requests | 2011-01-13 | MISUG | HIGH | ERCOT follow-up for late 06/2011 meeting
13 | Display 1 minute values for Total Generation, Wind Generation, Frequency, Spinning Reserve, instantaneous load, instantaneous wind, Instantaneous flows on CSC/CRE | Create new displays and ability to download for Nodal and make public MISUG 1/13 - in zonal it is refreshing almost every minute. Will likely be combined with the discussion on the Real Time System conditions dashboard (see #7). Instantaneous wind generation by zone (if possible) - public display and instantaneous load (this is new) How much generation reserves are online and capable of being deployed, if needed - this is in the Sys Wide AS capacity monitor, would like to see this public - this isthe current SECURE MIS dashboard Instantaneous flows on CSC/CRE - shadow prices when there was a binding CSC | display | New | Public Requests | 2011-01-13 | MISUG | HIGH | 3/31 - addressed dashboard SCR and rpt requirements 4/28 - address rpt NPRR 6/1 - SCR765 at TAC on 6/2
14 | Make fuel/generation mix of fuel types available on a display publicly | Create new displays for fuel/generation mix of fuel types and make public. Http://spp.org/realtimedata.asp MISUG 1/13 - Remove this work item | display | New | Public Requests | 2011-01-13 | MISUG | CLOSED | CLOSED
15 | Outage Scheduler UI - show active outages | Outage Summary, add a new column depicting which outages are currently active. Presently the only way to see which outages are active is to open each individual outage and view whether or not it has been timed out. MISUG 1/13 - Specific to TDSPs. No feedback provided. | OSUI | Modification | LCRA | 2011-01-13 | MISUG | MEDIUM
16 | Outage Scheduler UI - ERCOT waive 3 day window for unavoidable extensions | Unavoidable extensions, presently unable to submit unless the present Planned, Maintenance or Forced outage is within 3 days of ending. MISUG 1/13 - Likely a rules change for OS. | OSUI | Modification | LCRA | 2011-01-13 | ROS; NDSWG
17 | MMUI - screen landscape not sized to full page | Only partial data sets are viewable and headers are lost when scrolling. For example, only able to view HR 01:00-09:00 of each resource, scroll down to the bottom of the screen, then scroll to over to see the remaining hours. There is a lot of screen not utilized. Once we have scrolled all the way to the right, you cannot see the Quantity Blocks nor the resource name and we lose track of which unit is in view. MISUG 1/13 - Throughout the MMUI | MMUI | Modification | LCRA | 2011-01-13 | MISUG | LOW
18 | MMUI - COP navigation functionality and available data to view | While viewing the COP for a particular resource, add the ability to also see the TPO, Output Schedule, A/S Offer and Inc/Dec Offer of the resource you’ve selected without having to select each tab, then re-selecting the same resource again. MISUG 1/13 - Aggregation of all data onto one screen on MMUI would be very useful. Good for validation and for data entry. | MMUI | Modification | LCRA | 2011-01-13 | MISUG | LOW
19 | MMUI - multi-selection of notices and usability of notices dropdown menu | Notice Type pull down menu, add the ability to select more than one field (select four of the thirteen choices). Instead of having to select each individual selection and then refresh. • If possible, a refresh that occurs automatically without a Trader having to manually click the show results. MISUG 1/13 - Looking for a shift and click to find multiple units. | MMUI | Modification | LCRA | 2011-01-13 | MISUG | LOW
20 | MMUI - Telemetry alerts for consistency checks | Telemetry • Nuisance alarms are generated mainly due to two reasons, hydro and wind. Both causing an alert due to inconsistent resource status and mw value. Meaning when no wind is scheduled in the COP but then does generate a small amount, we receive an alarm. • Suggest removing wind and/or hydro from their telemetry data base or at the least install a dead band with more tolerance. • Or suggest changing them from high to low priority. MISUG 1/13 - No feedback. | alerts/notifications | Modification | LCRA | 2011-01-13 | MISUG | See #1
21 | MMUI - number of SASM alerts and wording of SASM notices for report downloads to the general market | SASM Notices • ERCOT sends out SASM low priority study period, one for SASM Market Clearing Prices, one for SASM market open (which we have not seen yet) and a last notice for SASM awards are available. • We don’t need a notice for the study period when a QSE has not supplied their part of the whole ERCOT model. It’s confusing because we believe a SASM has opened but in reality it did not. • We don’t need a notice for the SASM awards report is available when the SASM was never opened to begin with. • We don’t need a notice for the SASM MCPC report is available when the SASM was never opened to begin with. MISUG 1/13 - ERCOT sends SASM study open when SASM is running. Valid notices for the QSEs. ERCOT work with LCRA on this issue to see if there is anything for the MISUG to look into. | MMUI | Modification | LCRA | 2011-01-13 | MISUG | ERCOT | discuss 6/1
22 | Non-Spin Notifications - change to receive via ICCP | MISUG 1/13 - Non-spin alerts needing to come in through ICCP as an option. Going to discuss at next NATF. Not efficient for all MPs because only generation resources currently use ICCP and web services was the direction the market chose to take for data acess. | ICCP | New | MISUG | 2011-01-13 | NATF | HIGH | discuss late 6/2011 meeting
23 | Non-Spin Notifications - need new one for non-spin deployments to all MPs | MISUG 1/13 - need new non-spin notification for non-spin deployments to all MPs Until we get the non-spin issue resolved, could we consider a hotline call when non-spin is deployed in the short term? | alerts/notifications | New | MISUG | 2011-01-13 | MISUG | HIGH | 3/31 - included in list of alert/notification changes 6/1 - review list
24 | historical information for the sys wide AS capacity monitor | MISUG 1/13 - Display at least 7 days of historical information The SCED up/down may address some of this - available capacity to dec/inc base points. Also included to an extent in ICCP (only address those with generation fleets; rest of market relies on APIs). | dashboards-data | Modification | MISUG | 2011-01-13 | MISUG | MEDIUM
25 | Market not aware of when EVENTS are started/executed/completed causing higher requests for downloads | MISUG 1/13 - No notification of when EVENTS are started/executed/completed, so MPs are polling the ERCOT systems for downloads in excess of event data publishing Need to look at pushing data versus notifications Example given - when SCED is running | alerts/notifications | New | MISUG | 2011-01-13 | MISUG | MEDIUM | discuss 6/1
26 | ERCOT Market Data Transparency SLA - look at the use of screen scraping, pushing data, subscription services | MISUG 1/13 - Determine what data is necessary to be pushed to the market in lieu of MPs and public using screen scraping techniques to download data from ERCOT | SLA | Modification | MISUG | 2011-01-13 | MISUG | MEDIUM
27 | Price Corrections - create in same format as prices | MISUG 1/13 - Price postings - MT - ran into situations where SCED would miss a price posting and this would possibly cause sys issues at MP. A reposting mechanism was put into place at ERCOT. One issue - normally prices are posted in both csv and xml, repostings were only being done in csv and this was corrected to post both types. Increased controls put into place to allow for automated reposting because this was manual intervention prior where repostings would be days later. this seems to be stable at this pt. Mid-dec there was a price correction where prices were fixed close to the deadline of when prices become final and the prices were not reposted. they were posted in a different section in a different format. Price corrections by design are posted to a different place. Consider EWS to consume prices when price corrections are made so that formats are the same for MPs to upload to their systems. Price corrections are not ever put into MMS where the data could be reprovided in the prices reporting format. What can be done since this only goes to the Settlement System? Suggestion - when a price needs to be posted due to missing data or a correction, post in the same format that the MP can consume using the web services. (XML) | EWS/ext/rpt | Modification | MISUG | 2011-01-13 | MISUG | MEDIUM | SCR761
28 | MIS Dashboards - unable to view the entire source of information on the screen | MISUG 1/13 - Launch the portlets - like to have an independent and dynamically size; My page | dashboards-configuration | Modification | MISUG | 2011-01-13 | MISUG | MEDIUM
29 | Unconfirmed trades - new report | MISUG 1/13 - A report for unconfirmed trades at the time of each RUC that is certified for QSEs | ext/rpt | New | MISUG | 2011-01-13 | MISUG | HIGH | 3/31 - addressed market rpt requirements 4/28 - review NPRR/SCR 6/1 - review NPRR
30 | NDCRC - where season HSL and VAR tests | MISUG 1/13 - Fields not consistent with the data they have to put into the application (doesn't necessarily accept negatives and have to enter a negative value) | NDCRC | Modification | MISUG | 2011-01-13 | MISUG | HIGH | discuss late 6/2011 meeting
31 | MMUI - | MISUG 1/13 - When using MMUI for submissions, must close and not refresh - have to relaunch then refresh queries | MMUI | Modification | MISUG | 2011-01-13 | MISUG | LOW
32 | Validation difference in what EWS accepts and what MMUI accepts | MISUG 1/13 - Client side validation between MIS and EWS should be consistent. Issue seen with MMUI and outages. ERCOT captured in defects and is currently being worked. | MMUI/OSUI | Modification | MISUG | 2011-01-13 | MISUG | ERCOT | ERCOT follow-up for late 06/2011 meeting
33 | Settlement Statement modification to add more data | MISUG 1/13 - Receive the price and quantity in the CODE and looking to get the MW quantities in the Settlement Statement. | ext/rpt | Modification | MISUG | 2011-01-13 | SEWG | MEDIUM
34 | Shift Factors report in the DAM | MISUG 1/13 - New Report. For binding constraints in the DAM, see the shift factors for those constraints for the electrical buses similar to what we have in RTM. | ext/rpt | New | MISUG | 2011-01-13 | MISUG | MEDIUM
35 | Copy feature in MMUI | MISUG 1/13 - ERCOT provide link to document ERCOT response: http://nodal.ercot.com/readiness/markettrials/connectivity/keydocs/Market_Manager_User_Guide_06.doc, page 9-10. the long term home will be on ercot.com on the services/market data transparency page. | ext/rpt | Modification | MISUG | 2011-01-13 | ERCOT | CLOSED | CLOSED
36 | MIS Dashboards - amount of windows needed to be open to see operational data | MISUG 1/13 - Doesn't display the data to make a judgement at a glance. Eliminate the frames/portlets and the individual popups where all dashboard data is in one screen sectionalized and can be custimized | dashboards-configuration | Modification | MISUG | 2011-01-13 | MISUG | MEDIUM
37 | Weather data assumptions for DAM | MISUG 1/13 - Create a new dashboard compared to actual weather | dashboards-new | New | MISUG | 2011-01-13 | MISUG | HIGH | discuss late 6/2011 meeting
38 | LMP contour map - change to contour | MISUG 1/13 - Change to be a contour, not pixelated dot map - hard to see what is constrained Filtering capability to go into a particilar zone or whole state. Looking for better color change. | dashboards-configuration | Modification | MISUG | 2011-01-13 | MISUG | MEDIUM
39 | Time flows - CSCs and CREs by hour (configurable on how many) |  | dashboards-new | New | MISUG | 2011-01-13 | MISUG | MEDIUM
40 | Load page dashboard | MISUG 1/13 - Currently have DAM, RTM and actual - could we include forecasts? ERCOT doesn't have the RUC snapshots. Looking for most recent HRUC snapshot looking at current load. | dashboards-new | New | MISUG | 2011-01-13 | MISUG | MEDIUM
41 | Emergency tab on dashboards | MISUG 1/13 - Create an emergency tab to see any emergencies at a glance | dashboards-new | New | MISUG | 2011-01-13 | MISUG | MEDIUM
42 | Constraints dashboard | MISUG 1/13 - what's active from an hour ago to current - active, inactive, temp, removed | dashboards-new | New | MISUG | 2011-01-13 | MISUG | MEDIUM
43 | LMP graph | MISUG 1/13 - Want to look at multiple prices on one chart. | dashboards-configuration | Modification | MISUG | 2011-01-13 | MISUG | MEDIUM
44 | Wind graph dashboard | MISUG 1/13 - looking for current and forecasted wind | dashboards-data | Modification | MISUG | 2011-01-13 | MISUG | HIGH | 3/31 - reviewed SCR 6/1 - SCR765 at TAC on 6/2
45 | System ACE | MISUG 1/13 - Graph of ACE | dashboards-new | New | MISUG | 2011-01-13 | MISUG | HIGH | discuss late 6/2011 meeting
46 | Proper notification of system changes to be more transparent to market | MISUG 1/13 - Input to be taken back to ERCOT |  | Modification | MISUG | 2011-01-13 | ERCOT | CLOSED | CLOSED
47 | Settlement point List change to public | MISUG 1/13 - Settlement point list to be provided publicly | security classification | Modification | MISUG | 2011-01-13 | MISUG | See #6
48 | Sum of HDLs and LDLs to secure | MISUG 1/13 - New report for secure | ext/rpt | New | MISUG | 2011-01-13 | MISUG | HIGH | discuss 6/1
49 | API for public | MISUG 1/13 - Public should have access to some form of an API to download data from ERCOT | access point | New | MISUG | 2011-01-13 | MISUG | LOW
50 | ICCP - add wind attribute | MISUG 1/13 - Total wind MW within ICCP |  | Modification | MISUG | 2011-01-13 | MISUG
51 | Communication of Alerts | MISUG 1/13 - Timestamps for RUC awards off by an hour - looking to be delivered by ERCOT 1/19 release. | EWS | Modification | qse_issues_list - 1 | 2011-01-13 | QSEMWG | CLOSED | Complete - 1/19/2011
52 | Active Binding Constraints | MISUG 1/13 - Looking for current real time active binding constraints public display for DAM and RTM. Tied to #8 above and the security classification change. | display | New | MISUG | 2011-01-13 | MISUG | See #8
53 | Short Term System Adequacy Report - add column | Specifically this file has a column called, "CapGenRes" which has the Generation Capacity of the total COP submissions summed on an hourly basis. This "CapGenRes" does not to take into account Generation Capacity that is not available for dispatch. Request to create an additional field removing the capacity for hours where plants are ramping 'ONTEST' would provide market participants the ability to self-mitigate the high prices we see during the traditional ramp-on hours of the morning. This also would be done in summation and wouldn't expose any one QSE's data. | ext/rpt | Modification | Direct Energy | 2011-01-21 | MISUG | MEDIUM
54 | ERCOT meeting calendar | Add button to "Add to my calendar" | website | New | Excelon | 2011-01-24 | MISUG | LOW
55 | Monthly TDSP Load reporting by LSE for NERC | NERC has placed additional reporting requirements on MPs. ERCOT staff is requesting this annually from the MPs. Monthly peak demands by LSE and hourly load by LSE (both demand and energy) - must supply all hours for NERC requirement. This metering is not available any longer. LTDSPUFE data cut is now provided in the RTM CODE, which must be downloaded daily from the extract then aggregated to get to the numbers being requested. | ext/rpt | New | Oncor/MISUG | 2011-02-22 | MISUG | HIGH | 3/31 - collected market requirements 4/28 - discuss NPRR/SCR 6/1 - NPRR359 at PRS 6/23
56 | DCTIE schedules | Post at 1430 (have wind and load) looking at the next day. Total MW by DCTIE. Public. NP6-626 shows DC Tie flows - need to investigate | ext/rpt | New | MISUG | 2011-02-22 | MISUG | HIGH | 4/28 - collect market requirements
57 | DCTIE schedules - historical | Need historical by DCTIE. Looking at a year's activity. Public. ERCOT planning staff used historical hour by hour information to determine what needed to be included in the planning models. | ext/rpt | New | MISUG | 2011-02-22 | MISUG | MEDIUM
58 | CRR Shift Factors | For the binding constraints (similar to DAM Shift Factors) | ext/rpt | New | MISUG | 2011-02-22 | MISUG | MEDIUM
59 | SCED UpDown Dashboard | Merge to be on same axis so SCED Up is positive, and SCED down is negative | dashboards-modify | New | MISUG | 2011-02-22 | MISUG | HIGH | included in SCR764
60 | System-wide RUC Charges | Post daily system wide RUC charges similar to Monthly RUC Make Whole Charge and Clawback Payment Report, but by day. | ext/rpt | New | DC-Energy | 2011-02-24 | MISUG | MEDIUM
61 | Historical LMP Report | Public posting of historical LMPdata. | ext/rpt | New | ERCOT | 2011-03-01 | MISUG
62 | Historical SPP Report | Public posting of historical SPP data. | ext/rpt | New | ERCOT | 2011-03-01 | MISUG
63 | Total and Groupings of Wind Output Report | Report for task #43 | ext/rpt | New | ERCOT | 2011-03-01 | MISUG | HIGH | NPRR361 PRS 6/23
64 | ERCOT Actual Load Report | Public posting of ERCOT Actual Load in the form of a report. ERCOT currently only has a display of Actual Loads of Weather Zones on the website for consumption. | ext/rpt | New | Goldman, Sachs | 2011-03-16 | MISUG
65 | NH Interface Limit |  | ext/rpt | New | Goldman, Sachs | 2011-06-01 | MISUG
66 | LMP Contour map - add negative prices | Extend price range to include negative prices | dashboards | Modification | DC-Energy | 2011-06-01 | MISUG

## Closed
Item # | Short Description | Notes | Issue Group | New/Modification/Delete | Source | Date Added | Assigned to | Priority | Status
2 | Reports and Extracts- Frequency of Queries | Discussed reasonable number of queries MISUG 1/13 - Addressing screen scraping | ext/rpt | Modification | qse_issues_list - 2 | 2011-01-13 | MISUG | CLOSED | CLOSED
6 | Reports only available on MIS secure, that may need to be more accessible: Load Forecast, Wind ….. There is no Non-Spin Deployment report | MISUG 1/13 - Kenan (NATF) working on a list of rpts/exts that are currently secure to be reclassified as public. | security classification | Modification | qse_issues_list - 14 | 2011-01-13 | MISUG | CLOSED | 2/22 - moved to MISUG for discussion from City Public Service/NATF; NPRR329; implemented 05/2011
14 | Make fuel/generation mix of fuel types available on a display publicly | Create new displays for fuel/generation mix of fuel types and make public. Http://spp.org/realtimedata.asp MISUG 1/13 - Remove this work item | display | New | Public Requests | 2011-01-13 | MISUG | CLOSED | CLOSED
35 | Copy feature in MMUI | MISUG 1/13 - ERCOT provide link to document ERCOT response: http://nodal.ercot.com/readiness/markettrials/connectivity/keydocs/Market_Manager_User_Guide_06.doc, page 9-10. the long term home will be on ercot.com on the services/market data transparency page. | ext/rpt | Modification | MISUG | 2011-01-13 | ERCOT | CLOSED | CLOSED
46 | Proper notification of system changes to be more transparent to market | MISUG 1/13 - Input to be taken back to ERCOT |  | Modification | MISUG | 2011-01-13 | ERCOT | CLOSED | CLOSED
51 | Communication of Alerts | MISUG 1/13 - Timestamps for RUC awards off by an hour - looking to be delivered by ERCOT 1/19 release. | EWS | Modification | qse_issues_list - 1 | 2011-01-13 | QSEMWG | CLOSED | Complete - 1/19/2011
8 | Active Binding Constraints | Make public MISUG 1/13 - Looking for current real time active binding constraints to be moved from SECURE MIS to PUBLIC MIS. List them for RTM. DAM runs - shadow price report will show binding constraints for DAM. | security classification | Modification | Reliant | 2011-01-13 | MISUG | CLOSED | NPRR329
11 | Short Term Load Forecast Wind Forecasts (STWPF, WGRPP) | Make public MISUG 1/13 - numbers like in zonal. Wind forecast report from SECURE to public - (see #6) Aggregated Wind Generation Resource Power Potential Forecast Short term Load Forecast - change from SECURE to public (see#6) 7 day and 36 month load forecast | security classification | Modification | Public Requests | 2011-01-13 | MISUG | CLOSED | NPRR329
47 | Settlement point List change to public | MISUG 1/13 - Settlement point list to be provided publicly | security classification | Modification | MISUG | 2011-01-13 | MISUG | CLOSED | NPRR329
61 | Historical LMP Report | Public posting of historical LMPdata. | ext/rpt | New | ERCOT | 2011-03-01 | MISUG | duplicate
62 | Historical SPP Report | Public posting of historical SPP data. | ext/rpt | New | ERCOT | 2011-03-01 | MISUG | duplicate

## In Progress
Item # | Short Description | Notes | Issue Group | New/Modification/Delete | Source | Date Added | Assigned to | Priority | Status
1 | Communication of Alerts | Discussed a Subscription type service NATF 1-4-11: James Jackson to receive input from the Market on which alerts are not needed and which should have a higher priority. To be addressed at the MIS Users Group. MISUG 1/13 - Telemetry alerts coming every 2 seconds. ERCOT looking into short cycle alerts, as well. ERCOT has msgs coming out with no importance - DAM postings are done. DRUC market is closed. - why sending msgs with no meaning? Need more definition around notices/alerts and define meaning. Focus from NATF - RLC alerts, many not be high priority, confusing and don't know what they mean. Subscription service - so you are receiving and performing what is necessary on what is critical. Non-spin specifically - do something different. MISUG sees this would be covered by another group View key notifications on dashboards. Although delivered to all MP types, QSEs are the primary users and those acting on the notifications/alerts received. Need to look into what the TSPs are using, as well. Alerts are big and hard to define. | EWS | Modification | qse_issues_list - 1 | 2011-01-13 | MISUG | HIGH | 2/22 - moved back to MISUG for discussion from QSEWG
13 | Display 1 minute values for Total Generation, Wind Generation, Frequency, Spinning Reserve, instantaneous load, instantaneous wind, Instantaneous flows on CSC/CRE | Create new displays and ability to download for Nodal and make public MISUG 1/13 - in zonal it is refreshing almost every minute. Will likely be combined with the discussion on the Real Time System conditions dashboard (see #7). Instantaneous wind generation by zone (if possible) - public display and instantaneous load (this is new) How much generation reserves are online and capable of being deployed, if needed - this is in the Sys Wide AS capacity monitor, would like to see this public - this isthe current SECURE MIS dashboard Instantaneous flows on CSC/CRE - shadow prices when there was a binding CSC | display | New | Public Requests | 2011-01-13 | MISUG | HIGH | 3/31 - addressed dashboard SCR and rpt requirements 4/28 - address rpt NPRR 6/1 - SCR765 at TAC on 6/2
23 | Non-Spin Notifications - need new one for non-spin deployments to all MPs | MISUG 1/13 - need new non-spin notification for non-spin deployments to all MPs Until we get the non-spin issue resolved, could we consider a hotline call when non-spin is deployed in the short term? | alerts/notifications | New | MISUG | 2011-01-13 | MISUG | HIGH | 3/31 - included in list of alert/notification changes 6/1 - review list
29 | Unconfirmed trades - new report | MISUG 1/13 - A report for unconfirmed trades at the time of each RUC that is certified for QSEs | ext/rpt | New | MISUG | 2011-01-13 | MISUG | HIGH | 3/31 - addressed market rpt requirements 4/28 - review NPRR/SCR 6/1 - review NPRR
44 | Wind graph dashboard | MISUG 1/13 - looking for current and forecasted wind | dashboards-data | Modification | MISUG | 2011-01-13 | MISUG | HIGH | 3/31 - reviewed SCR 6/1 - SCR765 at TAC on 6/2
55 | Monthly TDSP Load reporting by LSE for NERC | NERC has placed additional reporting requirements on MPs. ERCOT staff is requesting this annually from the MPs. Monthly peak demands by LSE and hourly load by LSE (both demand and energy) - must supply all hours for NERC requirement. This metering is not available any longer. LTDSPUFE data cut is now provided in the RTM CODE, which must be downloaded daily from the extract then aggregated to get to the numbers being requested. | ext/rpt | New | Oncor/MISUG | 2011-02-22 | MISUG | HIGH | 3/31 - collected market requirements 4/28 - discuss NPRR/SCR 6/1 - NPRR359 at PRS 6/23
56 | DCTIE schedules | Post at 1430 (have wind and load) looking at the next day. Total MW by DCTIE. Public. NP6-626 shows DC Tie flows - need to investigate | ext/rpt | New | MISUG | 2011-02-22 | MISUG | HIGH | 4/28 - collect market requirements
59 | SCED UpDown Dashboard | Merge to be on same axis so SCED Up is positive, and SCED down is negative | dashboards-modify | New | MISUG | 2011-02-22 | MISUG | HIGH | included in SCR764
63 | Total and Groupings of Wind Output Report | Report for task #43 | ext/rpt | New | ERCOT | 2011-03-01 | MISUG | HIGH | NPRR361 PRS 6/23
27 | Price Corrections - create in same format as prices | MISUG 1/13 - Price postings - MT - ran into situations where SCED would miss a price posting and this would possibly cause sys issues at MP. A reposting mechanism was put into place at ERCOT. One issue - normally prices are posted in both csv and xml, repostings were only being done in csv and this was corrected to post both types. Increased controls put into place to allow for automated reposting because this was manual intervention prior where repostings would be days later. this seems to be stable at this pt. Mid-dec there was a price correction where prices were fixed close to the deadline of when prices become final and the prices were not reposted. they were posted in a different section in a different format. Price corrections by design are posted to a different place. Consider EWS to consume prices when price corrections are made so that formats are the same for MPs to upload to their systems. Price corrections are not ever put into MMS where the data could be reprovided in the prices reporting format. What can be done since this only goes to the Settlement System? Suggestion - when a price needs to be posted due to missing data or a correction, post in the same format that the MP can consume using the web services. (XML) | EWS/ext/rpt | Modification | MISUG | 2011-01-13 | MISUG | MEDIUM | SCR761
22 | Non-Spin Notifications - change to receive via ICCP | MISUG 1/13 - Non-spin alerts needing to come in through ICCP as an option. Going to discuss at next NATF. Not efficient for all MPs because only generation resources currently use ICCP and web services was the direction the market chose to take for data acess. | ICCP | New | MISUG | 2011-01-13 | NATF | HIGH | NPRR 354 - Revisions to Non-Spin Performance Criteria Language and Provision for ICCP Telemetry of Non-Spin Deployment; submitted via WMS
53 | Short Term System Adequacy Report - add column | Specifically this file has a column called, "CapGenRes" which has the Generation Capacity of the total COP submissions summed on an hourly basis. This "CapGenRes" does not to take into account Generation Capacity that is not available for dispatch. Request to create an additional field removing the capacity for hours where plants are ramping 'ONTEST' would provide market participants the ability to self-mitigate the high prices we see during the traditional ramp-on hours of the morning. This also would be done in summation and wouldn't expose any one QSE's data. | ext/rpt | Modification | Direct Energy | 2011-01-21 | MISUG | LOW - MPs revisit | NPRR348 is eliminating the use of the status for ramping on/off.
7 | MIS existing Dashboards * DAM & RTM LMPs * LMP Contour Map * LMP Ticker * Load Forecast vs. Actual * Real-Time System Conditions * SCED Up Down * System Ancillary Service Capacity Monitor | Make MIS existing Dashboards public MISUG 1/13 - Most information on dashboards was public prior to go-live. No security classification issues. Benefit is in how you display the data. Information in zonal market were much more friendly. If the data is available in other formats, likely don't need to implement the dashboards. Consider NPRR that the public is looking to registered as a market participant and be in MIS SECURE. This is another solution. | security classification | Modification | Market feedback | 2011-01-13 | MISUG | HIGH | SCR 764

## Reprioritized06.01-to be worked
Priority Assignments
Low
Low - MPs revisit
Medium
High
ERCOT
Other working group or subcommittee
Item # | Short Description | Notes | Issue Group | New/Modification/Delete | Source | Date Added | Assigned to | Priority | Status
3 | Report Requirements when “no data is available” | When RUC commits zero Resources, there is no report ----- but there is a message that says "see report". For this one report, can we create a report with a message like "this page intentionally left blank"? MISUG 1/13 - Looking for notification that HRUC ran successfully but no units were chosen. incidents on Dec 23rd - no data ahead market invoices or statements posted that day - caused scramble - no CRRs cleared in DAM, so no invoices - in lieu of calling ERCOT client services - get some notification - need some communication. Expecting something, but not receiving. <SEWG? MISUG?> Attempting to download an extract and never got data for a DUNS because there was no data for a couple of days per ERCOT confirmation. Looking for this for all instances where MPs would get something that says we ran the report and there was no data to provide. | ext/rpt | Modification | qse_issues_list - 5 | 2011-01-13 | MISUG | LOW
4 | HRUC after Approval (Reporting Issue) | In rare occasions, after RUC has been executed and the approval has been made there may be a Verbal RUC issued. We need to come up with a way to share with the entire Market the Verbal RUC instructions. MISUG 1/13 - Looking for a notification and report pair similar to what is provided for the RUC events. Data in same format specifically for the verbal RUCs. Cancelled RUCs to be modeled in the same way in the RUC Commit/Decommit Report | alerts/notifications/ext/rpt | New | qse_issues_list - 12 | 2011-01-13 | MISUG | HIGH | discuss 6/1 - NPRR drafted
5 | Portal Time-outs | 1-4-11: NATF defined this item a little better and suggest it should be addressed by the MIS Users Group. MISUG 1/13 - When using dashboards and MMUI, timeouts are occurring where the dashboards are refreshed and MM UI go blank and then you have to close, relaunch. What version of IE is being used when you have this occur? - IE6 Maybe associated to timeouts on the app server, so resources don't get tied up. Why does this happen for some people and not others? ERCOT needs to perform analysis on best practices | MIS dashboards | Modification | qse_issues_list - 13 | 2011-01-13 | MISUG | LOW - MPs revisit
9 | Load Zone/Hub monthly price spreadsheet | Would like to see a posting of the historical prices for both DAM & RTM similar to what used to be available for MCPE in zonal. http://www.ercot.com/mktinfo/prices/ MISUG 1/13 - Used by commercial industrial customers today to check their bills, prices, etc. Excel spreadsheet. Frequency - just looking for prices (HUB, zones) could be 2-3 days after the operating day. Daily and compiled by month. Public. Add a separate tab for price corrections. Would like to see original price and the corrected price. | ext/rpt | New | Reliant | 2011-01-13 | MISUG | MEDIUM | ERCOT update 6/24
10 | Settlement Statement Totals | Create a new public report for nodal providing what was provided in zonal at http://www.ercot.com/mktinfo/settlements/. MISUG 1/13 - Specific bill determinants (RUC, direct shortfall, LRS <uplift charges>, AS including SASMs, load related charges, DA congestion rent, CRR balancing account) Public. looking for at least daily like with zonal. MP feedback - Please provide for each DAM and Each RUC the following system billing determinates: DAMWAMTTOT; RMRDAMWREVTOT; DAETOT; RUCMWAMTRUCTOT; RUCCAPTOT; RUCSFTOT | ext/rpt | New | Reliant | 2011-01-13 | MISUG | LOW - MPs revisit
12 | Daily Grid Operations Report | Create report for Nodal and make public. MISUG 1/13 - Non-spin deployments happen. Transmission alerts. Unit trips (redacted). Reserves. OCNs. Report was perfect the way it was in zonal. Units that were RUCd with the beginning interval. Transparency to things that weren't like OOMC and OOME. Anything not already available somewhere: SCED offsets VDIs Other instructions Follow base point instructions for wind units Responsive deployments Available capacity - how much is dispatchable in a SCED interval - is this a real time piece of information that would be displayed somewhere else? may be a dashboard requirements Any changes to the K factors used in the SCED equation (generation to be dispatched calculation) Quick synopsis for people that are using information on the front. Look into a monthly report | ext/rpt | New | Public Requests | 2011-01-13 | MISUG | HIGH | ERCOT follow-up for late 06/2011 meeting
15 | Outage Scheduler UI - show active outages | Outage Summary, add a new column depicting which outages are currently active. Presently the only way to see which outages are active is to open each individual outage and view whether or not it has been timed out. MISUG 1/13 - Specific to TDSPs. No feedback provided. | OSUI | Modification | LCRA | 2011-01-13 | MISUG | MEDIUM
16 | Outage Scheduler UI - ERCOT waive 3 day window for unavoidable extensions | Unavoidable extensions, presently unable to submit unless the present Planned, Maintenance or Forced outage is within 3 days of ending. MISUG 1/13 - Likely a rules change for OS. | OSUI | Modification | LCRA | 2011-01-13 | ROS; NDSWG | MEDIUM
17 | MMUI - screen landscape not sized to full page | Only partial data sets are viewable and headers are lost when scrolling. For example, only able to view HR 01:00-09:00 of each resource, scroll down to the bottom of the screen, then scroll to over to see the remaining hours. There is a lot of screen not utilized. Once we have scrolled all the way to the right, you cannot see the Quantity Blocks nor the resource name and we lose track of which unit is in view. MISUG 1/13 - Throughout the MMUI | MMUI | Modification | LCRA | 2011-01-13 | MISUG | LOW
18 | MMUI - COP navigation functionality and available data to view | While viewing the COP for a particular resource, add the ability to also see the TPO, Output Schedule, A/S Offer and Inc/Dec Offer of the resource you’ve selected without having to select each tab, then re-selecting the same resource again. MISUG 1/13 - Aggregation of all data onto one screen on MMUI would be very useful. Good for validation and for data entry. | MMUI | Modification | LCRA | 2011-01-13 | MISUG | LOW
19 | MMUI - multi-selection of notices and usability of notices dropdown menu | Notice Type pull down menu, add the ability to select more than one field (select four of the thirteen choices). Instead of having to select each individual selection and then refresh. • If possible, a refresh that occurs automatically without a Trader having to manually click the show results. MISUG 1/13 - Looking for a shift and click to find multiple units. | MMUI | Modification | LCRA | 2011-01-13 | MISUG | LOW
20 | MMUI - Telemetry alerts for consistency checks | Telemetry • Nuisance alarms are generated mainly due to two reasons, hydro and wind. Both causing an alert due to inconsistent resource status and mw value. Meaning when no wind is scheduled in the COP but then does generate a small amount, we receive an alarm. • Suggest removing wind and/or hydro from their telemetry data base or at the least install a dead band with more tolerance. • Or suggest changing them from high to low priority. MISUG 1/13 - No feedback. | alerts/notifications | Modification | LCRA | 2011-01-13 | MISUG | HIGH | address with telemetry alerts
21 | MMUI - number of SASM alerts and wording of SASM notices for report downloads to the general market | SASM Notices • ERCOT sends out SASM low priority study period, one for SASM Market Clearing Prices, one for SASM market open (which we have not seen yet) and a last notice for SASM awards are available. • We don’t need a notice for the study period when a QSE has not supplied their part of the whole ERCOT model. It’s confusing because we believe a SASM has opened but in reality it did not. • We don’t need a notice for the SASM awards report is available when the SASM was never opened to begin with. • We don’t need a notice for the SASM MCPC report is available when the SASM was never opened to begin with. MISUG 1/13 - ERCOT sends SASM study open when SASM is running. Valid notices for the QSEs. ERCOT work with LCRA on this issue to see if there is anything for the MISUG to look into. | MMUI | Modification | LCRA | 2011-01-13 | MISUG | HIGH | discuss 6/1
24 | historical information for the sys wide AS capacity monitor | MISUG 1/13 - Display at least 7 days of historical information The SCED up/down may address some of this - available capacity to dec/inc base points. Also included to an extent in ICCP (only address those with generation fleets; rest of market relies on APIs). | dashboards-data | Modification | MISUG | 2011-01-13 | MISUG | LOW - MPs revisit
25 | Market not aware of when EVENTS are started/executed/completed causing higher requests for downloads | MISUG 1/13 - No notification of when EVENTS are started/executed/completed, so MPs are polling the ERCOT systems for downloads in excess of event data publishing Need to look at pushing data versus notifications Example given - when SCED is running | alerts/notifications | New | MISUG | 2011-01-13 | MISUG | MEDIUM | addressed 6/1 conversation on alerts/notices
26 | ERCOT Market Data Transparency SLA - look at the use of screen scraping, pushing data, subscription services | MISUG 1/13 - Determine what data is necessary to be pushed to the market in lieu of MPs and public using screen scraping techniques to download data from ERCOT | SLA | Modification | MISUG | 2011-01-13 | MISUG | ERCOT
28 | MIS Dashboards - unable to view the entire source of information on the screen | MISUG 1/13 - Launch the portlets - like to have an independent and dynamically size; My page | dashboards-configuration | Modification | MISUG | 2011-01-13 | MISUG | LOW - MPs revisit
30 | NDCRC - where season HSL and VAR tests | MISUG 1/13 - Fields not consistent with the data they have to put into the application (doesn't necessarily accept negatives and have to enter a negative value) | NDCRC | Modification | MISUG | 2011-01-13 | MISUG | HIGH | discuss late 6/2011 meeting
31 | MMUI - | MISUG 1/13 - When using MMUI for submissions, must close and not refresh - have to relaunch then refresh queries | MMUI | Modification | MISUG | 2011-01-13 | MISUG | LOW - MPs revisit
32 | Validation difference in what EWS accepts and what MMUI accepts | MISUG 1/13 - Client side validation between MIS and EWS should be consistent. Issue seen with MMUI and outages. ERCOT captured in defects and is currently being worked. | MMUI/OSUI | Modification | MISUG | 2011-01-13 | MISUG | ERCOT | ERCOT follow-up for late 06/2011 meeting
33 | Settlement Statement modification to add more data | MISUG 1/13 - Receive the price and quantity in the CODE and looking to get the MW quantities in the Settlement Statement. | ext/rpt | Modification | MISUG | 2011-01-13 | SEWG | MEDIUM
34 | Shift Factors report in the DAM | MISUG 1/13 - New Report. For binding constraints in the DAM, see the shift factors for those constraints for the electrical buses similar to what we have in RTM. | ext/rpt | New | MISUG | 2011-01-13 | MISUG | LOW - MPs revisit
36 | MIS Dashboards - amount of windows needed to be open to see operational data | MISUG 1/13 - Doesn't display the data to make a judgement at a glance. Eliminate the frames/portlets and the individual popups where all dashboard data is in one screen sectionalized and can be custimized | dashboards-configuration | Modification | MISUG | 2011-01-13 | MISUG | LOW - MPs revisit
37 | Weather data assumptions for DAM | MISUG 1/13 - Create a new dashboard compared to actual weather | dashboards-new | New | MISUG | 2011-01-13 | MISUG | HIGH
38 | LMP contour map - change to contour | MISUG 1/13 - Change to be a contour, not pixelated dot map - hard to see what is constrained Filtering capability to go into a particilar zone or whole state. Looking for better color change. MISUG 6/1 include negative prices broader span of prices up to price cap | dashboards-configuration | Modification | MISUG | 2011-01-13 | MISUG | MEDIUM
39 | Time flows - CSCs and CREs by hour (configurable on how many) | posted limits and flows display SE reports provide the data in a report format | dashboards-new | New | MISUG | 2011-01-13 | MISUG | LOW - MPs revisit
40 | Load page dashboard | MISUG 1/13 - Currently have DAM, RTM and actual - could we include forecasts? ERCOT doesn't have the RUC snapshots. Looking for most recent HRUC snapshot looking at current load. | dashboards-new | New | MISUG | 2011-01-13 | MISUG | MEDIUM
41 | Emergency tab on dashboards | MISUG 1/13 - Create an emergency tab to see any emergencies at a glance | dashboards-new | New | MISUG | 2011-01-13 | MISUG | MEDIUM
42 | Constraints dashboard | MISUG 1/13 - what's active from an hour ago to current - active, inactive, temp, removed | dashboards-new | New | MISUG | 2011-01-13 | MISUG | MEDIUM
43 | LMP graph | MISUG 1/13 - Want to look at multiple prices on one chart. | dashboards-configuration | Modification | MISUG | 2011-01-13 | MISUG | MEDIUM
45 | System ACE | MISUG 1/13 - Graph of ACE | dashboards-new | New | MISUG | 2011-01-13 | MISUG | HIGH
48 | Sum of HDLs and LDLs to secure | MISUG 1/13 - New report for secure | ext/rpt | New | MISUG | 2011-01-13 | MISUG | HIGH | discuss 6/1
49 | API for public | MISUG 1/13 - Public should have access to some form of an API to download data from ERCOT | access point | New | MISUG | 2011-01-13 | MISUG | LOW
50 | ICCP - add wind attribute | MISUG 1/13 - Total wind MW within ICCP |  | Modification | MISUG | 2011-01-13 | MISUG | WMS
52 | Active Binding Constraints | MISUG 1/13 - Looking for current real time active binding constraints public display for DAM and RTM. Tied to #8 above and the security classification change. | display | New | MISUG | 2011-01-13 | MISUG | MEDIUM
54 | ERCOT meeting calendar | Add button to "Add to my calendar" | website | New | Excelon | 2011-01-24 | MISUG | ERCOT | look to add to scope of ERCOT website enhancements 2012
57 | DCTIE schedules - historical | Need historical by DCTIE. Looking at a year's activity. Public. ERCOT planning staff used historical hour by hour information to determine what needed to be included in the planning models. | ext/rpt | New | MISUG | 2011-02-22 | MISUG | LOW - MPs revisit | posted in SE reports
58 | CRR Shift Factors | For the binding constraints (similar to DAM Shift Factors) | ext/rpt | New | MISUG | 2011-02-22 | MISUG | HIGH
60 | System-wide RUC Charges | Post daily system wide RUC charges similar to Monthly RUC Make Whole Charge and Clawback Payment Report, but by day. | ext/rpt | New | DC-Energy | 2011-02-24 | MISUG | MEDIUM
64 | ERCOT Actual Load Report | Public posting of ERCOT Actual Load in the form of a report. ERCOT currently only has a display of Actual Loads of Weather Zones on the website for consumption. | ext/rpt | New | Goldman, Sachs | 2011-03-16 | MISUG | HIGH
65 | NH Interface Limit |  | ext/rpt | New | Goldman, Sachs | 2011-06-01 | MISUG | WMS